## Sheet1
Meta Code | Project Code | Legacy Code | Agency | Cluster | Region | Country | Type | Sector | Project Title | Date Approved | Date of Completion per Proposal | Status | First Disbursement Date | Planned Date of Completion | Date Completed (Actual) | Date of Financial Completion | Consumption ODP/MT to be Phased Out per Proposal | Production ODP/MT to be Phased Out per Proposal | Consumption to be Phased Out per Proposal in CO2-eq Tonnes | Production to be Phased Out per Proposal in CO2-eq Tonnes | Consumption ODP/MT Phased Out | Consumption Phased Out in CO2-eq Tonnes | Production ODP/MT Phased Out | Production Phased Out in CO2-eq Tonnes | Approved Funding (US$) | Adjustment (US$) | Approved Funding plus Adjustments (US$) | Per Cent of Funds Disbursed | Balance (US$) | Support Cost Approved (US$) | Support Cost Adjustment (US$) | Support Costs Approved Funding plus Adjustments (US$) | Support Cost Balance (US$) | Funds Disbursed (US$) | Funds Committed (US$) | Estimated Disbursement in Current Year (US$) | Support Cost Disbursed (US$) | Support Cost Committed (US$) | Disbursements made to final beneficiaries from FECO/ MEP | Funds advanced (US$) | Implementation Delays/Status Report Decisions | Date of Completion per Agreements or per Decisions | Remarks (as of 31 December XXXX) | Remarks (Current year) | Gender Policy for All Projects Approved from 85th Mtg (Yes/No)
|  | ARM/EEF/93/TAS/30 | UNEP | EE | EUR | ARM | TAS | Refrigeration | Additional activities to maintain energy efficiency for the servicing sector under decision 89/6(b) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 100000 | 0 | 100000 | 0% | 100000 | 13000 | 0 | 13000 |  | 0 | 0 | 25000 | 0 | 0 |  | 0 |  |  | Project approved in December 2023. | SSFA signed in February 2024 and payment 1 of USD 49,000 released in March 2024. | Yes
|  | TLS/SEV/93/INS/25 | UNIDO | Government Support | ASP | TLS | INS | National Ozone Unit | Extension of institutional strengthening (phase VII: 7/2024-6/2027) | 2023-12-01 | 2027-06-01 | ONG |  | 2027-06-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  |  | The newly approved project at the Excom-93 in December 2023. | UNEP discussed with the NOU to develop the workplan, which was finalized and agreed by NOU. The draft SSFA was submitted to the Government for review and agreement. UNEP is waiting for the NOU to confirm agreement on SSFA. | Yes
|  | KUW/SEV/92/INS/47 | UNIDO | Government Support | ASP | KUW | INS | National Ozone Unit | Extension of institutional strengthening project (phase IX: 6/2023-5/2026) | 2023-06-01 | 2026-05-01 | ONG |  | 2026-05-01 |  |  | 0 | 0 | [6 empty] | 279056 | 0 | 279056 | 0% | 279056 | 0 | 0 | 0 | 0 | 0 | 0 | 97669.6 | 0 | 0 |  | 0 |  |  | Newly approved project. | Progress report: -Legal Instrument: SSFA signed in April 2024 and first payment made in April 2024; the planned activities have been initiated soundly and A7 and CP data and A7 reporting for 2022 submitted; NOU participated and contributed in global and regional Meetings; the public awareness and information dissemination activities initiated. - Overall assessment of project progress: Project is progressing as planned. - Impact of these activities: the ISP is playing key role in facilitating the compliance of Kuwait with MP targets and sound implementation of related projects. | Yes
|  | ANT/SEV/93/INS/20 | UNIDO | Government Support | LAC | ANT | INS | National Ozone Unit | Extension of institutional strengthening project (phase VI: 1/2024-12/2026) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  |  | Newly approved project. | UNEP awaiting completion of ISP V which is planned for 2024, in order to open agreement for ISP VI. | Yes
|  | IRQ/SEV/93/INS/33 | UNIDO | Government Support | ASP | IRQ | INS | National Ozone Unit | Extension of institutional strengthening project (phase VI: 1/2024-12/2026) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 635904 | 0 | 635904 | 0% | 635904 | 0 | 0 | 0 | 0 | 0 | 0 | 158976 | 0 | 0 |  | 0 |  |  | Newly approved project. | Progress report: -Legal Instrument: SSFA has been prepared and shared with the NOU for their consent and signature along with the implementation plan; - Overall assessment of project progress: Project is progressing - Impact of these activities: the ISP is playing key role in facilitating the compliance of Iraq with MP targets and sound implementation of related projects. | Yes
|  | MAR/SEV/93/INS/34 | UNIDO | Government Support | AFR | MAR | INS | National Ozone Unit | Extension of institutional strengthening project (phase VIII: 1/2024-12/2026) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  |  | Newly approved project | The licensing and quota system is in place and functioning. The collection of data was undertaken to report A7 and CP data for the year 2023. A7 data and CP data for year 2023 submitted in April 2024. The NOU conducted one Steering Committee meeting held on 14 February 2024. Provision has been made in the Environment Protection Bill which is being debated at the National Assembly (April 2024) for the introduction of quota system. Indeed section 147 2 (d) of the Bill states that: The Minister may make such regulations as may be necessary for the purposes of this Act: for the implementation or enforcement of an obligation under an MEA, including the introduction of a quota system. The EPA 2024 will be promulgated. Sustained awareness on the legislation to ensure that imports of refrigerants are done in compliance with the law. Import quotas have been updated and importers informed accordingly. The NOU attended the 12th Meeting of the Ozone Research Managers in Geneva from 24th to 26th April 2024. The project is progressing satisfactorily. | Yes
|  | SWA/SEV/92/INS/35 | UNIDO | Government Support | AFR | SWA | INS | National Ozone Unit | Extension of institutional strengthening project (phase VIII: 7/2023-6/2026) | 2023-06-01 | 2026-06-01 | ONG |  | 2026-06-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 63000 | 0 | 0 |  | 90000 |  |  | The first disbursement of USD90,000 was released to the country in October 2023. Import quotas for 2023 was issued to ODS and HFC importers. The NOU conducted two inspections on importers’ premises and workshops jointly with the Police Service in Siteki and Big bend. One workshop for Police was conducted at the Police Academy in Matsapha from 26- 27 July 2023 and 44 officers trained on enforcement (18 females and 26 males). The collection of data was undertaken to report A7 and CP data for the year 2022. 2022 Country Programme (CP) data reported in May 2023. A7 data for 2022 reported in September 2023. The NOU conducted three meetings for the steering committee as follows; 31st January 2023 at Emafini Country Lodge (There were 2 females and 6 males); 4th of April 2023 at Emafini Country Lodge (5 Females and 4 Males); 28th November to the at Emafini Country Lodge (5 females and 6 males). The NOU conducted three meetings; With the Fire Protection industry, a meeting was held on the 16th November 2023 at The George Hotel (15 Males and 4 females); With ODS importers on the 12th of October 2023 at The George Hotel (13 males and 4 females); Meeting for RAC technicians was held Mbabane on the 9th November 2023 (48 male and 9 Female technicians in attendance). The 2023 International World Ozone Day was commemorated on the 21st of September 2023, at Mavuso Trade and Exhibition Centre, Manzini. As part of commemoration, there was an official launch of grade testing standard for refrigeration and air conditioning technicians. The Honorable Minister of Tourism and Environmental Affairs was the guest speaker. The NOU conducted two roadshows; Nhlangano Shopping Complex on the 1st July 2023; and 11th November 2023 at Siphofaneni Bus Rank. The NOU participated at the Regional Network Meeting for National Ozone Officers of the English-Speaking African Countries back-to-back with Thematic Workshop for Customs Officers from 8-12 May 2023 in Kigali, Rwanda. The Regional Network Meeting, attended by 26 out of 28 countries of the English-speaking African networks (37 male, 30 female), provided opportunity for the countries to further discuss key information and data to be collected in preparation of a KIP Strategy and approaches. The NOU participated at the 45th OEWG meeting held in Bangkok, Thailand from 3rd to 7th July 2023 and the 35th meeting of the parties to the Montreal Protocol in Nairobi, Kenya from 23rd to 24th October 2023.The project is progressing satisfactorily. | The NOU conducted two meetings for the ozone steering committee held to approve workplans and further assist in responding to comments for country project proposal submissions. The meetings were held from 20-21 March 2024 at Bethel Court Hotel, attended by 5 males and 5 females and 4-5 April 2024 at Emafini Country Lodge. The NOU has conducted three awareness outreach activities have been undertaken: One roadshow at Simunye Plaza bus rank with the Police Service on the 19th January 2024; 16-18 February 2024 at Buhleni Maganu Festival; 8-10 March 2024 Hlane Maganu Festival; which is a national event thus providing a suitable platform for dissemination of information; and Motjane high school commemorating environmental awareness including ozone issues activity on the 15th February 2024 eight (8) schools were represented. The NOU conducted one training for RAC from 25 March 2024 to 28 March 2024 held at Gwamile Voctim. (22 RAC Technicians, 5 females and 17 males); and 30 Toolbox kits were procured for distribution to the RAC technicians after training. The project is progressing satisfactorily. | Yes
|  | PAR/SEV/93/INS/46 | UNIDO | Government Support | LAC | PAR | INS | National Ozone Unit | Extension of institutional strengthening project (phase XI: 1/2024-12/2026) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  |  | Newly approved project | Good progress. Work plan and timetable to implement the project agreed with the NOU. SSFA-2024-04 is under discussion. This SSFA will facilitate obtaining products and expected results as mentioned below:(1) Adoption/enforcement of Montreal Protocol Controlled Substances laws and regulations to control and monitor the consumption of Montreal Protocol Controlled Substances, (2) Efficient and timely data collection and reporting, (3) Intra- and inter-institutional coordination to implement the Montreal Protocol with other organizations/national stakeholders, (4) Supervision of timely execution of activities to eliminate and reduce the consumption of Substances controlled by the Montreal Protocol, (5) Increase awareness raising and information exchange, (6) Regional cooperation and participation in Montreal Protocol meetings. | Yes
|  | BOL/SEV/93/INS/56 | UNIDO | Government Support | LAC | BOL | INS | National Ozone Unit | Extension of institutional strengthening project (phase XII: 1/2024-12/2026) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 208966 | 0 | 208966 | 0% | 208966 | 0 | 0 | 0 | 0 | 0 | 0 | 52241.5 | 0 | 0 |  | 0 |  |  | Newly approved project | Good progress. Work plan and timetable to implement the project agreed with the NOU. SSFA-2024-04 is under discussion. This SSFA will facilitate obtaining products and expected results as mentioned below:(1) Adoption/enforcement of Montreal Protocol Controlled Substances laws and regulations to control and monitor the consumption of Montreal Protocol Controlled Substances, (2) Efficient and timely data collection and reporting, (3) Intra- and inter-institutional coordination to implement the Montreal Protocol with other organizations/national stakeholders, (4) Supervision of timely execution of activities to eliminate and reduce the consumption of Substances controlled by the Montreal Protocol, (5) Increase awareness raising and information exchange, (6) Regional cooperation and participation in Montreal Protocol meetings. | Yes
|  | SAM/SEV/92/INS/27 | UNIDO | Government Support | ASP | SAM | INS | National Ozone Unit | Extension of institutional strengthening project (phase XII: 1/2024-12/2026) | 2023-06-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 63000 | 0 | 0 |  | 0 |  |  | The project was approved at the 92nd Executive Committee meeting in June 2023. UNEP worked with the NOU to prepare the project plan and SSFA. The workplan incorporated gender mainstreaming. | The SSFA was signed in February 2024. The first payment of US$ 62,000 was released in March 2024. The NOU continues to enforce HCFC/HFC quota and licensing system. CP data for the year 2023 collection has been completed and will be submitted by May. The NOU participated the Twinning Workshop of Montreal Protocol Officers, Energy-Efficiency Policy Makers and Financial Mechanisms Focal Points to Support Kigali Amendment Objectives, Thematic Workshop on Establishment and Implementation of Competency- based Certification, Thematic Workshop on Strategy of Stage I of the KIP and Integration with the HPMP Stage II for Pacific Island Countries from 5-10 February 2024 in Cook Islands. In June 2024 in Palau, the country will participate in the regional network meeting, regional training of NOUs, and thematic workshop on finalization of KIP Stage I. | Yes
|  | KAM/SEV/92/INS/43 | UNIDO | Government Support | ASP | KAM | INS | National Ozone Unit | Extension of institutional strengthening project (phase XII:1/2024-12/2026) | 2023-06-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 298522 | 0 | 298522 | 0% | 298522 | 0 | 0 | 0 | 0 | 0 | 0 | 104482.7 | 0 | 0 |  | 0 |  |  | The newly approved project at the Excom-92 in June 2023. UNEP discussed with the NOU to develop the workplan, which was finalized and agreed by NOU. The agreed workplan was used to prepare the Project Corporation Agreement (PCA). However, due to the change of legal agreement from SSFA to PCA, the Government of Cambodia needed to obtain internal approval on the PCA. | The Government of Cambodia confirmed agreement to the PCA in March 2024. The PCA was processed and signed by UNEP and is waiting for the Government signature. While waiting for PCA to be effective, the NOU continues to enforce HCFC/HFC quota and licensing system through the electronic licensing system. HFC quota system has been implemented since 1 January 2024. The CP data for the year 2023 was reported to the MLFS in April 2024. The NOU collaborated with relevant stakeholders and supported UNEP in the preparation of the Additional activities for the introduction of alternatives to HCFCs with low or zero GWP refrigerants and for maintaining energy efficiency in the refrigeration servicing sector (decision 89/6) and preparation of national inventory of banks of used or unwanted controlled substances. The NOU will participate in the Energy Efficiency Twinning Workshop back-to-back with the Joint Network Meeting of South Asia and Southeast Asia National Ozone Officers in China in May 2024. NOU continues to implement the following gender activities: encouraging female participants in the meetings/training under the project and collection of gender-disaggregation data in project activities. | Yes
|  | KEN/SEV/92/INS/66 | UNIDO | Government Support | AFR | KEN | INS | National Ozone Unit | Extension of institutional strengthening project (phase XIII: 7/2023-6/2026) | 2023-06-01 | 2026-06-01 | ONG |  | 2026-06-01 |  |  | 0 | 0 | [6 empty] | 401857 | 0 | 401857 | 0% | 401857 | 0 | 0 | 0 | 0 | 0 | 401857 | 140649.95 | 0 | 0 |  | 150000 |  |  | The SSFA with a total of US$ 401,857was signed in November 2023. The first disbursement of US$150,000 was released to the country in November 2023. The licensing and quota system is in place and functioning. The collection of data was undertaken to report A7 and CP data for the year 2023. The NOU participated in the Regional Network Meeting, held back-to-back with the Thematic Meeting for Customs Officers, in Kigali, Rwanda, from May 8-10 and 11-12, 2023. The NOU participated at the 35th Meeting of the Parties to the Montreal Protocol, held in Nairobi from October 23 to 27, 2023. The overall performance of the project is satisfactory. The project is progressing satisfactorily | The licensing and quota system is in place and functioning. The collection of data was undertaken to report A7 and CP data for the year 2023. The collection of data was undertaken to report A7 and CP data for the year 2023. The project is progressing successfully. | Yes
|  | PHI/SEV/92/INS/110 | UNIDO | Government Support | ASP | PHI | INS | National Ozone Unit | Extension of institutional strengthening project (phase XIV: 1/2024-12/2026) | 2023-06-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 479930 | 0 | 479930 | 0% | 479930 | 0 | 0 | 0 | 0 | 0 | 0 | 167975.5 | 0 | 0 |  | 0 |  |  | The newly approved project at the Excom-92 in June 2023. UNEP discussed with the NOU to develop the workplan, which was finalized and agreed by NOU. The agreed workplan was used to prepare the PCA, which was signed between UNEP and the Government in December 2023. | The first payment of US$ 164,000 was released to the country in February 2024. The NOU continued to enforce HCFC quota and HCFC/HFC licensing system through Certificates of Registration; Integrated Online Permitting and Monitoring System with electronic Licensing Database for importers and local traders (dealers, resellers and retailers) and Pre-Shipment Importation Clearances. HFC quota has been implemented since 1 January 2024. The collection of data was undertaken to report A7 and CP data for the year 2023. CP data for 2023 was reported to the MLFS in April 2024. NOU continued to coordinate implementation of newly approved HPMP Stage III and KIP Preparation. NOU continued to implement the following gender activities: encouraging female participants in the meetings/training under the project, collection of gender-disaggregation data in project activities and introduction of gender mainstreaming in the agenda item of the meetings with stakeholders. | Yes
|  | GUY/SEV/93/INS/37 | UNIDO | Government Support | LAC | GUY | INS | National Ozone Unit | Extension of the institutional strengthening project (phase IX: 1/2024-12/2026) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  |  | Newly approved project | SSFA is being drafted for consideration by the Country. UNEP agreed with the country on an implementation plan for the closure of ISP VIII. UNEP is awaiting the closure of ISP VIII before entering into an agreement for ISP IX. | Yes
|  | NIU/SEV/92/INS/18 | UNIDO | Government Support | ASP | NIU | INS | National Ozone Unit | Extension of the institutional strengthening project (phase IX: 1/2024-12/2026) | 2023-06-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 100000 | 0 | 100000 | 0% | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 |  | 0 |  |  | The project was newly approved at the 92nd Executive Committee meeting in June 2023. UNEP worked with the NOU to prepare the project plan and SSFA. The workplan incorporated gender mainstreaming. | UNEP discussed with the NOU to develop the workplan, which was finalized and agreed by NOU. The draft SSFA was submitted to the Government for review and agreement. UNEP is waiting for the NOU to confirm agreement on SSFA. While waiting for signing of the SSFA, the NOU enforces HFC quota and licensing system. No HCFC importer allowed in 2024 in accordance with the Agreement with the ExCom. CP data for the year 2023 collection has been completed and will be submitted by May. The NOU participated the Twinning Workshop of Montreal Protocol Officers, Energy-Efficiency Policy Makers and Financial Mechanisms Focal Points to Support Kigali Amendment Objectives, Thematic Workshop on Establishment and Implementation of Competency- based Certification, Thematic Workshop on Strategy of Stage I of the KIP and Integration with the HPMP Stage II for Pacific Island Countries from 5-10 February 2024 in Cook Islands. In June 2024 in Palau, the country will participate in the regional network meeting, regional training of NOUs, and thematic workshop on finalization of KIP Stage I. | Yes
|  | TUV/SEV/92/INS/19 | UNEP | Government Support | ASP | TUV | INS | National Ozone Unit | Extension of the institutional strengthening project (phase IX: 1/2024-12/2026) | 2023-06-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 63000 | 0 | 0 |  | 0 |  |  | The project was approved at the 92nd Executive Committee meeting in June 2023. UNEP and the country prepared the project plan and SSFA. The workplan incorporated gender mainstreaming. | The SSFA was signed in February 2024. The first payment of US$ 62,000 was released in March 2024. NOU continues to enforce HCFC/HFC quota and licensing system. HFC quota system has been implemented with the allocated amount of 2,206 tonnes CO2 equivalent. CP data for the year 2023 collection has been completed and will be submitted by May. Four (4) inspections were conducted in January, February and April 2024. In April, the inspection team found a Tuvalu passenger boat from New Zealand carrying RAC equipment for household use without permits, and therefore discussed this case with the Customs. The investigation is still ongoing. The NOU participated the Twinning Workshop of Montreal Protocol Officers, Energy-Efficiency Policy Makers and Financial Mechanisms Focal Points to Support Kigali Amendment Objectives, Thematic Workshop on Establishment and Implementation of Competency- based Certification, Thematic Workshop on Strategy of Stage I of the KIP and Integration with the HPMP Stage II for Pacific Island Countries from 5-10 February 2024 in Cook Islands. In June 2024 in Palau, the country will participate in the regional network meeting, regional training of NOUs, and thematic workshop on finalization of KIP Stage I. | Yes
|  | YEM/SEV/93/INS/47 | UNEP | Government Support | ASP | YEM | INS | National Ozone Unit | Extension of the institutional strengthening project (phase IX: 1/2024-12/2026) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 450429 | 0 | 450429 | 0% | 450429 | 0 | 0 | 0 | 0 | 0 | 0 | 112607.25 | 0 | 0 |  | 0 |  |  | Newly approved project | Progress report: -Legal Instrument: SSFA has been prepared and shared with the NOU for their consent and signature along with the implementation plan; - Overall assessment of project progress: Project is progressing | Yes
|  | ZAM/SEV/92/INS/46 | UNEP | Government Support | AFR | ZAM | INS | National Ozone Unit | Extension of the institutional strengthening project (phase IX: 7/2023-6/2026) | 2023-06-01 | 2026-06-01 | ONG |  | 2026-06-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 63000 | 0 | 0 |  | 90000 |  |  | Newly approved project. The SSFA with a total of USD180,000 was signed by the country in September 2023. The first disbursement was USD90,000 was released to the country in October 2023. The Licensing system is fully operational. The quota for the year 2023 was issued. The NOU conducted monitoring of illegal ODS trade and conducted one customs training workshop in Ndola on 14th February 2023 for 20 Enforcement Officers (8 female and 12 males). The collection of data was undertaken to report A7 and CP data for the year 2023. CP data for 2023 reported on April 2024. A7 data for 2023 reported in April 2024. The NOU conducted one Steering Committee meeting in April 2023. The consultative meeting with Refrigeration and Air-conditioning Association of Zambia and its membership was held in December 2023. The World ozone day for 2023 was organized and held in Livingstone. The event focused on the environmental quiz for secondary school in the Southern Part of the Country. The NOU participated at the Regional Network Meeting for National Ozone Officers of the English-Speaking African Countries back-to-back with Thematic Workshop for Customs Officers from 8-12 May 2023 in Kigali, Rwanda. The Regional Network Meeting, attended by 26 out of 28 countries of the English-speaking African networks (37 male, 30 female), provided opportunity for the countries to further discuss key information and data to be collected in preparation of a KIP Strategy and approaches. The NOU participated at the 45th OEWG meeting held in Bangkok, Thailand from 3rd to 7th July 2023 and the 35th meeting of the parties to the Montreal Protocol in Nairobi, Kenya from 23rd to 24th October 2023. The project is progressing satisfactorily. | The Licensing system is fully operational. The NOU conducted one inspection visit to importers /suppliers in Northwestern part of the Country. The project is progressing satisfactorily. | Yes
|  | CKI/SEV/93/INS/19 | UNEP | Government Support | ASP | CKI | INS | National Ozone Unit | Extension of the institutional strengthening project (phase IX: 7/2024-6/2027) | 2023-12-01 | 2027-06-01 | ONG |  | 2027-06-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  |  | The project was newly approved at the 93rd Executive Committee meeting in December 2023. UNEP worked with the NOU to prepare the project plan and SSFA. The workplan incorporated gender mainstreaming. | UNEP discussed with the NOU to develop the workplan, which was finalized and agreed by NOU. The draft SSFA was submitted to the Government for review and agreement. UNEP is waiting for the NOU to confirm agreement on SSFA. Project implementation will commence from July 2024. | Yes
|  | SOM/SEV/93/INS/20 | UNEP | Government Support | AFR | SOM | INS | National Ozone Unit | Extension of the institutional strengthening project (phase VI: 1/2024-12/2026) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  |  | Newly approved project | The SSFA with a total of USD180,000 was prepared and sent to country for signature in March 2024. The Licensing system is fully operational. The collection of data was undertaken to report A7 and CP data for the year 2023. The NOU conducted the first meeting on the establishment of TAC technicians on 25 February 2024. The meeting was attended by 40 participants (4 female and 36 male). The project is progressing satisfactorily. | Yes
|  | DMI/SEV/93/INS/27 | UNEP | Government Support | LAC | DMI | INS | National Ozone Unit | Extension of the institutional strengthening project (phase VIII: 1/2024-12/2026 ) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  |  | Newly approved project. | UNEP awaiting closure of ISP VII before entering into agreement for ISP VIII. Draft SSFA to be prepared in advance. | Yes
|  | RWA/SEV/92/INS/40 | UNEP | Government Support | AFR | RWA | INS | National Ozone Unit | Extension of the institutional strengthening project (phase X: 1/2024-12/2026) | 2023-06-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 63000 | 0 | 0 |  | 0 |  |  | The SSFA with a total of US$ 180,000 was signed by the country in October 2023. The Licensing system is fully operational. The quota for the year 2023 was issued to 8 importers. The country hosted the Regional Network Meeting for National Ozone Officers of the English-Speaking African Countries back-to-back with Thematic Workshop for Customs Officers from 8-12 May 2023 in Kigali, Rwanda. The Regional Network Meeting, attended by 26 out of 28 countries of the English-speaking African networks (37 male, 30 female), provided opportunity for the countries to further discuss key information and data to be collected in preparation of a KIP Strategy and approaches. The NOU participated at the 45th OEWG meeting held in Bangkok, Thailand from 3rd to 7th July 2023 and the 35th meeting of the parties to the Montreal Protocol in Nairobi, Kenya from 23rd to 24th October 2023. The project is progressing satisfactorily. | The first disbursement of USD90,000 was released to the country in January 2024. The Licensing system is fully operational. The collection of data was undertaken to report A7 and CP data for the year 2023. The project is progressing satisfactorily. | Yes
|  | LIR/SEV/92/INS/34 | UNEP | Government Support | AFR | LIR | INS | National Ozone Unit | Extension of the institutional strengthening project (phase X: 11/2023-10/2026) | 2023-06-01 | 2026-10-01 | ONG |  | 2026-10-01 |  |  | 0 | 0 | [6 empty] | 225780 | 0 | 225780 | 0% | 225780 | 0 | 0 | 0 | 0 | 0 | 225780 | 79023 | 0 | 0 |  | 80000 |  |  | The SSFA with a total of US$ 225780 was signed in September 2023. The first disbursement of US$80,000 was released to the country in October 2023. The licensing and quota system is in place and functioning. The NOU participated in the Regional Network Meeting for National Ozone Officers of the English-Speaking African Countries back-to-back with Thematic Workshop for Customs Officers held from 8-12 May 2023 in Kigali, Rwanda. The NOU participated at the 35th Meeting of the Parties to the Montreal Protocol, held in Nairobi from October 23 to 27, 2023. The overall performance of the project is satisfactory. The project is progressing satisfactorily. | The licensing and quota system is in place and functioning. The collection of data was undertaken to report A7 and CP data for the year 2023. Both the Article 7 and Country Programme data for 2023 were reported. The project is progressing satisfactorily. | Yes
|  | MLI/SEV/92/INS/44 | UNEP | Government Support | AFR | MLI | INS | National Ozone Unit | Extension of the institutional strengthening project (phase X: 7/2023-6/2026) | 2023-06-01 | 2026-06-01 | ONG |  | 2026-06-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 63000 | 0 | 0 |  | 0 |  |  | Newly approved project | The SSFA was signed in November 2023. The first payment was released to the country in January 2024. Licensing system is fully operational | Yes
|  | GAB/SEV/93/INS/44 | UNEP | Government Support | AFR | GAB | INS | National Ozone Unit | Extension of the institutional strengthening project (phase XII: 1/2024-12/2026) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  |  | Newly approved project. | The SSFA was signed by both in April 2024. The first payment was disbursed in May 2024. Licensing system is fully operational. | Yes
|  | TOG/SEV/93/INS/43 | UNEP | Government Support | AFR | TOG | INS | National Ozone Unit | Extension of the institutional strengthening project (phase XII: 1/2024-12/2026) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  |  | Newly approved project. | The SSFA was signed in April 2024. First payment was disbursed in May 2024. Licensing system is fully operational. | Yes
|  | DOM/SEV/92/INS/74 | UNEP | Government Support | LAC | DOM | INS | National Ozone Unit | Extension of the institutional strengthening project (phase XII: 7/2023-6/2026) | 2023-06-01 | 2026-06-01 | ONG |  | 2026-06-01 |  |  | 0 | 0 | [6 empty] | 355929 | 0 | 355929 | 0% | 355929 | 0 | 0 | 0 | 0 | 0 | 0 | 124575.15 | 0 | 0 |  | 0 |  |  | Newly approved project | Good progress. Work plan and timetable to implement the project agreed with the NOU. SSFA-2023-01 has been signed in January 2024 with an overall amount of USD 313,014 payable in three disbursements. First disbursement with an amount of USD 165,507 has been received by the country in March 2024. This SSFA will facilitate obtaining products and expected results as mentioned below:(1) Adoption/enforcement of Montreal Protocol Controlled Substances laws and regulations to control and monitor the consumption of Montreal Protocol Controlled Substances, (2) Efficient and timely data collection and reporting, (3) Intra- and inter-institutional coordination to implement the Montreal Protocol with other organizations/national stakeholders, (4) Supervision of timely execution of activities to eliminate and reduce the consumption of Substances controlled by the Montreal Protocol, (5) Increase awareness raising and information exchange, (6) Regional cooperation and participation in Montreal Protocol meetings. | Yes
|  | GAM/SEV/92/INS/46 | UNEP | Government Support | AFR | GAM | INS | National Ozone Unit | Extension of the institutional strengthening project (phase XII: 7/2023-6/2026) | 2023-06-01 | 2026-06-01 | ONG |  | 2026-06-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 63000 | 0 | 0 |  | 90000 |  |  | The SSFA with a total of US$180,000 was signed in October 2023. The first disbursement of US$90,000 was released to the country in November 2023. The licensing and quota system is in place and functioning. Four importers were issued licenses and quota for the year 2023. All the importers complied with the licensing and quota system. Two steering committee meetings held and each of the steering meetings was attended by 25 members, (6 female and 19 male). One training programme organized for enforcement officers, clearing agents and other security agents in Banjul at the Gambia Revenue Authority head office in October 2023. Enforcement officers equipped with 2 of refrigerants identifiers for the Sea port of Banjul. The International World Ozone Day was celebrated in Basse upper River Region with several awareness activities. The regional Scout Band supported in the match pass. Traditional communicators provided local music and educated the general public on the importance of the Ozone Layer and the negative impacts associated with the depletion of the Ozone Layer. The NOU conducted the training of female refrigeration and air conditioning technicians and the development of their constitution. The NOU participated in the Regional Network Meeting, held back-to-back with the Thematic Meeting for Customs Officers, in Kigali, Rwanda, from May 8-10 and 11-12, 2023. The NOU participated at the 35th Meeting of the Parties to the Montreal Protocol, held in Nairobi from October 23 to 27, 2023. The overall performance of the project is satisfactory. The project is progressing satisfactorily. | The licensing system is fully operational. The collection of data was undertaken to report A7 and CP data for the year 2023. One steering committee meeting organized for 25 participants ( 10 female, 15 male). The project is progressing successfully. | Yes
|  | MOL/SEV/92/INS/47 | UNEP | Government Support | EUR | MOL | INS | National Ozone Unit | Extension of the institutional strengthening project (phase XII: 7/2023-6/2026) | 2023-06-01 | 2026-06-01 | ONG | 2023-12-31 | 2026-06-01 |  |  | 0 | 0 | [6 empty] | 183707 | 0 | 183707 | 3.587% | 177117 | 0 | 0 | 0 | 0 | 6590 | 177117 | 61990.95 | 0 | 0 |  | 53410 |  |  | SSFA signed in September 2023 and payment 1 of USD 60,000 released in November 2023. | HCFC import quotas for 2024 were allocated on 17 January 2024, to 4 importers for an amount of 6,600 MT of HCFCs (R-22). HFC import quotas for 2024 were allocated on 17 January 2024, to 8 importers for an amount of 511,825,120 kg CO2 equivalent (mainly R134A, R404A, R410A, R407C, R507A, R32). MPU supported the preparation of Moldova HPMP stage III tranche 2. The projects was submitted in March 2024 for consideration by ExCom 94 with UNDP as lead and UNEP as cooperating agency. ODS import and consumption data for 2023 were collected. CP data were submitted to MFS in April 2024 and A7 data to the Ozone Secretariat in April 2024. Training of customs officers, environmental inspectors and technicians with emphasis on servicing equipment using low-GWP alternatives and flammable refrigerants is progressing as planned. Inter-ministerial coordination mechanism is established. The Commission of experts (including MPU staff and RAC representatives) met annually and allocated HCFC and HFCs import quota to companies according to the Regulation on establishing the mechanism for distributing the annual quota for the import of HCFCs and HFC. Country is actively involved in the discussions and decision-making process on the international level. MPU staff and national experts participated at regular ECA meetings. | Yes
|  | BKF/SEV/93/INS/49 | UNEP | Government Support | AFR | BKF | INS | National Ozone Unit | Extension of the institutional strengthening project (phase XV: 1/2024-12/2026) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 191858 | 0 | 191858 | 0% | 191858 | 0 | 0 | 0 | 0 | 0 | 0 | 47964.5 | 0 | 0 |  | 0 |  |  | Newly approved project. | SSFA was signed in April 2024. The first payment will be sent to the NOU in May 2024. | Yes
|  | KYR/EEF/92/TAS/49 | UNEP | HPMP1 | EUR | KYR | TAS | SERVCEE-89/6 | HCFC phase-out management plan (energy efficiency - related activities under decision 89/6) | 2023-06-01 | 2024-12-01 | ONG | 2023-12-31 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 100000 | 0 | 100000 | 8.265% | 91735 | 13000 | 0 | 13000 | 11925.55 | 8265 | 91735 | 32107.25 | 1074.45 | 11925.55 |  | 40735 |  |  | Project approved in June 2023, SSFA signed in September 2023, and payment 1 of USD 49,000 released in November 2023. On 14 December 2023, a training seminar was held in Naryn city for staff of State Customs Service staff on regulating import, export and transit of HFCs. On 15 December 2023, a workshop on "Energy Efficiency in the Refrigeration Equipment Sector" was held in Narym oblast for refrigeration technicians and environmental inspectors. Participants discussed the strategy and issues of improving energy-efficiency in the HVRAC sector. The bidding for developing outreach materials and for conducting the consumer behavior study was launched on 20 November 2023, but was not successful. | Interim progress and expenditures reports were submitted in January and April 2024, and payment 2 of USD 49,000 released in April 2024. The bidding for developing outreach materials was re-launched on 9 January 2024. The bidding for conducting the consumer behaviour study including assessmetn of barriers was re-launched on 12 January 2024. | Yes
|  | BDI/PHA/93/TAS/45 | UNEP | HPMP1 | AFR | BDI | TAS | AC | HCFC phase-out management plan (stage I, fifth tranche) | 2023-12-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 33200 | 0 | 33200 | 0% | 33200 | 4316 | 0 | 4316 | 4316 | 0 | 0 | 8300 | 0 | 0 |  | 0 |  | 2024-12-01 | SSFA was signed in March 26th 2024. The first payment was sent to the NOU in April 2024. | SSFA was signed in March 26th 2024. The first payment was sent to the NOU in April 2024. | Yes
|  | MLI/PHA/92/TAS/45 | UNEP | HPMP1 | AFR | MLI | TAS | AC | HCFC phase-out management plan (stage I, fifth tranche) | 2023-06-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 28000 | 0 | 28000 | 0% | 28000 | 3640 | 0 | 3640 | 3640 | 0 | 28000 | 9800 | 0 | 3640 |  | 14000 |  | 2024-12-01 | Newly approved project | The SSFA was signed in November 2023. The first payment was released to the country in December 2023. Licensing system is fully operational | Yes
|  | SUR/PHA/92/TAS/33 | UNEP | HPMP1 | LAC | SUR | TAS | AC | HCFC phase-out management plan (stage I, fourth tranche) | 2023-06-01 | 2024-06-01 | ONG |  | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 13500 | 0 | 13500 | 0% | 13500 | 1755 | 0 | 1755 | 1755 | 0 | 0 | 4725 | 0 | 0 |  | 0 |  | 2024-06-01 | Newly approved project. | SSFA drafted for negotiation with Country. UNEP was informed of a change in the NOO on 18 Jan 2024, resulting in decreased rate of implematation. UNEP met with newly assigned Officer on 19 Feb 2024 to present the full portfolio of Montreal Protocol projects, highlighting areas requiring urgent attention including the review of the draft SSFA for the HPMP I Tranche 4. SSFA in portal to be signed. | Yes
|  | STK/PHA/93/TAS/24 | UNEP | HPMP1 | LAC | STK | TAS | AC | HCFC phase-out management plan (stage I, third tranche) | 2023-12-01 | 2024-06-01 | ONG |  | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 16900 | 0 | 16900 | 0% | 16900 | 2197 | 0 | 2197 | 2197 | 0 | 0 | 4225 | 0 | 0 |  | 0 |  | 2024-06-01 | Newly approved project. | SSFA drafted and negotiated with Country. Draft shared for review of banking, signatory and other details with Country, to facilitate signing, Mar 2024. The SSFA was signed in April 2024 and the first payment was processed. | Yes
|  | MOZ/EEF/93/TAS/42 | UNEP | EE | AFR | MOZ | TAS | Refrigeration | HCFC phase-out management plan (stage II) (Additional activities to maintain energy efficiency for the servicing sector under decision 89/6(b)) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 120000 | 0 | 120000 | 0% | 120000 | 15265 | 0 | 15265 | 15265 | 0 | 0 | 30000 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | The Terms of Reference (ToR) for hiring the a national MEPs on the domestication of MEPs and development/implementation of a labelling system is underway. The project is progressing satisfactorily. | Yes
|  | MON/EEF/93/TAS/40 | UNEP | EE | ASP | MON | TAS | Refrigeration | HCFC phase-out management plan (stage II) (Additional activities to maintain energy efficiency in the refrigeration servicing (decision 89/6)) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 100000 | 0 | 100000 | 0% | 100000 | 13000 | 0 | 13000 | 13000 | 0 | 0 | 25000 | 0 | 0 |  | 0 |  | 2031-12-01 | Project newly approved at the 93rd Meeting. | SSFA was signed in March 2024 for the amount of USD 172,000 (T2+EE). First payment transferred in April 2024. NOU organized meeting with Energy Regulatory Commission during UNEP mission in May 2024, discussed project scope and collaboration between NOU and ERC, planning for activities ongoing, drafting of ToR for economic analysis ongoing. | Yes
|  | BOL/EEF/93/TAS/59 | UNIDO | EE | LAC | BOL | TAS | Refrigeration | HCFC phase-out management plan (stage II) (Additional activities to maintain energy efficiency in the refrigeration servicing sector (decision 89/6)) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 40000 | 0 | 40000 | 0% | 40000 | 5200 | 0 | 5200 | 5200 | 0 | 0 | 10000 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | Good progress. UNEP and Bolivia agreed on the 'direct implementation' modality. Currently the TOR of a consultancy to support the NOU office on the implementation of energy efficiency (EE) activities are under discussion and the consultant is planned to be hired by September 2024. | Yes
|  | GAM/EEF/93/TAS/49 | UNIDO | EE | AFR | GAM | TAS | Refrigeration | HCFC phase-out management plan (stage II) (Additional activities to maintain energy efficiency in the refrigeration servicing sector (decision 89/6)) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 55000 | 0 | 55000 | 0% | 55000 | 7150 | 0 | 7150 | 7150 | 0 | 0 | 13750 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project. | The SSFA with a total of US$55,000 was signed in March 2024. The first disbursement of US$20,000 was released to the country in April 2024. The NOU organized one public awareness campaign to educate the general public about energy-efficient practices related to refrigeration and air conditioning held in April 2024. A total of 60 participants (26 females and 34 males) were in attendance. The project is progressing successfully. | Yes
|  | GUA/EEF/93/TAS/66 | UNIDO | EE | LAC | GUA | TAS | Refrigeration | HCFC phase-out management plan (stage II) (Additional activities to maintain energy efficiency in the refrigeration servicing sector (decision 89/6)) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 40000 | 0 | 40000 | 0% | 40000 | 5200 | 0 | 5200 | 5200 | 0 | 0 | 10000 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | Good progress. UNEP and Guatemala agreed on the 'direct implementation' modality. Currently the TOR of a consultancy to support the NOU office on the implementation of energy efficiency (EE) activities are under discussion and the consultant is planned to be hired by September 2024. | Yes
|  | SIL/EEF/93/TAS/47 | UNIDO | EE | AFR | SIL | TAS | Refrigeration | HCFC phase-out management plan (stage II) (Additional activities to maintain energy efficiency in the refrigeration servicing sector (decision 89/6)) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 70000 | 0 | 70000 | 0% | 70000 | 9100 | 0 | 9100 | 9100 | 0 | 0 | 17500 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | The SSFA with a total of USD70,000 was signed by the country in April 2024. The first payment of USD30,000 was released to the country in April 2024. The NOU conducted training workshop for 20 RAC Technicians from 28-29 March 2024 at Magborakak, on best refrigeration practice, safe handling of flammable refrigerants, Leak detection, the legal provision and instrumentations. The participants were 5 female and 15 males. The NOU conducted a workshop for Customs officers and Other law Enforcement Officers at Gbalamuya on how to tackle illegal trade of ODSs, and other controlled substances covered by the Montreal Protocol, The legal provision, Safe storage of flammable and toxic refrigerants. The training was held from 11-12 April 2024. Twenty (20) participants took part in the training (14 Male and 6 Female). The NOU organized female RAC Technicians training Workshop in Makeni from the 17-19th April, 2024. Twenty Female RAC Technicians participated in the training held at the Lodge Valley Hotel in Makeni City. The Two days hands on training focused on instrumentation, safety in working with flammable refrigerants and the Montreal Protocol. The NOU with additional support by the Government of Sierra Leone via the EPA-SL conducted from 29th April – 3rd May, 2024 a certification and License training at the Government Technical Institute in Bo City . The training session was organised for RAC technicians in the Southern Region and some part of the Eastern Region A total of ten (10) RAC technicians were certified (9 Male and 1 Female). The training covers a range of topic e.g. Refrigerants recovery, Leak detection, handling of flammable refrigerants, other good refrigeration practices, First aid in case of an accident/emergency during work and legal provisions to enhance compliance. The project is progressing satisfactorily. | Yes
|  | BKF/PHA/92/TAS/47 | UNIDO | HPMP2 | AFR | BKF | TAS | FOAM | HCFC phase-out management plan (stage II, first tranche) | 2023-06-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 1.3 | 0 | [6 empty] | 125000 | 0 | 125000 | 0% | 125000 | 15536 | 0 | 15536 | 15536 | 0 | 0 | 43750 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project. | The SSFA was signed in January 2024. The first payment was released to the country in January 2024. | Yes
|  | GUI/PHA/93/TAS/42 | UNIDO | HPMP2 | AFR | GUI | TAS | AC | HCFC phase-out management plan (stage II, first tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0.9 | 0 | [6 empty] | 81000 | 0 | 81000 | 0% | 81000 | 10530 | 0 | 10530 | 10530 | 0 | 0 | 20250 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project. | The SSFA of HPMP Stage II, first tranche was signed by UNEP and the Government of Guinea in March 2024. The first tranche was sent in May 2024. Licensing system is fully operational. Coordinated with all stakeholders. | Yes
|  | MOZ/PHA/93/TAS/41 | UNIDO | HPMP2 | AFR | MOZ | TAS | AC | HCFC phase-out management plan (stage II, first tranche) | 2023-12-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0.6 | 0 | [6 empty] | 195000 | 0 | 195000 | 0% | 195000 | 24804 | 0 | 24804 | 24804 | 0 | 0 | 48750 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved | The SSFA with a total of US$ 195,000 was prepared and sent to country for signature. The licensing and quota system is in place and functioning. The collection of data was undertaken to report A7 and CP data for the year 2023. | Yes
|  | SUR/PHA/93/TAS/34 | UNIDO | HPMP2 | LAC | SUR | TAS | AC | HCFC phase-out management plan (stage II, first tranche) | 2023-12-01 | 2026-09-01 | ONG |  | 2026-09-01 |  |  | 0.5 | 0 | [6 empty] | 166100 | 0 | 166100 | 0% | 166100 | 21593 | 0 | 21593 | 21593 | 0 | 0 | 41525 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project. | SSFA drafted and shared with Country, details to be negotiated. SSFA expected to be signed by May 2024, based on the level of response by the new Focal Point. | Yes
|  | BAH/PHA/93/TAS/45 | UNIDO | HPMP2 | ASP | BAH | TAS | AC | HCFC phase-out management plan (stage II, second tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 79500 | 0 | 79500 | 0% | 79500 | 10335 | 0 | 10335 | 10335 | 0 | 0 | 19875 | 0 | 0 |  | 0 |  | 2026-12-01 | New approval at ExCom-93 in Nov. 2023. Required arrangements for inititting the project implementation have been taken. | Progress: Two contracts signed in Mar 2024 with SCE and BSE for the implementation of the second tranche (US$ 50,000 for BSE and US$ 26,500 for SCE). Project is progressing satisfactorily. A training of 40 technicians for category II has been completed. 40 customs officers have been trained in two workshops. the national technical committee that has been established to review and update related standards is functioning. | Yes
|  | BOL/PHA/93/TAS/54 | UNIDO | HPMP2 | LAC | BOL | TAS | Refrigeration | HCFC phase-out management plan (stage II, second tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0.3 | 0 | [6 empty] | 32500 | 0 | 32500 | 0% | 32500 | 4225 | 0 | 4225 | 4225 | 0 | 0 | 8125 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | Good progress. Implementation modality is under discussion with the NOU. A mix between direct and indirect implementation modality has been agreed and the TOR for the first consultancy contracts will be prepared with in the Q4 2024. | Yes
|  | GAM/PHA/93/TAS/47 | UNEP | HPMP2 | AFR | GAM | TAS | Refrigeration | HCFC phase-out management plan (stage II, second tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0.2 | 0 | [6 empty] | 90000 | 0 | 90000 | 0% | 90000 | 11700 | 0 | 11700 | 11700 | 0 | 0 | 22500 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | The SSFA with a total of US$90,000 was prepared and sent to country for signature in March 2024. The licensing and quota system is in place and functioning. The collection of data was undertaken to report A7 and CP data for the year 2023. The project is progressing successfully. | Yes
|  | GUA/PHA/93/INV/62 | UNEP | HPMP2 | LAC | GUA | INV | Refrigeration | HCFC phase-out management plan (stage II, second tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0.3 | 0 | [6 empty] | 36000 | 0 | 36000 | 0% | 36000 | 4680 | 0 | 4680 | 4680 | 0 | 0 | 9000 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | Good progress. Work plan and timetable to implement the project agreed with the NOU. SSFA-2024-04 is under discussion. This SSFA will facilitate obtaining products and expected results as mentioned below:(1) Adoption/enforcement of Montreal Protocol Controlled Substances laws and regulations to control and monitor the consumption of Montreal Protocol Controlled Substances, (2) Efficient and timely data collection and reporting, (3) Intra- and inter-institutional coordination to implement the Montreal Protocol with other organizations/national stakeholders, (4) Supervision of timely execution of activities to eliminate and reduce the consumption of Substances controlled by the Montreal Protocol, (5) Increase awareness raising and information exchange, (6) Regional cooperation and participation in Montreal Protocol meetings. | Yes
|  | HON/PHA/92/TAS/57 | UNEP | HPMP2 | LAC | HON | TAS | Refrigeration | HCFC phase-out management plan (stage II, second tranche) | 2023-06-01 | 2025-09-01 | ONG |  | 2025-09-01 |  |  | 0.6 | 0 | [6 empty] | 36500 | 0 | 36500 | 0% | 36500 | 4745 | 0 | 4745 | 4745 | 0 | 0 | 12775 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | Good progress. UNEP and Honduras agreed on the 'direct implementation' modality. Currently the TOR of two consultancies to support the implementation of Honduras HPMP II tranche 2 are under discussion. The consultants will be support the implementation of the implementation of the following activities. 1) Strengthening the regulatory framework: formulate measures for handling HCFC-based equipment/products and substances during their import, use, and final disposal. 2) Strengthening the national capacity of customs and trade controls: conduct an updated training on ODS import control for 120 customs and enforcement officers, brokers and importers; update the online training modules for customs officers. | Yes
|  | MLW/PHA/92/TAS/55 | UNEP | HPMP2 | AFR | MLW | TAS | Refrigeration | HCFC phase-out management plan (stage II, second tranche) | 2023-06-01 | 2026-06-01 | ONG |  | 2026-06-01 |  |  | 2 | 0 | [6 empty] | 140000 | 0 | 140000 | 0% | 140000 | 17697 | 0 | 17697 | 17697 | 0 | 140000 | 49000 | 0 | 17697 |  | 80000 |  | 2031-12-01 | Newly approved project | The SSFA with a total of US$ 140,000 was signed in October 2023. The first disbursement of US$80,000 was released to the country in November 2023. The NOU conducted three training session for refrigeration experts on safe handling of flammable and toxic refrigerants held from 26-27th May in Lilongwe;7th to 9th June;28th to 30th August in Mzuzu. A total of 60 refrigeration technicians (44 Males and 16 Females) were trained. The training enhanced the capacity of refrigeration servicing experts on handling new alternative technologies and also reducing emissions of controlled substances. The NOU conducted two training sessions for enforcement officers on monitoring imports of controlled substances and prevention of illegal trade from 20th to 22nd March in Blantyre and 29th to 31st May in Mzuzu. A total 45 custom officers were trained, and their capacity was strengthened on monitoring controlled substances. The capacity building of enforcement officers has assisted in preventing illegal trade on these substances. The project is progressing satisfactorily. | Yes
|  | MON/PHA/93/TAS/39 | UNEP | HPMP2 | ASP | MON | TAS | Refrigeration | HCFC phase-out management plan (stage II, second tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 92000 | 0 | 92000 | 0% | 92000 | 11960 | 0 | 11960 | 11960 | 0 | 0 | 23000 | 0 | 0 |  | 0 |  | 2031-12-01 | Project newly approved at the 93rd Meeting. | SSFA was signed in March 2024 for the amount of USD 172,000 (T2+EE). First payment transferred in April 2024. NOU in collaboration with Customs is organizing one custom training in June. | Yes
|  | NIC/PHA/92/TAS/47 | UNEP | HPMP2 | LAC | NIC | TAS | Refrigeration | HCFC phase-out management plan (stage II, second tranche) | 2023-06-01 | 2026-06-01 | ONG |  | 2026-06-01 |  |  | 0.5 | 0 | [6 empty] | 55932 | 0 | 55932 | 0% | 55932 | 7271 | 0 | 7271 | 7271 | 0 | 0 | 19576.2 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | Good progress. Work plan and timetable to implement the project agreed with the NOU. SSFA-2024-04 is under discussion. This SSFA will facilitate obtaining products and expected results as mentioned below: 1) Organizing a training course for 20 customs officers and 20 brokers, distributors, and importers on HS codes and the prevention of illegal trade; and three coordination meetings with stakeholders on controlling imports of HCFC-based RAC equipment. 2) Conducting an awareness-raising campaign to encourage the certification of technicians and good refrigeration practices; and two training seminars for large RAC end-users on servicing with low-GWP technologies and good refrigeration practices 3) Project monitoring and implementation | Yes
|  | QAT/PHA/93/TAS/29 | UNEP | HPMP2 | ASP | QAT | TAS | Refrigeration | HCFC phase-out management plan (stage II, second tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 4.5 | 0 | [6 empty] | 144500 | 0 | 144500 | 0% | 144500 | 18785 | 0 | 18785 | 18785 | 0 | 0 | 36125 | 0 | 0 |  | 0 |  | 2027-12-01 | Newly approved project. | Progress report: -Legal Instrument: SSFA has been prepared and shared with the NOU for their consent and signature along with the implementation plan; - Overall assessment of project progress: Project is progressing | Yes
|  | SIL/PHA/93/TAS/45 | UNEP | HPMP2 | AFR | SIL | TAS | Refrigeration | HCFC phase-out management plan (stage II, second tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0.1 | 0 | [6 empty] | 90000 | 0 | 90000 | 0% | 90000 | 11700 | 0 | 11700 | 11700 | 0 | 0 | 22500 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | The SSFA with a total of US$ 90,000 was signed by country in April 2024. The first disbursement of USD 50,000 was released to the country in April 2024. The licensing and quota system is in place and functioning. The allocated HCFC quota for the year 2024 is 9.02 tons. The collection of data was undertaken to report A7 and CP data for the year 2023. CP Data for 2023 was submitted on 18th April 2024, and A7 data on 6th May 2024. The project is progressing satisfactorily | Yes
|  | TUN/PHA/92/TAS/81 | UNEP | HPMP2 | AFR | TUN | TAS | Refrigeration | HCFC phase-out management plan (stage II, second tranche) | 2023-06-01 | 2025-06-01 | ONG |  | 2025-06-01 |  |  | 2.8 | 0 | [6 empty] | 100000 | 0 | 100000 | 0% | 100000 | 13000 | 0 | 13000 | 13000 | 0 | 100000 | 35000 | 0 | 13000 |  | 50000 |  | 2026-12-01 | The SSFA was signed in November 2023. The first payment has been released to the country in November 2023. | OzonAction has requested the interim progress report, which is due in May 2024. The country is preparing the report and will submit it to CAP in June 2024. | Yes
|  | ZIM/PHA/92/TAS/68 | UNEP | HPMP2 | AFR | ZIM | TAS | Refrigeration | HCFC phase-out management plan (stage II, second tranche) | 2023-06-01 | 2027-06-01 | ONG |  | 2027-06-01 |  |  | 3.2 | 0 | [6 empty] | 192500 | 0 | 192500 | 0% | 192500 | 23591 | 0 | 23591 | 23591 | 0 | 192500 | 67375 | 0 | 23591 |  | 92500 |  | 2031-12-01 | The first disbursement of USD92,500 was released to the country in October 2023. The NOU is working with SAZ, DOE, RAC Associations, Customs Officers and other stakeholders to implement the MEPS The NOU conducted a total of fourteen training workshops on safe use of Hydrocarbon refrigerants and a total of were 341 RAC technicians were trained (214 males and 127 females). These were conducted in Harare, Bulawayo, Chegutu, Chinhoyi, Masvingo, Marondera, KweKwe and Kadoma. The project is progressing satisfactorily. | The Licensing system is fully operational. The Quota allocations for 2024 were issued to importers in line with the phase out measures under the Montreal Protocol and with the agreement between the Government of Zimbabwe and the Multilateral Fund. The collection of data was undertaken to report A7 and CP data for the year 2023. A7 data for 2023 was reported on 12th April 2024; CP data for 2023 was reported on 12th April 2024. The project is progressing satisfactorily. | Yes
|  | MLW/EEF/92/TAS/56 | UNIDO | HPMP2 | AFR | MLW | TAS | SERVCEE-89/6 | HCFC phase-out management plan (stage II, second tranche) (energy efficiency - related activities under decision 89/6) | 2023-06-01 | 2026-06-01 | ONG |  | 2026-06-01 |  |  | 0 | 0 | [6 empty] | 120000 | 0 | 120000 | 0% | 120000 | 15169 | 0 | 15169 | 15169 | 0 | 120000 | 42000 | 0 | 15169 |  | 0 |  | 2031-12-01 | The SSFA with a total of US$ 120,000 was signed in October 2023. The first disbursement of US$70,000 was released to the country in November 2023. The draft Regulations that have incorporated provisions under Kigali Amendment is being finalized by Ministry of Justice. The overall performance of the project is satisfactory. The project is progressing satisfactorily. | The NOU conducted one training session for refrigeration experts from 15th to 17th April in Lilongwe. A total of 22 (14 males and 8 females) were trained on ozone and climate friendly activities. Stakeholder consultation meeting was conducted from 16th to 18th January. The participants were drawn from local councils and were sensitized on the phase out of HCFCs. A total of 35 officers (15 females and 20 males) participated at this meeting. | Yes
|  | NIC/EEF/92/TAS/50 | UNIDO | HPMP2 | LAC | NIC | TAS | SERVCEE-89/6 | HCFC phase-out management plan (stage II, second tranche) (energy efficiency - related activities under decision 89/6) | 2023-06-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 51000 | 0 | 51000 | 0% | 51000 | 6630 | 0 | 6630 | 6630 | 0 | 0 | 17850 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | Good progress. UNEP and Nicaragua agreed on the 'direct implementation' modality. Currently the TOR of a consultancy to support the NOU office on the implementation of energy efficiency (EE) activities are under discussion and the consultant is planned to be hired by September 2024. | Yes
|  | ZIM/EEF/92/TAS/69 | UNIDO | HPMP2 | AFR | ZIM | TAS | SERVCEE-89/6 | HCFC phase-out management plan (stage II, second tranche) (energy efficiency - related activities under decision 89/6) | 2023-06-01 | 2027-06-01 | ONG |  | 2027-06-01 |  |  | 0 | 0 | [6 empty] | 120000 | 0 | 120000 | 0% | 120000 | 14706 | 0 | 14706 | 14706 | 0 | 120000 | 42000 | 0 | 14706 |  | 0 |  | 2031-12-01 | The first disbursement USD 70,000 was released to the country in October 2023. A total of 35 import permits were issued to importers of HCFCs, HFCs and appliances that contain these substances. The HCFC and HFC dependent appliances included mainly refrigerated trucks, refrigeration accessories such as compressors, among others. The NOU conducted public awareness campaign to educate the public on the importance and benefits of energy-efficient appliances. The project is progressing satisfactorily. | The Terms of Reference (ToR) for hiring a national MEPs on the domestication of MEPs and development/implementation of a labelling system is underway. The project is progressing satisfactorily. | Yes
|  | HON/EEF/92/TAS/60 | UNIDO | HPMP2 | LAC | HON | TAS | SERVCEE-89/6 | HCFC phase-out management plan (stage II, second tranche) (energy efficiency - related activitites under decision 89/6) | 2023-06-01 | 2025-09-01 | ONG |  | 2025-09-01 |  |  | 0 | 0 | [6 empty] | 40000 | 0 | 40000 | 0% | 40000 | 5200 | 0 | 5200 | 5200 | 0 | 0 | 14000 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | Good progress. UNEP and Honduras agreed on the 'direct implementation' modality. Currently the TOR of a consultancy to support the NOU office on the implementation of energy efficiency (EE) activities are under discussion and the consultant is planned to be hired by September 2024. | Yes
|  | CPR/PHA/93/TAS/620 | UNEP | HPMP2 | ASP | CPR | TAS | Refrigeration | HCFC phase-out management plan (stage II, sixth tranche) (refrigeration servicing sector and national enabling programme) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 73.3 | 0 | [6 empty] | 2000000 | 0 | 2000000 | 0% | 2000000 | 219467 | 0 | 219467 | 219467 | 0 | 0 | 500000 | 0 | 0 |  | 0 |  | 2027-12-01 | The project was newly approved at the 93rd ExCom. | PCA with FECO was signed in April 2024 for a total budget of $1,820,000. PCA with CRAA signed for $60,000 in April 2024. 2024 Ozone2Climate Event held. | Yes
|  | GUY/PHA/92/TAS/35 | UNEP | HPMP2 | LAC | GUY | TAS | Refrigeration | HCFC phase-out management plan (stage II, third tranche) | 2023-06-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0.1 | 0 | [6 empty] | 45500 | 0 | 45500 | 0% | 45500 | 5915 | 0 | 5915 | 5915 | 0 | 0 | 15925 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project. | The SSFA was signed in March 2024. The first payment is preparing to be disbursed. The NOU has an agreed work plan and is preparing to conduct activities related to: Improved policy, legislative and regulatory framework; and, public and stakeholders’ awareness. | Yes
|  | DOM/PHA/92/TAS/75 | UNEP | HPMP3 | LAC | DOM | TAS | Refrigeration | HCFC phase-out management plan (stage III, second tranche) | 2023-06-01 | 2026-06-01 | ONG |  | 2026-06-01 |  |  | 1.5 | 0 | [6 empty] | 111160 | 0 | 111160 | 0% | 111160 | 14451 | 0 | 14451 | 14451 | 0 | 0 | 38906 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | Good progress. Work plan and timetable to implement the project agreed with the NOU. SSFA-2023-08 has been signed in January 2024 with an overall amount of USD 111,160 payable in three disbursements. First disbursement with an amount of USD 55,580 has been received by the country in March 2024. This SSFA will facilitate obtaining products and expected results as mentioned below: 1)Certification system for technicians in the RAC sector 2) Safety standards/guidelines for flammable refrigerants. | Yes
|  | OMA/PHA/93/TAS/47 | UNEP | HPMP3 | ASP | OMA | TAS | Refrigeration | HCFC phase-out management plan (stage III, second tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 2.6 | 0 | [6 empty] | 116000 | 0 | 116000 | 0% | 116000 | 14612 | 0 | 14612 | 14612 | 0 | 0 | 29000 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project. | Progress report: -Legal Instrument: SSFA has been prepared and shared with the NOU for their consent and signature along with the implementation plan; - Overall assessment of project progress: Project is progressing | Yes
|  | NER/KIP/93/TAS/49 | UNEP | KIP1 | AFR | NER | TAS | AC | Kigali HFC implementation plan (stage I) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 5.8 | 0 | [6 empty] | 15000 | 0 | 15000 | 0% | 15000 | 1950 | 0 | 1950 | 1950 | 0 | 0 | 3750 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | The SSFA was signed by both in April 2024. The first payment was disbursed in May 2024. HFC Licensing system is fully operational. The country submitted the HFC Art7 data to the secretariat in May 2024. | Yes
|  | ALB/KIP/93/TAS/53 | UNEP | KIP1 | EUR | ALB | TAS | AC | Kigali HFC implementation plan (stage I, first tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 5.4 | 0 | [6 empty] | 50000 | 0 | 50000 | 0% | 50000 | 6500 | 0 | 6500 | 6500 | 0 | 0 | 12500 | 0 | 0 |  | 0 |  | 2031-12-01 | Project approved in December 2023. | SSFA signed in April 2024 and release of payment 1 of USD 20,000 initiated. | Yes
|  | BOL/KIP/93/TAS/60 | UNEP | KIP1 | LAC | BOL | TAS | AC | Kigali HFC implementation plan (stage I, first tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 6.3 | 0 | [6 empty] | 40500 | 0 | 40500 | 0% | 40500 | 5265 | 0 | 5265 | 5265 | 0 | 0 | 10125 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | Good progress. Implementation modality is under discussion with the NOU. A mix between direct and indirect implementation modality has been agreed and the TOR for the first consultancy contracts will be prepared with in the Q4 2024. | Yes
|  | KAM/KIP/93/TAS/45 | UNEP | KIP1 | ASP | KAM | TAS | AC | Kigali HFC implementation plan (stage I, first tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 22.8 | 0 | [6 empty] | 126300 | 0 | 126300 | 0% | 126300 | 16419 | 0 | 16419 | 16419 | 0 | 0 | 31575 | 0 | 0 |  | 0 |  | 2030-12-01 | Newly approved project at the Excom-93 in December 2023. | UNEP discussed with the NOU to develop the workplan, which was finalized and agreed by NOU. The draft SSFA was submitted to the Government for review and agreement. | Yes
|  | CHI/KIP/93/TAS/212 | UNEP | KIP1 | LAC | CHI | TAS | AC | Kigali HFC implementation plan (stage I, first tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 22.1 | 0 | [6 empty] | 123900 | 0 | 123900 | 0% | 123900 | 16107 | 0 | 16107 | 16107 | 0 | 0 | 30975 | 0 | 0 |  | 0 |  | 2030-12-01 | Newly approved project | Implementation modalites, i.e. consultancies and/or SSFAs are under discussion with Government. Mission was organsed in May-2024 | Yes
|  | PRC/KIP/93/TAS/40 | UNEP | KIP1 | AFR | PRC | TAS | AC | Kigali HFC implementation plan (stage I, first tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 8.4 | 0 | [6 empty] | 13750 | 0 | 13750 | 0% | 13750 | 1788 | 0 | 1788 | 1788 | 0 | 0 | 3437.5 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project. | OzonAction has prepared and sent the SSFA to the country for the signature in March 2024. The country has notified that the document is still undergoing administrative procedures. | Yes
|  | DOM/KIP/93/TAS/80 | UNEP | KIP1 | LAC | DOM | TAS | AC | Kigali HFC implementation plan (stage I, first tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 21.5 | 0 | [6 empty] | 120774 | 0 | 120774 | 0% | 120774 | 15701 | 0 | 15701 | 15701 | 0 | 0 | 30193.5 | 0 | 0 |  | 0 |  | 2030-12-01 | Newly approved project | Good progress. Implementation modality is under discussion with the NOU. A mix between direct and indirect implementation modality has been agreed and the TOR for the first consultancy contracts will be prepared with in the Q4 2024. | Yes
|  | GHA/KIP/93/TAS/57 | UNIDO | KIP1 | AFR | GHA | TAS | AC | Kigali HFC implementation plan (stage I, first tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 86.6 | 0 | [6 empty] | 51000 | 0 | 51000 | 0% | 51000 | 6630 | 0 | 6630 | 6630 | 0 | 0 | 12750 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | The NOU held one consultative meeting with stakeholders to develop import quotas for RAC equipment. The licensing system is fully operational. The collection of data was undertaken to report A7 and CP data for the year 2023. The project is progressing successfully. | Yes
|  | GRN/KIP/93/TAS/35 | UNIDO | KIP1 | LAC | GRN | TAS | AC | Kigali HFC implementation plan (stage I, first tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0.5 | 0 | [6 empty] | 27500 | 0 | 27500 | 0% | 27500 | 3575 | 0 | 3575 | 3575 | 0 | 0 | 6875 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | SSFA has been drafted and negotiated with the Country which has agreed with the proposed work plan. The SSFA has been submitted for signing to the Government representative in April. The signed SSFA is expected to be sent to UNEP by June 2024. | Yes
|  | KYR/KIP/93/TAS/52 | UNIDO | KIP1 | EUR | KYR | TAS | AC | Kigali HFC implementation plan (stage I, first tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 3.3 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 0 | 7500 | 0 | 0 |  | 0 |  | 2030-12-01 | Project approved in December 2023. | SSFA signed in February 2024 and payment 1 of USD 20,000 released in April 2024. | Yes
|  | MLW/KIP/93/TAS/57 | UNIDO | KIP1 | AFR | MLW | TAS | Refrigeration | Kigali HFC implementation plan (stage I, first tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 28.2 | 0 | [6 empty] | 39000 | 0 | 39000 | 0% | 39000 | 5070 | 0 | 5070 | 5070 | 0 | 0 | 9750 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | The SSFA with a total of US$39,000 was signed in March 2024. The first disbursement of US$25,000 was released to the country in April 2024. Malawi ratified the Kigali amendment in 2017. One training session for refrigeration experts was conducted from 15th to 17th April in Lilongwe. A total of 22 (14 males and 8 females) were trained on ozone and climate friendly activities. The project is progressing successfully | Yes
|  | NIC/KIP/93/TAS/55 | UNIDO | KIP1 | LAC | NIC | TAS | Refrigeration | Kigali HFC implementation plan (stage I, first tranche) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 3.5 | 0 | [6 empty] | 40000 | 0 | 40000 | 0% | 40000 | 5200 | 0 | 5200 | 5200 | 0 | 0 | 10000 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | The consultant contract for a international consultant have been discussed by the end of April 2024 that will support the implementation of UNEP projects for the Latin American region. | Yes
|  | GHA/KIP/93/TAS/58 | UNIDO | KIP1 | AFR | GHA | TAS | Refrigeration | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 7.6 | 0 | [6 empty] | 4500 | 0 | 4500 | 0% | 4500 | 585 | 0 | 585 | 585 | 0 | 0 | 1125 | 0 | 0 |  | 0 |  | 2031-12-01 | Newly approved project | The NOU held one consultative meeting with stakeholders to develop import quotas for RAC equipment. The licensing system is fully operational. The collection of data was undertaken to report A7 and CP data for the year 2023. The project is progressing successfully. | Yes
|  | MEX/KIP/93/TAS/212 | UNIDO | KIP1 | LAC | MEX | TAS | Refrigeration | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 2.4 | 0 | [6 empty] | 12695 | 0 | 12695 | 0% | 12695 | 1574 | 0 | 1574 | 1574 | 0 | 0 | 3173.75 | 0 | 0 |  | 0 |  | 2030-12-01 | Newly approved project | Implementation modalites, i.e. consultancies and/or SSFAs are under discussion with Government. Mission Planned for May-2024 | Yes
|  | VIE/KIP/93/TAS/98 | UNIDO | KIP1 | ASP | VIE | TAS | Refrigeration | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 5.8 | 0 | [6 empty] | 35533 | 0 | 35533 | 0% | 35533 | 4244 | 0 | 4244 | 4244 | 0 | 0 | 8883.25 | 0 | 0 |  | 0 |  | 2030-12-01 | The newly approved project at the Excom-93 in December 2023. | UNEP discussed with the NOU to develop the workplan. UNEP conducted a country mission in April 2024 and obtained agreement with the Government on workplan and budget, which will be used to finalize the Project Corporation Agreement (PCA). | Yes
|  | MEX/KIP/93/TAS/211 | UNEP | KIP1 | LAC | MEX | TAS | Refrigeration | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 40.6 | 0 | [6 empty] | 215100 | 0 | 215100 | 0% | 215100 | 26669 | 0 | 26669 | 26669 | 0 | 0 | 53775 | 0 | 0 |  | 0 |  | 2030-12-01 | Newly approved project | Implementation modalites, i.e. consultancies and/or SSFAs are under discussion with Government. Mission was held in May-2024 | Yes
|  | VIE/KIP/93/TAS/97 | UNEP | KIP1 | ASP | VIE | TAS | Refrigeration | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 69.7 | 0 | [6 empty] | 426163 | 0 | 426163 | 0% | 426163 | 50906 | 0 | 50906 | 50906 | 0 | 0 | 106540.75 | 0 | 0 |  | 0 |  | 2030-12-01 | The newly approved project at the Excom-93 in December 2023. | UNEP discussed with the NOU to develop the workplan. UNEP conducted a country mission in April 2024 and obtained agreement with the Government on workplan and budget, which will be used to finalize the Project Corporation Agreement (PCA). | Yes
|  | KYR/EEF/93/DEM/51 | UNEP | EE | EUR | KYR | DEM | AC | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 206000 | 0 | 206000 | 0% | 206000 | 26780 | 0 | 26780 | 26780 | 0 | 0 | 51500 | 0 | 0 |  | 0 |  |  | Project approved in December 2023. | SSFA signed in February 2024 and payment 1 of USD 67,000 released in April 2024. | Yes
|  | NIC/EEF/93/DEM/54 | UNEP | EE | LAC | NIC | DEM | AC | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 0 | 7500 | 0 | 0 |  | 0 |  |  | Newly approved project | Good progress. UNEP and Honduras agreed on the 'direct implementation' modality. Currently the TOR of a consultancy to support the NOU office on the implementation of energy efficiency (EE) activities are under discussion and the consultant is planned to be hired by September 2024. | Yes
|  | BDI/KIP/92/PRP/43 | UNEP | KIPIND | AFR | BDI | PRP | Refrigeration | Preparation of a Kigali HFC implementation plan | 2023-06-01 | 2025-06-01 | ONG |  | 2025-06-01 |  |  | 0 | 0 | [6 empty] | 119000 | 0 | 119000 | 0% | 119000 | 15470 | 0 | 15470 | 15470 | 0 | 0 | 41650 | 0 | 0 |  | 0 |  |  | Newly approved project. OzonAction prepared the SSFA. SSFA not yet signed. | SSFA drafted and waiting for signature from the country. The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management on 18 April 2024. International consultant identified. | Yes
|  | ERI/KIP/93/PRP/27 | UNEP | KIPIND | AFR | ERI | PRP | Refrigeration | Preparation of a Kigali HFC implementation plan (stage I) | 2023-12-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 91000 | 0 | 91000 | 0% | 91000 | 11830 | 0 | 11830 | 11830 | 0 | 0 | 22750 | 0 | 0 |  | 0 |  |  | Newly approved project | The SSFA of USD91,000 was signed by the country in March 2024. The first payment of USD40,000 was released to the country in April 2024. The terms of reference (TOR) for consultancy services to prepare a national survey on ODS alternatives have been developed. The process of hiring a competent consultant to carry out this task is underway. The project is progressing successfully. | Yes
|  | GEO/KIP/93/PRP/47 | UNEP | KIPIND | EUR | GEO | PRP | Refrigeration | Preparation of a Kigali HFC implementation plan (stage I) | 2023-12-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 130000 | 0 | 130000 | 0% | 130000 | 16900 | 0 | 16900 | 16900 | 0 | 0 | 32500 | 0 | 0 |  | 0 |  |  | Project approved in December 2023. | SSFA with REC Caucasus signed in February 2024 and payment 1 of USD 48,000 released in April 2024. | Yes
|  | KEN/KIP/93/PRP/70 | UNEP | KIPIND | AFR | KEN | PRP | Refrigeration | Preparation of a Kigali HFC implementation plan (stage I) | 2023-12-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 95000 | 0 | 95000 | 0% | 95000 | 12350 | 0 | 12350 | 12350 | 0 | 0 | 23750 | 0 | 0 |  | 0 |  |  | Newly approved project | The coordinating meeting between UNEP, GIZ and the Government was organized. The project is progressing successfully. The NOU is in a process to recruit national consultants to organize the data collection. | Yes
|  | MLI/KIP/93/PRP/48 | UNEP | KIPIND | AFR | MLI | PRP | Refrigeration | Preparation of a Kigali HFC implementation plan (stage I) | 2023-12-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 135000 | 0 | 135000 | 0% | 135000 | 17550 | 0 | 17550 | 17550 | 0 | 0 | 33750 | 0 | 0 |  | 0 |  |  | Newly approved project. | SSFA drafted and waiting for signature from the country. The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management on 30 April 2024. International consultant identified. | Yes
|  | MOL/KIP/93/PRP/49 | UNEP | KIPIND | EUR | MOL | PRP | Refrigeration | Preparation of a Kigali HFC implementation plan (stage I) | 2023-12-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 130000 | 0 | 130000 | 0% | 130000 | 16900 | 0 | 16900 | 16900 | 0 | 0 | 32500 | 0 | 0 |  | 0 |  |  | Project approved in December 2023. | SSFA signed in February 2024 and payment 1 of USD 42,500 released in March 2024. International policy expert engaged in March 2024 to review legislation, progress and verification reports and to draft recommendations for KIP preparation. TOR for international KIP experts submitted for approval in April 2024 to draft Moldova's KIP and energy-efficiency pilot project. | Yes
|  | STV/KIP/93/PRP/29 | UNDP | KIPIND | LAC | STV | PRP | Refrigeration | Preparation of a Kigali HFC implementation plan (stage I) | 2023-12-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 70000 | 0 | 70000 | 0% | 70000 | 9100 | 0 | 9100 | 9100 | 0 | 0 | 17500 | 0 | 0 |  | 0 |  |  | Newly approved project | SSFA has been drafted and negotiated with the Country which has agreed with the proposed work plan. The SSFA has been submitted for signing to the Government representative. The SSFA has to be reviwed and approved by the Country's Cabinet of Ministers which is forseen to the length of time needed for signature. The SSFA is expected to be signed during the 3rd Quarter of 2024. | Yes
|  | SSD/PHA/93/PRP/09 | UNDP | HPMPIND | AFR | SSD | PRP | Refrigeration | Preparation of an HCFC phase-out management plan (stage II) (Overarching) | 2023-12-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 20000 | 0 | 20000 | 0% | 20000 | 2600 | 0 | 2600 | 2600 | 0 | 0 | 5000 | 0 | 0 |  | 0 |  |  | Newly approved project | The SSFA was signed in July 2024. The first payment of USD 12,000 was made in August 2024. The country is in the process of preparation of HPMP stage II. The project is progressing satisfactorily. | Yes
|  | ALB/PHA/92/PRP/49 | UNDP | HPMPIND | EUR | ALB | PRP | Refrigeration | Preparation of HCFC phase-out management plan (stage III) (Overarching) | 2023-06-01 | 2025-06-01 | ONG |  | 2025-06-01 |  |  | 0 | 0 | [6 empty] | 10000 | 0 | 10000 | 0% | 10000 | 1300 | 0 | 1300 | 1300 | 0 | 9900 | 3500 | 0 | 1287 |  | 0 |  |  | International expert to prepare UNEP's components was engaged in December 2023. | UNEP's input with proposed components was prepared in consultation with Albania's Montreal Protocol Focal Point and shared with the lead agency UNIDO. | Yes
|  | KIR/SEV/92/INS/19 | UNDP | Government Support | ASP | KIR | INS | National Ozone Unit | Renewal of institutional strengthening project (phase IX: 1/2024-12/2026) | 2023-06-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 63000 | 0 | 0 |  | 0 |  |  | The project was newly approved at the 92nd Executive Committee meeting in June 2023. UNEP worked with the NOU to prepare the project plan and SSFA. The workplan incorporated gender mainstreaming. | UNEP and the country are preparing the project plan and SSFA for finalization and signing. There has been a delay in the finalization of the SSFA due to the absence of the NOO and confirming commitment of the Government to recruit the successor of the NOO to resume project implementation. Despite the delay in signing of the SSFA, the Government assigned officer-in-charge who is the ex-NOO of Kiribati to temporary take care of the project. The Government continues to enforce HCFC/HFC quota and licensing system. The 2024 HCFC quota is 0.45 MT. HFC quota system has been implemented with the allocated amount of 8,176 tonnes CO2 equivalent distributed to authorized importers. CP data for the year 2023 collection has been completed and will be submitted by May. The Government plans to conduct quarterly inspections and the steering committee meetings twice a year. The Prior to departure from the NOU, the firmer NOO participated the Twinning Workshop of Montreal Protocol Officers, Energy-Efficiency Policy Makers and Financial Mechanisms Focal Points to Support Kigali Amendment Objectives, Thematic Workshop on Establishment and Implementation of Competency- based Certification, Thematic Workshop on Strategy of Stage I of the KIP and Integration with the HPMP Stage II for Pacific Island Countries from 5-10 February 2024 in Cook Islands. In June 2024 in Palau. The officer-in-charge will participate in the regional network meeting and thematic workshop on finalization of KIP Stage I in Palau in June 2024. | Yes
|  | FSM/SEV/93/INS/18 | UNDP | Government Support | ASP | FSM | INS | National Ozone Unit | Renewal of institutional strengthening project (phase IX: 7/2024-6/2026) | 2023-12-01 | 2026-06-01 | ONG |  | 2027-06-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  |  | The project was newly approved at the 93rd Executive Committee meeting in December 2023. UNEP worked with the NOU to prepare the project plan and SSFA. The workplan incorporated gender mainstreaming. | UNEP discussed with the NOU to develop the workplan, which was finalized and agreed by NOU. The draft SSFA was submitted to the Government for review and agreement. UNEP is waiting for the NOU to confirm agreement on SSFA. Project implementation will commence from July 2024. | Yes
|  | TON/SEV/92/INS/19 | UNDP | Government Support | ASP | TON | INS | National Ozone Unit | Renewal of institutional strengthening project (phase X: 1/2024-12/2026 | 2023-06-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 63000 | 0 | 0 |  | 0 |  |  | The project was approved at the 92nd Executive Committee meeting in June 2023. UNEP worked with the NOU to prepare the project plan and SSFA. The workplan incorporated gender mainstreaming. | The SSFA was signed in February 2024. The first payment of US$ 62,000 was released in March 2024. The NOU continues to enforce HCFC/HFC quota and licensing system. The HFC quota system has been implemented with the allocated amount of 7,677 tonnes CO2 equivalent. CP data for the year 2023 collection has been completed and will be submitted by May. The NOU participated the Twinning Workshop of Montreal Protocol Officers, Energy-Efficiency Policy Makers and Financial Mechanisms Focal Points to Support Kigali Amendment Objectives, Thematic Workshop on Establishment and Implementation of Competency- based Certification, Thematic Workshop on Strategy of Stage I of the KIP and Integration with the HPMP Stage II for Pacific Island Countries from 5-10 February 2024 in Cook Islands. In June 2024 in Palau, the country will participate in the regional network meeting, regional training of NOUs, and thematic workshop on finalization of KIP Stage I. | Yes
|  | MAG/SEV/93/INS/39 | UNDP | Government Support | AFR | MAG | INS | National Ozone Unit | Renewal of institutional strengthening project (phase X: 1/2024-12/2026) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  |  | Newly approved project. | The SSFA of IS was signed by UNEP and the Government of Madagascar in March 2024. The first tranche was sent in May 2024. Licensing system is fully operational. Stakeholder consultation to review the draft procedure: National data collection. | Yes
|  | TTR/SEV/92/INS/19 | UNDP | Government Support | ASP | TTR | INS | National Ozone Unit | Renewal of institutional strengthening project (phase X: 1/2024-12/2026) | 2023-06-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 63000 | 0 | 0 |  | 0 |  |  | The project was approved at the 92nd Executive Committee meeting in June 2023. UNEP worked with the NOU to prepare the project plan and SSFA. The workplan incorporated gender mainstreaming. | The SSFA was signed in February 2024. The first payment of US$ 62,000 was released in March 2024. NOU continues to enforce HCFC/HFC quota and licensing system. CP data for the year 2023 collection has been completed and will be submitted by May. The NOU participated the Twinning Workshop of Montreal Protocol Officers, Energy-Efficiency Policy Makers and Financial Mechanisms Focal Points to Support Kigali Amendment Objectives, Thematic Workshop on Establishment and Implementation of Competency- based Certification, Thematic Workshop on Strategy of Stage I of the KIP and Integration with the HPMP Stage II for Pacific Island Countries from 5-10 February 2024 in Cook Islands. In June 2024 in Palau, the country will participate in the regional network meeting, regional training of NOUs, and thematic workshop on finalization of KIP Stage I. | Yes
|  | SOI/SEV/93/INS/21 | UNDP | Government Support | ASP | SOI | INS | National Ozone Unit | Renewal of institutional strengthening project (phase X: 7/2024-6/2027) | 2023-12-01 | 2027-06-01 | ONG |  | 2027-06-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  |  | The project was newly approved at the 93rd Executive Committee meeting in December 2023. UNEP worked with the NOU to prepare the project plan and SSFA. The workplan incorporated gender mainstreaming. | UNEP discussed with the NOU to develop the workplan, which was finalized and agreed by NOU. The draft SSFA has received agreement from the Government and it is pending for signature. Project implementation will commence from July 2024. | Yes
|  | NIC/SEV/92/INS/51 | UNEP | Government Support | LAC | NIC | INS | National Ozone Unit | Renewal of institutional strengthening project (phase XI: 7/2023-6/2026) | 2023-06-01 | 2026-06-01 | ONG |  | 2026-06-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 63000 | 0 | 0 |  | 0 |  |  | Newly approved project | Good progress. Work plan and timetable to implement the project agreed with the NOU. SSFA-2024-03 is under discussion. This SSFA will facilitate obtaining products and expected results as mentioned below:(1) Adoption/enforcement of Montreal Protocol Controlled Substances laws and regulations to control and monitor the consumption of Montreal Protocol Controlled Substances, (2) Efficient and timely data collection and reporting, (3) Intra- and inter-institutional coordination to implement the Montreal Protocol with other organizations/national stakeholders, (4) Supervision of timely execution of activities to eliminate and reduce the consumption of Substances controlled by the Montreal Protocol, (5) Increase awareness raising and information exchange, (6) Regional cooperation and participation in Montreal Protocol meetings. | Yes
|  | STL/SEV/93/INS/38 | UNEP | Government Support | LAC | STL | INS | National Ozone Unit | Renewal of institutional strengthening project (phase XII: 1/2024-12/2026) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  |  | Newly approved project. | SSFA drafted for consideration by the country. The workplan has been agreed and incorporated to the SSFA. CP data and A7 data for the year of 2023 were submitted. The activities are planned and waiting for the SSFA to be signed. | Yes
|  | BEN/SEV/93/INS/48 | UNEP | Government Support | AFR | BEN | INS | National Ozone Unit | Renewal of institutional strengthening project (phase XIII: 1/2024-12/2026) | 2023-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  |  | Newly approved project. | SSFA was signed in March 2024. The first payment was sent to the NOU in April 2024. The collection of data was initiated to report A7 and CP data for the year 2023. | Yes
|  | ERI/SEV/92/INS/25 | UNEP | Government Support | AFR | ERI | INS | National Ozone Unit | Renewal of the institutional strengthening project (phase VI: 7/2023-6/2026) | 2023-06-01 | 2026-06-01 | ONG |  | 2026-06-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 180000 | 63000 | 0 | 0 |  | 90000 |  |  | The SSFA with a total of USD 180,000 was signed by the country in September 2023. The first payment of USD90,000 was released to the country in October 2023. The quota and licensing system are supporting all HCFCs phase-out programme. The consumption in 2023 was 0.523 ODP which was below the allowable limit. Additionally, a refrigerant identification service identified only one instance of counterfeit refrigerant among over 30 cylinders checked for RAC technicians and importers in 2023. Eritrea ratified the Kigali Amendment on 7th February 2023. The collection of data was conducted to report A7 and CP data for the year 2022. CP data for 2022 reported on 1st March 2023 and A7 data reported on 30th May 2023. Training workshops were held for technicians from Zara Mining Share Company on 16-20 February 2023. The International Ozone Day for 2023 was celebrated with various activities; General Knowledge Competition on the issues related to the Ozone layer was made on a national TV program; Documentary film that reflect the ozone science, MP and country’s efforts and achievements prepared; Article was also prepared by local language (Tigrigna) and published in Hadas Eritrea on 16th September 2023 under the theme ‘Twin responsibility of Ozone day-Ozone layer preservation and combating climate change’. Awareness raising seminars were organized for 70 participants at the Zara Mining Share Company on February 17th and 18th, 2023. Two articles in Tigrigna, targeting the general public, were prepared to raise awareness. The themes were "Cold chain for food safety and food security" and "The good news on the healing of the Ozone layer," explaining the report from the Scientific Assessment Panel. On International Children's Day, November 20, 2023, the NOO issued a call to action for all stakeholders and responsible bodies to prioritize raising children's awareness and promoting environmentally friendly lifestyles. The NOO has committed to placing a greater emphasis on children's awareness programs in 2024. The Eritrean Chemical Engineering Festival (CheFest 2023) took place in December 2023. The NOO organized a seminar on 20th December titled "The Role of Chemical Engineers in Creating a Cleaner Environment." Over 100 chemical engineering students, teachers, and interested scholars participated. In addition, forty-five female students from the College of Engineering in Mainefhi attended. The seminar highlighted the environmental impact of different refrigerants, national and global efforts to address it, and discussions on potential innovative approaches. A NOO representative attended the Regional Network Meeting, held back-to-back with the Thematic Meeting for Customs Officers, in Kigali, Rwanda, from May 8-10 and 11-12, 2023, respectively. Two NOO members participated in a training on Strengthening Negotiation Skills for the Montreal Protocol Context, organized by GIZ in Nairobi, Kenya, from October 19-21, 2023. Eritrea was represented by a delegation of two NOO members and the Eritrean Ambassador to Kenya at the 35th Meeting of the Parties to the Montreal Protocol, held in Nairobi from October 23 to 27, 2023. The overall performance of the project is satisfactory. The project has demonstrably achieved its objective. Stakeholder participation in both awareness campaigns and training programs has increased significantly. Additionally, the quality of awareness materials has been noticeably improved. | The licensing system is fully operational. Refrigerant Identification service is provided for 10 RAC technicians and end-users. The collection of data was undertaken to report A7 and CP data for the year 2023. Both CP data and Article 7 data were submitted in April 2024. RAC Training workshop was organized to 45 young Eritrean Crop and Livestock cooperation technicians including 18 female technicians on 16th January 2024 at Adi-Guadad cold store. Preparation for 2024 ozone day celebration is underway. UNEP Ozone action’s animation video of Ozzy Ozone is in a process of translating into local language (Tigrigna) with a national context. The NOO is actively developing engaging materials to broaden its reach and raise awareness among children. Training for 18 female RAC technicians of ECLC were carried out on 16 January 2024. The project is progressing successfully. | Yes
|  | ZIM/SEV/92/INS/70 | UNEP | Government Support | AFR | ZIM | INS | National Ozone Unit | Renewal of the institutional strengthening project (phase XII: 7/2023-6/2026) | 2023-06-01 | 2026-06-01 | ONG |  | 2026-06-01 |  |  | 0 | 0 | [6 empty] | 392782 | 0 | 392782 | 0% | 392782 | 0 | 0 | 0 | 0 | 0 | 392782 | 137473.7 | 0 | 0 |  | 150000 |  |  | The first disbursement USD 150,000 was released to the country in October 2023. A total of 35 import permits were issued to importers of HCFCs, HFCs and appliances that contain these substances. The HCFC and HFC dependent appliances included mainly refrigerated trucks, refrigeration accessories such as compressors, among others. The NOU conducted three two day training workshop for customs officers in Harare, Kadoma and Bulawayo. A total of sixty-eight customs officers were trained (29 males and 39 females). The NOU conducted a one day training workshop for customs officers from South Africa and Zimbabwe at the Beit Bridge Border post on 29th September on monitoring and controlling ODS and HFC trade under the provisions of the new regulations, SI 49 of 2023. A total of fifteen customs officers were trained (8 males and 7 females) from both countries. The Regional Manager and Enforcement Manager for Beit Bridge also attended the training. The collection of data was undertaken to report A7 and CP data for the year 2022. A7 data for 2022 was reported on 28th February 2023 CP data for 2022 was reported on the 28th February 2023. Four Project Steering committee meetings were held during the year 2023; one for each Quarter to present plans and monitor progress. A one-day workshop was held on the 18th May 2023 at the Hotel Redcliff. Twenty five refrigeration and air conditioning technicians met in Redcliff and finalized the codes of conduct and codes of practices for the refrigeration and air conditioning sector. The codes of conduct enunciate the expected behaviour of RAC practitioners while the codes of practices outline the procedures to be followed by RAC practitioners when working on RAC appliances to minimise emissions of refrigerants and follow best practices. A SADC RAC Association meeting was held in Livingstone, Zambia at the Courtyard Hotel from the 20th t0 21st September. Ten members of HEVACRAZ and ZRAA attended the meeting (seven males & three females) which had RAC Association members from Zambia, South Africa, Eswatini, Malawi, Namibia and Zimbabwe. The SADC RAC Association members discussed on ways to improve cooperation with NOUs in phasing out HCFCs and phasing down HFCs. They exchanged information on challenges facing the RAC sector in the SADC Region. The Hon Minister issued a Press Statement on the 16th September highlighting the achievements Zimbabwe has made in phasing out ODSs and phasing down HFCs. A symposium was organised at the Cresta Jameson Hotel and was attended by 45 stakeholders mostly in the RAC Sector. Presentations were made of HCFC phase out activities and the Kigali Implementation Plan preparation. Promotional materials such as caps, sunhats, shirts, pens and rulers were distributed to stakeholders. The NOU Project Manager was invited to the Shipping and Forwarding Agents Association of Zimbabwe (SFAAZ) Annual General Meeting in Masvingo from the 27th to the 28th August 2023 at the Great Zimbabwe Hotel. A presentation on the provisions of the SI 49 of 2023 was made to raise awareness amongst clearing agents on imports and exports of ODSs and HFCs. The NOU participated at the Regional Network Meeting for National Ozone Officers of the English-Speaking African Countries back-to-back with Thematic Workshop for Customs Officers from 8-12 May 2023 in Kigali, Rwanda. The Regional Network Meeting, attended by 26 out of 28 countries of the English-speaking African networks (37 male, 30 female), provided opportunity for the countries to further discuss key information and data to be collected in preparation of a KIP Strategy and approaches. The NOU participated at the 45th OEWG meeting held in Bangkok, Thailand from 3rd to 7th July 2023 and the 35th meeting of the parties to the Montreal Protocol in Nairobi, Kenya from 23rd to 24th October 2023. The project is progressing satisfactorily. | The Licensing system is fully operational. The Quota allocations for 2024 were issued to importers in line with the phase out measures under the Montreal Protocol and with the agreement between the Government of Zimbabwe and the Multilateral Fund. The collection of data was undertaken to report A7 and CP data for the year 2023. A7 data for 2023 was reported on 12th April 2024; CP data for 2023 was reported on 12th April 2024. The project is progressing satisfactorily | Yes
|  | MON/SEV/92/INS/36 | UNEP | Government Support | ASP | MON | INS | National Ozone Unit | Renewal of the institutional strengthening project (phase XIII: 1/2024-12/2026) | 2023-06-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 0 | 0 | [6 empty] | 180000 | 0 | 180000 | 0% | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 63000 | 0 | 0 |  | 0 |  |  | Project newly approved at the 93rd Meeting. | SSFA was signed on January 2024 for the amount of USD 180,000. First payment transferred in February 2024. Licensing/quota system is being enforced. HCFC and HFC import quota for 2024 allocated to importers. CP data for 2023 submitted to MLFS in a timely manner. | Yes
|  | BEN/PHA/92/TAS/46 | UNIDO | HPMPIND | AFR | BEN | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2023-06-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 0 | 10500 | 0 | 0 |  | 0 |  |  | Newly approved project. | The Terms of Reference (ToR) for hiring the international consultant will be prepared, cleared by the management and advertised. The international consultant will be recruited by UNEP to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of Benin following the relevant decisions of the ExCom and guidelines for the verification of national consumption targets for the multi-year agreements. | Yes
|  | DRC/PHA/92/TAS/50 | UNIDO | HPMPIND | AFR | DRC | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2023-06-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 0 | 10500 | 0 | 0 |  | 0 |  |  | Newly approved project. | The Terms of Reference (ToR) for hiring the international consultant will be prepared and advertised. The international consultant will then be recruited by UNEP to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of DRC, following the relevant decisions of the ExCom and guidelines for the verification of national consumption targets for the multi-year agreements. | Yes
|  | ERI/PHA/92/TAS/26 | UNIDO | HPMPIND | AFR | ERI | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2023-06-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 0 | 10500 | 0 | 0 |  | 0 |  |  | Newly approved project | The Terms of Reference (ToR) for hiring the international consultant for Verification of the implementation of stage II of the HCFC phase-out management plan was prepared, cleared by the management in March 2024. The consultant was hired in May 2024 and verification exercise is progressing well. | Yes
|  | ETH/PHA/92/TAS/38 | UNIDO | HPMPIND | AFR | ETH | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2023-06-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 0 | 10500 | 0 | 0 |  | 0 |  |  | Newly approved project. | The Terms of Reference (ToR) for hiring the international consultant for Verification of the implementation of stage II of the HCFC phase-out management plan was prepared, cleared by the management in March 2024. The consultant was hired in May 2024 and verification exercise is progressing well. | Yes
|  | LIR/PHA/92/TAS/35 | UNIDO | HPMPIND | AFR | LIR | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2023-06-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 0 | 10500 | 0 | 0 |  | 0 |  |  | Newly approved project | The Terms of Reference (ToR) for hiring the international consultant for Verification of the implementation of stage II of the HCFC phase-out management plan was prepared, cleared by the management in March 2024. Verification exercise is progressing well. | Yes
|  | TTR/PHA/92/TAS/20 | UNEP | HPMPIND | ASP | TTR | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2023-06-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 0 | 10500 | 0 | 0 |  | 0 |  |  | The project was approved at the 92nd Executive Committee meeting in June 2023. Given that the HPMP Stage II, Second Tranche is originally scheduled for submission to the ExCom meeting in 2025 and UNEP’s rules on engagement of consultant 24/36 months, it was planned that the consultant be engaged in second half of 2024 to shorten the contract of consultant, but enabling the consultant to cover 2020-2024 verification of HCFC consumption. | In accordance with the conclusion in meeting in Cook Islands to shift the submission of HPMP Stage II, Second Tranche to the 95th ExCom meeting in December 2024, UNEP initiated the process to engage the international consultant to conduct verification of HCFC consumption. The Terms of Reference (ToR) for the international consultant was prepared in consultation with the country, cleared by the management in February 2024 and was advertised in March 2024. Following selection process, the international consultant was recruited by UNEP in April 2024 to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of Palau, following the relevant decisions of the ExCom and guidelines for the verification of national consumption targets for the multi-year agreements. The consultant will be conducting the verification of HCFC consumption in Palau from 18-21 June 2024. | Yes
|  | SAM/PHA/92/TAS/28 | UNEP | HPMPIND | ASP | SAM | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2023-06-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 0 | 10500 | 0 | 0 |  | 0 |  |  | The project was approved at the 92nd Executive Committee meeting in June 2023. Given that the HPMP Stage II, Second Tranche is originally scheduled for submission to the ExCom meeting in 2025 and UNEP’s rules on engagement of consultant 24/36 months, it was planned that the consultant be engaged in second half of 2024 to shorten the contract of consultant, but enabling the consultant to cover 2020-2024 verification of HCFC consumption. | In accordance with the conclusion in meeting in Cook Islands to shift the submission of HPMP Stage II, Second Tranche to the 95th ExCom meeting in December 2024. UNEP initiated the process to engage the international consultant to conduct verification of HCFC consumption. The Terms of Reference (ToR) for the international consultant was prepared in consultation with the country, cleared by the management in February 2024 and was advertised in March 2024. Following selection process, the international consultant was recruited by UNEP in April 2024 to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of Samoa, following the relevant decisions of the ExCom and guidelines for the verification of national consumption targets for the multi-year agreements. The consultant will be conducting the verification of HCFC consumption in Samoa from 23-26 July 2024. | Yes
|  | SOI/PHA/92/TAS/20 | UNEP | HPMPIND | ASP | SOI | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2023-06-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 0 | 10500 | 0 | 0 |  | 0 |  |  | The project was approved at the 92nd Executive Committee meeting in June 2023. Given that the HPMP Stage II, Second Tranche is originally scheduled for submission to the ExCom meeting in 2025 and UNEP’s rules on engagement of consultant 24/36 months, it was planned that the consultant be engaged in second half of 2024 to shorten the contract of consultant, but enabling the consultant to cover 2020-2024 verification of HCFC consumption. | In accordance with the conclusion in meeting in Cook Islands to shift the submission of HPMP Stage II, Second Tranche to the 95th ExCom meeting in December 2024, UNEP initiated the process to engage the international consultant to conduct verification of HCFC consumption. The Terms of Reference (ToR) for the international consultant was prepared in consultation with the country, cleared by the management in February 2024 and was advertised in March 2024. Following selection process, the international consultant was recruited by UNEP in April 2024 to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of Solomon Islands, following the relevant decisions of the ExCom and guidelines for the verification of national consumption targets for the multi-year agreements. The consultant will be conducting the verification of HCFC consumption in Solomon Islands from 1-4 July 2024. | Yes
|  | TON/PHA/92/TAS/20 | UNEP | HPMPIND | ASP | TON | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2023-06-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 0 | 10500 | 0 | 0 |  | 0 |  |  | The project was approved at the 92nd Executive Committee meeting in June 2023. Given that the HPMP Stage II, Second Tranche is originally scheduled for submission to the ExCom meeting in 2025 and UNEP’s rules on engagement of consultant 24/36 months, it was planned that the consultant be engaged in second half of 2024 to shorten the contract of consultant, but enabling the consultant to cover 2020-2024 verification of HCFC consumption. | In accordance with the conclusion in meeting in Cook Islands to shift the submission of HPMP Stage II, Second Tranche to the 95th ExCom meeting in December 2024, UNEP initiated the process to engage the international consultant to conduct verification of HCFC consumption. The Terms of Reference (ToR) for the international consultant was prepared in consultation with the country, cleared by the management in February 2024 and was advertised in March 2024. Following selection process, the international consultant was recruited by UNEP in April 2024 to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of Tonga, following the relevant decisions of the ExCom and guidelines for the verification of national consumption targets for the multi-year agreements. The consultant will be conducting the verification of HCFC consumption in Tonga from 29 July – 1 August 2024. | Yes
|  | BHU/PHA/92/TAS/32 | UNEP | HPMPIND | ASP | BHU | TAS | Verification | Verification report on the implementation of the HCFC phase-out management plan | 2023-06-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 0 | 10500 | 0 | 0 |  | 0 |  |  | Newly approved project. Finalized ToR for international consultant. UNEP started recruitment process. | SSFA for organization of stakeholder workshops and draft workplan finalized. International consultant onboarded by UNEP to conduct the HPMP verification for the years 2016 to 2023, data collection and drafting of report ongoing. | Yes
|  | STV/PHA/92/TAS/28 | UNEP | HPMPIND | LAC | STV | TAS | Verification | Verification report on the implementation of the HCFC phase-out management plan | 2023-06-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 0 | 10500 | 0 | 0 |  | 0 |  |  | Newly approved project | Verification Report programmed for submission with Tranche 4 which is programmed for 2025. | Yes
|  | ELS/SEV/91/INS/46 | UNIDO | Government Support | LAC | ELS | INS | National Ozone Unit | Extension of institutional strengthening project (phase VI: 1/2023 - 12/2024) | 2022-12-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 120000 | 0 | 120000 | 0% | 120000 | 0 | 0 | 0 | 0 | 0 | 108464 | 60000 | 0 | 0 |  | 44650 |  |  | Good progress. Work plan and timetable to implement the project agreed with the NOU. SSFA-2023-02 has been signed in August 2023 with an overall amount of USD 89,300 payable in three disbursements. First disbursement with an amount of USD 44,650 has been received by the country in October 2023. his SSFA will facilitate obtaining products and expected results as mentioned below:(1) Adoption/enforcement of Montreal Protocol Controlled Substances laws and regulations to control and monitor the consumption of Montreal Protocol Controlled Substances, (2) Efficient and timely data collection and reporting, (3) Intra- and inter-institutional coordination to implement the Montreal Protocol with other organizations/national stakeholders, (4) Supervision of timely execution of activities to eliminate and reduce the consumption of Substances controlled by the Montreal Protocol, (5) Increase awareness raising and information exchange, (6) Regional cooperation and participation in Montreal Protocol meetings. International Ozone Day has been celebrated on 16th of Semptember 2023 by the organization of a national event. CP data was submitted in May 2023 and A7 data was submitted in September 2023. NOU/Government representatives participated in the virtual webinars organized by OzonAction Latin American team: Communication strategy "Kigali in Action, Inclusive Language " (November 2023) | Good progress. Work plan and timetable to implement the project agreed with the NOU. SSFA-2023-02 has been signed in August 2023 with an overall amount of USD 89,300 payable in three disbursements. First disbursement with an amount of USD 44,650 has been received by the country in October 2023. CP Data for 2023 reported in May 2024. The NOU office has sucessfully supervised the implementation of HPMP activities and planned the renewal of the new tranche. The KIP programme document has been drafted and sent for approval. In February 2023 a custom training has been organized by the NOU for a total number of 36 participants (24 male / 12 female). In March 2023 several trainings for male and female RAC technicians have been organized with a total number of 180 participants (105 male / 75 female), to train tecnicians on good practises and start the preparation of a gender mapping exericse in the country. | Yes
|  | BOT/SEV/91/INS/31 | UNIDO | Government Support | AFR | BOT | INS | National Ozone Unit | Extension of institutional strengthening project (phase VI: 1/2023-12/2024) | 2022-12-01 | 2024-12-01 | ONG | 2023-09-29 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 138085 | 0 | 138085 | 1.261% | 136343.06 | 0 | 0 | 0 | 0 | 1741.94 | 136343.06 | 68171.53 | 0 | 0 |  | 70000 |  |  | The NOU conducted Importers stakeholder engagement meeting to discuss 2024 quotas, application form and procedure, and requirements in November 2023. Call for expression of interest for ODS import permits was sent out in November 2023. Applications were received and evaluated in December 2023. A total of 98 MT of ODS quota was issued for the year 2024. The NOU conducted a meeting in November 2023 with the Botswana Refrigeration and Air Conditioning Association (BRACA) to discuss implementation of the HPMP and requirements for the KIP. Monitoring of HPMP implementation has progressed well. The NOU holds a meeting once every quarter to update Management and the Ministry on the status of implementation. The NOU participated at the 35th Meeting of the Parties to the Montreal Protocol on Substances that Deplete the Ozone Layer (23 to 27 October 2023). | The NOU conducted Importers stakeholder engagement meeting to discuss 2024 quotas, application form and procedure, and requirements in November 2023. Call for expression of interest for ODS import permits was sent out in November 2023. Applications were received and evaluated in December 2023. A total of 98 MT of ODS quota was issued for the year 2024. The NOU conducted a meeting in November 2023 with the Botswana Refrigeration and Air Conditioning Association (BRACA) to discuss implementation of the HPMP and requirements for the KIP. Monitoring of HPMP implementation has progressed well. The NOU holds a meeting once every quarter to update Management and the Ministry on the status of implementation. The NOU participated at the 35th Meeting of the Parties to the Montreal Protocol on Substances that Deplete the Ozone Layer (23 to 27 October 2023). Project progress was delayed due to NOU institutional arrangement, which had to halt implementation of activities. A total of 98 MT of ODS quota was issued for the year 2024. In February 2024 and April 2024, three targeted awareness raising were conducted to Senior Management of 2 mining companies in Botswana: Debswana and Morupule Coal Mine. The meetings were meant to appraise them on the national and legal requirements under the Montreal Protocol and formulate a strategy for phasing out of ODS-dependent equipment in their operations. The NOU has facilitated the setting up of the Women in Refrigeration Association and is anticipating their official launch in 2024. Project is now progressing well and funds utilization for the various activities is at 60%. | Yes
|  | MAS/SEV/90/INS/18 | UNIDO | Government Support | ASP | MAS | INS | National Ozone Unit | Extension of institutional strengthening project (phase VIII: 1/2023-12/2024) | 2022-06-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 85000 | 0 | 85000 | 0% | 85000 | 0 | 0 | 0 | 0 | 0 | 85000 | 42500 | 0 | 0 |  | 40000 |  |  | The SSFA was signed in March 2023. The first payment of US$ 40,000 was released in March 2023. NOU did not issue HCFC quota in 2023 to maintain zero consumption in accordance with the maximum allowable consumption indicated in the Agreement under the HPMP Stage II and continued to implement HFC licensing system. The NOU worked with UNEP in establishing the HFC Quota. Three domestic market inspections were conducted in May 2023. A7 and CP data collection and reporting were undertaken for the year 2022. The NOU conducted awareness activities and the World Ozone Day. NOU actively participated in regional meetings organized by UNEP, Network Meeting of the Pacific Island Countries National Ozone Officer, Refrigeration and Air-conditioning (RAC) Industry Roundtable, Future Gas Forum and Thematic Workshop on Strengthening Partnership in the RAC Servicing Sector in May 2023 and the 45th OEWG Meeting. In September 2023 in Samoa, the country joined the 1) regional network meeting, 2) thematic workshop on nation-wide data collection under the KIP preparation, and 3) Twinning workshop on ODS/HFC trade control and reporting. The gender activities included promotion of gender mainstreaming into project activities such as equal access and equal treatment to participate in training and meetings. | The NOU enforces HFC quota and licensing system. No HCFC importer allowed in 2024 in accordance with the Agreement with the ExCom. CP data for the year 2023 collection has been completed and will be submitted by May. The NOU participated the Twinning Workshop of Montreal Protocol Officers, Energy-Efficiency Policy Makers and Financial Mechanisms Focal Points to Support Kigali Amendment Objectives, Thematic Workshop on Establishment and Implementation of Competency- based Certification, Thematic Workshop on Strategy of Stage I of the KIP and Integration with the HPMP Stage II for Pacific Island Countries from 5-10 February 2024 in Cook Islands. In June 2024 in Palau, the country will participate in the regional network meeting, regional training of NOUs, and thematic workshop on finalization of KIP Stage I. UNEP is working with the NOU to expedite implementation. | Yes
|  | STK/SEV/90/INS/23 | UNIDO | Government Support | LAC | STK | INS | National Ozone Unit | Extension of institutional strengthening project (phase VIII: 7/2022-6/2024) | 2022-06-01 | 2024-06-01 | ONG |  | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 85000 | 0 | 85000 | 0% | 85000 | 0 | 0 | 0 | 0 | 0 | 85000 | 42500 | 0 | 0 |  | 42000 |  |  | The SSFA was signed on 28 July 2023. The first payment has been released to the Country 1 Nov 2023. 2024 HCFC quotas issues to importers. 2023 Ozone Day celebrations were not implemented as planned as the Country was focussed on preparing for the 2024 LQS implementation as a result of the recommendations from the MLFS and the UNEP Country mission. The Country participated in the following meeting: Workshop for Women in RAC, Trinidad and Tobago, 15 Nov 2023, where one female technician participated. | The SSFA was signed on 28 July 2023. The fist payment has been released to the Country 1 Nov 2023. Licensing system fully operational. The collection of data to report A7 and CP data for the year 2023 is being undertaken. On 19th Jan 2024, UNEP was informed of the loss of the NOO and informed of the assignemnt of a interim officer who will manage the portfolio until a new Ozone Officer is recuited. UNEP was also informed that a New NOO was selected, however, on their officer start date, the indivdual recieved another offer and declined the position. The Government is restarting the recruitment process. UNEP held a introductory meeting with the Officer on 22 Feb 2024. | Yes
|  | JAM/SEV/90/INS/44 | UNIDO | Government Support | LAC | JAM | INS | National Ozone Unit | Extension of institutional strengthening project (phase XI: 7/2022-6/2024) | 2022-06-01 | 2024-06-01 | ONG |  | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 85000 | 0 | 85000 | 0% | 85000 | 0 | 0 | 0 | 0 | 0 | 85000 | 42500 | 0 | 0 |  | 25500 |  |  | The SSFA was signed on 08 Aug 2023. The first payment advanced to the country on 22 September 2023. The licensing system is fully operational. The quota for the year 2023 was issued. Importers comply with issued quotas for the year 2023. Ozone Day 2023 was celebrated and included the publicising on print and digital media; The Country participated in the following meetings: Caribbean network meeting back to back with Women in RAC both held in Nov 2023 in Trinidad and Tobago; | Licensing system fully operational. The quota for the year 2024 was issued. Importers comply with issued quotas for the year 2024. The collection of data was undertaken to report A7 and CP data for the year 2023. 2023 A7 CP data submitted in February 2024. 2 training workshops for the RAC sector held in March 2024; Country preparing interim financial report to process second disbursment. | Yes
|  | NER/SEV/90/INS/45 | UNIDO | Government Support | AFR | NER | INS | National Ozone Unit | Extension of institutional strengthening project (phase XIII: 7/2022-6/2024) | 2022-06-01 | 2024-06-01 | ONG | 2023-12-31 | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 85000 | 0 | 85000 | 47% | 45050 | 0 | 0 | 0 | 0 | 39950 | 45050 | 22525 | 0 | 0 |  | 50 |  |  | Licensing system is fully operational. The quota for the year 2023 was issued. Importers complied with issued quotas for the year 2022. A7 and CP data for 2022 reported to the 2 Secretariats in may 2023. The National Ozone Unit celebrated the Ozone Layer, which took place on September 16, 2023. In January 2023, 15 participants attended the meeting of the National Ozone Committee to discuss the allocation of HCFC import quotas for the year 2023 and the import licensing system for HFCs for the same year. In March 2023, 18 participants attended the meeting of the National Ozone Committee to share the decree No. 0042/ME/LCD/SG/OGE/DD of February 22, 2023, which establishes the creation, responsibilities, and composition of a National Ozone Committee for the implementation of the Montreal Protocol on Substances that Deplete the Ozone Layer with the members of the said Committee. Participate in the 35th Meeting of the Parties to the Montreal Protocol on Substances that Deplete the Ozone Layer, from July 2nd to July 7th, 2023. Meeting with the Refrigeration Technicians Association in Niamey, Niger on March 30, 2023, involved introducing new members and presenting the 2023-2025 action plan by the National Bureau of Niger Professionals of the Cold (APFN), as well as addressing the expressed training needs of refrigeration technicians. | The second payment was disbursed in January 2024. The final payment was disbursed in May 2024. The project is completed. | Yes
|  | SAU/SEV/90/INS/37 | UNIDO | Government Support | ASP | SAU | INS | National Ozone Unit | Extension of the institutional strengthening project (phase III: 7/2022-6/2024) | 2022-06-01 | 2024-06-01 | ONG |  | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 256000 | 0 | 256000 | 0% | 256000 | 0 | 0 | 0 | 0 | 0 | 256000 | 128000 | 0 | 0 |  | 100000 |  |  | Progress report: -Legal Instrument: SSFA signed in Dec. 2022 ($256,000) and first payment made in Feb. 2023); the planned activities have been implemented successfully including submission of A7 and CP data reporting for 2022; NOU participated and contributed in global and regional Meetings including the network meeting in Sept. 2023 and standards workshop in Riyadh in Feb. 2023; the quota and LS are operational with full control and monitoring of ODS trade; the NOU actively participated in the GCC work to update the ODS unified regulations and initiate the work update RAC standards; extensive public awareness and information dissemination activities implemented. - Overall assessment of project progress: Project is progressing as planned. - Impact of these activities: the ISP is playing key role in facilitating the compliance of Kuwait with MP targets and sound implementation of related projects. | Progress report: -Legal Instrument: SSFA signed in Dec. 2022 ($256,000) and first payment made in Feb. 2023); the planned activities have been implemented successfully including submission of A7 and CP data reporting for 2022; NOU participated and contributed in global and regional Meetings including the network meeting in Sept. 2023 and standards workshop in Riyadh in Feb. 2023; the quota and LS are operational with full control and monitoring of ODS trade; the NOU actively participated in the GCC work to update the ODS unified regulations and initiate the work update RAC standards; extensive public awareness and information dissemination activities implemented. a renewal request of the project has been finalized and submitted to ExCom-94. - Overall assessment of project progress: Project is progressing as planned. - Impact of these activities: the ISP is playing key role in facilitating the compliance of Kuwait with MP targets and sound implementation of related projects. | Yes
|  | ETH/SEV/90/INS/37 | UNIDO | Government Support | AFR | ETH | INS | National Ozone Unit | Extension of the institutional strengthening project (phase IX: 1/2023-12/2024) | 2022-06-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 85000 | 0 | 85000 | 0% | 85000 | 0 | 0 | 0 | 0 | 0 | 85000 | 42500 | 0 | 0 |  | 40000 |  |  | The SSFA with a total of US$85,000 was signed in March 2023. The first disbursement of US$40,000 was released to the country in March 2023. The licensing and quota system is in place and functioning. The NOU conducted one Steering Committee meeting in February 2023 to allocate import quotas. The annual approved import quotas for 2023 is 3.15 ODP. The monitoring system established by the NOU works well as it allows a good control of the quotas allocated. The collection of data was undertaken to report A7 and CP data for the year 2022 on 9th May 2023. | The licensing system is fully operational. The collection of data was undertaken to report A7 and CP data for the year 2023. The project is progressing successfully. | Yes
|  | SIL/SEV/91/INS/44 | UNIDO | Government Support | AFR | SIL | INS | National Ozone Unit | Extension of the institutional strengthening project (phase IX: 1/2023-12/2024) | 2022-12-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 151557 | 0 | 151557 | 0% | 151557 | 0 | 0 | 0 | 0 | 0 | 151557 | 75778.5 | 0 | 0 |  | 0 |  |  | Licensing system is fully operational. The quota for the year 2023 was issued to 17 registered importers. The collection of data was undertaken to report A7 and CP data for the year 2022. A7 data for 2022 reported in April 2023; CP data for 2022 reported in April 2023. The NOU participated in the Regional Training Workshop for Female RAC Technicians held from 17 to 19 January 2023, in Cairo, Egypt, attended by 18 female technicians. The NOU conducted one training workshop for Customs and other Law enforcement officers for Gbalamuya and Gendema borders from 20-22 February 2023. The NOU conducted RAC training meeting for the Northern region held from 27-29 March 2023 with a total number of 40 participants (male 39 and Female 1)and for Eastern Region from 4-6 April 2023. A total of 40 male and 5 female participants were trained. The NOU participated in the Regional Network Meeting of the English-speaking African countries held in Kigali from 8 to 10 May 2023. The 2023 International Ozone Day was celebrated in the Northern Regional City of Markeni. The event was held in the Northern Regional City for the first time in such a grand style with resounding victory in terms of the impacts the Montreal Protocol has created in Sierra Leone. The celebration started on the 15th September, 2023 with a road public education and side melo-drama done by the RAC technicians at the city center in the Northern Regional city of Makeni highlighting the certification process, best refrigeration practices, environmental protection permit process for importing refrigerants which was an excellent public education for by –standers, roadside users providing information to over hundreds of people about the Montreal protocol and its related activities, and the national legal provisions covering it. On the 16th September, 2023 stakeholders, school pupils, RAC associations across the country matched across the streets of Makeni to the University of Makeni Auditorium were statement were delivered by major stakeholders including statement from the Director of climate Change, Mr. Tamba Emmanuel Nyaka, the Executive Chairman of the Environment Protection Agency, Sierra Leone, Dr. Bondi Gevao, with the keynote address delivered by the Deputy Minister of the Environment and Climate Change. This was followed by the establishment of the first Ozone Graden at the university two main campuses during which stakeholders, School Pupils, RAC association planted 500 trees (300 fruit trees and 200 Forestry trees) with the symbolic message of the Montreal Protocol supporting the fight to help address climate change. Over 200 people attended. This celebration was followed by radio and television interviews and discussion across the country. The NOU together with the Refrigeration Engineers and Technicians Association in Kono District organised Awareness raising workshop on the Montreal Protocol, activities of the Montreal Protocol in Sierra Leone, available Alternative technologies etc. The event took place from the 2-3 May, 2023 at the Koidu New Sembehun City Hall, Koidu City, Kono Eastern Region. There were 30 participants (Male 24 and 6 Female). The NOU has regularly participated in the EPA-SL every Thursday TV and Radio Programs aimed at educating the Public about ongoing activities both project activities and the usual EPA-SL activities. Furthermore the NOU undertook special awareness program via radios across the country from 14-18 September 2024 during which other relevant stakeholders like the Police, customs, RAC Technicians and consumer protection Agency participated. It is estimated that over thousands of Sierra Leonean benefited. The NOU also produced information, education and Communication materials as follows: 400 t-shirts, 200 Cap, 500 pen, 50 Water bottles, 300 Cup, Bags 100 that were distributed to the stakeholders and some sectors of the public. 20 Custom Officers and other law enforcement officers (17 Male and 3 Female) at the Dogolia Customs Post, Koinadugu District, and from Kabala township were trained on the illegal trade in ODSs and provisions of the ODS Regulations to enhance compliance. The training was held at the Kabala District Council Hall from 19-20 September 2023. Similar training workshop was organised in Kailahun District from 13-14 October 2023 by NOU in consultation with the Customs Department of the National Revenue Authority for Custom Officers and Other Law Enforcement Officers at the Sambaru customs post and other enforcement officers within the District. The training which took place at the Kailahun District Council Hall, Kailahun Township was on the Illegal trade in ODS substances, safe storage of confiscated refrigerants and the legal provisions within the ODS regulations. There were 20 participants (18 Male and 2 Female). The NOU participated in the Network Meeting of English-Speaking African National Ozone Officers back-to-back with the Customs Officers Meeting held in Kigali, Rwanda, 8-12 May 2023. The NOU participated at the 45th OEWG meetings held in Bangkok Thailand from the 3 to 7 July 2023, and the workshop on strengthening effective implementation and enforcement of the Montreal Protocol 2nd July 2023. The NOU participated at the 45th OEWG meeting held in Bangkok, Thailand from 3rd to 7th July 2023 and the 35th meeting of the parties to the Montreal Protocol in Nairobi, Kenya from 23rd to 24th October 2023. The project is progressing satisfactorily. | The NOU conducted training workshop for 20 RAC Technicians from 28-29 March 2024 at Magborakak, on best refrigeration practice, safe handling of flammable refrigerants, Leak detection, the legal provision and instrumentations. The participants were 5 female and 15 males. The NOU conducted a workshop for Customs officers and Other law Enforcement Officers at Gbalamuya on how to tackle illegal trade of ODSs, and other controlled substances covered by the Montreal Protocol, The legal provision, Safe storage of flammable and toxic refrigerants. The training was held from 11-12 April 2024. Twenty (20) participants took part in the training (14 Male and 6 Female). The NOU organized female RAC Technicians training Workshop in Makeni from the 17-19th April, 2024. Twenty Female RAC Technicians participated in the training held at the Lodge Valley Hotel in Makeni City. The Two days hands on training focused on instrumentation, safety in working with flammable refrigerants and the Montreal Protocol. The NOU with additional support by the Government of Sierra Leone via the EPA-SL conducted from 29th April – 3rd May, 2024 a certification and License training at the Government Technical Institute in Bo City . The training session was organised for RAC technicians in the Southern Region and some part of the Eastern Region A total of ten (10) RAC technicians were certified (9 Male and 1 Female). The training covers a range of topic e.g. Refrigerants recovery, Leak detection, handling of flammable refrigerants, other good refrigeration practices, First aid in case of an accident/emergency during work and legal provisions to enhance compliance. The project is progressing satisfactorily. | Yes
|  | UGA/SEV/90/INS/33 | UNIDO | Government Support | AFR | UGA | INS | National Ozone Unit | Extension of the institutional strengthening project (phase V: 1/2023-12/2024) | 2022-06-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 85000 | 0 | 85000 | 0% | 85000 | 0 | 0 | 0 | 0 | 0 | 85000 | 42500 | 0 | 0 |  | 40000 |  |  | The first payment of USD40,000 was released to the country in June 2023. The licensing and quota systems are in place and operational. One importer (Transa Electricals) was licensed to import HCFC-22/ R22 from 1st January 2023 to 30th September, 2023. Xtreme Uganda Limited took over the importation of R22. This was agreed during the meeting on allocation of quotas. Both companies will not exceed the quota for Uganda which is 1300kg. The Kigali Amendment was ratified in June 2018, and it was included in the National Environment Act, 2019 and the National Environment (Management of Ozone Depleting Substances and Products) Regulations, 2020. Enforcement of the Kigali Amendment provisions is on-going. The NOU conducted training workshop for NEMA Staff in November 2023. 20 NEMA staff participated (8 female and 12 female). The NOU conducted training workshop for importers in May 2023. 65 people participated (20 female, 45 male); The NOU conducted 4 training workshops for RAC Technicians were conducted in 2023. 152 RAC Technicians were trained (42 females; 110 males). A meeting with the Uganda electronic single window team was held in November 2023, and the main agenda was about the NOU joining the single window. The controlled substances (ODSs) had already been added to the single window and the NOU was given log in details and tasked to test the system. The International Day for the Protection of the Ozone Layer was celebrated on 16th September 2023. The Ozone Officer raised awareness on the Montreal Protocol. An article was also circulated in two Newspapers of widest circulation in Uganda (The New Vision and The Daily Monitor). Four workshops were organized to raise awareness on the Montreal Protocol. The stakeholders involved included the RAC Technicians, UNARA, importers, DIT and NOU/NEMA. The NOU participated at the Regional Network Meeting for National Ozone Officers of the English-Speaking African Countries back-to-back with Thematic Workshop for Customs Officers from 8-12 May 2023 in Kigali, Rwanda. The Regional Network Meeting, attended by 26 out of 28 countries of the English-speaking African networks (37 male, 30 female), provided opportunity for the countries to further discuss key information and data to be collected in preparation of a KIP Strategy and approaches. The NOU participated at the 45th OEWG meeting held in Bangkok, Thailand from 3rd to 7th July 2023 and the 35th meeting of the parties to the Montreal Protocol in Nairobi, Kenya from 23rd to 24th October 2023.The project is progressing satisfactorily. | The National Code of Practice and Code of Conduct for the Refrigeration and Air Conditioning Sector is being developed. Three meetings have been held to this effect and a draft code of practice was circulated to stakeholders for comments in March 2024. A meeting involving the Directorate of Industrial Training (DIT), Uganda National Association of Refrigeration and Air-conditioning (UNARA) and the National Ozone Unit (NOU)/ National Environment Management Authority (NEMA) was held to streamline the training and certification procedure. The streamlining was as follows: training institutions/ companies for refrigeration and air conditioning (RAC) shall be accredited by DIT; all RAC Practitioners shall be registered with UNARA; all RAC Practitioners shall be certified by DIT; and, the NOU shall take the lead in creating awareness on the law, policies and standards concerning RAC. A technical committee on management of ozone depleting substances and products was formed and this committee is supposed to process authorisations to importers including allocation of quotas to importers. The national ozone unit is part of the single window electronic platform. Application for licenses is online. The NOU conducted inspections for 23 importers in 2024. Banned refrigerants were not imported in the Jan-Dec 2023 period. The collection of data was undertaken to report A7 and CP data for the year 2023. The project is progressing satisfactorily. | Yes
|  | ALG/SEV/90/INS/87 | UNIDO | Government Support | AFR | ALG | INS | National Ozone Unit | Extension of the institutional strengthening project (phase VII: 7/2022-6/2024) | 2022-06-01 | 2024-06-01 | ONG |  | 2025-06-01 |  |  | 0 | 0 | [6 empty] | 329472 | 0 | 329472 | 0% | 329472 | 0 | 0 | 0 | 0 | 0 | 0 | 164736 | 0 | 0 |  | 0 | To request UNEP to submit a status report to the 95th meeting on implementation progress of activities |  | The SSFA was drafted and sent to the country in November 2022. The SSFA is not yet signed. | The SSFA was drafted and sent to the country in November 2022. The SSFA is not yet signed. | Yes
|  | CBI/SEV/90/INS/29 | UNIDO | Government Support | AFR | CBI | INS | National Ozone Unit | Extension of the institutional strengthening project (phase VIII: 1/2023-12/2024) | 2022-06-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 85000 | 0 | 85000 | 0% | 85000 | 0 | 0 | 0 | 0 | 0 | 85000 | 42500 | 0 | 0 |  | 40000 |  |  | The SSFA was signed in October 2022. The first payment was released to the country in November 2022. Licensing system fully operational. The collection of data was undertaken to report A7 and CP data for the year 2022. A7 data for 2022 and CP data for 2022 were reported. Two Steering Committee meetings were held in 2022 to evaluate the way forward in the implementation of 2022 action plan of NOU. Steering Committee meetings were held in March 2023. One information workshop on the phasing-out schedule of HCFCs and HFCs and dissemination of alternatives to these substances were organized for 22 industry associations in 2022. The National Ozone Unit celebrated the Ozone Layer, which took place on September 16, 2022. The NOU participated in the Regional Thematic Meeting for Francophone Network of Ozone Officers in 2022. NOU participated at the Open-ended Working Group and Meeting of the Parties in 2022. | Due to internal administrative issues, and major changes in the NOO, The interim progress report is still pending. CAP is following up. | Yes
|  | DJI/SEV/91/INS/30 | UNIDO | Government Support | AFR | DJI | INS | National Ozone Unit | Extension of the institutional strengthening project (phase VIII: 1/2023-12/2024) | 2022-12-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 120000 | 0 | 120000 | 0% | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 60000 | 0 | 0 |  | 60000 |  |  | The SSFA was signed in November 2023. The first payment was disbursed in November 2023. The Licensing system fully operational. | The Licensing system fully operational. Art7 data submitted to the Ozone Secretariat in March 2024. Zero CFC consumption is maintained for the year 2023. Periodic meeting in January with the NOC to validate the annual work program, set annual HCFC import quotas fro the year 2024. | Yes
|  | URT/SEV/91/INS/46 | UNIDO | Government Support | AFR | URT | INS | National Ozone Unit | Extension of the institutional strengthening project (phase VIII: 1/2023-12/2024) | 2022-12-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 120000 | 0 | 120000 | 0% | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 |  | 0 |  |  | The Licensing system is fully operational. The quota for the year 2023 was issued. Importers complied with issued quotas for the year 2022. The NOU conducted 4 inspection visits to the importers/exporters or market or end-users. The NOU conducted Customs training for 100 enforcement officers on prevention of illegal trade in April, June, and November 2023. The collection of data was undertaken to report A7 and CP data for the year 2022. A7 data for 2022 reported on May 2023); CP data for 2022 reported on March 2023. The International Ozone Day for 2023 was celebrated. The commemoration of the Ozone Day/week involved: public sensitization through press release in the country newspapers; press conference conducted by the Minister of State in the Vice President’s Office – Environment to reporter of different news media; training workshop to 50 members of Tanzania Freight Forwarders Association (TAFFA) on implementation of Montreal Protocol; and training to 50 members of Journalists' Environmental Association of Tanzania (JET) on the importance of preserving the ozone layer. The NOU conducted 6 awareness raising workshops/seminars/meetings for 120 participants. The NOU commemorated the World Environmental Day with Public/media campaign in June, 2023. The NOU produced and disseminated publications/information materials/leaflets produced in 1,000 copies. The NOU participated at the Regional Network Meeting for National Ozone Officers of the English-Speaking African Countries back-to-back with Thematic Workshop for Customs Officers from 8-12 May 2023 in Kigali, Rwanda. The Regional Network Meeting, attended by 26 out of 28 countries of the English-speaking African networks (37 male, 30 female), provided opportunity for the countries to further discuss key information and data to be collected in preparation of a KIP Strategy and approaches. The NOU participated at the 45th OEWG meeting held in Bangkok, Thailand from 3rd to 7th July 2023 and the 35th meeting of the parties to the Montreal Protocol in Nairobi, Kenya from 23rd to 24th October 2023. The project is progressing satisfactorily. | The Licensing system is fully operational. The quota for the year 2024 was issued. Importers complied with issued quotas for the year 2023. The NOU conducted 1 inspection visit to the importers/exporters or market or end-users conducted in March 2024. The NOU conducted one monitoring of illegal ODS trade and training for 30 enforcement officers on prevention of illegal trade in March 2024. The collection of data was undertaken to report A7 and CP data for the year 2023. A7 data for 2023 reported on May 2024); CP data for 2023 reported on March 2024. The NOU conducted 1 of 2 Steering Committee meeting involving 15 members from key institutions and was conducted at the Vice President’s Office in Dodoma in April 2024. The NOU conducted a training workshop for 30 female RAC technicians at Vocation Training Centre in Dar es Salaam in March 2024. The project is progressing satisfactorily. | Yes
|  | BHA/SEV/90/INS/34 | UNIDO | Government Support | LAC | BHA | INS | National Ozone Unit | Extension of the institutional strengthening project (phase VIII: 7/2022-6/2024) | 2022-06-01 | 2024-06-01 | ONG |  | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 85000 | 0 | 85000 | 0% | 85000 | 0 | 0 | 0 | 0 | 0 | 85000 | 42500 | 0 | 0 |  | 42000 |  |  | The SSFA signed Sept 2023. 1st Cash Advance issued 19 Dec 2023. | The SSFA signed Sept 2023. 1st Cash Advance issued 19 Dec 2023. Licensing system fully operational with support from the Electronic Single Window System. The quota for the year 2024 was issued. The collection of data to report A7 and CP data for the year 2023 is being undertaken. The NOU has been promoting the particiation of women through greater visibility as presenters and greater use of imagery in awareness materials. | Yes
|  | IVC/SEV/91/INS/51 | UNIDO | Government Support | AFR | IVC | INS | National Ozone Unit | Extension of the institutional strengthening project (phase X: 1/2023-12/2024) | 2022-12-01 | 2024-12-01 | ONG | 2023-11-15 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 187839 | 0 | 187839 | 47.91% | 97839.41 | 0 | 0 | 0 | 0 | 89999.59 | 97839 | 48919.705 | 0 | 0 |  | 50000 |  |  | The SSFA was signed in April 2023. The first payment has been released to the country in May 2023. The second payment has been released to the country in november 2023. Licensing system is fully operational. The quota for the year 2023 was issued. Importers complied with issued quotas for the year 2022. The implementation of three (03) Centers of Excellence in Refrigeration and Air Conditioning Training in Abidjan (CPMME of Koumassi), in Bouake, and in San Pedro.The organization of annual surveys on the consumption of ODS. The delivery of refrigeration equipment and tools to the Centers of Excellence in refrigeration and air conditioning training in Bouake and San Pedro. The establishment of import quotas for HCFCs for the year 2024. The transmission of HFC consumption data in 2023. | The final payment was disbursed in May 2024. In May 2024, data for Article 7 and CP for the year 2023 were submitted to two secretariats. Licensing system is fully operational. | Yes
|  | MOZ/SEV/91/INS/39 | UNEP | Government Support | AFR | MOZ | INS | National Ozone Unit | Extension of the institutional strengthening project (phase X: 1/2023-12/2024) | 2022-12-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 142725 | 0 | 142725 | 0% | 142725 | 0 | 0 | 0 | 0 | 0 | 142725 | 71362.5 | 0 | 0 |  | 70000 |  |  | The import Licensing System is fully operational. The NOU conducted Project Steering Committee meetings to review progress on implementation of project activities and allocation of quotas to importers for HCFCs held on 23 January 2023. The committee provided guidance and direction on the implementation of all activities under the protocol. The meeting also approved HCFCs quotas for 2023. Article 7 and Country Programme data reporting was done. The collection of data was undertaken to report A7 and CP data for the year 2022. A7 data for 2022 was reported in March 2023. Project is progressing satisfactorily. | The licensing and quota system is in place and functioning. The collection of data was undertaken to report A7 and CP data for the year 2023. The Project is progressing satisfactorily. | Yes
|  | SEY/SEV/91/INS/29 | UNEP | Government Support | AFR | SEY | INS | National Ozone Unit | Extension of the institutional strengthening project (phase X: 1/2023-12/2024) | 2022-12-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 120000 | 0 | 120000 | 0% | 120000 | 0 | 0 | 0 | 0 | 0 | 120000 | 60000 | 0 | 0 |  | 60000 |  |  | Licensing system on both HCFCs and HFCs are fully operational since 2021for HFCs and 2010 for HCFCs. No quota is given for HCFCs as it has been banned since 2018. The Green Custom Initiatives was held at H-STORY Hotels & Resort (Bel-ombre) from 18th to 20th April 2023 for Custom/Law Enforcement officers. It was attended by a total of 26 participants from Aviation (SCAA) (4 females, 4 male); Port (SPA) (4 females, 4 males); and from Custom (8 females, 2 males). The collection of data was undertaken to report A7 and CP data for the year 2022. 2022 Article 7 data online was done on 3rd February 2023 and Country Program data reporting for 2022 was done on the 5th April 2023. First Steering Committee met on 23rd June 2023, which comprises members of SIT director, ozone unit, Import office and from Licensing Authority. The NOU conducted a training workshop for 19 RAC technicians from 20th -24th June 2023. The International Ozone Day was celebrated on the 18th September 2023 through a musical Show which include a video clip on the Montreal Protocol and its progress from 1987, and the Seychelles’ progress since its first ratification. The NOU conducted presentation of certificates to RAC technicians who had undergo training on Handling & Safety Aspects of HC, plus presentation of prizes to winning schools who had taken part in the school competition. The NOU conducted continued awareness raising to all public schools both primary & secondary throughout the year & on the national Television as follows: Cool Talks which is an Environmental program aired on TV 6th April (recorded program); 4 Degrees South (T.V Environment Program) aired in May; Bonzour Seychelles (5th September) TV live interview whereby public can phone and ask questions relating to the Montreal Protocol & existing legislation in place was done in early September; Workshop on Protection against UV Radiation which includes farmers, Police officers, students from maritime & agriculture schools; and Road show on sensitization on Kigali Amendment. The NOU participated at the Regional Network Meeting for National Ozone Officers of the English-Speaking African Countries back-to-back with Thematic Workshop for Customs Officers from 8-12 May 2023 in Kigali, Rwanda. The Regional Network Meeting, attended by 26 out of 28 countries of the English-speaking African networks (37 male, 30 female), provided opportunity for the countries to further discuss key information and data to be collected in preparation of a KIP Strategy and approaches. The NOU participated at the 45th OEWG meeting held in Bangkok, Thailand from 3rd to 7th July 2023 and the 35th meeting of the parties to the Montreal Protocol in Nairobi, Kenya from 23rd to 24th October 2023. The project is progressing satisfactorily. | The collection of data was undertaken to report A7 and CP data for the year 2023. 2023 Article 7 data online was done on 23 February 2024 and Country Program data reporting for 2023 was done on the 28th March 2024. Public awareness is still ongoing especially on the Kigali Amendment and its implications. This is being done through adverts both on the media & national newspapers once a month for week on the do’s & don’t in regard to importation of both equipment & gas. Articles are done on a quarterly basis. The NOU conducted Interviews on TV which includes some industries using Natural Refrigerants specifically ammonia had encouraged other stakeholders on 29th February 2024. The NOU conducted Radio interview on 6th April 2024. The project is progressing satisfactorily. | Yes
|  | CHD/SEV/90/INS/42 | UNEP | Government Support | AFR | CHD | INS | National Ozone Unit | Extension of the institutional strengthening project (phase X: 7/2022-6/2024) | 2022-06-01 | 2024-06-01 | FIN | 2023-05-18 |  | 2023-12-01 | 2023-12-01 | 0 | 0 | [6 empty] | 85000 | 0 | 85000 | 100% | 0 | 0 | 0 | 0 | 0 | 85000 | 0 | 0 | 0 | 0 |  | 0 |  |  | The project is completed and operationnaly closed. | The project is financialy completed | Yes
|  | HON/SEV/90/INS/56 | UNEP | Government Support | LAC | HON | INS | National Ozone Unit | Extension of the institutional strengthening project (phase X: 7/2022-6/2024) | 2022-06-01 | 2024-06-01 | ONG |  | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 85000 | 0 | 85000 | 0% | 85000 | 0 | 0 | 0 | 0 | 0 | 85000 | 42500 | 0 | 0 |  | 42500 |  |  | Good progress. Work plan and timetable to implement the project agreed with the NOU. SSFA was signed by UNEP and submitted in April 2023 to the country for countersignature. The SSFA has an overall amount of USD 85,000 payable in three disbursements. The first disbursment of an amount of USD 42,500 has been submitted the country September 2023. This SSFA will facilitate obtaining products and expected results as mentioned below:(1) Adoption and implementation of ODS legislation and ODS consumption monitoring and control regulation, (2) Efficient and timely data collection and submission, (3) Consultation and coordination with other national agencies/stakeholders, ( 4) Supervision of timely implementation of ODS consumption elimination and reduction activities, (5) Awareness raising and information exchange, (6) Regional cooperation and participation in Montreal Protocol meetings. CP Data for 2022 reported in May 2023 and A7 data in September 2023. World Ozone Day has been celebreated in September 2023. NOU/Government representatives participated in the virtual webinars organized by OzonAction Latin American team: Communication strategy "Kigali in Action, Inclusive Language " (November 2023). | Good progress. Work plan and timetable to implement the project agreed with the NOU. SSFA was signed by UNEP and submitted in April 2023 to the country for countersignature. The SSFA has an overall amount of USD 85,000 payable in three disbursements. The first disbursment of an amount of USD 42,500 has been submitted the country September 2023. CP Data for 2023 reported in May 2024. he NOU organized several trainings for important companies, totally 65 (15 woman / 40 man) particpated during the sessions organized between January 2024 to March 2024. The licesing system for HFCs and HCFCs is fully operation and quota has been established. Several inspections have been conducted in the framework to combate illegal trade. | Yes
|  | KYR/SEV/91/INS/48 | UNEP | Government Support | EUR | KYR | INS | National Ozone Unit | Extension of the institutional strengthening project (phase XI: 1/2023-12/2024) | 2022-12-01 | 2024-12-01 | ONG | 2023-11-28 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 204602 | 0 | 204602 | 37.99% | 126877 | 0 | 0 | 0 | 0 | 77725 | 126877 | 63438.5 | 0 | 0 |  | 122275 |  |  | The current ODS legislation was analyzed and recommendations for improvement compiled. On 16 October 2023, a workshops for Customs Officers on the state regulations related to the import, export and transit of HFCs, and the prevention of illegal trade took place in Osh on 16 October 2023, and in Leninskoe on 18 October 2023. To collect import data for HFCs and alternative refrigerants for 2022, official letters were sent to the State Customs Service, National Statistical Committee of and to organizations using ODS, F-gases and alternative refrigerants. The updated survey data were submitted to the lead agency UNDP on 24 February 2023. CP data for 2022 were submitted to MFS in March 2023. Article 7 data for 2022 were submitted to the Ozone Secretariat in June 2023. On 19 September 2023, the Interagency Commission on Ozone and the development of the State Program for the HFC phase-down for 2024-2029 met in Bishkek. On 26-27 June 2023, the 17th Congress of Refrigeration Industry Specialists of took place in Cholpon-Ata, Issyk-Kul region. The draft KIP stage I was prepared with UNDP as lead agency and UNEP as cooperating agency. It was presented during a seminar in Bulan Sogottu village on 23 June 2023. On 16-22 July 2023, an information campaign with the theme “Fixing the ozone layer”. Stakeholders were consulted on the development of a communication and awareness strategy. Word Ozone Day activities were organized during the children’s summer camps in Issyk-Kul oblast. About 2000 children participated in this campaign. A series of WOD seminars took were organized at the Secondary School No. 35 in Bishkek on 19 September 2023, the Kyrgyz State Technical University and the Vocational Lyceum No. 93 on 20 September 2023, the school in the village of Budenovka, Issyk-Ata district on 26 September 2023, the Gymnasium School No. 69 in Bishkek on 28 September 2023, at the Secondary School No. 13 in the KyzylKiya, Batken oblast 3 October 2023, at the Secondary School No. 21 in JalalAbad on 5 October 2023, at the Osh Technological University on 6 October 2023, at Zhetygen Secondary School on 7 October 2023 In 2023, the following websites were updated: www.climate.kg, www.ozonecenter.kg, www.ecoholod.com.kg. Project activities were covered the the mass media. MPU staff participated in Montreal Protocol meetings as well as ECA network meetings (physical and online meetings). An initial gender assessment related to women’s participation in RACHP sector activities has been conducted. In 2023, the participation of women in meetings was monitored: 5 workshops on the HFC phase-down (12% women), 2 training seminars for customs services (18% women), 9 public awareness events (63% women). | The Government introduced an annual quota for import of HFCs for the period 2024-2029. An interdepartmental working group on standards development was established. The Government enacted five new interstate standards in the RAC sector. Analysis of legislation on energy efficiency in the RAC sector and harmonization of EE policy with the legislation of the Eurasian Economic Union was carried out. CP data report for 2023 was submitted to MLF in April 30, 2024. Four seminars were held to raise awareness of equipment importers and sellers, as well as for RAC sector specialists on good maintenance practices to improve energy efficiency. Based on the tenders, 11 manuals and brochures, 2 posters on energy efficiency, MEPS, EE labeling, good maintenance practices for energy efficiency were prepared and published in printing house. NOU staff participated in ECA meetings in North Macedonia and Albania. The NOU staff participated and made presentations at the international RAC scientific-practical conference in Kazakhstan. Based on the conducted work with HFC importers, a report on HFC consumption for 2023 was developed. A tender for the development of video clips and info posters was held, based on the results of which 2 video clips and 2 infographics on EE were created. Market assessment is being conducted to analyze the type of equipment that is imported. Stakeholder consultations on MEPS and EE labeling are conducted. Updating of the NOU website is carried out on a regular basis. Gender data is tracked during the workshops in accordance with the Multilateral Fund's gender policy. | Yes
|  | LES/SEV/90/INS/29 | UNEP | Government Support | AFR | LES | INS | National Ozone Unit | Extension of the institutional strengthening project (phase XI: 1/2023-12/2024) | 2022-06-01 | 2024-12-01 | ONG | 2023-08-18 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 85000 | 0 | 85000 | 47.06% | 45000 | 0 | 0 | 0 | 0 | 40000 | 45000 | 22500 | 0 | 0 |  | 35000 |  |  | The second payment of USD 35,0000 was released to the country in August 2023. The Draft ODS and HFCs Regulation was submitted to the Office of Parliamentarians Council (OPC) for Review in September 2023. The NOU conducted awareness and sensitisation workshop on Multilateral Environment Agreements (MEAs) from 22nd to 24th May 2023. The collection of data was undertaken to report A7 and CP data for the year 2022. Both the Article 7 and Country Programme data for 2022 were reported by April 2023. The NOU conducted three meetings for industry associations. The trainings were held at Lerotholi Polytechnics from 15th to 17th November 2023, Catholic Comprehensive Community College from 27th to 29th November 2023 and Technical Institute of Leloaleng from 4th to 6th December 2023. The training workshops were attended by 15 female and 75 male. The customs training workshops were held at Mmelesi Lodge from 6th to 7th November 2023, Mountain View Hotel from 8th to 9th November 2023 and from 13th to 14th November 2023. The participants were 26 males and 64 females. The International Ozone Day for 2023 was celebrated in Lesotho with several activities. 500 T shirts and Caps were printed. The activities were attended by 90 female and 100 male. 600 leaflets and brochures were distributed to the stakeholders, the media and factory workers to raise awareness on Ozone Layer protection. The NOU participated in the Regional Training Workshop for Female RAC Technicians held from 17 to 19 January 2023 in Cairo, Egypt, attended by 18 female technicians. The NOU participated in the Regional Network Meeting for National Ozone Officers of the English-Speaking African Countries back-to-back with Thematic Workshop for Customs Officers held from 8-12 May 2023 in Kigali, Rwanda. The NOU participated in the border dialogue meeting from 24th to 26th July 2023, Mhlume, Eswatini. The NOU participated at the 35th Meeting of the Parties to the Montreal Protocol, held in Nairobi from October 23 to 27, 2023. The overall performance of the project is satisfactory. The project is progressing satisfactorily. | The ODS and non-ODS Regulations 2024 was signed to include control of hydrofluorocarbons (HFCs). The NOU conducted border post inspections from 15 to 26 April 2024 for Mafeteng, Mohale’s Hoek, Quthing, Qacha’s Nek, Butha Buthe, Maputsoe and Maseru Bridges. The NOU conducted environmental inspectors and law enforcement training workshops from 27th to 28th March 2024. The meeting was attended by 30 participants (14 female and 16 male). The collection of data was undertaken to report A7 and CP data for the year 2023. Both the Article 7 and Country Programme data for 2023 were reported by May 2024. The NOU conducted a meeting for the Association of Refrigeration and Air conditioning held on 19th April 2024. The implementation is satisfactory and on schedule. The programme activities are satisfactory. | Yes
|  | BAH/SEV/90/INS/44 | UNEP | Government Support | ASP | BAH | INS | National Ozone Unit | Extension of the institutional strengthening project (phase XI: 7/2022-6/2024) | 2022-06-01 | 2024-06-01 | ONG | 2022-09-01 | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 85000 | 0 | 85000 | 47.06% | 45000 | 0 | 0 | 0 | 0 | 40000 | 45000 | 22500 | 0 | 0 |  | 35000 |  |  | Progress Report: - SSFA signed in Aug. 2022 and first payment made in Sep. 2022; The quota for the year 2023 issued and strictly enforced. Regular meetings of the NOC are held under the leadership of the SCE. E-licensing is operational. - Project related activities have been progressing according to the plan. CP data reporting for 2022 has been submittted. interim progress report has been received in May 2023. - ISP is played key role in facilitating the compliance of Bahrain with MP targets and sound implementation of the HPMP stage I and prep of stage II HPMP in addition to the KEA project. | Progress Report: - SSFA signed in Aug. 2022 and first payment made in Sep. 2022; all planned activities have been implemented successfully including quota for the year 2024 issued and being strictly enforced. Regular meetings of the NOC are continued under the leadership of the SCE. E-licensing is operational. renewal request for next phase have been finalized and submitted to ExCom-94. - Project related activities have been progressing according to the plan. CP data reporting for 2022 has been submittted. interim progress report has been received in May 2023. - ISP is played key role in facilitating the compliance of Bahrain with MP targets and sound implementation of the HPMP stage I and prep of stage II HPMP in addition to the KEA project. | Yes
|  | MDV/SEV/90/INS/37 | UNEP | Government Support | ASP | MDV | INS | National Ozone Unit | Extension of the institutional strengthening project (phase XII: 12/2022-11/2024) | 2022-06-01 | 2024-11-01 | ONG | 2023-12-31 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 85000 | 0 | 85000 | 50% | 42500 | 0 | 0 | 0 | 0 | 42500 | 42500 | 21250 | 0 | 0 |  | 0 |  |  | SSFA was signed in January 2023 for USD 85,000. First payment transferred in February 2023. NOU hired 1 Project Assistant in October 2023. Licensing/quota system enforced. NOU received the import data quarterly from Maldives Customs Service. NOU monitored the amount of refrigerants imported through the Makudi system and compared it with the yearly data provided by Maldives Customs Service. The NOU has submitted A7 & CP data report for the year 2022 in a timely manner. Training held for Customs brokers in July 2023 with total 35 (M:23, F:12) participants. Refrigerant Driving License (RDL) training programme was conducted for 12 (M:12, F;0) technicians. Steering committee has been formed but need to be reconfirmed following the change of government administration. Pemphis (the inhouse publication for ozone related articles) articles released on World Ozone day, elections was scheduled close to Ozone day therfore no special event could be organized this year. NOU in collaboration with UNEP organized the SA regional network meeting in the Maldives in May 2023. NOU staff participated in the network meeting in Phuket, Thailand in November 2023, and represented Maldives in the OEWG and MOP. | Second payment transferred in February 2024. Licensing/quota system is being enforced. HFC import quota for 2024 allocated to importers. CP data for 2023 submitted to MLFS and A7 data for 2023 submitted to OS in a timely manner. | Yes
|  | GUI/SEV/90/INS/41 | UNEP | Government Support | AFR | GUI | INS | National Ozone Unit | Extension of the institutional strengthening project (phase XII: 7/2022-6/2024) | 2022-06-01 | 2024-06-01 | ONG |  | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 85000 | 0 | 85000 | 0% | 85000 | 0 | 0 | 0 | 0 | 0 | 85000 | 42500 | 0 | 0 |  | 40000 |  |  | Licensing system is fully operational. The quota for the year 2023 was issued. Importers complied with issued quotas for the year 2022. A7 and CP data for 2022 reported to the 2 Secretariats. The National Ozone Unit celebrated the Ozone Layer, which took place on September 16, 2023. Two Steering Committee meeting was held in JAnuary and August 2023 to evaluate the way forward in the implementation of 2023 action plan of NOU. The NOU participated in the Regional Thematic Meeting for Francophone Network of Ozone Officers in 2023. | The Licensing system fully operational. 2023 Art7 data submitted to the Ozone Secretariat in May 2024. Zero CFC consumption is maintained for the year 2023. Periodic meeting in January with the NOC to validate the annual work program, set annual HCFC import quotas fro the year 2024. | Yes
|  | MLW/SEV/90/INS/52 | UNEP | Government Support | AFR | MLW | INS | National Ozone Unit | Extension of the institutional strengthening project (phase XIII: 1/2023-12/2024) | 2022-06-01 | 2024-12-01 | FIN | 2023-05-19 |  | 2023-12-01 | 2023-12-01 | 0 | 0 | [6 empty] | 85418 | 0 | 85418 | 100% | 0 | 0 | 0 | 0 | 0 | 85418 | 0 | 0 | 0 | 0 |  | 0 |  |  | The second payment of USD 35,000 was released to the country in June 2023. A draft revised Environmental Management (Ozone Depleting Substances) Regulations are being finalized by the Ministry of Justice and Constitutional Affairs to include control measures for HFCs. Follow-ups have been made in January 2023. A stakeholder meeting with enforcement agencies was held on 13th March 2023. During the meeting, enforcement officers were re-oriented on ODS regulations and urged to continue enforcing the regulations to prevent illegal trade in ODS. The NOU organized two meetings / trainings with enforcement bodies from 14th to 15th February 2023 and on 10th April 2023. A total of 40 customs officers (25 men and 15 women) were trained on identification and control of HCFCS and other ODS including CFCs, implementation of ODS Regulations, licensing and quota system for ODS including the phase out of HCFC. Six compliance monitoring inspections were conducted; 16th to 18th January in Blantyre and Zomba; 14th to 15th March in Mzuzu;19th to 21st June in Lilongwe; 17th to 23rd September in Mzuzu and Karonga;14th to 16th November and 19th to 22nd December. Total of 15 importers and 22 suppliers of refrigeration equipment and refrigerants were visited to ensure compliance to the ODS Regulations. Furthermore 8 customs boarder stations were visited to enhance enforcement of ODS Regulations. The NOU further updated the database of all importers of controlled substances on 24th April 2023to ensure effective monitoring processes on imports of the substances. Article 7 data and Country programme data for 2022 was timely submitted to the Ozone and MLF Secretariats respectively in April 2023. Project Steering Committee meeting to review progress on implementation of project activities and allocation of quotas to importers for HCFCs was held on 9th January 2023. The committee provided guidance and direction on the implementation of all activities under the protocol. The meeting also approved HCFCs quotas for 2023. A training session for RAC technician was held from 26-27th April 2023 in Lilongwe. A total of 20 RAC experts (15 Males and 5 Females) were trained on good refrigeration practices including safe handling of flammable and toxic refrigerants. The NOU facilitated two meetings of RAC associations which were held in Lilongwe on 4th April and in Mzuzu on 19th November. The meetings reviewed the activities of the association with regards to implementation of code of conduct of RAC technicians as well as the certification of the technicians. Celebrated the World Ozone Day under the theme “Montreal Protocol: fixing the ozone layer and reducing climate change”. Key activities included panel discussions and orientation meeting with importers on adoption of energy efficiency technologies in the country. Awareness meeting on the phase-down of HFCs was undertaken on 8th January 2023. The meeting sensitized members of district councils on benefits of adopting HFCs-alternatives to maximize climate and energy efficiency benefits. A total of 23 officers attended the meeting. The NOU facilitated the commemoration of world refrigeration day for female RAC technicians on 26th June in Lilongwe and Blantyre. Women RAC technicians were encouraged to actively participate in all programs on the protection of ozone layer. The NOU participated at a Network Meeting for Anglophone Ozone Officers in Rwanda from 8th to 12th May 2023. The NOU participated at the 45th OEWG meeting held in Bangkok, Thailand from 3rd to 7th July 2023 and the 35th meeting of the parties to the Montreal Protocol in Nairobi, Kenya from 23rd to 24th October 2023. The project impact is the reduced consumption of controlled substances in the country. The overall assessment of the project is satisfactorily completed. | The project is financialy completed | Yes
|  | FIJ/SEV/91/INS/43 | UNEP | Government Support | ASP | FIJ | INS | National Ozone Unit | Extension of the institutional strengthening project (phase XIII: 7/2023-6/2025) | 2022-12-01 | 2025-06-01 | ONG | 2023-10-01 | 2025-06-01 |  |  | 0 | 0 | [6 empty] | 120000 | 0 | 120000 | 17.75% | 98700 | 0 | 0 | 0 | 0 | 21300 | 98700 | 49350 | 0 | 0 |  | 38700 |  |  | Although the project is planned to start from July 2023, there was delay in the signature of the SSFA in September 2023 due to lengthy legal process and government national approval processes. Despite the delay the NOU continued with project implementation. The first payment of US$ 60,000 was released in October 2023. The NOU continues to enforce HCFC/HFC quota and licensing system. NOU liaised with UNEP on the establishment of the HFC quota. NOU continued to conduct 35 inspections of importers/exporters including market/end-users. One inspection was conducted for 20 companies in the North. One RAC association meetings was conducted. For the World Ozone Day in 2023, the NOU organized a commemoration with schools and set up a booth to interact with and raise awareness of the event participants. The NOU also utilized newspaper and social media in raising awareness of general public. Awareness materials such as mousepads for customs and businesses as well as “snakes and ladders” for schools were produced. The country actively participated in meetings organized by UNEP, the 45th OEWG and in Samoa, participated in the; 1) regional network meeting, 2) thematic workshop on nation-wide data collection under the KIP preparation, and 3) Twinning workshop on ODS/HFC trade control and reporting. The gender activities included promotion of gender mainstreaming into project activities such as equal access and equal treatment to participate in training and meetings | The NOU continues to enforce HCFC/HFC quota and licensing system. HFC quota system has been implemented with the allocated amount of 411,964 tonnes CO2 equivalent distributed to authorized importers. CP data for the year 2023 collection has been completed and will be submitted by May 2024. Two (2) inspections were conducted in 2024 for 52 companies in the west and 26 companies in the north. RAC association meetings was held in 2nd quarter of 2024. The NOU is carrying out a social media campaign involving influencers, and set up a digital display advertisement stand at the office entrance showing awareness materials about permits and videos. The NOU participated the Twinning Workshop of Montreal Protocol Officers, Energy-Efficiency Policy Makers and Financial Mechanisms Focal Points to Support Kigali Amendment Objectives, Thematic Workshop on Establishment and Implementation of Competency- based Certification, Thematic Workshop on Strategy of Stage I of the KIP and Integration with the HPMP Stage II for Pacific Island Countries from 5-10 February 2024 in Cook Islands. In June 2024 in Palau, the country will participate in the regional network meeting, regional training of NOUs, and thematic workshop on finalization of KIP Stage I. | Yes
|  | VIE/SEV/91/INS/84 | UNEP | Government Support | ASP | VIE | INS | National Ozone Unit | Extension of the institutional strengthening project (phase XIV: 7/2023-6/2025) | 2022-12-01 | 2025-06-01 | ONG | 2023-09-19 | 2025-06-01 |  |  | 0 | 0 | [6 empty] | 210159 | 0 | 210159 | 17.59% | 173199.25 | 0 | 0 | 0 | 0 | 36959.75 | 128549.4 | 86599.625 | 0 | 0 |  | 49260.4 |  |  | The project was approved at the Excom-91 in December 2022. The SSFA was signed in September 2023 with retroactive clause to cover the expenditure incurred from 1 July 2023. The first payment of US$ 73,000 was released in October 2023. The Article 7 was submitted to the Ozone Secretariat on 29 September 2023. The NOU continued to coordinate implementation of the HPMP Stage II and preparation for KIP Stage I and HPMP Stage III. NOU organized the 2023 World Ozone Day celebration. The NOU participated in the Advanced National Ozone Officers Training Workshop back-to-back with the Joint Network Meeting of South Asia and Southeast Asia National Ozone Officers in Thailand in November 2023. NOU also attended the Open-ended Working Group (OEWG45) in July 2023 and the Meeting of the Parties in October 2023. NOU continued to implement the following gender activities: encouraging female participants in the meetings/training under the project and collection of gender-disaggregation data in project activities. | HFC quota system has been implemented since 1 January 2024. Therefore, HCFC quota and HCFC/HFC licensing system are fully operational in 2024. NOU cooperated with the General Department of Vietnam Customs to control HCFC and HFCs import/export in accordance with amended regulations. The collection of data was undertaken to report CP data for the year 2023 which included HFC import/export data. The CP data was submitted to the MLFS on 4 May 2024. The NOU will participate in the Energy Efficiency Twinning Workshop back-to-back with the Joint Network Meeting of South Asia and Southeast Asia National Ozone Officers in China in May 2024. | Yes
|  | KAM/PHA/90/TAS/42 | UNEP | HPMP1 | ASP | KAM | TAS | Servicing | HCFC phase-out management plan (stage I, fifth tranche) | 2022-06-01 | 2025-12-01 | ONG | 2023-09-19 | 2025-12-01 |  |  | 4.9 | 0 | [6 empty] | 200000 | 0 | 200000 | 33.96% | 132075.81 | 26000 | 0 | 26000 | 17169.8553 | 67924.19 | 121665.48 | 66037.905 | 8830.1447 | 15816.5124 |  | 6256.48 |  | 2032-12-01 | The project was approved at the Excom-90 in June 2022. The SSFA was signed in January 2023. The first payment of US$ 70,000 was released in February 2023. UNEP conducted a country mission in March 2023 to discuss workplan of the tranche. NOU continued to inspect type of HCFC-22 and apply sticker before allowing importers to release HCFC-22 to domestic market as part of mandatory labeling requirement. NOU conducted 3 customs training workshops with total 70 participants (45 M/25 F), 1 train-the-trainer for RAC GSP and 4 training workshops for RAC technicians with total 191 participants. NOU worked closely with the IT consultant to design the mobile application for certified RAC technicians based on experience of other countries presented during the Network Meeting in October 2022. The mobile application will facilitate owners of air-conditioner to assess the information on contact detail and rating of certified RAC technicians for the installation and servicing of appliance. NOU followed up with the Department of Standard and Curriculum, Ministry of Labor and Vocational Training, Vocational Training School on agreement/MOU as well as the launching of competency-based certification. NOU and relevant stakeholders attended the study visit on establishment and implementation of competency-based certification of RAC servicing sector in Indonesia in October 2023. 2 identified master assessors from Cambodia also attended training of master assessors on competency-based certification in Kuala Lumpur in November 2023. The following gender activities were implemented: encouraging female participants in the meetings/training under the project and collection of gender-disaggregation data in project activities. | The second payment of US$ 63,000 was released in April 2024. NOU plans for training of Customs and RAC technicians. NOU held discussion with the Ministry of Labor and Vocational Training and training centers to identify the assessment centers and establish mechanism to assess and certify RAC technician. The mobile application is being developed and planned to be completed by end of 2024. | Yes
|  | PRC/PHA/91/TAS/39 | UNEP | HPMP1 | AFR | PRC | TAS | Servicing | HCFC phase-out management plan (stage I, fifth tranche) | 2022-12-01 | 2023-12-01 | COM |  |  | 2023-12-01 |  | 0 | 0 | [6 empty] | 35000 | 0 | 35000 | 0% | 35000 | 4550 | 0 | 4550 | 4550 | 0 | 35000 | 35000 | 0 | 4550 |  | 17500 |  | 2023-12-01 | The SSFA was signed in May 2023. The first payment has been released to the country in May 2023. A workshop training for 19 refrigeration technicians participated on the first day and 19 on the second day, making 38 participants, including two females. Refrigeration specialists received training on R-22 recovery and recycling methods | The second and final payment has been disbursed in June 2024. The project is completed. | Yes
|  | IVC/PHA/90/TAS/48 | UNEP | HPMP1 | AFR | IVC | TAS | Servicing | HCFC phase-out management plan (stage I, fifth tranche) | 2022-06-01 | 2022-12-01 | FIN | 2022-11-01 |  | 2022-12-01 | 2023-12-01 | 0 | 0 | [6 empty] | 185740 | -380 | 185360 | 100% | 0 | 22482 | -46 | 22436 | 0 | 185360 | 0 | 0 | 22436 | 0 |  | 0 |  | 2022-12-01 | The project is completed and operationnaly closed. | The project is financialy completed | Yes
|  | EQG/PHA/90/TAS/19 | UNEP | HPMP1 | AFR | EQG | TAS | Servicing | HCFC phase-out management plan (stage I, fifth tranche) | 2022-06-01 | 2023-12-01 | COM |  |  | 2023-12-01 |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 30000 | 30000 | 0 | 3900 |  | 15000 |  | 2023-12-01 | SSFA was signed by both in June 2023. First payment disbursed in September 2023. From 20 to 23 September and 09 to 12 October 2023, 15 customs officers trained at the workshop for customs inspectors, enabling them to identify controlled refrigerants, understand the characteristics of licenses, and the authorized HCFC import quota for each importer. From 22 to 28 october 2023, Conducting surveys to gather information on HCFCs used in the service sector, gathering information on policy initiatives related to the elimination of HCFCs. | The second and final payment has been released to the country in April 2024, due to delayed reporting from the NOO. The project is completed | Yes
|  | MOZ/PHA/90/TAS/38 | UNEP | HPMP1 | AFR | MOZ | TAS | Servicing | HCFC phase-out management plan (stage I, fifth tranche) | 2022-06-01 | 2023-06-01 | FIN | 2023-07-11 |  | 2023-06-01 | 2023-12-01 | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 100% | 0 | 3900 | 0 | 3900 | 0 | 30000 | 0 | 0 | 3900 | 0 |  | 0 |  | 2023-06-01 | The final payment of USD 5,000 was released to the country in August 2023. The NOU participated at the Network Meeting for Anglophone Ozone Officers in Rwanda from 8th to 12th May 2023. The NOU participated at the 45th OEWG meeting held in Bangkok, Thailand from 3rd to 7th July 2023 and the 35th meeting of the parties to the Montreal Protocol in Nairobi, Kenya from 23rd to 24th October 2023. The project impact is the reduced consumption of controlled substances in the country. The project is completed satisfactorily. | The project is financially completed | Yes
|  | BAR/PHA/91/TAS/35 | UNIDO | HPMP1 | LAC | BAR | TAS | Servicing | HCFC phase-out management plan (stage I, fourth tranche) | 2022-12-01 | 2023-12-01 | COM |  |  | 2023-12-01 |  | 0 | 0 | [6 empty] | 28000 | 0 | 28000 | 0% | 28000 | 3640 | 0 | 3640 | 3640 | 0 | 28000 | 28000 | 0 | 3640 |  | 22400 |  | 2023-12-01 | SSFA was signed on 06 September 2023. 1st cash advance payment of 22,400 disbursed 13 Nov 2023. The following activities have been implemented: Customs consulted on an HCFC prohibited list; Standards institution consulted on labelling standards for the RAC sector; The following reports were prepared 1) A report of the feasibility of incentives reviewed with preliminary recommendations, 2) A draft framework for licensing and certification of RAC technicians proposed, 3) A draft ozone-depleting substances phase-out policy prepared; 1 sensitisation meeting convened in September 2023 promoting Caribbean Vocational Qualification to 70 participants including 7 females; Consultation with customs for continued future training; draft brochure on HCFC phase-out prepared for dissemination; 48 Radio and 12 television PSAs were disseminated. | Project COM. UNEP processing the final cash advance under the SSFA. | Yes
|  | MAU/PHA/91/TAS/30 | UNIDO | HPMP1 | AFR | MAU | TAS | Servicing | HCFC phase-out management plan (stage I, second tranche) | 2022-12-01 | 2025-12-01 | ONG | 2023-12-30 | 2025-12-01 |  |  | 2.2 | 0 | [6 empty] | 66750 | 0 | 66750 | 49.44% | 33750 | 8678 | 0 | 8678 | 4387.7528 | 33000 | 33750 | 16875 | 4290.2472 | 4387.7528 |  | 0 |  | 2026-12-01 | The SSFA was signed by both in March 2023. The first payment was disbursed in May 2023. Licensing system is fully operational. | The second payment was disbursed in Februaty 2024.The National Ozone Bureau in Mauritania successfully conducted a data collection mission on HCFC R-22 consumption from September 25 to October 12 in Dakhlet Nouadhibou, Inchiri, and Trarza regions to assess its impact on the ozone layer. Improvement of the licensing and quota system aims to structure the database for inter-agency exchange integration. Organizing a mission to reassess HCFC consumption stock nationwide. Workshop training for 30 refrigeration technician trainers on best practices, including refrigerant recovery, recycling, reuse techniques, safety, and handling. Training workshop for 15 customs officers, 15 Environmental Police Officers, and decentralized Environmental Delegation members on HCFC and SAO-based equipment control and identification. Import traders' workshop on licensing and quotas, emphasizing refrigerant risks. Date: August 15, 2023, Nouadhibou. Awareness campaign for traders and technicians on import procedures and refrigerant risks during Ozone layer restoration. Includes manual and poster distribution. | Yes
|  | SSD/PHA/91/TAS/07 | UNIDO | HPMP1 | AFR | SSD | TAS | Servicing | HCFC phase-out management plan (stage I, second tranche) | 2022-12-01 | 2024-04-01 | ONG | 2023-10-31 | 2024-12-01 |  |  | 0.3 | 0 | [6 empty] | 70500 | 0 | 70500 | 0.0899% | 70436.62 | 9165 | 0 | 9165 | 9156.7606 | 63.38 | 70436.62 | 35218.31 | 8.2394 | 9156.7606 |  | 42000 |  | 2025-12-01 | The first payment of USD 42,000 was released to the country in June 2023. The Ratification of the Kigali Amendment is on process. Thee Ministry of Foreigner Affairs and International Cooperation forwarded the Instrument of Ratification to the Ministry of Justice for legal considerations on 10th January, 2023. The collection of data was undertaken to report A7 and CP data for the year 2022. The A7 Data Reporting for 2022 was reported on 20th April, 2023. The Country Programme data for 2022 was reported on 24th February, 2023. The NOU participated at the Regional Network Meeting for National Ozone Officers of the English-Speaking African Countries back-to-back with Thematic Workshop for Customs Officers from 8-12 May 2023 in Kigali, Rwanda. The Regional Network Meeting, attended by 26 out of 28 countries of the English-speaking African networks (37 male, 30 female), provided opportunity for the countries to further discuss key information and data to be collected in preparation of a KIP Strategy and approaches. The NOU participated at the 45th OEWG meeting held in Bangkok, Thailand from 3rd to 7th July 2023 and the 35th meeting of the parties to the Montreal Protocol in Nairobi, Kenya from 23rd to 24th October 2023.The project is progressing satisfactorily. | The NOU conducted a training workshop for 5 female technicians on best refrigerant practices from 27-28 March 2024. The NOU conducted two trainings for RAC Technicians on best refrigeration practices including recovery and recycling of refrigerants and safe handling of flammable refrigerant alternatives from 27- 28 March 2024 in Juba, South Sudan. The project is progressing satisfactorily. | Yes
|  | SYR/PHA/91/TAS/114 | UNIDO | HPMP1 | ASP | SYR | TAS | Servicing | HCFC phase-out management plan (stage I, second tranche) | 2022-12-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 4.6 | 0 | [6 empty] | 418100 | 0 | 418100 | 0% | 418100 | 49448 | 0 | 49448 | 49448 | 0 | 0 | 209050 | 0 | 0 |  | 0 |  | 2026-12-01 | Negotiation is still ongoing with the NOU to agree the modality for implementing this tranche noting the challenge to enter into agreement with the Government. | Negotiation is still ongoing with the NOU to agree the modality for implementing this tranche noting the challenge to enter into agreement with the Government. | Yes
|  | GRN/PHA/90/TAS/31 | UNIDO | HPMP1 | LAC | GRN | TAS | Servicing | HCFC phase-out management plan (stage I, third tranche) | 2022-06-01 | 2023-12-01 | COM |  |  | 2023-12-01 |  | 0 | 0 | [6 empty] | 21000 | 0 | 21000 | 0% | 21000 | 2730 | 0 | 2730 | 2730 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 2023-12-01 | The SSFA was signed on 9 December 2023. The following activities have been implemented: 3 final rounds of stakeholder consultations held with RAC stakeholders on the revised ODS legislation; ODS leglisation submitted for cabinet approval; Review of existing standards for RSS completed; Drafting of new/revised standards ongoing; 48 technicians trained and certified in alternative low-GWP refrigerant technologies; 16 Customs officers trained in the control and Monitoring of Trade in ODS; 44 importers trained in the safe handling, transportation, storage, and disposal of refrigerants; 100 print materials on alternative refrigerant technologies developed and distributed; Activities were completed in the 2023. Country to submit final reports to complete the project | Final progress report and final expenditure reports received in Febuary 2024. Project is completed. | Yes
|  | CPR/PHA/91/TAS/615 | UNIDO | HPMP2 | ASP | CPR | TAS | Servicing | HCFC phase-out management plan (stage II, fifth tranche) (servicing sector plan and enabling programme) | 2022-12-01 | 2023-12-01 | ONG | 2023-12-29 | 2025-12-01 |  |  | 65.2 | 0 | [6 empty] | 1780000 | 0 | 1780000 | 22.5% | 1379546 | 195325 | 0 | 195325 | 151381.9227 | 400454 | 1145846 | 689773 | 43943.0773 | 125737.2865 |  | 99546 |  | 2027-12-01 | Tranche 5 under the HPMP Stage II was approved by the ExCom at its 91st meeting at the amount of US$ 2,000,000, consisting of US$ 1,78,000 for UNEP and US$ 220,000 for Germany. The PCA for tranche 5 was signed in July 2023 between FECO/MEE and UNEP with the amount of US$ 1,546,300. The first instalment of US$ 500,000 was released to FECO/MEE in August 2023. The total expenditure of FECO/MEE US$400,454 as of 31 December 2023. Furthermore, FECO/MEE has obligated total of US$ 1,149,500 under the signed contracts with various partners, but does not cover the funds for the planned outreach or enabling training activities. The retained component by UNEP was committed in the amount of US$ 203,700. ACTIVITY 1.1 POLICY STUDIES AND STANDARDS/CODES DEVELOPMENT: Continued work from Tranche 4 on standards/technical code development, ACTIVITY 1.3: OUTREACH AND PILOT ACTIVITIES: Made preparations and held planning meetings for the 2024 Ozone2Climate Roadshow and Roundtable Event. Continued iplementation of activities for Pilot Cities (Zhejiang and Tianjin). ACTIVITY 2.1: CAPACITY BUILDING: National Training workshop/seminar (Training of about 240 EEB management officials/200 law enforcement officers through four (4) training workshops), Local capacity building of six (6) EEBs (continuation), Organize coordination meeting(s), Overseas training/study tour, Expert consultations held. ACTIVITY 2.2: OUTREACH AND COMMUNICATIONS: Held Celebration of World Ozone Day, Designed and produced outreach materials, Maintained the ozone website ACTIVITY 2.3: STRENGTHENING IMPORT & EXPORT (I&E) MANAGEMENT: Study relationship of national trade policy and ODS control (continuation), Training on ODS import/export control; Outreach materials; (2 training workshops for customs both supervision departments and anti-smuggling deportments with 150 officers lo be trained, and 2 training workshops for enterprises with 200 participants), Strengthening the law enforcement capacity building of China Customs to combat ODS illegal trade (phase Ill) (continuation), Establishment of the law enforcement cooperation center for combating illegal trade of ODS (continuation), Develop Guidance of Operation for the investigation and processing ODS illegal trade and case studies (continuation), Certification Authority service on the ODS paperless approval system (continuation). | PCA with CAR signed in April 2024 for $130,000. PCA with CRAA signed in April 2024 for $70,000. 1.3.3: Ozone2Climate Roadshow and Roundtable Events: 2024 Ozone2Climate Technologies Roadshow and Roundtable organized April 8-10 2024, online exhibition to widely promote and display the Ozone friendly technology in development. | Yes
|  | BHA/PHA/90/TAS/33 | UNIDO | HPMP2 | LAC | BHA | TAS | Servicing | HCFC phase-out management plan (stage II, first tranche) | 2022-06-01 | 2025-06-01 | ONG |  | 2025-06-01 |  |  | 1 | 0 | [6 empty] | 81200 | 0 | 81200 | 0% | 81200 | 10556 | 0 | 10556 | 10556 | 0 | 0 | 40600 | 0 | 0 |  | 0 |  | 2031-12-01 | SSFA signed 22 Sept 2023. First cash advance being processed. Country preparing a workplan for the implementation of activities. NOU organizing the training workshops for RAC technicians, with the focus of also identifying more women in the RSS that need to be trained or participate in training activities as presenter or in orther forms; identifying suitable consultants to undertake the legislative amendments and market analysis on the use of R22; and consulting on suitable public awareness programme to support activities and mainstrem gender. | SSFA signed 22 Sept 2023. First cash advance disbursed 20 Feb 2024. The NOU has completed the following: The Electronic Licensing and Quota System (e-LQS) has been operational successfully since its establishment in Dec 2022; A special awareness and education progamme for the HPMP II, developed and has been incorprated into the training syllabus of the trade school. This is geared towards importers, technicians and service shops. The programme is also incorported into their consultative process and targets industry to ensure their are fully updated on the HPMP II and the transtion to low GWP, more energy efficient alternatives; The NOU has been consultting with the Trade School to determine the number of certified techncians that have been hired by service workshops; The NOU has been promoting the particiation of women in the RSS through more training opportunities, greater visibility as presenters and greater use of imagery in awareness materials. The NOU has been cooperating with the trade shcool to continue the certification of RAC technicians. | Yes
|  | BAR/PHA/91/TAS/34 | UNIDO | HPMP2 | LAC | BAR | TAS | Servicing | HCFC phase-out management plan (stage II, first tranche) | 2022-12-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0.7 | 0 | [6 empty] | 36000 | 0 | 36000 | 0% | 36000 | 4680 | 0 | 4680 | 4680 | 0 | 36000 | 18000 | 0 | 4680 |  | 18000 |  | 2031-12-01 | SSFA was signed on 06 September 2023. 1st cash advance payment of 18,000 disbursed 10 Nov 2023. Workplan endorsed and NOU organizing meetings, sensitization and consultations along with the various activities related to implementation, monitoring and reporting under the tranche. | SSFA was signed on 06 September 2023. 1st cash advance payment of 18,000 disbursed 10 Nov 2023. NOU is preparing to conduct activities to Improve policy, legislative and regulatory framework; The NOU has planned sensitisation meetings with key stakeholders in the 3rd quarter of 2024 to provide information on the ban and other legislative measures. Printed materials, that portray females, in HPMP phase-down activities, have been drafted and planned to be distributed to all stakeholders including the general public. The project progress is satisfactory. | Yes
|  | BEN/PHA/90/TAS/45 | UNEP | HPMP2 | AFR | BEN | TAS | Servicing | HCFC phase-out management plan (stage II, first tranche) | 2022-06-01 | 2025-06-01 | ONG | 2023-07-04 | 2025-06-01 |  |  | 4.6 | 0 | [6 empty] | 125000 | 0 | 125000 | 48.18% | 64774.49 | 15536 | 0 | 15536 | 8050.6918 | 60225.51 | 58000 | 32387.245 | 7485.3082 | 7208.704 |  | 30000 |  | 2031-12-01 | The second payment has been released to the country in September 2023. NOU conducted the followin activities: - Training and awareness campaigns for RAC maintenance specialists on best refrigeration practices, including techniques for recovery, recycling, and reuse of refrigerants, as well as safety and handling of refrigerants and equipment. - Organization of eight (08) training workshops for 200 RAC technicians. Development of regulatory standards and protocols for the use of flammable and toxic substances in RAC equipment.- Establishment of a certification scheme for refrigeration technicians and implementation of a national certification in the RAC sector. - Organization of eight (08) training workshops for 160 customs officers and law enforcement agents. - Organization of three (03) information and awareness workshops.- Recruitment of two local consultants for monitoring and evaluation of the implementation of the PGEH and collection of relevant data. | The second payment has been released to the country in September 2023. NOU conducted the followin activities: - Training and awareness campaigns for RAC maintenance specialists on best refrigeration practices, including techniques for recovery, recycling, and reuse of refrigerants, as well as safety and handling of refrigerants and equipment. - Organization of eight (08) training workshops for 200 RAC technicians. Development of regulatory standards and protocols for the use of flammable and toxic substances in RAC equipment.- Establishment of a certification scheme for refrigeration technicians and implementation of a national certification in the RAC sector. - Organization of eight (08) training workshops for 160 customs officers and law enforcement agents. - Organization of three (03) information and awareness workshops.- Recruitment of two local consultants for monitoring and evaluation of the implementation of the PGEH and collection of relevant data. | Yes
|  | CHD/PHA/90/TAS/41 | UNEP | HPMP2 | AFR | CHD | TAS | Servicing | HCFC phase-out management plan (stage II, first tranche) | 2022-06-01 | 2025-06-01 | ONG | 2023-07-04 | 2025-06-01 |  |  | 3.2 | 0 | [6 empty] | 128500 | 0 | 128500 | 46.25% | 69065.94 | 16146 | 0 | 16146 | 8678.1219 | 59434.06 | 61500 | 34532.97 | 7467.8781 | 7727.463 |  | 31500 |  | 2031-12-01 | The second payment has been released to the country in december 2023. NOU conducted the followin activities: 1:The organization of five (5) training workshops for 167 customs officers and agents of the Mobile Brigade for Environmental Protection, including 75 women, on the implementation of regulations regarding the control of imports of pure HCFCs and those contained in equipment, as well as the identification of HCFCs using new ULTIMA ID PRO brand identifiers. 2: The organization of three (3) information and exchange workshops aimed at importers, distributors, and transit agents on the procedures for issuing licenses and allocating annual import quotas for HCFCs. A total of one hundred and twenty-four (124) participants, including 51 women, took part in these training sessions. Among the participants, there were 43 importers, 25 distributors, 10 transit agents, as well as company executives, end consumers, etc. 3:The realization of three (3) information and exchange workshops on potential risks and hazards associated with the use of certain refrigerant substances for the benefit of importers, distributors, and transit agents of refrigerant products. A total of one hundred and twenty-two (122) individuals, including 48 women, benefited from these training sessions. Among the participants were 43 importers, 25 distributors, and 10 transit agents, as well as company executives, end consumers, etc. | The second payment has been released to the country in december 2023. NOU conducted the followin activities: 1:The organization of five (5) training workshops for 167 customs officers and agents of the Mobile Brigade for Environmental Protection, including 75 women, on the implementation of regulations regarding the control of imports of pure HCFCs and those contained in equipment, as well as the identification of HCFCs using new ULTIMA ID PRO brand identifiers. 2: The organization of three (3) information and exchange workshops aimed at importers, distributors, and transit agents on the procedures for issuing licenses and allocating annual import quotas for HCFCs. A total of one hundred and twenty-four (124) participants, including 51 women, took part in these training sessions. Among the participants, there were 43 importers, 25 distributors, 10 transit agents, as well as company executives, end consumers, etc. 3:The realization of three (3) information and exchange workshops on potential risks and hazards associated with the use of certain refrigerant substances for the benefit of importers, distributors, and transit agents of refrigerant products. A total of one hundred and twenty-two (122) individuals, including 48 women, benefited from these training sessions. Among the participants were 43 importers, 25 distributors, and 10 transit agents, as well as company executives, end consumers, etc. | Yes
|  | ERI/PHA/91/TAS/24 | UNEP | HPMP2 | AFR | ERI | TAS | Servicing | HCFC phase-out management plan (stage II, first tranche) | 2022-12-01 | 2025-12-01 | ONG |  | 2025-12-01 |  |  | 0.2 | 0 | [6 empty] | 115000 | 0 | 115000 | 0% | 115000 | 14950 | 0 | 14950 | 14950 | 0 | 115000 | 57500 | 0 | 14950 |  | 70000 |  | 2031-12-01 | The NOU conducted a consultative meeting on 26th July 2023, held at the Hall of the Ministry of Land, Water and Environment. The meeting involved a UNEP OzonAction representative, the NOO, national RAC technicians, and other stakeholders. It aimed to further enhance Eritrea's compliance with the Montreal Protocol. Eritrea was represented by a delegation of two NOO members and the Eritrean Ambassador to Kenya at the 35th Meeting of the Parties to the Montreal Protocol, held in Nairobi from October 23 to 27, 2023. The overall performance of the project is satisfactory. | The SSFA with a total of USD 115,000 was signed by the country in February 2023. The first payment of USD70,000 was released to the country in April 2023. The second payment of USD35,000 was released to the country in March 2024. The NOU conducted a training session for 45 RAC technicians, with 18 female participants in April 2024. The project is progressing satisfactorily. | Yes
|  | GRN/PHA/90/TAS/32 | UNDP | HPMP2 | LAC | GRN | TAS | Servicing | HCFC phase-out management plan (stage II, first tranche) | 2022-06-01 | 2025-06-01 | ONG |  | 2025-06-01 |  |  | 0.1 | 0 | [6 empty] | 111000 | 0 | 111000 | 0% | 111000 | 14430 | 0 | 14430 | 14430 | 0 | 0 | 55500 | 0 | 0 |  | 0 |  | 2031-12-01 | The country informed UNEP of changes in the Ministry and banking information which initiated a process of registration of new details in UMOJA. The SSFA was signed on 9 December 2023. | The first payment has been released to the country in Febuary 2024. Workplan endorsed and NOU organizing finalizing legislation, training and certification activities, and various education and awarensss activities. | Yes
|  | LIR/PHA/90/TAS/33 | UNDP | HPMP2 | AFR | LIR | TAS | Servicing | HCFC phase-out management plan (stage II, first tranche) | 2022-06-01 | 2025-06-01 | ONG |  | 2025-06-01 |  |  | 1 | 0 | [6 empty] | 116000 | 0 | 116000 | 0% | 116000 | 15080 | 0 | 15080 | 15080 | 0 | 106000 | 58000 | 0 | 13780 |  | 76000 |  | 2031-12-01 | The second payment of USD 76,0000 was released to the country in June 2023. The licensing and quota system is in place and functioning. The NOU participated in the Regional Training Workshop for Female RAC Technicians held from 17 to 19 January 2023 in Cairo, Egypt, attended by 18 female technicians. The NOU participated in the Regional Network Meeting for National Ozone Officers of the English-Speaking African Countries back-to-back with Thematic Workshop for Customs Officers held from 8-12 May 2023 in Kigali, Rwanda. The NOU participated at the 35th Meeting of the Parties to the Montreal Protocol, held in Nairobi from October 23 to 27, 2023. The overall performance of the project is satisfactory. The project is progressing satisfactorily. | The licensing and quota system is in place and functioning. The collection of data was undertaken to report A7 and CP data for the year 2023. Both the Article 7 and Country Programme data for 2023 were reported. The NOU conducted one training workshop for custom officers, attended by 20 participants (8 female and 12 male) in March 2024. The overall performance of the project is satisfactory. The project is progressing satisfactorily. | Yes
|  | MAG/PHA/90/TAS/38 | UNDP | HPMP2 | AFR | MAG | TAS | Servicing | HCFC phase-out management plan (stage II, first tranche) | 2022-06-01 | 2025-06-01 | ONG | 2023-07-04 | 2025-06-01 |  |  | 3.4 | 0 | [6 empty] | 120000 | 0 | 120000 | 44.6% | 66477.08 | 15094 | 0 | 15094 | 8361.7087 | 53522.92 | 57500 | 33238.54 | 6732.2913 | 7232.5417 |  | 0 |  | 2031-12-01 | The SSFA of HPMP Stage II, first tranche was signed by UNEP and the Government of Madagascar in December 2022. The first tranche was sent in January 2023. Licensing system is fully operational. Training workshop for 75 trainer technicians in refrigeration on best practices, including recovery, recycling, and reuse techniques for refrigerants, as well as safety and handling of refrigerants and equipment. | The second payment was disbursed in January 2024. Working session between the BNO, the Union of Refrigeration Technicians of Madagascar (UFM), the Training Service of the General Directorate of Customs (DGD), the Ministry of Commerce, and the General Directorate of Sustainable Development to discuss the strengthening and implementation of legislation and regulations regarding HCFCs. Licensing system is fully operational. | Yes
|  | NER/PHA/90/INV/43 | UNDP | HPMP2 | AFR | NER | INV | Refrigeration | HCFC phase-out management plan (stage II, first tranche) | 2022-06-01 | 2025-06-01 | ONG | 2023-01-26 | 2025-06-01 |  |  | 1.7 | 0 | [6 empty] | 108000 | 0 | 108000 | 7.048% | 100388.48 | 14040 | 0 | 14040 | 13050.5024 | 7611.52 | 100388.48 | 50194.24 | 989.4976 | 13050.5024 |  | 46500 |  | 2031-12-01 | The SSFA of HPMP Stage II, first tranche was signed by UNEP and the Government of Niger in December 2022. The first tranche was sent in January 2023. Licensing system is fully operational. | The SSFA of HPMP Stage II, first tranche was signed by UNEP and the Government of Niger in December 2022. The first tranche was sent in January 2023. Licensing system is fully operational. The NOO organized meetings with refrigerant importers and the Association of Refrigeration Professionals of Niger (APFN) to discuss import quotas for 2023 and 2024. 162 customs agents were trained on the control and identification of SAO, as well as equipment containing them. Additionally, 270 refrigeration technicians were trained in best practices for refrigeration and safety related to the use of hydrocarbons. | Yes
|  | TOG/PHA/91/TAS/41 | UNDP | HPMP2 | AFR | TOG | TAS | Servicing | HCFC phase-out management plan (stage II, first tranche) | 2022-12-01 | 2026-12-01 | ONG | 2023-04-07 | 2026-12-01 |  |  | 3.9 | 0 | [6 empty] | 125000 | 0 | 125000 | 47.1% | 66124.46 | 15536 | 0 | 15536 | 8218.4769 | 58875.54 | 58000 | 33062.23 | 7317.5231 | 7208.704 |  | 30000 |  | 2031-12-01 | The SSFA of HPMP Stage II, first tranche was signed by UNEP and the Government of Togo in April 2023. The first tranche was sent in April 2023. The second payment was sent in October 2023. Licensing system is fully operational. Throughout 2023, the National Ozone Office actively engaged in awareness campaigns, including radio broadcasts on September 16th and 17th, 2023, explaining ozone layer preservation. They conducted inspections in Lomé on March 3rd, 2023, and from August 7th to 16th, 2023, in other cities, educating distributors about HCFCs' harmful effects. Workshops for refrigeration technicians were held from May 9th to 10th, 2023, in Lomé, May 15th to 16th, 2023, in Kpalimé, and May 18th to 19th, 2023, in Sokodé, with 85 participants. Additionally, they identified 13 accredited refrigerant importers. These efforts underscore their commitment to ozone layer protection, culminating in the celebration of International Ozone Day. | The HPMP Stage II tranche 1 interim prorgess report was submitted by the country in March 2024 | Yes
|  | IND/PHA/91/TAS/501 | UNDP | HPMP2 | ASP | IND | TAS | Servicing | HCFC phase-out management plan (stage II, fourth tranche) | 2022-12-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 1 | 0 | [6 empty] | 90000 | 0 | 90000 | 0% | 90000 | 10900 | 0 | 10900 | 10900 | 0 | 0 | 45000 | 0 | 0 |  | 0 |  | 2024-12-01 | NOU has been working with UNEP on the staffing needs and have recently received confirmation that they are able to hire someone for the PMU component through their internal process instead of through UNEP's process. The previous staff departed the NOU in mid-2023 and other staff have been implementing Stage II. UNEP recently had a mission to agree on the terms for the SSFA and transfer of funding. Further to this staff change, UNEP also experienced some staffing changes which took some time for adjustment which added to the delay. | SSFA was signed in April 2024 for the amount of USD 90,000. Activity planning has been ongoing. | Yes
|  | MEX/PHA/90/TAS/201 | UNDP | HPMP2 | LAC | MEX | TAS | Servicing | HCFC phase-out management plan (stage II, fourth tranche) | 2022-06-01 | 2024-12-01 | FIN | 2023-10-03 |  | 2023-11-01 | 2023-12-31 | 0.5 | 0 | [6 empty] | 40000 | 0 | 40000 | 91.56% | 3377.22 | 5200 | 0 | 5200 | 439.0386 | 36622.78 | 0.36 | 0 | 4760.9614 | 0.0468 |  | 0 |  | 2024-12-01 | The training workshops took place in November 2023 with the attendance of 20 customs officers (12 females, 8 males). The two-day workshop included theoretical and practical sessions in the Manzanillos Customs Laboratory where participants were introduced to the use of refrigerant identifiers. Further virtual sessions were scheduled for December 2023 and the first quarter of 2024. The activities of the project were completed in Nov-23 | The project is financialy completed | Yes
|  | ALB/PHA/91/TAS/48 | UNDP | HPMP2 | EUR | ALB | TAS | Servicing | HCFC phase-out management plan (stage II, second tranche) | 2022-12-01 | 2025-12-01 | ONG | 2023-06-01 | 2025-12-01 |  |  | 0.6 | 0 | [6 empty] | 39500 | 0 | 39500 | 61.64% | 15151.48 | 5135 | 0 | 5135 | 1969.6924 | 24348.52 | 15151.48 | 7575.74 | 3165.3076 | 1969.6924 |  | 19000 |  | 2027-12-01 | Working group has been established in July 2023 to update training materials and curricula for enforcement / RAC training, working group meetings took place during July - October 2023, and training materials updated. Technicians training took place in Elbasan on 3 October 2023, in Durres on 22 November 2023, and in Tirana on 6-7 December 2023.The training, assessment and certification of 19 RAC trainers / technicians as per the EU F-gas legislation by Centro Studi Galileo took place in Tirana on 6-8 November 2023. | New F-gas law (adopted by Parliament on 26 January 2023) ented into force on 1 January 2024. Albania hosted the ECA network and enforcement meeting in Tirana on 23-25 April 2024. | Yes
|  | YUG/PHA/91/TAS/61 | UNDP | HPMP2 | EUR | YUG | TAS | Servicing | HCFC phase-out management plan (stage II, second tranche) | 2022-12-01 | 2024-12-01 | ONG | 2023-12-31 | 2024-12-01 |  |  | 0.4 | 0 | [6 empty] | 22000 | 0 | 22000 | 26.34% | 16204.24 | 2860 | 0 | 2860 | 2106.5512 | 5795.76 | 16204.24 | 8102.12 | 753.4488 | 2106.5512 |  | 16204.24 |  | 2026-12-01 | HPMP stage II activities in 2023 were mainly covered under tranche 1 with some funding from tranche 2. | No HPMP stage II tranche 2 activities have yet been initatiated in 2024. | Yes
|  | PER/PHA/90/TAS/61 | UNEP | HPMP2 | LAC | PER | TAS | Servicing | HCFC phase-out management plan (stage II, third tranche) | 2022-06-01 | 2025-06-01 | ONG | 2023-09-01 | 2025-06-01 |  |  | 2.2 | 0 | [6 empty] | 83200 | 0 | 83200 | 30.18% | 58094.28 | 10816 | 0 | 10816 | 7552.2564 | 25105.72 | 12574.96 | 29047.14 | 3263.7436 | 1634.7448 |  | 0 |  | 2026-12-01 | Good Progress. Work plan and timetable to implement the project are under discussion with the NOU. Direct implementation modality has been selected for this tranche. By September 2023 a study tour has been organized to Cartagena, Colombia (Acaire fair) for trainings of technical insitutes in Colombia to showcase best practises to develop a labour competancy standard (11 male). Also a consultant has been hired work on the assessment of the new standard. The assessment of the consultant concluded that an updated standard is required to ensure that it can be widely applied in Perú. | Good Progress. Work plan and timetable to implement the project are under discussion with the NOU. Direct implementation modality has been selected for this tranche. A mission was organized during March 2024 to update the labour compatency standard together with the NOU and the ministry of labour in Perú. Several coordination meetings have been organized together with national training institutes. Also the work of gender expert has been started to assist in the formalution of a gender assessment and incoperation of a gender inclusive language into the standard. | Yes
|  | IND/PHA/91/TAS/502 | UNEP | HPMP3 | ASP | IND | TAS | Servicing | HCFC phase-out management plan (stage III, first tranche) (enabling activities) | 2022-12-01 | 2025-12-01 | ONG |  | 2027-12-01 |  |  | 7.7 | 0 | [6 empty] | 668215 | 0 | 668215 | 0% | 668215 | 75486 | 0 | 75486 | 75486 | 0 | 0 | 334107.5 | 0 | 0 |  | 0 |  | 2031-12-01 | NOU has been working with UNEP on the staffing needs and have recently received confirmation that they are able to hire someone for the PMU component through their internal process instead of through UNEP's process. The previous staff departed the NOU in mid-2023 and other staff have been implementing Stage II. UNEP recently had a mission to agree on the terms for the SSFA and transfer of funding. Further to this staff change, UNEP also experienced some staffing changes which took some time for adjustment which added to the delay. | PCA is undergoing signature process. | Yes
|  | PAK/PHA/90/TAS/114 | UNEP | HPMP3 | ASP | PAK | TAS | Servicing | HCFC phase-out management plan (stage III, first tranche) (refrigeration servicing sector) | 2022-06-01 | 2025-06-01 | ONG |  | 2026-12-01 |  |  | 4.6 | 0 | [6 empty] | 426750 | 0 | 426750 | 0% | 426750 | 49034 | 0 | 49034 | 49034 | 0 | 0 | 213375 | 0 | 0 |  | 0 |  | 2031-12-01 | SSFA was signed in Dec 2023 for the amount of USD 406,750. | First payment transferred in February 2024. UNEP discussed with NOU to develop workplan, which was finalized and agreed by NOU. | Yes
|  | NER/KIP/91/TAS/47 | UNEP | KIP1 | AFR | NER | TAS | AC | Kigali HFC implementation plan (stage I, first tranche) (start-up) | 2022-12-01 | 2026-12-01 | ONG |  | 2026-12-01 |  |  | 7.7 | 0 | [6 empty] | 20000 | 0 | 20000 | 0% | 20000 | 2600 | 0 | 2600 | 2600 | 0 | 20000 | 10000 | 0 | 2600 |  | 10000 |  | 2031-12-01 | The SSFA was signed in April 2023. The first payment was released to the country in May 2023. The country ratified the Kigali Amendment in August 2018. The HCF licensing system has been in place and operational since 2019. The country submitted the HFC Art7 data to the secretariat in May 2023. | The country ratified the Kigali Amendment in August 2018. The HCF licensing system has been in place and operational since 2019. The country submitted the HFC Art7 data to the secretariat in May 2024. The NOO has coordinated with all stakeholders for the implementation of the Kigali HFC plan for the year 2024. The NOO has coordinated with the RAC association on the need to integrate gender mainstreaming into training on best refrigeration practices and the safe handling of flammable and toxic refrigerants such as R-600. | Yes
|  | BGD/KIP/90/PRP/57 | UNEP | KIPIND | ASP | BGD | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-06-01 | 2024-06-01 | ONG |  | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 40000 | 0 | 40000 | 0% | 40000 | 5200 | 0 | 5200 | 5200 | 0 | 5000 | 20000 | 0 | 650 |  | 0 |  |  | The timing for proposal submission was updated based on discussions and coordination with lead agency and NOU, accordingly the recruitment process was pushed to a later date. UNEP had developed ToR for local consultant, identified the consultant and started preliminary discussions, however, in order to avoid outdated information by the time the proposal is submitted, UNEP delayed the onboarding process to coincide with the lead Agency's onboarding. | Recruitment of KIP consultant finalized, consultant onboarded in March 2024. Consultant has started data collection. UNEP is actively coordinating with lead agency. International Consultant was hired and document strucure as well as document text developed including baground information and analysis of past HFC data. | Yes
|  | BEN/KIP/90/PRP/43 | UNEP | KIPIND | AFR | BEN | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-06-01 | 2024-06-01 | ONG | 2023-05-03 | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 133000 | 0 | 133000 | 2.155% | 130133.27 | 17290 | 0 | 17290 | 16917.3251 | 2866.73 | 75000 | 65066.635 | 372.6749 | 9750 |  | 60000 |  |  | The SSFA was signed in December 2023. The first payment was released to the country in December 2023. The country ratified the Kigali Amendment in March 2018. The HCF licensing system has been in place and operational since 2019. A consultant was hired by the country to prepare the KIP for submission. | The project is progressing. The consultant and the NOO are conducting a nationwide survey on HFC consumption, analyzing alternatives and import/export stats, and developing an HFC phase-down strategy. The interim progress report is under preparation and will be submitted by the country in June 2024. | Yes
|  | BOT/KIP/90/PRP/30 | UNIDO | KIPIND | AFR | BOT | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-06-01 | 2024-06-01 | ONG | 2023-03-12 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 119000 | 0 | 119000 | 25.46% | 88700 | 15470 | 0 | 15470 | 11531 | 30300 | 79000 | 44350 | 3939 | 10270 |  | 59000 |  |  | The Terms of Reference (ToR) for hiring the local consultant was prepared, cleared by the management and advertised in December 2023. National consultants were hired by the NOU for data surveys which includes appropriate methodology, data collection, evaluation and reporting. Consultants collected information on the current status and consumption of HFCs in servicing sector including industrial and commercial refrigeration sectors and end-user air conditioning sub sectors, as well as on the ongoing refrigerant recovery and recycling practices. Project is progressing satisfactorily. | Terms of Reference (ToR) and hiring of local consultant for data collection was completed in February 2024. The team (consultant and NOU) had its first meeting in March 2024 and the consultant is due to begin the survey in May 2024. | Yes
|  | CBI/KIP/91/PRP/30 | UNIDO | KIPIND | AFR | CBI | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-12-01 | 2024-12-01 | ONG | 2023-05-02 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 130000 | 0 | 130000 | 2.004% | 127395.17 | 16900 | 0 | 16900 | 16561.3721 | 2604.83 | 0 | 63697.585 | 338.6279 | 0 |  | 0 |  |  | OzonAction prepared the SSFA. SSFA not yet signed. | SSFA drafted and waiting for signature from the country.The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management on 30 May 2024. International consultant identified. | Yes
|  | CHD/KIP/90/PRP/39 | UNIDO | KIPIND | AFR | CHD | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-06-01 | 2024-06-01 | ONG | 2023-05-02 | 2025-06-01 |  |  | 0 | 0 | [6 empty] | 119000 | 0 | 119000 | 4.506% | 113638.42 | 15470 | 0 | 15470 | 14772.9946 | 5361.58 | 69000 | 56819.21 | 697.0054 | 8970 |  | 55200 |  |  | The SSFA was signed in December 2023. The first payment was released to the country in December 2023. The country ratified the Kigali Amendment in March 2019. The HCF licensing system has been in place and operational since 2019. A consultant was hired by the country to prepare the KIP for submission. | The SSFA was signed in December 2023. The first payment was released to the country in December 2023. The country ratified the Kigali Amendment in March 2019. The HCF licensing system has been in place and operational since 2019. A consultant was hired by the country to prepare the KIP for submission. | Yes
|  | COI/KIP/91/PRP/33 | UNIDO | KIPIND | AFR | COI | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-12-01 | 2024-12-01 | ONG | 2023-04-28 | 2025-12-01 |  |  | 0 | 0 | [6 empty] | 100000 | 0 | 100000 | 2.994% | 97006.02 | 13000 | 0 | 13000 | 12610.7826 | 2993.98 | 0 | 48503.01 | 389.2174 | 0 |  | 0 |  |  | OzonAction prepared the SSFA. SSFA not yet signed. | SSFA drafted and waiting for signature from the country. The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management on 22 May 2024. International consultant identified. | Yes
|  | PRC/KIP/91/PRP/37 | UNIDO | KIPIND | AFR | PRC | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-12-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 51000 | 0 | 51000 | 0% | 51000 | 6630 | 0 | 6630 | 6630 | 0 | 0 | 25500 | 0 | 0 |  | 0 |  |  | OzonAction prepared the SSFA. SSFA not yet signed. | SSFA drafted and waiting for signature from the country. The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management on 30 April 2024. International consultant identified. | Yes
|  | IVC/KIP/91/PRP/49 | UNIDO | KIPIND | AFR | IVC | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-12-01 | 2024-12-01 | ONG | 2023-04-28 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 133000 | 0 | 133000 | 1.275% | 131304 | 17290 | 0 | 17290 | 17069.52 | 1696 | 0 | 65652 | 220.48 | 0 |  | 0 |  |  | The SSFA was signed in November 2023. The first payment was released to the country in December 2023. The country ratified the Kigali Amendment in December 2019. The HCF licensing system has been in place and operational since 2019. A consultant was hired by the country to prepare the KIP for submission. | The project is progressing. The consultant and the NOO are conducting a nationwide survey on HFC consumption, analyzing alternatives and import/export stats, and developing an HFC phase-down strategy. The interim progress report is under preparation and will be submitted by the country in June 2024. | Yes
|  | ETH/KIP/90/PRP/36 | UNIDO | KIPIND | AFR | ETH | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-06-01 | 2024-06-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 91000 | 0 | 91000 | 0% | 91000 | 11830 | 0 | 11830 | 11830 | 0 | 69000 | 45500 | 0 | 8970 |  | 39000 |  |  | The SSFA with a total of US$ 91,000 was signed by the country in March 2023. The first payment of US$ 39,000 was released to the country in April 2023. A nation-wide survey on HFC in Ethiopia was undertaken to ascertain the country’s status regarding the utilization of these high Global Warming Potential (GWP) substances from April to May 2023. The survey report is being finalized. The project is progressing satisfactorily. | The survey report is being finalised. The project is progressing satisfactorily. | Yes
|  | GAB/KIP/91/PRP/43 | UNIDO | KIPIND | AFR | GAB | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-12-01 | 2024-12-01 | ONG | 2023-04-28 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 133000 | 0 | 133000 | 2.892% | 129153.82 | 17290 | 0 | 17290 | 16789.9966 | 3846.18 | 0 | 64576.91 | 500.0034 | 0 |  | 0 |  |  | OzonAction prepared the SSFA. SSFA not yet signed. | SSFA drafted and waiting for signature from the country. The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management on 22 May 2024. International consultant identified. | Yes
|  | GAM/KIP/90/PRP/45 | UNIDO | KIPIND | AFR | GAM | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-06-01 | 2024-06-01 | COM | 2023-11-01 |  | 2023-12-01 |  | 0 | 0 | [6 empty] | 91000 | 0 | 91000 | 45.11% | 49950 | 11830 | 0 | 11830 | 6493.5 | 41050 | 40000 | 40000 | 5336.5 | 5200 |  | 15000 |  |  | The second disbursement of USD 15,000 was released to the country in December 2023. The NOU conducted a nationwide survey and data collection on HFC consumption and analysis of the use of HFCs and alternatives in June 2023. A Kigali HFC implementation plan was prepared and submitted to ExCom 93 which was approved. The project is completed. | The project is completed | Yes
|  | GUI/KIP/90/PRP/40 | UNIDO | KIPIND | AFR | GUI | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-06-01 | 2024-06-01 | ONG | 2023-05-02 | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 133000 | 0 | 133000 | 1.203% | 131399.92 | 17290 | 0 | 17290 | 17081.9896 | 1600.08 | 75000 | 65699.96 | 208.0104 | 9750 |  | 60000 |  |  | The SSFA was signed in November 2023. The first payment was released to the country in December 2023. The country ratified the Kigali Amendment in December 2019. The HCF licensing system has been in place and operational since 2019. A consultant was hired by the country to prepare the KIP for submission. | The project is progressing. The consultant and the NOO are conducting a nationwide survey on HFC consumption, analyzing alternatives and import/export stats, and developing an HFC phase-down strategy. The interim progress report is under preparation and will be submitted by the country in June 2024. | Yes
|  | GBS/KIP/91/PRP/30 | UNIDO | KIPIND | AFR | GBS | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-12-01 | 2024-12-01 | ONG | 2023-05-02 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 91000 | 0 | 91000 | 5.818% | 85705.74 | 11830 | 0 | 11830 | 11141.7462 | 5294.26 | 0 | 42852.87 | 688.2538 | 0 |  | 0 |  |  | OzonAction prepared the SSFA. SSFA not yet signed. | SSFA drafted and waiting for signature from the country. The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management on 30 May 2024. International consultant identified. | Yes
|  | MON/KIP/91/PRP/35 | UNIDO | KIPIND | ASP | MON | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-12-01 | 2024-12-01 | ONG | 2023-12-23 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 130000 | 0 | 130000 | 21.98% | 101420 | 16900 | 0 | 16900 | 13184.6 | 28580 | 71420 | 50710 | 3715.4 | 9284.6 |  | 16420 |  |  | SSFA was signed in June 2023 for the amount of USD 90,000. First payment transferred July 2023. NOU hired a local consultant team to conduct the KIP PRP data collection. The consultant team and NOU started the data collection in the third quarter 2023. International Consultant was hired and document strucure as well as document text developed including baground information and analysis of past HFC data (from Country Assessment Report). | Consultant and NOU have completed the data collection, the data is being discussed with stakeholders and verified. UNEP conducted a mission in May 2024 to further improve the data collection, identify priority sectors and activities. Project proposal under development. | Yes
|  | MOZ/KIP/90/PRP/37 | UNEP | KIPIND | AFR | MOZ | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-06-01 | 2024-06-01 | COM | 2023-08-29 |  | 2023-12-01 |  | 0 | 0 | [6 empty] | 119000 | 0 | 119000 | 25.46% | 88700 | 15470 | 0 | 15470 | 11531 | 30300 | 79000 | 79000 | 3939 | 10270 |  | 59000 |  |  | The Terms of Reference (ToR) for hiring the local consultant was prepared, cleared by the management and advertised in January 2023. The recruited of the consultant was completed in February 2023. The Consultant conducted a nation-wide survey on consumption of HFCs. The NOU attended the Regional Network Meeting for National Ozone Officers of the English-Speaking African Countries back-to-back with Thematic Workshop for Customs Officers from 8-12 May 2023 in Kigali, Rwanda. The Regional Network Meeting, attended by 26 out of 28 countries of the English-speaking African networks (37 male, 30 female), provided opportunity for the countries to further discuss key information and data to be collected in preparation of a KIP Strategy and approaches. Project is progressing satisfactorily. | The NOU conducted a nation-wide survey with relevant stakeholders on HFC consumption and analysis of the use of HFCs and alternatives, including import and export statistics of ODS alternatives. The survey report was completed and submitted to UNEP. A national overarching HFC phase-down strategy was developed and submitted to ExCom 94. | Yes
|  | STL/KIP/91/PRP/36 | UNEP | KIPIND | LAC | STL | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-12-01 | 2024-12-01 | ONG | 2023-11-13 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 90000 | 0 | 90000 | 29.88% | 63106.41 | 11700 | 0 | 11700 | 8203.8333 | 26893.59 | 0 | 31553.205 | 3496.1667 | 0 |  | 0 |  |  | The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management and advertised on Jan 2023. Consultant contracted 24 Feb 2023. Consultant prepared a detailed workplan, undertook detailed desk studies and held initial virtual consultations with the NOU Mar to Apr 2023. Country mission planned for 26-29 Jun 2023 to hold stakeholder consultations for the KIP preparation in Saint Lucia however can postponed. KIP was prepared without the inperson national consultations, however virtual. The first stakeholders workshop was organized by the NOU Mar 2023 virtually, with the main goal to sensitize major stakeholders about HCFC phase out schedule, data survey and the Government’s strategy for phasing out of HCFCs. Final draft submitted Sept 2023. SSFA to transfer funds from UNEP to Country, to undertake national activities signed by UNEP on 21 Dec 2023. Country noted some erros in their information which requires changes in the system. UNEP working with country on those adjustments. | The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management and advertised on Jan 2023. Consultant contracted 24 Feb 2023. Consultant prepared a detailed workplan, undertook detailed desk studies and held initial virtual consultations with the NOU Mar to Apr 2023. Country mission planned for 26-29 Jun 2023 to hold stakeholder consultations for the KIP preparation in Saint Lucia however cancelled. KIP was prepared without the inperson national consultations, however virtual. The first stakeholders workshop was organized by the NOU Mar 2023 virtually, with the main goal to sensitize major stakeholders about HCFC phase out schedule, data survey and the Government’s strategy for phasing out of HCFCs. Final draft submitted Sept 2023. The Final KIP submitted Jan 2024. KIP submitted to MLFS 5 Feb 2024. The SSFA to undertake national activities signed by UNEP on 25 Jan 2024 following UNEP's signature on 21 Dec 2023 as a result of systematic errors on Country information reflected in the SSFA, requiring changes. First Cash advance disbursed 4 Mar 2024. Country in the process of preapring final reports to allow UNEP to close project. | Yes
|  | STP/KIP/90/PRP/34 | UNEP | KIPIND | AFR | STP | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-06-01 | 2024-06-01 | ONG | 2023-05-21 | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 130000 | 0 | 130000 | 4.483% | 124171.74 | 16900 | 0 | 16900 | 16142.3262 | 5828.26 | 0 | 62085.87 | 757.6738 | 0 |  | 0 |  |  | OzonAction prepared the SSFA. SSFA not yet signed. | SSFA drafted and waiting for signature from the country. The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management on 18 April 2024. International consultant identified. | Yes
|  | YUG/KIP/90/PRP/58 | UNEP | KIPIND | EUR | YUG | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-06-01 | 2024-06-01 | ONG |  | 2025-06-01 |  |  | 0 | 0 | [6 empty] | 55000 | 0 | 55000 | 0% | 55000 | 7150 | 0 | 7150 | 7150 | 0 | 0 | 27500 | 0 | 0 |  | 0 |  |  | Joint messages of UNIDO and UNEP were sent to the Ministry in January and March 2023 proposing next steps and an online meeting to proceed with the signature of contractual arrangements and KIP preparation. Serbia's Montreal Protocol Officer resumed work in May 2023 and suggested to discuss KIP preparation in July 2023. However, staff changes in UNIDO prevented any joint coordination meeting in 2023. UNEP met with Ministry staff in Belgrade in December 2023 and agreed on an UN2UN agency agreement with UNDP Serbia for local arrangements, on engaging an international policy expert to review legislation, progress and verification reports and to draft recommendations for KIP stage I, and on engaging an international KIP expert to prepare UNEP's components for KIP stage I. | As agreed during the meeting with the Ministry staff in December 2023, the UN2UN agency agreement with UNDP Serbia for local arrangements was signed in March 2024 and the funds released in April 2024. The international policy expert to review legislation, progress and verification reports and to draft recommendations for KIP stage I was engaged in March 2024, and he immediately initiated the review process. The international KIP expert to prepare UNEP's components for KIP stage I shall be engaged in October 2024, and the TORs have already been prepared. | Yes
|  | SEY/KIP/90/PRP/28 | UNEP | KIPIND | AFR | SEY | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-06-01 | 2024-06-01 | ONG | 2023-04-27 | 2024-09-01 |  |  | 0 | 0 | [6 empty] | 81000 | 0 | 81000 | 69.38% | 24800 | 10530 | 0 | 10530 | 3224 | 56200 | 15000 | 12400 | 7306 | 1950 |  | 10000 |  |  | Seychelles ratified the Kigali Amendment on 23 May 2019. The Terms of Reference (ToR) for hiring the local consultant was prepared, cleared by the management and advertised in January 2023. The recruited of the consultant was completed in February 2023. The Consultant conducted a nation-wide survey on consumption of HFCs. The first Phase of the National survey Consultative meeting was done on 18th August & 2nd meeting on 9th august 2023 at Seychelles Trading Centre Conference Center with relevant stakeholders on Kigali Amendment. Participant who attended the 2 meeting were mostly RAC Technicians, 30 participants per meeting. Licensing System was reviewed in 2020 and officially gazette in January 2021. Stakeholders’ meetings were held in 2023 which comprises mainly of representatives from Custom, Ministry of Trades & Finance, Energy Commission, & Ozone. The project is progressing successfully. | The second Phase of the KIP Consultative meeting on the strategic Action Plan was held on 12th January 2024 at Eden Bleu Hotel, Roche Caiman with a total of 44 participants from different sectors which include government sectors, Hotels, importers, fishery industry & RAC technicians. (25 males & 19 female) participated. The NOU conducted a second meeting held at Coral Strand Hotels Beau Vallon with a total of 54 participants from different sectors which again include government such as Import, trades, Custom, Environment sectors, Hotels, importers, fishery industries & RAC technicians (40 males & 14 female participated). The National Kigali Strategy Paper was developed after the consultative workshop on 24th January 2024. The Project is progressing satisfactorily. | Yes
|  | SOM/KIP/90/PRP/18 | UNEP | KIPIND | AFR | SOM | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-06-01 | 2024-06-01 | ONG | 2023-12-13 | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 51000 | 0 | 51000 | 19.8% | 40900 | 6630 | 0 | 6630 | 5317 | 10100 | 31000 | 20450 | 1313 | 4030 |  | 16000 |  |  | Somalia ratified the Kigali Amendment on 27 November 2019. The Terms of Reference (ToR) for hiring the local consultant was prepared, cleared by the management and advertised in January 2023. The recruited of the consultant was completed in February 2023. The Consultant conducted a nation-wide survey on consumption of HFCs. The NOU attended the Regional Network Meeting for National Ozone Officers of the English-Speaking African Countries back-to-back with Thematic Workshop for Customs Officers from 8-12 May 2023 in Kigali, Rwanda. The Regional Network Meeting, attended by 26 out of 28 countries of the English-speaking African networks (37 male, 30 female), provided opportunity for the countries to further discuss key information and data to be collected in preparation of a KIP Strategy and approaches. Project is progressing satisfactorily. | The NOU conducted a nation-wide survey with relevant stakeholders on HFC consumption and analysis of the use of HFCs and alternatives, including import and export statistics of ODS alternatives. The survey report is being drafted. The project is progressing satisfactorily. | Yes
|  | URT/KIP/91/PRP/43 | UNEP | KIPIND | AFR | URT | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-12-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 91000 | 0 | 91000 | 0% | 91000 | 11830 | 0 | 11830 | 11830 | 0 | 69000 | 45500 | 0 | 8970 |  | 40000 |  |  | Tanzania ratified the Kigali Amendment on 25 March 2022. The Terms of Reference (ToR) for hiring the local consultant was prepared, cleared by the management and advertised in January 2023. The recruitement of the consultant was completed in February 2023. The Consultant conducted a nation-wide survey on consumption of HFCs. The survey report is being finalized. The project is progressing satisfactorily. | The NOU conducted a nation-wide survey with relevant stakeholders on HFC consumption and analysis of the use of HFCs and alternatives, including import and export statistics of ODS alternatives. The survey report is being drafted. The project is progressing satisfactorily. | Yes
|  | TOG/KIP/90/PRP/39 | UNEP | KIPIND | AFR | TOG | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-06-01 | 2024-06-01 | ONG | 2023-02-05 | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 119000 | 0 | 119000 | 2.092% | 116510.02 | 15470 | 0 | 15470 | 15146.3026 | 2489.98 | 69000 | 58255.01 | 323.6974 | 8970 |  | 55200 |  |  | The SSFA was signed in November 2023. The first payment was released to the country in December 2023. The country ratified the Kigali Amendment in March 2018. The HCF licensing system has been in place and operational since 2019. A consultant was hired by the country to prepare the KIP for submission. | The project is progressing. The consultant and the NOO are conducting a nationwide survey on HFC consumption, analyzing alternatives and import/export stats, and developing an HFC phase-down strategy. The interim progress report is under preparation and will be submitted by the country in June 2024. | Yes
|  | ZIM/KIP/91/PRP/65 | UNEP | KIPIND | AFR | ZIM | PRP | Servicing | Preparation of a Kigali HFC implementation plan | 2022-12-01 | 2024-12-01 | ONG | 2023-09-20 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 119000 | 0 | 119000 | 83.36% | 19800 | 15470 | 0 | 15470 | 2574 | 99200 | 0 | 9900 | 12896 | 0 |  | 40000 |  |  | The NOU conducted a nation-wide survey with relevant stakeholders on HFC consumption and analysis of the use of HFCs and alternatives, including import and export statistics of ODS alternatives. The survey report is being finalized. The project is progressing satisfactorily. | National consultants were hired by the NOU for data surveys which includes appropriate methodology, data collection, evaluation and reporting. Consultants collected information on the current status and consumption of HFCs in servicing sector using HFCs including industrial and commercial refrigeration sectors and end-user air conditioning, as well as on the ongoing refrigerant recovery and recycling practices. The Government of Zimbabwe and consultants in close consultation with UNEP and UNDP drafted a preliminary strategy taking into consideration the results of the surveys, data analysis, consultation meetings as well as the policy and legislation review. The draft covers policy, training, investment and capacity building needs of the country. The project is progressing well. | Yes
|  | PER/SEV/91/INS/62 | UNEP | Government Support | LAC | PER | INS | National Ozone Unit | Renewal of institutional strengthening project (phase VI: 1/2023-12/2024) | 2022-12-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 235832 | 0 | 235832 | 0% | 235832 | 0 | 0 | 0 | 0 | 0 | 0 | 117916 | 0 | 0 |  | 0 |  |  | Good progress. Work plan and timetable to implement the project agreed with the NOU. SSFA was submitted to the country for signature. UN-UN agreement was submitted to UNDP-Perú for signature. This SSFA will facilitate obtaining products and expected results as mentioned below:(1) Adoption/enforcement of Montreal Protocol Controlled Substances laws and regulations to control and monitor the consumption of Montreal Protocol Controlled Substances, (2) Efficient and timely data collection and reporting, (3) Intra- and inter-institutional coordination to implement the Montreal Protocol with other organizations/national stakeholders, (4) Supervision of timely execution of activities to eliminate and reduce the consumption of Substances controlled by the Montreal Protocol, (5) Increase in awareness and exchange of information, (6) Regional and international cooperation. | Good progress. Work plan and timetable to implement the project agreed with the NOU. SSFA was submitted to the country for signature. UN-UN agreement was submitted to UNDP-Perú for signature. This SSFA will facilitate obtaining products and expected results as mentioned below:(1) Adoption/enforcement of Montreal Protocol Controlled Substances laws and regulations to control and monitor the consumption of Montreal Protocol Controlled Substances, (2) Efficient and timely data collection and reporting, (3) Intra- and inter-institutional coordination to implement the Montreal Protocol with other organizations/national stakeholders, (4) Supervision of timely execution of activities to eliminate and reduce the consumption of Substances controlled by the Montreal Protocol, (5) Increase in awareness and exchange of information, (6) Regional and international cooperation. SSFA was signed in March 2024. UN-UN agreement was signed in March 2024. | Yes
|  | BAR/SEV/90/INS/32 | UNEP | Government Support | LAC | BAR | INS | National Ozone Unit | Renewal of institutional strengthening project (phase VIII: 7/2022-6/2024) | 2022-06-01 | 2024-06-01 | ONG |  | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 149760 | 0 | 149760 | 0% | 149760 | 0 | 0 | 0 | 0 | 0 | 149760 | 74880 | 0 | 0 |  | 74880 |  |  | SSFA was signed in August 2023. 1st cash advance payment of 74,880 on 06 September 2023. The licensing and quota system is fully operational. Importers comply with issued quotas for the year 2023. The collection of data was undertaken to report A7 and CP data for the year 2022. CP data for 2022 was reported in 27 April 2023. A7 for 2022 was submitted on 27 April 2023; 1 sensitisation session was conducted with customs brokers (18 participants - 9 females); 1 meeting was held with RAC association and RSS (25 participants - 6 females); 1 meeting held with officials of technical school and vocational qualification organization discussion certification, licensing, standards, policy and incentives; 1 virtual presentation to customs brokers association on import and export issues conducted; NOU hosted ceremony to present ODS Scholarships to 3 awardees in Nov 2023; Ozone day 2023 celebrated and included publicising on social media; Barbados attended the following meetings: workshop on strengthening implemention of the montreal protocol in July 2023, Bangkok; OEWG45 in July 2023, Bangkok; Bureau of the 34th meeting of the parties to the MP in October 2023, Kenya; Workshop on energy efficiency in October 2023, Kenya; and, MOP34 in October 2023, Kenya. | Awaiting additional interim report showing at least 80% expenditure of 1st cash advance payment in order to process 2nd cash advance. The country continues to implement activities inline with the work plan. The NOU has been promoting the particiation of women in the RSS through more training opportunities and creating ways to increase the use of female imagery in awareness materials. | Yes
|  | BZE/SEV/91/INS/43 | UNEP | Government Support | LAC | BZE | INS | National Ozone Unit | Renewal of institutional strengthening project (phase XI: 7/2023-6/2025) | 2022-12-01 | 2025-06-01 | ONG |  | 2025-06-01 |  |  | 0 | 0 | [6 empty] | 135483 | 0 | 135483 | 0% | 135483 | 0 | 0 | 0 | 0 | 0 | 135483 | 67741.5 | 0 | 0 |  | 67742 |  |  | The SSFA was signed on 4 August 2023. The first payment has been released to the country in September 2023. The licensing system was fully operational. Importers comply with issued quotas for the year 2023. No importation or consumption of CFCs was sustained; Importers complied with issued quotas for the year 2022; No reported cases of illegal trade; International Ozone Day for 2023 was celebrated, with public awareness activities and dissemination of print and digial media. The Country participated in the following meetings: Caribbean network meeting back to back with Women in RAC both held in Nov 2023 in Trinidad and Tobago; | Licensing system fully operational. The quota for the year 2024 was issued. Importers comply with issued quotas for the year 2024. The collection of data was undertaken to report A7 and CP data for the year 2023. A7 data for 2023 reported on Febuary 2024; CP data for 2023 reported on Febuary 2024. The NOU has been promoting the particiation of women in the RSS through more training opportunities and creating ways to increase the use of female imagery in awareness materials. Country preparing interim report. | Yes
|  | QAT/SEV/90/INS/28 | UNEP | Government Support | ASP | QAT | INS | National Ozone Unit | Renewal of the institutional strengthening project (phase VI: 7/2022-6/2024) | 2022-06-01 | 2024-06-01 | ONG |  | 2024-06-01 |  |  | 0 | 0 | [6 empty] | 113920 | 0 | 113920 | 0% | 113920 | 0 | 0 | 0 | 0 | 0 | 113920 | 56960 | 0 | 0 |  | 50000 |  |  | Progress report: Agreement signed in Mar. 2023 ($113,920). the NOU is fully functional and actively continued imlementing the planned activities including reporting the data for 2022 and supervising the implementation of the HPMP stage II. several consultation meetings have been organized along with a national awareness campaign for raising awareness; the NOU actively participated in the global and regional meetings including the network meeting in Sept. 2023 and standards workshop in Feb. 2023. | Progress report: Agreement signed in Mar. 2023 ($113,920). the NOU has successfully implemented almost all planned activities under this phase including reporting the CP data for 2023 and finalized the submission of the renewal request for next phase of the projejct for consideration at ExCom-94. | Yes
|  | BRU/SEV/91/INS/31 | UNEP | Government Support | ASP | BRU | INS | National Ozone Unit | Renewal of the institutional strengthening project (phase VIII: 1/2023-12/2024) | 2022-12-01 | 2024-12-01 | ONG | 2023-12-21 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 123648 | 0 | 123648 | 30.64% | 85759.41 | 0 | 0 | 0 | 0 | 37888.59 | 85759.41 | 42879.705 | 0 | 0 |  | 20111.41 |  |  | The SSFA was signed in September 2023. The first payment of US$ 58,000 was released to the country in October 2023. The NOU continued to enforce HCFC/HFC quota and licensing system through the National Single Window System. The 2023 quota is 59.09 MT of HCFC-22, which is lower than the maximum allowable consumption as agreed with the ExCom. The NOU maintains bilateral communication with the exporting countries through Informal Prior Inform Consent (iPIC). The CP data for the year 2022 was reported to the MLFS in April 2023 and Article 7 data was report to online in July 2023. NOU continued to coordinate implementation of the HPMP, provided support on verification of HCFC consumption, expedited implementation of the Enabling Activities for HFC Phase-down to close project in June 2023 and provide support on verification of HCFC consumption. NOU organized the 2023 World Ozone Day celebration. The NOU participated in the (i) Network Meeting of the SEA National Ozone Officer and the Twinning National Ozone Officers - Customs Workshop on ODS/HFC Trade Control and Reporting in Vietnam in March 2023 in Vietnam and (ii) Advanced National Ozone Officers Training Workshop back-to-back with the Joint Network Meeting of South Asia and Southeast Asia National Ozone Officers in Thailand in November 2023. NOU also attended the Open-ended Working Group (OEWG45) in July 2023 and the Meeting of the Parties in October 2023. NOU continued to implement the following gender activities: encouraging female participants in the meetings/training under the project and collection of gender-disaggregation data in project activities. | NOU continues to follow-up ratification of the Kigali Amendment. The NOU continues to enforce HCFC/HFC quota and licensing system through the Brunei Darussalam National Single Window System. The 2024 quota is 52.72 MT of HCFC-22. HFC quota system has been implemented since 1 January 2024 with the allocated amount of 380,393 tonnes CO2 equivalent. The NOU maintains bilateral communication with the exporting countries through Informal Prior Inform Consent (iPIC). The CP data for the year 2023 was reported to the MLFS in April 2024. The NOU will participate in the Energy Efficiency Twinning Workshop back-to-back with the Joint Network Meeting of South Asia and Southeast Asia National Ozone Officers in China in May 2024. NOU continues to implement the following gender activities: encouraging female participants in the meetings/training under the project and collection of gender-disaggregation data in project activities. The NOU has finalized the expenditure report and is preparing the progress report to process the second payment of US$ 58,000. | Yes
|  | MAU/SEV/91/INS/31 | UNEP | Government Support | AFR | MAU | INS | National Ozone Unit | Renewal of the institutional strengthening project (phase VIII: 1/2023-12/2024) | 2022-12-01 | 2024-12-01 | ONG | 2023-12-31 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 120000 | 0 | 120000 | 50% | 60000 | 0 | 0 | 0 | 0 | 60000 | 60000 | 30000 | 0 | 0 |  | 0 |  |  | The SSFA was signed by both in March 2023. The first payment was disbursed in May 2023. Licensing system is fully operational. | The second payment was disbursed in Februaty 2024. The National Ozone Bureau collaborated with a customs focal point to share annual import data on ODS and equipment containing these substances. Importation of CFC-containing refrigeration and air conditioning equipment, as well as pre-blended polyols, is banned. A meeting of the National Ozone Committee took place on December 25, 2023. The International Day for the Preservation of the Ozone Layer was commemorated in accordance with the themes selected by the Ozone Secretariat on September 15, 2023. | Yes
|  | LAO/SEV/91/INS/42 | UNEP | Government Support | ASP | LAO | INS | National Ozone Unit | Renewal of the institutional strengthening project (phase XI: 1/2023-12/2024) | 2022-12-01 | 2025-06-01 | ONG | 2023-12-21 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 120000 | 0 | 120000 | 45.83% | 65007.22 | 0 | 0 | 0 | 0 | 54992.78 | 65007.22 | 32503.61 | 0 | 0 |  | 5007.22 |  |  | The project was approved at the Excom-91 in December 2022. The SSFA was signed in April 2023. The first payment of US$ 60,000 was released in May 2023. The new NOU team worked closely with importers to understand the business plan to import HCFC-22 in 2023 for allocation of HCFC quota for 2023, which was 26.50 MT of HCFC-22, lower than the maximum allowable consumption. The collection of data was undertaken to report CP data and Article 7 for the year 2022, which was reported to the MLFS on 1 May 2023 and to the Ozone Secretariat on 19 October 2023. NOU organized HFC importer meeting in June 2023 to explain HFC quota system using CO2 equivalent tonnes concept and criteria for HFC quota allocation to be implemented from 1 January 2024. NOU continues to coordinate implementation of the HPMP and KIP Preparation and provided support on verification of HCFC consumption. NOU organized the 2023 World Ozone Day celebration. The NOU participated in the (i) Network Meeting of the SEA National Ozone Officer and the Twinning National Ozone Officers - Customs Workshop on ODS/HFC Trade Control and Reporting in Vietnam in March 2023 in Vietnam and (ii) the Joint Network Meeting of South Asia and Southeast Asia National Ozone Officers in Thailand in November 2023. NOU also attended the Open-ended Working Group (OEWG45) in July 2023 and the Meeting of the Parties in October 2023. NOU continued to implement the following gender activities: encouraging female participants in the meetings/training under the project and collection of gender-disaggregation data in project activities. | The NOU continues to enforce HCFC/HFC quota and licensing system in collaboration with the Ministry of Industry and Commerce. NOU organized importer meeting to discuss allocation of HCFC/HFC quota for 2024. The CP data for the year 2023 was reported to the MLFS in April 2024. The NOU collaborated with relevant stakeholders and supported UNEP in the preparation of the HPMP Stage II, Second Tranche request, Additional activities for the introduction of alternatives to HCFCs with low or zero GWP refrigerants and for maintaining energy efficiency in the refrigeration servicing sector (decision 89/6) and preparation of national inventory of banks of used or unwanted controlled substances. The NOU will participate in the Energy Efficiency Twinning Workshop back-to-back with the Joint Network Meeting of South Asia and Southeast Asia National Ozone Officers in China in May 2024. NOU continues to implement the following gender activities: encouraging female participants in the meetings/training under the project and collection of gender-disaggregation data in project activities. The second payment of US$ 57,000 was released in March 2024. | Yes
|  | MDV/EEF/91/TAS/38 | UNEP | HPMP1 | ASP | MDV | TAS | SERVCEE-89/6 | Technical assistance: additional activities to maintain energy efficiency for the servicing sector under decision 89/6(b) | 2022-12-01 | 2024-06-01 | ONG |  | 2025-06-30 |  |  | 0 | 0 | [6 empty] | 100000 | 0 | 100000 | 0% | 100000 | 13000 | 0 | 13000 | 13000 | 0 | 100000 | 50000 | 0 | 13000 |  | 0 |  | 2025-06-01 | SSFA was signed in October 2023 for USD 100,000. First payment transferred in November 2023. | NOU in collaboration with energy department has developed the concept for the awareness videos and the ToR for the procurement of communication agency. Planning and preparations for study tour is ongoing. | Yes
|  | COI/PHA/91/TAS/34 | UNEP | HPMPIND | AFR | COI | TAS | Verification | Verification report on the implementation of stage I of the HCFC phase-out management plan | 2022-12-01 | 2024-12-01 | ONG | 2023-09-17 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 14.81% | 25556 | 3900 | 0 | 3900 | 3322.28 | 4444 | 25100 | 12778 | 577.72 | 3263 |  | 0 |  |  | The consultant was hierd, the final payment was disbursed in February 2024 and the verification report was submitted for the ExCom94. | The consultant was hierd, the final payment was disbursed in February 2024 and the verification report was submitted for the ExCom94. | Yes
|  | TOG/PHA/91/TAS/42 | UNEP | HPMPIND | AFR | TOG | TAS | Verification | Verification report on the implementation of stage I of the HCFC phase-out management plan | 2022-12-01 | 2024-12-01 | ONG | 2023-01-08 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 57.23% | 12830 | 3900 | 0 | 3900 | 1667.9 | 17170 | 12500 | 6415 | 2232.1 | 1625 |  | 0 |  |  | The consultant was hired, the first payment was disbursed in July 2023 and the second payment was disbursed in September 2023. | The final payment was sent in January 2024 and the consultant has delivred the report. The report will be updated in may 2024 to include the 2023 data. | Yes
|  | BRU/PHA/91/TAS/30 | UNEP | HPMPIND | ASP | BRU | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2022-12-01 | 2024-12-01 | ONG | 2023-11-21 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 12.23% | 26332.44 | 3900 | 0 | 3900 | 3423.2172 | 3667.56 | 11475 | 13166.22 | 476.7828 | 1491.75 |  | 0 |  |  | The project was approved at the Excom-91 in December 2022. UNEP discussed with the government the implementation modality for verification of HCFC consumption, including: (i) guidelines for the verification of national HCFC consumption targets for the multi-year agreements, (ii) year covered under verification, (iii) data and supporting document required for international consultant to conduct verification and (iv) expected timeline for verification. The Terms of Reference (ToR) for the international consultant was prepared in consultation with the country, cleared by the management in May 2023 and was advertised in June 2023. Following selection process, the international consultant was recruited by UNEP in September 2023 to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of Brunei, following the relevant decisions of the ExCom and guidelines for the verification of national consumption targets for the multi-year agreements. The consultant prepared and presented the draft work plan which included timeline for conducting the verification as well as tasks and roles and responsibilities of each concerned stakeholders in the verification process. The consultant also informed the NOU about support/cooperation that was required from various stakeholders. The consultant conducted a mission to Brunei in December 2023 to review the national legislation, policies and procedures on ODS import and export and conducted an assessment of the existing licensing and quota system to control HCFC import and export. The consultant also reviewed official statistics on import and export maintained by different sources and analyzed and compare those statistics. In addition, the consultant conducted interviews, and analyzed and cross-check various data collected from different sources. | The consultant reviewed 2023 official statistics on import and export maintained by different sources and analyzed and compare those statistics drafted verification report for the years of 2020-2023. The report was produced in English and provides detailed data demonstrating and confirming whether the consumption targets in the Agreement were achieved, whether there is existence of an operational licensing and quota system for HCFC imports and exports and whether the system is capable to ensure the country's compliance with the targets as set out in the Agreement between Brunei and the ExCom. Once submitted by the consultant, UNEP and NOU will review the draft verification report for feedback, which will be finalized and submitted along with the second tranche request in the second meeting of the ExCom in 2024. | Yes
|  | CBI/PHA/91/TAS/31 | UNEP | HPMPIND | AFR | CBI | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2022-12-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 0 | 15000 | 0 | 0 |  | 0 |  |  | At the end of implementation of the HPMP Stage II, first tranche The Terms of Reference (ToR) for hiring the international consultant will be prepared and advertised. The international consultant will then be recruited by UNEP to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of Cabo Verde, following the relevant decisions of the ExCom and guidelines for the verification of national consumption targets for the multi-year agreements. | The Terms of Reference (ToR) were completed by the CAP in February 2024. The consultant has been identified, and the establishment of the contract is currently in progress. | Yes
|  | MLW/PHA/91/TAS/53 | UNDP | HPMPIND | AFR | MLW | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2022-12-01 | 2024-12-01 | FIN | 2023-07-27 |  | 2023-12-01 | 2023-12-01 | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 99.32% | 205 | 3900 | 0 | 3900 | 26.65 | 29795 | 0 | 0 | 3873.35 | 0 |  | 0 |  |  | The Terms of Reference (ToR) for hiring the international consultant for Verification of the implementation of stage II of the HCFC phase-out management plan was prepared, cleared by the management. Verification exercise was completed and the report submitted to UNEP. The project is completed. | The project is financially completed | Yes
|  | PAR/PHA/91/TAS/45 | UNDP | HPMPIND | LAC | PAR | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2022-12-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 20000 | 15000 | 0 | 2600 |  | 0 |  |  | Good progress. international specialist to conduct the verfication report has been hired in November 2023. The consultant has prepared the first output which consisted in preaparing a first version of the main chapters of the report and started with the coordination and compilation of the data remotely. | Good progress. international specialist to conduct the verfication report has been hired in November 2023. The consultant prepared the final report and adressed the comments by the Sec. which will be submitted for ExCom 94 for approval. | Yes
|  | RWA/PHA/91/TAS/39 | UNDP | HPMPIND | AFR | RWA | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2022-12-01 | 2024-12-01 | ONG |  | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 0% | 30000 | 3900 | 0 | 3900 | 3900 | 0 | 0 | 15000 | 0 | 0 |  | 0 |  |  | The consultant reviewed official statistics on import and export maintained by different sources and analyzed and compared those statistics. In addition, the consultant conducted the necessary on-site visits and interviews, and analyzed and cross-check various data collected. The consultant reviewed the national legislation, policies and procedures on ODS import and export in Rwanda and conducted an assessment of the existing licensing and quota system to control HCFC import and export. The verification exercise is progressing very well. | The consultant prepared the draft verification reports in English and provides detailed data demonstrating and confirming whether the consumption targets in the Agreement were achieved, whether there is existence of an operational licensing and quota system for HCFC. The draft verification report is under review. The verification exercise is progressing very well. | Yes
|  | URT/PHA/91/TAS/45 | UNDP | HPMPIND | AFR | URT | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2022-12-01 | 2024-12-01 | ONG | 2023-05-26 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 99.32% | 205 | 3900 | 0 | 3900 | 26.65 | 29795 | 0 | 102.5 | 3873.35 | 0 |  | 0 |  |  | The consultant reviewed the national legislation, policies and procedures on ODS import and export in Tanzania and conducted an assessment of the existing licensing and quota system to control HCFC import and export. The consultant also reviewed official statistics on import and export maintained by different sources and analyzed and compared those statistics. In addition, the consultant conducted the necessary on-site visits and interviews, and analyzed and cross-check various data collected from different sources. The consultant drafted verification report. The reports was produced in English and provides detailed data demonstrating and confirming whether the consumption targets in the Agreement were achieved, whether there is existence of an operational licensing and quota system for HCFC imports and exports and whether the system is capable to ensure the country's compliance with the targets as set out in the Agreement between Tanzania and the ExCom. The Verification exercise is progressing satisfactorily. | The consultant reviewed the national legislation, policies and procedures on ODS import and export in Tanzania and conducted an assessment of the existing licensing and quota system to control HCFC import and export. The consultant also reviewed official statistics on import and export maintained by different sources and analyzed and compared those statistics. In addition, the consultant conducted the necessary on-site visits and interviews, and analyzed and cross-check various data collected from different sources. The consultant drafted verification report. The reports was produced in English and provides detailed data demonstrating and confirming whether the consumption targets in the Agreement were achieved, whether there is existence of an operational licensing and quota system for HCFC imports and exports and whether the system is capable to ensure the country's compliance with the targets as set out in the Agreement between Tanzania and the ExCom. The Verification exercise is progressing satisfactorily. | Yes
|  | UGA/PHA/91/TAS/34 | UNEP | HPMPIND | AFR | UGA | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2022-12-01 | 2024-12-01 | ONG | 2023-05-26 | 2024-12-01 |  |  | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 99.32% | 205 | 3900 | 0 | 3900 | 26.65 | 29795 | 0 | 102.5 | 3873.35 | 0 |  | 0 |  |  | The Terms of Reference (ToR) for hiring the international consultant for Verification of the implementation of stage II of the HCFC phase-out management plan was prepared, cleared by the management in March 2023. The consultant was hired in May 2023 and verification exercise is progressing well. | The consultant reviewed the national legislation, policies and procedures on ODS import and export in Uganda and conducted an assessment of the existing licensing and quota system to control HCFC import and export. The consultant also reviewed official statistics on import and export maintained by different sources and analyzed and compared those statistics. In addition, the consultant conducted the necessary on-site visits and interviews, and analyzed and cross-check various data collected from different sources. The consultant drafted verification report. The consultant drafted verification report for the years of XXXXXX (please, insert years of verification). The reports was produced in English and provides detailed data demonstrating and confirming whether the consumption targets in the Agreement were achieved, whether there is existence of an operational licensing and quota system for HCFC imports and exports and whether the system is capable to ensure the country's compliance with the targets as set out in the Agreement between Uganda and the ExCom. Verification exercise was completed and the report submitted to UNEP. The project is completed. | Yes
|  | ZAM/PHA/91/TAS/45 | UNEP | HPMPIND | AFR | ZAM | TAS | Verification | Verification report on the implementation of stage II of the HCFC phase-out management plan | 2022-12-01 | 2024-12-01 | FIN | 2023-05-29 |  | 2023-12-01 | 2023-12-01 | 0 | 0 | [6 empty] | 30000 | 0 | 30000 | 99.32% | 205 | 3900 | 0 | 3900 | 26.65 | 29795 | 0 | 0 | 3873.35 | 0 |  | 0 |  |  | The consultant reviewed the national legislation, policies and procedures on ODS import and export in Zambia and conducted an assessment of the existing licensing and quota system to control HCFC import and export. The consultant also reviewed official statistics on import and export maintained by different sources and analyzed and compared those statistics. In addition, the consultant conducted the necessary on-site visits and interviews, and analyzed and cross-check various data collected from different sources. The consultant drafted verification report. The reports was produced in English and provides detailed data demonstrating and confirming whether the consumption targets in the Agreement were achieved, whether there is existence of an operational licensing and quota system for HCFC imports and exports and whether the system is capable to ensure the country's compliance with the targets as set out in the Agreement between Zambia and the ExCom. The Verification exercise is progressing satisfactorily. | The project is financialy completed | Yes
Note on AP1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: XX meeting, based on the year of the APR and the last ExCom meeting held before the APR. to be derived