## Lessons_Learnt_Database
COUNTRY | code | subcode | project_title | sector | type | agency | agency_lessons
Afghanistan | AFG/PHA/47/TAS/05 |  | National phase-out plan (1st tranche) | PHA | TAS | UNEP | 1) The main challenges faced during the phase out of chlorofluorocarbons were the lack of time to meet very stringent control measures of phase-out, and lack of technical capacity to implement the protocol. Though, through bilateral support and especially UNEP’s technical support and assistance in institutional building efforts along with technical assistance provided by GTZ-Proklima, Afghanistan successfully complied with all obligations under the Montreal Protocol. Continuing with and building up on the existing human and institutional set up for the Montreal Protocol, Afghanistan is in a better position to phase out HCFCs consumption according to the agreed timeline given, that required technical and financial assistance to be provided to the country. 2) CFC phase-out in Afghanistan is that awareness raising, customs training together with regulatory measures should be deployed simultaneously to gradually reduce and eventually meet the targets set by the Montreal Protocol.
Afghanistan | AFG/SEV/74/TAS/19 |  | Survey of ODS alternatives at he national level | SEV | TAS | UNEP | The ODS alternative survey was first of its kind exercise that was carried out in Afghanistan. It was difficlut to get suitable local experts to carry the survey, and the guidance from UNEP OzonAction was important for the survey tean to understand the methodology and carry out the survey. The NOU did not have direct access to the import data with the Customs Authority, and the lack of streamlining in data recording created a barrier for capturing information for different ODS alternatives. The service workshops fo not maintain accurate records of the ODS alternatives that are used by them, therefore it becomes difficult to cross check the import data with the service sector use. There is inadequate capacity of key stakeholders on ODS alternatives use and monitoring of this use. The NOU would need to develop adequate institutional framework, policies and capacity to manage the data monitoring and information collection of ODS alternatives in the future.
Region: AFR | AFR/DES/68/TAS/41 |  | Strategy for disposal and destruction of ODS for five low-volume-consuming Central African countries (Burundi, Cameroon, Central African Republic, Congo and Guinea) | DES | TAS | France | Lessons learned/General Findings /Recommendations related to: (A) COOPERATION: 1) Regional cooperation. No matter how efficient the ODS management is designed, for the LVC countries it will be still costly and requiring considerable institutional capacities. However, the similarities in missing legislation, infrastructure and low ODS stocks can be seen as an opportunity to create and implement one “fit-for-all” framework . 2) Choose the source and type of ODS with the best cost efficiency performance, focus on larger urban areas and/or industrial sources (especially oil industry) and focus on ODS with high GWP. 3) Build/improve operative waste management sector in the countries. a) Stringent rules for waste management, starting with waste definitions, stakeholders´ definitions and responsibilities, licensing and standards, reporting, are basic for functional ODS management and destruction. b) In the case of the five targeted countries, the good base is Cameroon´s legislation. Depending on the chosen ODS source/s and type/s, specific operative regulations should be developed to streamline the process. c) Specific focus should be paid to tackling the imported “second-hand” and end-of-life electric appliances. 4. Economy of scale. a) Collect from more sources and/or more countries to reduce unit costs; b) Plan and prepare enlargement and intensification in the future. 5) Cooperation within and synergy with other sectors. a) Establish network, links among the stakeholders in ODS management and destruction – both horizontally within each country and horizontally among individual types in the region. b) Create the ODS management system as a component of a more complex action, in order to reduce the unit cost – integrate the waste management sector, POPs and chemicals management sector, energy efficiency improvement. (B) INFRASTRUCTURE: 1) Need for national aggregation centres & regional solution/s. In countries with oil industry such as the Republic of the Congo, mining industry such as Guinea (or other facilities with large ODS stocks), the aggregation should be localized where the industrial stockpiles are. Negotiations on cooperation in establishing the centres (e.g. providing storage capacities) with the industry can be initiated. Since the conditions in Cameroon are the most developed and the country has access to marine transport, Douala is proposed as regional aggregation/shipment point. 2) Need for eligible ODS destruction facility in Africa. With assistance of UNIDO, the countries may approach the facilities listed as potential destruction facilities and identify the feasibility/willingness for technology upgrade. Update should be obtained from Ghana or any other African country on this issue.
Region: AFR | AFR/FUM/16/TRA/10 |  | Regional workshop on methyl bromide for English-speaking African countries | FUM | TRA | UNEP | The cooperation between government has been reinforced to promote legislation, catalyze regional strategies, and develop action plan for the methyl bromide sector.
Region: AFR | AFR/FUM/17/TAS/14 |  | Replacement of methyl bromide with non-ozone depleting alternative in grain storage | FUM | TAS | Australia | Insufficient data
Region: AFR | AFR/FUM/17/TAS/15 |  | Methyl bromide data collection for Africa | FUM | TAS | UNDP | 1) In spite of the fact that due to local circumstances depending from each country, it is difficult to determine a time frame for data survey, the individual surveys were all completed within the original timeframe. 2) Doing the data surveys as a pre-requisite to the workshops run by UNEP was essential to enable the participating countries to discuss how they should proceed with the phase-out of methyl bromide and seek guidance from international experts ion the available options and their costs. 3) UNDP ensured that each country had a national data team for the data collection and preliminary analysis of the collected data. Governments really appreciated the trust UNDP had in national staff to effectively carry out these tasks. This helped the Governments really feel they were part of the process. It also helped them to take a more active interest in the design of MeBr alternative demonstration and investment projects.
Region: AFR | AFR/FUM/21/TRA/18 |  | Regional survey and workshop on methyl bromide for French-speaking African countries | FUM | TRA | UNEP | The following issues required special attention: 1) Establishment, administration and follow-up of 24 contracts requiring 50 separate payments 2) weak responsiveness of some of the participating countries 3) Civil unrest in two of the participating countries 4) Difficult communication with some of the participating countries.
Region: AFR | AFR/FUM/27/TRA/23 |  | Regional training of trainer courses for extension workers | FUM | TRA | UNEP | This project is the first implemented by UNEP with FAO. There were a number of problems associated with working with another international organization that is NOT officially an implementing agency of the MF, especially those regarding project scheduling, and reporting requirements which were needed by the MF, and which clearly was something that FAO did not think they were supposed to do. Additional complications also arose administratively when UNEP decided to implement not only one, but a series of project with FAO, approved by the MF at the same time, and were related components of a whole farming training programme. On the substantive part of project implementation, it should be said that working with FAO who is the leading authority on food security, and has extensive experience in farmer training, and extension work benefited the project immensely. The project was able to use this experience in ensuring that the training sessions were targeted and especially for extension workers, as techniques for such kind of training is very different from what one is used to under the other training funded by the MF.
Region: AFR | AFR/FUM/27/TRA/24 |  | REGIONAL TRAINING WORKSHOP ON POLICY DEVELOPMENT | FUM | TRA | UNEP | One main lesson that is important from this project is the need to be very meticulous in ensuring that the right participants attend the workshop. It is also important that speakers be carefully considered, looking at a combination of both technical and communication skills, as an effective speaker can encourage participants to make their views known, hence enhancing the level of discussion during the workshops.
Region: AFR | AFR/FUM/34/TRA/28 |  | Regional workshop on the experiences of use of methyl bromide alternatives evaluated under the Multilateral Fund | FUM | TRA | UNEP | 1) The workshop highlighted wide range of methyl bromide alternatives that have proved successful and were recommended for adoption by other countries for similar treatment. One important aspect being the issue on sourcing of local materials and supplies, to replace the imported substitutes which are more expensive and less sustainable. Some farmers for instance, have gone a step further to source for local materials for replacement of imported ones. In the uses of floating tray, farmers are experimenting on alternative media like rice husks, groundnut shells and macadamia nut shells to replace the scarce and expensive pine bark. Promotion for local production and supply of alternatives was therefore highly recommended. 2) Promotion of awareness and dissemination of information on commercially available alternatives have contributed to adoption of alternatives and are important tools to phasing out methyl bromide. The role played by NGOs in the methyl bromide communication programme was significant in increasing public awareness. Networking between NGOs and NOUs can act as a key support in information exchange and enhancing awareness raising activities. 3) The need for practical training of stakeholders on use of specific alternatives was seen as essential for wider acceptance, adoption and sustained use. Stakeholders' workshop could be organized to demonstrated use of specific alternatives where, for example, they have not been demonstrated. Kenya success story on Farmer Field School was well appreciated with countries indicating interest to have similar projects. 4) The workshop recognizes that for a successful methyl bromide phase out, countries need to be supported by strong regulatory and policy framework.
Region: AFR | AFR/FUM/38/TAS/32 |  | Technical assistance for methyl bromide reductions and formulation of regional phase out strategies for low volume consuming countries | FUM | TAS | UNDP | (1) The countries covered in this project were: Burundi, Benin, Central African Republic, Chad, Comoros, Congo (Brazzaville), Democratic Republic of Congo, Djibouti, Gabon, Gambia, Guinea, Mali, Mauritania, Niger, Sao Tome, Sudan, Togo, Zambia. (2) Major difficulties: (a) Communication: very slow communication flow in general. Some countries do not have easy access to the Internet and the telecommunications are also not easy. (b) Implementation difficulties in consuming countries due in part to the lack of precise information and data regarding the location and the sector of use of methyl bromide. (c) Difficulties in collecting accurate information especially regarding methyl bromide consumption. The accuracy of the data remains a major issue. (d) Non-reported consumption: DR Congo conducted a national survey and did not identify any methyl bromide uses. Nevertheless, neighbouring countries reported that most of the illegal methyl bromide imports come from DR Congo. (e) The regional approach, and the large number of countries involved, required very intense follow-up at all stages of the implementation. Project was time and human resources consuming. (f) Translation of all documents into French. (g) In order to reinforce the ownership feeling of the participants, each country received its own contract to undertake some activities. This approach brought about important follow-up and administrative work (several extensions and modifications of contracts required in the course of the project). (h) A regional project with 20 countries has naturally resulted in the involvement of a large number of actors. It again required important follow-up work and solid coordination. (i) Because of the small amount of funding for each country, some countries did not really commit to the project. (j) Efforts were put into trying to collaborate with UNEP CAR ROA but this did not lead to the results hoped for. (k) Difficulty to reach a consensus among the 18 ozone officers. Approval of each document required time. (l)Because of the very nature of the project, we adopted a uniform approach and that was perfectly understood by the NOUs. Nevertheless, they also requested that we take into account their specific situation and this slowed down implementation. (3) Major achievements: (a) Public awareness activities conducted during the course of the project implementation. (b) Identification of major users and major uses in countries with consumption. (c) Identification of stakeholders in participating countries. The national legal consultant identified the major stakeholders and organised a workshop. The stakeholders are members of a methyl bromide consultation group. (d) Identification of national experts (legal and technical experts). (e) Interactions among countries (i.e. Togo and Benin) and information exchange especially during the network meetings. (f) Countries with consumption are in compliance and reduced their methyl bromide consumption even though technical assistance was not implemented (as a result of the public awareness campaigns and an improved monitoring of methyl bromide issues by NOUs). (g) Countries ratified the Copenhagen Amendment (Central African Republic, Comoros, Gambia, Mali, Mauritania, Swaziland, Zambia). (h) Legislation update prepared. (i) National strategies developed to prevent the introduction or reintroduction of methyl bromide in future. (j) We could use documents already finalised to explain what exactly needed to be done to countries with similarities. This approach was very much appreciated by the countries. (k) The project contributed to improve the understanding of methyl bromide issues among the countries. (l) Improvement of the data collection process in the visited countries and better understanding of the data that need to be collected. (m) Installation of alternatives in Congo and Sudan. (n) Technical training of national experts (technical experts) and methyl bromide users by international consultants during the onsite sessions. (o) Customs authorities were reluctant to deliver data in some countries but the missions we conducted in those countries helped in solving this issue. (p) The regional approach helped in centralising the information and this has been of some benefit (i.e. we managed to facilitate concrete exchange of information among some countries and to organise cross-countries meetings with customs officers).
Region: AFR | AFR/FUM/54/DEM/40 |  | Regional demonstration project on alternatives to the use of methyl bromide for treatment of high moisture dates (Algeria and Tunisia) | FUM | DEM | UNIDO | 1) Experience has shown that full involvement of local experts and expertise is needed for the successful preparation, design and implementation the activities. 2) This project contributed to the sustainable trade of high moisture dates, not only in Algeria and Tunisia, but also in other date producing countries in the region where the experience can easily be replicated. 3) Different combinations of key factors including the selection of appropriate alternatives, the demonstration of their technical and economic feasibility, and the provision of political, regulatory and institutional support, contributed significantly to successful project outcomes. 4) Implementations were delayed due to lack of appropriate technical expertise.
Region: AFR | AFR/HAL/35/TAS/29 |  | Establishment of a regional halon bank for Eastern and Southern African countries (Botswana, Ethiopia, Kenya, Lesotho, Namibia, Tanzania and Zimbabwe) | HAL | TAS | Germany | Regional activities need considerable more coordination and cooperation of the participating countries. Since the halon phase out required replacement of existing systems, the owners were required to invest in new fire fighting system. This was met with some opposition due to higher costs of replacement systems which could not be covered by the project budget.
Region: AFR | AFR/REF/06/TRA/04 |  | Regional training course on refrigeration for Africa | REF | TRA | UNEP | None.
Region: AFR | AFR/REF/10/TRA/05 |  | Training and demonstration programme in commercial/industrial refrigeration in West Africa (French) | REF | TRA | UNEP | 1) Training must be done in co-operation with Gov't 2) Intensify public awareness campaign 3) Gov't should develop more active strategies to phase-out ODS
Region: AFR | AFR/REF/10/TRA/06 |  | Training and demonstration programme in commercial/industrial refrigeration in Africa (English-speaking countries) | REF | TRA | UNEP | N/A
Region: AFR | AFR/REF/48/DEM/34 |  | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | REF | TAS | Germany | If the NOU is well informed and a forceful personality, she/he is able to get the national government to adopt actions in line with overall objectives. This was the case in Namibia where the NOU was able to push forward the need for government to take on investments in the chiller sector in order to phase out Rll.
Region: AFR | AFR/REF/48/DEM/36 |  | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | REF | DEM | France | 1) Lessons learned related to the role of implementing agency (UNIDO): Implementing agency has had a foremost role in the project implementation process through guidance, technical expertise, and invaluable feedback about specific experiences in other similar projects. 2) Lessons learned related to the project design: Project design should be kept as simple as possible even if the issues are complex. Despite the considerable complexity in this case, the implementation of this strategic demonstration project was facilitated by a simple and practical project design which included preparing the terrain for project implementation, technology transfer demonstrating energy efficiency and dissemination of lessons learned. 3) Lessons learned related to the coordination between various donors and IA: Strong and structured coordination between various donors can aid in project implementation. This project ensured that there was good coordination between the various cooperating agencies from the outset. 4) Lessons learned related to the partnership: This project is a good example of partnerships and cooperation between a multilateral donor through UNIDO, bilateral donors – France, Germany and Japan, – and commercial banks. To that respect, one could underline the specificity of its financial mechanism which will give the private sector the opportunity to take over public financing. 5) Lessons learned related to the transfer of green technology: The agreement between UNIDO and the French Global Environment Facility (Fonds Français pour l'Environnement Mondial - FFEM) helped implement an innovative and commercially viable strategy for replacing CFC-based chillers in six African countries. This helped remove relevant barriers and included the transfer of green technology, the creation of a working fund mechanism, the management of CFC stockpiles, and the dissemination of awareness to chiller operators and end-users, as well as to the Governments of the countries involved. 7) Lessons learned related to the building accommodations /actual site conditions: Before starting with activities/replacement of the chillers, inspection of the actual site and investigations of all conditions involved in executing the project are highly recommended. 8) Lessons learned related to the survey/inventory: At the very beginning of a national chiller replacement programme, an inventory of existing CFC (and other) chillers has to be established, and this must be updated regularly. 9) Lessons learned related to the difficulties to obtain details of the project: Due to the changing in staff assigned to the Africa chiller project at UNIDO and the age of the project, details of the project were difficult to obtain at a later stage. It is important that the achievements are well documented and retained not only by the Implementation Agency. Information should be well-documented and level of involvement by the donor countries and National Ozone Units is important to ensure that the necessary records are kept. 10) Lessons learned related to awareness –raising and capacity buildings: a) Consultation and direct involvement stakeholder at an early stage ensure that they act as the promoters for chiller replacement projects and thus assure the project’s sustainability. b) Capacities needed to be built as pre-requisites to assure proper handling of the technologies. With a proper design and installation of the new chiller system, allied to the proper operation and maintenance techniques. c) The identification of local banking partners and elaboration of a fund-mobilization strategy at the national level was necessary in order to demonstrate sustainable and innovative mechanisms to facilitate the replacement of chillers. d) Capacity-building efforts were vital in order to train investors in the technical analysis and modifications required to achieve the highest efficiency gains from chiller replacement. Transfer of technology (TOT) played an important role to ensure the introduction of adequate technology, which was appropriate to country-specific needs. Training of staff was a key component to ensure maximum benefits of the new equipment as different operational and maintenance approaches were required. 11) Lessons learned provided by the NOU Cameroon: Experience has been gained in the case of CFC replacement, this project and its impact can be replicated in the phase-out of HCFCs and phase down of HFCs currently in progress if funds for replacement of old equipment are made available for the end-users.
Region: AFR | AFR/REF/48/DEM/37 |  | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | REF | DEM | UNIDO | 1) Lessons learned related to the role of implementing agency (UNIDO): Implementing agency has had a foremost role in the project implementation process through guidance, technical expertise, and invaluable feedback about specific experiences in other similar projects. 2) Lessons learned related to the project design: Project design should be kept as simple as possible even if the issues are complex. Despite the considerable complexity in this case, the implementation of this strategic demonstration project was facilitated by a simple and practical project design which included, project development including preparing the terrain for project implementation, technology transfer demonstrating energy efficiency and dissemination of lessons learned. 3) Lessons learned related to the coordination between various donors and IA: Strong and structured coordination between various donors can aid in project implementation. This project ensured that there was good coordination between the various cooperating agencies from the outset. 4) Lessons learned related to the partnership: This project is a good example of partnerships and cooperation between a multilateral donor through UNIDO, bilateral donors – France, Germany and Japan, – and commercial banks. To that respect, one could underline the specificity of its financial mechanism which will give the private sector the opportunity to take over public financing. 5) Lessons learned related to the transfer of green technology: The agreement between UNIDO and the French Global Environment Facility (Fonds Français pour l'Environnement Mondial - FFEM) helped implement an innovative and commercially viable strategy for replacing CFC-based chillers in six African countries. This helped remove relevant barriers and includes the transfer of green technology, the creation of a working fund mechanism, the management of CFC stockpiles, and the dissemination of awareness to chiller operators and end-users, as well as to the Governments of the countries involved. 6) Lessons learned related to the building accommodations /actual site conditions: Before starting with activities/replacement of the chillers, inspection of the actual site and investigations of all conditions involved in executing the project are highly recommended. 7) Lessons learned related to the survey/inventory: At the very beginning of a national chiller replacement programme, an inventory of existing CFC (and other) chillers has to be established, and this must be updated regularly. 8) Lessons learned related to the difficulties to obtain details of the project Due to the changing in staff assigned to the Africa chiller project at the UNIDO and the age of the project, details of the project were difficult to obtain at a later stage. It is important that the achievements are well documented and retained not only by the Implementation Agency. Information should be well-documented and level of involvement by the donor countries and National Ozone Units is important to ensure that the necessary records are kept. 9) Lessons learned related to awareness –raising and capacity buildings: a) Consultation and direct involvement stakeholder at an early stage ensure that they act as the promoters for chiller replacement projects and thus assure the project’s sustainability. b) Capacities needed to be built as pre-requisites to assure proper handling of the technologies. With a proper design and installation of the new chiller system, allied to the proper operation and maintenance techniques. c) The identification of local banking partners and elaboration of a fund-mobilization strategy at the national level was necessary in order to demonstrate sustainable and innovative mechanisms to facilitate the replacement of chillers. d) Capacity-building efforts were vital in order to train investors in the technical analysis and modifications required to achieve the highest efficiency gains from chiller replacement. Transfer of technology (TOT) played an important role to ensure the introduction of adequate technology, which was appropriate to country-specific needs. Training of staff was a key component to ensure maximum benefits of the new equipment as different operational and maintenance approaches were required. 10) Lessons learned provided by the NOU Cameroon: Experience has been gained in the case of CFC replacement, this project and its impact can be replicated in the phase-out of HCFCs and phase down of HFCs currently in progress if funds for replacement of old equipment are made available for the end-users.
Region: AFR | AFR/SEV/06/TRA/01 |  | Regional workshop for Africa | SEV | TRA | UNEP | 1) Success of workshop depends on continuing contracts between ozone focal points & IA representatives
Region: AFR | AFR/SEV/11/TRA/07 |  | Industry workshop on the practical implementation of the Protocol for English-speaking countries | SEV | TRA | UNEP | None.
Region: AFR | AFR/SEV/12/TRA/08 |  | Follow-up on prior regional workshop and training activities | SEV | TRA | UNEP | Some elements have been identified as necessary to ensure the intended results of a training activity. 1) Political and social stability 2) Government commitment and capacity 3) Early involvement of stake holders at the planning and implementation Level
Region: AFR | AFR/SEV/17/TRA/11 |  | Technology transfer workshop for African countries on practical implementation of the Montreal Protocol | SEV | TRA | UNEP | None.
Region: AFR | AFR/SEV/19/TRA/16 |  | Regional workshop on monitoring and control of ODS consumption for English-speaking Africa | SEV | TRA | UNEP | None.
Region: AFR | AFR/SEV/32/TAS/28 |  | Harmonization of legislative and regulatory mechanisms to improve monitoring and control of ODS consumption in French-speaking African countries | SEV | TAS | UNEP | The adoption of a harmonized legislation on ODS import in western and central French speaking countries makes the enforcement of national regulations easier. The adoption of local regulations has been facilitated through this project.
Region: AFR | AFR/SEV/36/TAS/30 |  | Regional surveys in halon and methyl bromide sector | SEV | TAS | UNDP | 1) UNDP has been developing and conducting a survey on methyl bromide and halon in African countries. The surveys aimed to identify the countries needs (technical assistance and policy assistance) and to formulate national and regional strategies in the halon and methyl bromide sectors. Both surveys focused on providing assistance to the Low Volume Consuming countries. 2) Methyl bromide sector: A) In the methyl bromide sector, with respect to the Parties obligations under the Montreal Protocol, the survey helped to identify the most effective activities, timetables for actions steps and responsible organizations, and to formulate regional methyl bromide phase-out strategies. B) The survey has been developed by including and analyzing the results of previous methyl bromide projects in the region so as to allow for the development of regional strategies that begin by building upon prior experience in the methyl bromide sector. C) As a result, the survey helped with the identification of the major technical/agricultural and policy barriers faced by the LVCs, and perceived to be very difficult to overcome. 3) Halon sector: A) In the halon sector, the survey focused on the identification of the installed capacities in 6 French-Speaking countries. The survey also aimed to identify the various options to help the countries to meet with the 2002 freeze under the Montreal Protocol: needs for regulation enforcement, awareness activities, set up of a halon stock, etc. B) The halon survey also led to the formulation of national strategies and regional coordination to establish a halon bank in the region.
Region: AFR | AFR/SEV/45/TAS/33 |  | Sub-regional project on hannonization of legislative and regulatory mechanisms to improve monitoring and control of ODS consumption in English-speaking Africa | SEV | TAS | UNEP | 1) Co-operation between national governments and the industry is essential. It is essential to ensure that the obligations of the harmonized Regulation are communicated to all those affected and are being understood correctly; 2) The implementation of a harmonized piece of legislation such as the ODS Regulation takes time; and 3) The RAC industry is extremely diverse. Any regulatory measure needs to take into account this diversity. The choice of a refrigerant depends on a range of factors: Climate, application, energy efficiency, safety, cost, technical viability, direct and indirect emissions, etc.
Region: AFR | AFR/SEV/53/TAS/38 |  | African customs enforcement networks for preventing illegal trade of ODS in the African sub-regional trade organizations (CEMAC, COMESA, SACU and UEMOA) | SEV | TAS | UNEP | 1) Cooperation with relevant industry has proven to be generally advantageous in the ODS phase-out process in the African sub-regions as it involves those concerned in day-to-day operations which know the relevant user areas best and have the necessary technical know-how, including knowledge about potential alternatives. In the end, it is the relevant industry sectors which need to implement the ODS phase-out. Involving industry directly in the phase-out process and attaining their commitment in this respect greatly reduces the need for enforcement. Industry, on the other side, benefits by knowing about regulations to be passed and future policies at an early stage, which enables them to plan and adapt in good time; 2) One of the problems identified regarding enforcement is the difficulty for customs officials to identify ODS. Member States indicated that it was particularly difficult to distinguish products and equipment containing ODS from those that do not, especially when the substances are used in blends; and 3) Another problem identified was the lack of close cooperation between environmental and customs authorities, which Member States considered an important element of enforcement.
Albania | ALB/PHA/39/INV/10 |  | National ozone depleting substances phase-out plan: conversion of cleaning installations from carbon tetrachloride (CTC) to tetrachloroethylene (PER) at Energy Combinat Ltd., Elbasan | PHA | INV | UNIDO | (1) During the implementation, the design of the equipment was done in such way that the production and capacity were not affected. Intensive training for the employees for using the safety equipment needed to be given for the process/equipment. Maximum efforts should have been taken during the equipment commissioning period so that the product parameters and rated equipment output were properly established. (2) Well-established linkages between UNIDO, UNDP and National Ozone Unit facilitated the efficient and proactive arrangements for custom clearance of imported equipment and installation and commissioning.
Albania | ALB/PHA/39/TRA/07 |  | Training of Refrigeration Technicians | PHA | TRA | UNEP | The objectives set out for the workshop were fully met through the appropriate design of the workshop agenda. The second phase workshops were organised in 11 regional districts during which all aspects related to ODS were considered. The workshops have been completed with the following results: 1) 271 technicans have successfully been trained and certified in "Good practices in refrigeration". The workshops covered both theoretical and practical aspects of good service practices. 2) The training manual by UNEP on "Good Practices in Refrigeration and Chillers and Refrigerant Management" was used as a resource document. This training manual was fully translated into Albanian. Additionally a manual on Good practices in Alabanian was published. Each workshop participant was provided with a copy of the handbook on good practices (UNEP) in Albanian language and the manual. 3) Participants took keen interest in practical work to acquire hands-on experience in the use of servicing equipment for recovery/recycling, evacuation, charging etc. There were very interesting discussions during the discussion sessions about use of good practices in the practical situations. Several major alternative refrigerants were examined. 4) Exchange of information and experiences between the participants though a network of personal contacts.
Albania | ALB/PHA/71/TAS/27 |  | Verification report for stage I of HCFC phase-out management plan | PHA | TAS | UNIDO | 1) Annual consumption of HCFCs in 2015 and 2016 is below the maximum allowable total consumption of Annex C, Group I substances established by the Agreement between the Government of the Republic of Albania and the Executive Committee of the MLF. Albania is in compliance with the current Agreement. 2) Albania is an official candidate country for accessing the European Union. It would need to adjust the ODS legislation to the European Regulation on ODS. 3) The training program is very well organized. It is recommended to continue the training of technicians and environment inspectors.
Albania | ALB/PHA/82/TAS/37 |  | Verification report on the implementation of the HCFC phase-out management plan | PHA | TAS | UNIDO | 1) Related to monitoring and control of ODS imports and exports by the Customs: It is very important to establish a reliable national system of monitoring of ODS trade and consumption as early as possible and to strengthen the cooperation with the Customs authorities in order to monitor and prevent the illegal trade of HCFCs. The Albanian Customs, as well as those of the European countries, pay an increasingly important attention to monitor and control the imports and exports of controlled substances. ASYCUDAWorld is now fully operational in the Albanian Customs Administration and 100% of the declarations are processed through ASYCUDA. The Customs has established the Harmonized System codes that adequately identify the controlled substances. Customs Code of Albania includes the sanctions and penalties to be imposed in the cases of violation of legal regulation. It is important that the latest ozone-depleting substance identifiers (which can identify HCFCs and blends) are provided to enforcement officers to facilitate their work in controlling illicit trade in HCFCs. 2) Related to recovery and recycling scheme: The recovery and recycling scheme is functioning well. It is recommended to strengthen the cooperation between the service shops for the R & R scheme as well as to continue training of technicians. 3) Related to legislation: As an official candidate country for accessing the European Union, It would need to continue improving and adjusting the ODS legislation to the European Regulations.
Algeria | ALG/ARS/18/INV/12 |  | Phasing out CFCs at ENAD | ARS | INV | UNIDO | (1) Delay due to relocate the existing filling lines. (2) Because of safety reasons the filling with hydrocarbon propellant has to be made outside in an adjacent building.
Algeria | ALG/ARS/20/INV/15 |  | Phasing out of CFCs at Ets Has Mohamed. | ARS | INV | UNIDO | The level of funding of such projects is so low that the counterpart has to finance on his own additional equipment to optimize the conversion of the plant, creating additional delays.
Algeria | ALG/ARS/20/INV/16 |  | Phasing out of CFCs at Vague de Fraicheur. | ARS | INV | UNIDO | Level of funding insufficient.
Algeria | ALG/ARS/20/INV/17 |  | Phaing out of CFCs at Ets Wouroud. | ARS | INV | UNIDO | Although this project benefited from a higher level of funding, funds were still insufficient for the purchase of LPG storage tank. The method of calculation of the aerosol projects does not permit a full conversion.
Algeria | ALG/ARS/20/INV/18 |  | Phasing out of CFCs at Laboratoire Bendi. | ARS | INV | UNIDO | The fact that the counterpart had purchase at his own cost additional equipment for a complete conversion, delayed the whole project.
Algeria | ALG/ARS/20/INV/19 |  | Phasing out of CFCs at Ets COPHYD ALGERIA | ARS | INV | UNIDO | (1) Close statement with counterpart is essential (2) Close relations with supplier, ozone office are important.
Algeria | ALG/ARS/25/INV/28 |  | Replacement of CFC-11 & CFC-12 with hydrocarbons in the aerosol sector at Ets Djadir | ARS | INV | UNIDO | Some delays in the project implementation can be avoided through better coordination of activities among the parties concerned.
Algeria | ALG/ARS/28/INV/38 |  | Phase out of CFC11/CFC12 by conversion to Hydrocarbon Technology in the Manufacture of Aerosols at FLOREAL | ARS | INV | UNIDO | To avoid problems with LPG bulk supply and start of CFC-free aerosol production it will be most essential if the beneficiary company adheres to recommended specifications of the equipment funded with its own resources.
Algeria | ALG/ARS/28/INV/41 |  | Phase out of CFC11/CFC12 by conversion to Hydrocarbon Technology in the Manufacture of Aerosols at company SACO | ARS | INV | UNIDO | It will be more realistic if projects envisaging re-location of aerosol production are programmed for more than 12 months duration. Respective Government authorities (NOUs) should take better care of the issue of baseline equipment destruction.
Algeria | ALG/FOA/19/INV/13 |  | Phasing out of CFC-11 in the manufacture of sandwich panels by discontinuous method at PROSIDER Berrahal. | FOA | INV | UNIDO | Before starting the implementation of a project it is necessary to obtain the commitment of the company about its readiness to accomplish the project. If this commitment is not reached, the best solution is to cancel the project from very beginning.
Algeria | ALG/FOA/19/INV/14 |  | Phasing out of CFC-11in the manufacture of sandwich panels at BATIMETAL Béni Mansour. | FOA | INV | UNIDO | Change to hydrocarbon technology is not as easy issue if the company is not well aware of the problems involved. In this particular case it was necessary to provide extensive training to the counterpart staff. After some delays in the start of the training and after its completion, the commissioning of the factory took place.
Algeria | ALG/FOA/22/INV/21 |  | Phasing out of CFC at Ets LEULMI ESSAID flexible polyurethane Foam plant. | FOA | INV | UNIDO | If the company is not well established and shows a big interest; It is recommended for the future no to start a project preparation.
Algeria | ALG/FOA/22/INV/22 |  | Phasing out CFC-11 at SNAM flexible polyurethane Foam plant. (MP/ALG/97/080) | FOA | INV | UNIDO | It is necessary more coordination with the counterparts to allow contractors the installation of the new equipment. The training of the counterpart’s staff was basic in the success implementation of the project.
Algeria | ALG/FOA/22/INV/23 |  | Phasing out CFC-11 at SAMMO flexible polyurethane Foam plant. (MP/ALG/98/098) | FOA | INV | UNIDO | It is necessary more coordination with the counterparts to allow contractors the installation of the new equipment. The training of the counterpart’s staff was basic in the success implementation of the project.
Algeria | ALG/FOA/23/INV/25 |  | Phasing out CFC-11 at La Mousse du Sud flexible polyurethane foam plant. (MP/ALG/97/160) | FOA | INV | UNIDO | For the new projects in the future, we should include the complete LCD system; it means tank, transfer pump, primary recycling loops and piping. Because in this project it was not included the mentioned equipment. The consequence was a delay very important. When the company takes the decision to buy a new foam machine the planned duration should take in consideration the delivery time for the new foam machine, the time for the installation and the commissioning before to start the LCD commissioning.
Algeria | ALG/FOA/25/INV/27 |  | Phase out of CFC-11 in the manufacture of flexible polyurethane foam through the use of Methilene Chloride technology at ETS MATELAS DJURDJURA (MP/ALG/98/044) | FOA | INV | UNIDO | It is necessary more coordination with the counterparts to allow contractors for the installation of new equipment. The training of the counterpart’s staff was basic in the success implementation of the project.
Algeria | ALG/FOA/26/INV/29 |  | Phasing out CFC-11 at ETS Maghreb Mousse (MP/ALG/98/093) | FOA | INV | UNIDO | It is necessary more coordination with the counterparts to allow contractors the installation of the new equipment. Training of the counterpart’s staff was basic in the success implementation of the project.
Algeria | ALG/FOA/27/INV/33 |  | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Matelas Atlas (Sam Atlas) (MP/ALG/99/032) | FOA | INV | UNIDO | It is necessary to improve the coordination with the counterparts to obtain the best installation of the new equipment. The training of the counterpart’s staff is basic for a successful implementation of the project.
Algeria | ALG/FOA/27/INV/34 |  | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at King's Matelas. (MP/ALG/99/031) | FOA | INV | UNIDO | It is necessary to improve the coordination with the counterparts to obtain the best installation of the new equipment. The training of the counterpart’s staff is basic for a successful implementation of the project.
Algeria | ALG/FOA/28/INV/37 |  | Phasing out of CFC-11 by conversion of methylene chloride in the manufacture of flexible polyurethane slabstock foam at Matelas Mondial (MP/ALG/99/117) | FOA | INV | UNIDO | It is necessary to improve the coordination with the counterparts to obtain the best installation of the new equipment. The training of the counterpart’s staff is basic for a successful implementation of the project.
Algeria | ALG/FOA/28/INV/39 |  | Phasing out of CFC-11 by conversion of methylene chloride in the manufacture of flexible polyurethane slabstock foam at Orania Mousse Ameublement (MP/ALG/99/118) | FOA | INV | UNIDO | It is necessary to improve the coordination with the counterparts to obtain the best installation of the new equipment. The training of the counterpart’s staff is basic for a successful implementation of the project.
Algeria | ALG/FOA/31/INV/44 |  | Conversion No. 04 Zone Industrielle Route de Chetouane Tlemcen | FOA | INV | Germany | The use of the LCD technology for mattresses flexible PUF moulding, using high pressure dispensing equipment, is a perfectly viable proposition.
Algeria | ALG/FOA/32/INV/45 |  | Conversion of SOFTPM, Choupot Oran, to LCD technology | FOA | INV | Germany | The use of the LCD technology for the production of mattresses and furniture with flexible PUF moulding, using high pressure dispensing equipment, is a perfectly viable proposition.
Algeria | ALG/FOA/32/INV/46 |  | Conversion of Matelas Souf to LCD technology | FOA | INV | Germany | The use of the LCD technology for the production of mattresses and furniture with flexible PUF moulding, using high pressure dispensing equipment, is a perfectly viable proposition.
Algeria | ALG/HAL/35/TAS/51 |  | Sectoral phase out programme: establishment of a halon bank | HAL | TAS | Germany | In Algeria the cooperation with Sonatrach was the key to the project. Sonatrach is the biggest national and 11th largest petrol company in the world. They do represent the biggest halon user in Algeria. With them supporting the private company Gaz Industriel (now: Linde Gas Algeria (LGA)) the halon phase out in Algeria can be stated as sustainable. GI (or LGA) is the largest gas provider in Algeria and well experienced with handling high pressurized gas. They are the national provider for fire protection gases. Additionally they have a plant for liquid nitrogen at their premises. Thus being able to provide liquid nitrogen at minimal cost for the halon separation unit.
Algeria | ALG/REF/15/INV/09 |  | Investment Project for phasing out CFCs at ENIEM | REF | INV | UNIDO | (1) Postponement of decision and delays due because general contractor is not the manufacturer of the equipment. (2) The involvement of the counterpart were decisive in the success of the project.(3) Equipment component should be ordered directly from the manufacturer in order to benefit from reduced prices and immediate services.
Algeria | ALG/REF/25/INV/26 |  | Replacement of CFC-12 with HFC-134a for commercial refrigeration at E.N.A.P.A.T. | REF | INV | UNIDO | None.
Algeria | ALG/REF/26/INV/30 |  | Replacement of CFC-12 with HFC-134a for Domestic refrigeration at E.N.A.P.E.M. | REF | INV | UNIDO | None
Algeria | ALG/REF/32/INV/47 |  | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration at the RCA (Société de Réfrigeration et de Conditionnement de l'air) | REF | INV | UNIDO | Careful analysis of the company’s financial prospects prior to project completion might be desirable.
Algeria | ALG/REF/37/INV/56 |  | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the first group of commercial refrigerator manufacturers | REF | INV | UNIDO | More training on the transfer of technology proved to be beneficial in maintaining the product quality.
Algeria | ALG/REF/37/TAS/55 | Multi-Year | Refrigerant management plan to phase out the use of ODS in the refrigeration and air-conditioning sector: training in good refrigerant management practices, training of customs officers, and national recovery and recycling: first tranche | REF | TAS | UNIDO | 1) Discussion with the participants showed that more practical exercises are required with a special session on troubleshooting in case of failure of equipment. Therefore training on equipment delivered through the project is essential. Moreover, availability of spare parts for equipment delivered through the project in the local matter is enough to ensure full usage of machine. 2) Cooperation and sharing expertise between all involved stakeholders strengthens the results of the training.
Algeria | ALG/REF/39/TAS/58 | Multi-Year | Refrigerant management plan to phase out the use of ODS in refrigeration and air-conditioning sector (including training in good refrigerant management practices, training of customs officers, and national recovery and recycling): second tranche | REF | TAS | UNIDO | The training equipments including MAC were well arranged before the course started, which made the practical seession successful; Having deducated and practical sesssions during the workshops proved to be a good way to achieve the objectives of the workshop.
Algeria | ALG/REF/42/TAS/59 | Multi-Year | Refrigerant management plan to phase out the use of ODS in the refrigeration and air-conditioning sector: training in good refrigerant management practices, training of customs officers, and national recovery and recycling: third tranche | REF | TAS | UNIDO | Discussion with the participants showed that more practical exercises are required. Having dedicated theoretical and practical sessions during the workshops proved to be a good way to achieve the objectives of the workshop.
Algeria | ALG/REF/44/INV/62 |  | Conversion of CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the last group of commercial refrigerator manufactures (refrigeration sector terminal project) | REF | INV | UNIDO | (1) Identify reliable suppliers for the implementation of the new technology. (2) Create an experienced project management team from beginning to end.
Algeria | ALG/SEV/09/CPG/01 |  | Country programme preparation | SEV | CPG | UNEP | The accurate compilation of data and information is vital. If this is not done, phase out activities and possible projects are not properly identified.
Algeria | ALG/SOL/17/INV/10 |  | Investment Project for phasing out CFCs at ENAD | SOL | INV | UNIDO | None
Angola | ANG/PHA/73/TAS/13 |  | Verification report for stage I of HCFC phase-out management plan | PHA | TAS | UNDP | The funding for the verification report was approved at ExCom 73 and the report was submitted and accepted by the MLFS prior to ExCom 75. It can be considered a good practice.
Angola | ANG/REF/39/TAS/04 | Subproject1 | Refrigerant Management Plan for the Republic of Angola. | REF | TAS | Germany | a.) The implementation of the RMP-Angola started slowly and with some delay. This was not only due to the civil war in Angola, but was aided by the fact that the institutions involved (such as National Directorate of Environment, National Ozone Unit) at the beginning were not always aware of the tasks /duties they were supposed to comply and the way to approach them. One of the reasons to blame was the unavailability of Portuguese literature and brochures that could help to understand their mission in the framework of the Montreal Protocol (Being part of Southern Africa and SADCC the Republic of Angola had decided to join the English-speaking Network in Africa). However, together with NOUs from other Lusóphonos countries, the Angolan NOU repeatedly claimed the lack of Portuguese literature during OZONET-conferences. At the end it was rather due to the initiative of the Angolan NOU themselves (and gtz-Proklima as Implementing Agency) that they managed to get the necessary literature from Portugal, Brazil as well as through the Internet. Accordingly one of the lessons to learn would be, that NOUs of A5 countries should have access to the relevant literature in their language. b.) As for some other A5 countries for Angola the development of a legal framework aiming on the control of imports & consumption of CFC showed to be the most complicated task within its obligations towards the Montreal Protocol. These difficulties and the delays resulting thereof possibly could have been avoided through preparation of a standard version of a ODS related Legislation (through Funds Secretariat or Ozone Secretariat) which than could have been used by the respective countries as basis for the preparation of their Legislation and regulations.
Angola | ANG/REF/39/TAS/04 | Subproject2 | Refrigeration Management Plan for the Republic of Angola, R&R sub-project | REF | TAS | Germany | 1) For countries like Angola, with CFCs used mainly in the informal sector, the ref/Ac sector should be more equipped with basic Recovery-units, instead of the more expensive Recovery & Recycling units. 2) Furthermore NOUs have to follow up strictly with recipients of R&R equipment in order to be able to report accurately on how much refrigerants have been either recovered, (recycled) and reused, or have been stored.
Antigua and Barbuda | ANT/REF/26/TAS/06 |  | Implementation of the RMP: national recovery and recycling | REF | TAS | Canada | 1) An accurate assessment of a country’s needs is of vital importance to ensure that the correct types of R&R equipment are provided. In this case, more equipment could have been provided to the mobile sector, for example. However, this need was not properly identified in the country programme or the RMP project proposal. 2) R&R training sessions should incorporate as many practical exercises as possible. 3) Higher import taxes or duties on CFCs required in order to promote retrofitting and R&R activities.
Antigua and Barbuda | ANT/REF/26/TRA/04 |  | Training Programme for Customs Officers | REF | TRA | Canada | 1) Preparation of a country handbook may require up to 6 months; 2) Consultant identified weakness in the use of the External Trade Act as a means of restricting imports of ODS and suggested that the Act which governs the protection of the Ozone Layer should be amended to include some of the mechanisms as outlined in the External Trade Act; 3) Use standard labeling on refrigerators and air conditioners to identify refrigerant use and contents; 4) Introduction of the ASYCUDA computerized system automatically has the capacity to flag imports of all refrigerants.
Antigua and Barbuda | ANT/REF/26/TRA/05 |  | Training Programme on Good Practices in Refrigeration | REF | TRA | Canada | 1) The project benefited from the long-term partnership with HRAI who was conducting a whole series of train-the-trainer workshops in the Caribbean region; 2) The participation of UNEP provided the opportunity to meet with relevant Ministers, General Secretaries or other stakeholders in order to explain the importance of ozone layer depletion, raise awareness and to gain commitment; 3) The event was well covered by the media; 4) The back-to-back organization of similar training events in neighboring countries proved to be time and cost efficient; 5) A section on how to construct your own R&R equipment was well received by the participants since the R&R programme will not provide sufficient equipment for all workshops and technicians; 6) For the practical hands-on training, sufficient adapters and extension cables should be available in the technical workshops, especially in countries operating with different standards, plugs, currencies in parallel such as the Caribbean. 7) The practical hands-on training in Antigua was held at the premises of a private company installing, servicing, repairing, assembling and selling refrigerators and ovens. This was a good venue for the training since it was free of charge and tools/equipment for demonstration was on hand, however, it requires some additional effort in the terms of logistics concerning transport of participants, training equipment and lunch.
Argentina | ARG/ARS/36/INV/128 |  | Conversion from CFC-11, CFC-12, CFC-113 and MCF into HCFC for technical aerosols at Electroquimica Delta | ARS | INV | IBRD | N/A
Argentina | ARG/ARS/38/INV/131 |  | Conversion from CFC-11, CFC-12, CFC-113 and MCF into HCFC for technical aerosols at Servex S.R.L. | ARS | INV | IBRD | N/A
Argentina | ARG/ARS/56/INV/159 |  | Phase-out of CFC consumption in the manufacture of aerosol MDIs | ARS | INV | IBRD | The HFA replacement formulation could be introduced with little difficulty despite the known sensitivities of the MDI sector where patients must adapt to changes to receive needed medicine because of adequate information campaigns that were conducted by all laboratories involved.
Argentina | ARG/FOA/13/INV/09 |  | Phasing out of CFC's at BANDEX S.A. | FOA | INV | UNIDO | (1) Counterpart company must have good technical background and economic resources to finance the project.(Must be highly motivated).(2) New extruder budget instead of modification of screw of existing extender.
Argentina | ARG/FOA/13/INV/10 |  | Phasing out of CFCs at CELPACK S.A. | FOA | INV | UNIDO | Counterpart company must have good technical background and economic resources. (Highly motivated) Projects with negative incremental cost reducing the budget are almost impossible to implement if the counterpart is not well motivated and aware of the importance of its economic contribution.
Argentina | ARG/FOA/14/INV/13 |  | Conversion to non-CFC technology in the manufacture of flexible and integral skin polyurethane foam at Prensiplast. | FOA | INV | UNDP | 1) UNDP/UNOPS will always try to assist enterprises in their efforts to go to full non-ODP technologies. However, realism and practicality are important considerations also. The conversion to HCFC-141b as an interim replacement could have been completed in two years. However the enterprise's insistence on trying for a water-based technology, despite the fact that the trails were successful, delayed project completion by three additional years. 2) The Prensiplast project shows that the problems of going to and attaining a final non-ODP solution may be significant and may not be resolved within the project scope (time frame and funds allocated). Both the Government and UNDP were penalized for the additional time taken by the enterprise in its unsuccessful efforts to go to a water-based solution. Perhaps a shorter time limit should have been set for such a conversion so that the project could have ended earlier. 3) The enterprise is, however, commended in its efforts and determination to go towards a full non-ODP solution. This project also demonstrates the extent to which UNDP/UNOPS assists enterprises determined to do so.
Argentina | ARG/FOA/15/INV/14 |  | CINTER S.R.L. -Elimination of the use of CFC's in the Manufacture of Sandwich Polyurethane Panels. | FOA | INV | UNDP | Even exceedingly difficult projects can be successfully implemented given sufficient time, patience, persuasion, creativity and willingness by the stakeholders to compromise. This was a difficult implementation, hampered by many problems, but by working closely with the enterprise, educating them on technology through study tours and expert visits, a successful completion was finally accomplished. This project helped to point out the challenges posed by new business introduction, and the need for flexibility to accommodate evolving business products while still maintaining the integrity of the ODS phaseout commitments under the project.
Argentina | ARG/FOA/18/INV/26 |  | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Belmo Buenos Aires and Belmo San Luis. | FOA | INV | UNDP | 1) In slabstock foam operations, converting to LCD, the technical support during the phase-in period is critical and should be factored into the budget. 2) The project duration should be estimated realistically after the re-evaluation of the conversion process. 3) The change of the original technology caused significant delays. 4) The conversion to a rather newly developed, licensed technology caused further delays due to formal/legal implications (establishing of license agreement). 5) The implementation duration is strongly dependent on the cooperation/reliable delivery scheduling by the equipment supplier as well as the subcontracted suppliers of auxiliary items. 6) The recipient company has shown very strong commitment to the project objective and cooperation during the implementation and invested considerably from its own funds to achieve the technology change to LCD.
Argentina | ARG/FOA/18/INV/28 |  | Mentvil SA - Conversion to non-CFC technology in the manufacture of flexible foams (slabstock). | FOA | INV | UNDP | 1) The conversion of production facilities to enable usage of low-index technology and additives systems (in place of the earlier CFC-11 based systems) as a technology for manufacture of flexible slabstock polyurethane foam, established the feasibility and commercial viability of this technology in this application in Argentina. 2) The technology employed is expensive in terms of recurring costs due to increased densities, but an effective way to reach a zero-ODP solution for such applications with negligible investments. 3) Close co-operation from chemical suppliers is an essential component for success of such a technology. 4) The technical competence of the enterprise was essential in the succesful move to this new technology
Argentina | ARG/FOA/18/INV/29 |  | LIMANSKY: Conversion to non-CFC technology in the manufacture of flexible foam (slabstock). | FOA | INV | UNDP | 1) This project had a duration of 12 months. This was completely unrealistic given the normal duration needed of at least 30 months for investment project completion. This 12-month period was extended by UNDP in future projects. 2) The change of the original technology caused significant delays since the ExCom had to agree to it. This has subsequently been handled by the ExCom deciding that projects should be implemented as approved. 3) The conversion to a rather newly developed, licensed technology will cause further delays due to formal/legal implications. 4) The implementation duration is strongly dependant on the cooperation/reliable delivery scheduling of the equipment supplier.
Argentina | ARG/FOA/18/INV/30 |  | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Piero SAIC (UNDP project No. ARG/95/G66) and Nuvel Corp. S.A. | FOA | INV | UNDP | Conversion of slabstock foam manufacturing to LCD systems is a complex process requiring a great deal of dedication of the enterprises, as well as a significant amount of planning during the execution of the conversion. A two-year timeframe is very challenging unless a significant amount of planning has been done during the project planning stage. While this zero-ODP technology is preferable from a techncial standpoint, the expense and effort involved in the conversion is significantly greater than conversion to methylene chloride. Enterprises need to be very aware of the commitment required before committing to this phaseout technology, and be prepared to accept a substantial “learning curve”. But LCD is cost effective (CO2 is low priced and less is needed) and environmentally acceptable (CO2 is obtained from natural sources, no ODP and low GWP.)
Argentina | ARG/FOA/18/INV/31 |  | Sueno Estelar S.A.and Estelar San Luis S.A.: Conversion to non-CFC technology in the manufacture of flexible foam (slabstock). | FOA | INV | UNDP | 1) This project had a duration of 12 months. This was completely unrealistic given the normal duration needed of at least 30 months for investment project completion. This 12-month period was extended by UNDP in future projects. 2) The change of the original technology caused significant delays since the ExCom had to agree to it. This has subsequently been handled by the ExCom deciding that projects should be implemented as approved. 3) The conversion to a rather newly developed, licensed technology will cause further delays due to formal/legal implications. 4) The implementation duration is strongly dependant on the cooperation/reliable delivery scheduling of the equipment supplier. 5) Any additional equipment which is partly paid for by the recipient company needs to be declared to avoid custom clearance complications.
Argentina | ARG/FOA/20/INV/47 |  | Phasing out CFC-12 at Mallol Saic. (MP/ARG/96/176) | FOA | INV | UNIDO | UNIDO was ready to cancel this project several times, during the implementation many problems were found. The perseverance and interest from UNIDO and counterpart to solve the difficulties and to finish the implementation is remarkable. This kind of projects with many unexpected situations is a good source of lessons.
Argentina | ARG/FOA/20/INV/48 |  | Conversion to non-CFC technology in the manufacture of flexible foam (slabstocks) at Suavestar S.A. (UNDP project No. ARG/96/G62) | FOA | INV | UNDP | Conversion of slabstock foam manufacturing to LCD systems is a complex process requiring a great deal of dedication of the enterprises, as well as a significant amount of planning during the execution of the conversion. A two-year timeframe is very challenging unless a significant amount of planning has been done during the project planning stage. While this zero-ODP technology is preferable from a technical standpoint, the expense and effort involved in the conversion is significantly greater than conversion to methylene chloride. Enterprises need to be very aware of the commitment required before committing to this phaseout technology, and be prepared to accept a substantial “learning curve”. But LCD is cost effective (CO2 is low priced and less is needed) and environmentally acceptable (CO2 is obtained from natural sources, no ODP and low GWP.)
Argentina | ARG/FOA/20/INV/49 |  | Phasing out of CFC-12 at Multiespuma Saic (MP/ARG/96/117) | FOA | INV | UNIDO | It is clearly proved that funds allocated by MFS are not enough to cover all the necessary investment of the project. This has created a very difficult situation because the counterpart, normally, is not in a position to make its contribution to the project, creating supplementary delays in implementation.
Argentina | ARG/FOA/22/INV/55 |  | Elimination of the use of CFC's in the manufacture of sandwicch polyurethane panels and spray foams at Rheem S.A.. | FOA | INV | UNDP | 1. The change to water blown technology requires the availability of suitable formulations in the local market. 2. The high level of technical sophistication of the recipient company and strong commitment and cooperation was critical in the success of its implementation. 3. The development of water blown formulations by chemical suppliers is not sufficient, thereby requiring the initial conversion to HCFC-141 b and the necessary follow-up monitoring by the Government in order to ensure the actual conversion to a zero-ODP technology at later stage.
Argentina | ARG/FOA/22/INV/56 |  | Conversion to non CFC technology in the manufacture of flexible foam (slabstocks) at FPV S.A. (UNDP No. ARG/97/G62) | FOA | INV | UNDP | When several companies owned by the same persons are granted projects for conversion, delays may occur because the management may not want to start implementation in all of the plants at the same time. From a managerial point of view, it may make more sense to implement the conversion in only one plant and decide on the implementation in the other plants only after being able to witness a successful conversion in the first plant. This choice must be allowed, even if it entails some delays.
Argentina | ARG/FOA/22/INV/57 |  | Elimination of the use of CFC's in the manufacture of sandwich panels and spray foams at Montisol Argentina S.A. and Art Nouveau Puntana, S.A. and Elimination of the use of CFCs in the manufacture of sandwich polyuretha… | FOA | INV | UNDP | During the delivery and installation of the equipment from CAN, there were difficulties incorporating the CAN equipment into the baseline Hennecke machine. Calofrig hired a local electronics engineer who was very helpful in identifying and solving the problems. The supplier should have foreseen the difficulties. As a result of the problems encountered, the quality of the retrofit was somewhat disappointing. The lesson learned through implementation of this project is that retrofit through a supplier other than the original equipment supplier is a delicate issue, and should be approached with much caution and careful planning.
Argentina | ARG/FOA/23/INV/61 |  | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Bonano. (UNDP Project No. ARG/97/G64) | FOA | INV | UNDP | Conversion of a panel manufacturing installation to pentane-based systems is a complex conversion requiring a great deal of dedication of the enterprise, as well as a significant amount of planning during the execution of the conversion. A two-year timeframe is challenging unless a significant amount of planning has been done during the project planning stage. While this zero-ODP technology is preferable from a technical standpoint, the expense and effort involved in the conversion is significantly greater than conversion to HCFC-141b. Enterprises need to be very aware of the commitment required before committing to this phaseout technology, and be prepared to continue the vigilant safety requirements and personnel training dictated by this technology.
Argentina | ARG/FOA/23/INV/63 |  | Conversion to non CFC technology in the manufacture of moulded foam at Cifor S.A. (UNDP project No. ARG/97/G65) | FOA | INV | UNDP | Cifor manufactures integral skin foam and flexible molded foam for automotive applications including door panels, steering wheels, armrests, headrest and front panels. These automotive specifications are very strict and require the customer to be informed on any chemical change. Extensive trials programs, involving chemical suppliers and clients were therefore necessary. Such extensive trial programs and customers approvals should be factored into the timeline and trial expenses when they are customer requiremetns.
Argentina | ARG/FOA/25/INV/76 |  | Conversion to low index additive technology in the manufacture of flexible boxfoam at Rozen S.R.L. | FOA | INV | UNDP | 1) The equipment supplier, OMS, did not make a visit to the installation site to participate in a work plan and specification meeting. During this meeting the exact specifications and responsibilities for local works and utilities are normally decided upon as well as a specified work plan for delivery, installation and start-up. 2) OMS informed UNOPS that they normally do not make pre-installation visits for checking the plant area. The decision that a pre-installation visit is required is part of the specifications on which the UNOPS purchase order is based. 3) UNOPS has to follow-up with the selected bidder, to confirm that a pre-installation visit has taken place.
Argentina | ARG/FOA/26/INV/78 |  | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Comenco (UNDP No. ARG/98/G62) | FOA | INV | UNDP | The higher than originally budgeted equipment costs are related to the fact that the actual baseline equipment was different from the baseline equipment in the project document. This required a revision of the equipment plan. Sprayfoam contractors, like Comenco, have their equipment normally out in the field, which makes the baseline equipment verification process more complicated. Despite the fact that the initial information is provided by the enterprise representatives, errors in the baseline situation are not uncommon in this type of application, and can significantly impact the project implementation. Due to this experience, extra emphasis has been put on the company representatives to provide accurate baseline information when they have equipment out in the field.
Argentina | ARG/FOA/27/INV/81 |  | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam in panels for thermal insulation at Arneg Raffo | FOA | INV | IBRD | The company is currently producing panels without CFC and the quality of its products has improved. Also, productivity has increased in the company.
Argentina | ARG/FOA/28/INV/110 |  | Phasing out CFC-11 by conversion to HCFC-141B as a blowing agent in the manufacture of P.U. blocks and tank spraying at Polwer S.R.L. (MP/ARG/99/107) | FOA | INV | UNIDO | If possible, is really important to provide equipment with local representation.
Argentina | ARG/FOA/29/INV/94 |  | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at OSIR (Organización de Servicios Integrales Rosario) (UNDP No. ARG/99/G63) | FOA | INV | UNDP | OSIR did a very good job. It is considered by UNOPS as one of the best executed projects from the side of the recipient. This project was finished ahead of schedule. Since then, the timeframe for HCFC-141b projects has been shortened based on the experience of projects such as this.
Argentina | ARG/FOA/29/INV/95 |  | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Obras de Ingenieria (UNDP No. ARG/99/G62) | FOA | INV | UNDP | Obras did an excellent job. It is considered by UNOPS as one of the best executed projects from the side of the recipient. This project was finished far ahead of schedule. The project demonstrates the efficiency that can be achieved in project execution if the recipient enterpirse is fully committed to the project from the start.
Argentina | ARG/FOA/29/INV/96 |  | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray and boxfoam) at Mendoza de Poliuretanos | FOA | INV | UNDP | 1) One of the general requirements for this project was that bidders offer manuals in Spanish. It took the selected equipment supplier OMS more than one year to translate the required manual into Spanish, despite several reminders by UNOPS. 2) Failure to comply with the specifications for Poliuretanos Mendoza on a timely basis makes it difficult for UNOPS to include OMS in upcoming bids for other projects in Latin America.
Argentina | ARG/FOA/29/INV/97 |  | Phasing out of CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid P.U. foams: umbrella project (Tarco, Mondino, Schaum, Fadep, Occhipinti and Friolatina) (MP/ARG/99/158) | FOA | INV | UNIDO | It is necessary more coordination with the counterparts to allow contractors the installation of the new equipment. Training of the counterpart’s staff was basic in the success implementation of the project.
Argentina | ARG/FOA/30/INV/106 |  | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at Fasax. | FOA | INV | UNDP | In projects, where a sub-contract is made with a recipient company to make the required retrofit, it may make more sense to make the contract directly with the entity doing the work, in order to ensure that the work is being paid as should be.
Argentina | ARG/FOA/31/INV/111 |  | Conversion from CFC-11 to LIA technology in the manufacture of flexible polyurethane boxfoam at four enterprises: Cosmos; La Cardeuse; Jovis; and Micropore | FOA | INV | UNDP | Two of the four participants, Cosmos and Micropore, in this group project went out of business. Substitution was pursued, but was not successful. Careful monitoring of the stabillty of particiapting enterprises is required, especially during challenging economic situations, and financial viability must be confirmed before beginning implementation and expending funds. Fortunately, in this case, no funds were expended before the enterprises went bankrupt; therefore there was no need for complicated attempts to reassign purchased equipment.
Argentina | ARG/FOA/32/INV/113 |  | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at 9 enterprises (Produmerc; Produnova; Carlos Masciotta; Elido Palermo; Carlos Castillo; Estanislao Kowcz; Constructora Vimac; Gaspar Adragna; Placido Sandova... | FOA | INV | UNDP | Complex group projects should reflect a longer timeframe than individual projects due to the logistics of completing all actions at all enterprises included in the project. Most actions at most companies may be completed in a timely manner, but delays at one enterprise can affect the timeliness of the entire project.
Argentina | ARG/FOA/32/INV/117 |  | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid polyurethane foams at 7 companies (Aislaciones y Servicios; Maximo Baducco; D and D Bolatti; Hi-Tec Poliuretanos; Alberto Najera; Jose Stefanelli and Vincer,... | FOA | INV | UNIDO | For the final projects, the consumption of CFC is mainly in small amounts therefore; the machines to be bought are small and if possible made in the region. The Brazilian equipment purchased for this project fulfills the requirements and is not expensive.
Argentina | ARG/FOA/34/INV/122 |  | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at 4 foam manufacturers (Artestamp, Pasissan, Forever, Termica) | FOA | INV | UNDP | Complex group projects should reflect a longer timeframe than individual projects due to the logistics of completing all actions at all enterprises included in the project. Most actions at most companies may be completed in a timely manner, but delays at one enterprise can affect the timeliness of the entire project.
Argentina | ARG/FOA/34/INV/123 |  | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid foam insulation panels at Frio Star | FOA | INV | UNDP | A cooperative recipient enterprise can enhance the project completion. This project was completed well ahead of schedule, while also solving a problem of equipment disposition from a cancelled project. The enterprise was very cooperative in helping to make the equipment from the Fruehauf project workable for their application. Their cooperation with the equipment supplier and its representatives represents the cooperative attitude necessary for a satisfactory outcome for all involved.
Argentina | ARG/FOA/38/INV/132 |  | Terminal umbrella project for phase-out of the use of CFC-11 in the manufacture of polyurethane foam | FOA | INV | UNDP | the staggered implementation worked very well. News about the success of the first phase motivated other enterprises to complete their information required to participate and in this way helped in the success of the project.
Argentina | ARG/FUM/23/DEM/71 |  | Demonsration Project alternatives to the use of MeBr in tomato, cut flowers and strawbwrry production. | FUM | DEM | UNIDO | The main reason to delays was the timing of the agricultural season which does not correspond with the date of approval
Argentina | ARG/FUM/26/DEM/79 |  | Demonstration and training in viable alternatives, information dissemination and development of a national plan for phasing out methyl bromide in the tobacco sector | FUM | DEM | UNDP | Demonstration trials identified 3 effective alternative soil treatments that could support the elimination of methyl bromide use for tobacco production in Argentina. Each is suited to specific regions and types of growers. They include: Floating tray systems. This alternative is suitable for most tobacco-producing locations in Argentina, as well as most types of growers. It is considered suitable for introduction in the provinces of Misiones, Tucumán, Catamarca, Corrientes and Salta. Non-floating tray systems. This alternative is also considered suitable for most types of growers in most tobacco-producing areas. Metam Sodium - This alternative has proven sufficiently effective in specific, limited areas where pest pressures are lower (e.g. than in comparison with pest pressures in the regions listed above). It is considered suitable for use by certain growers in the province of Jujuy. The demonstration project has shown that these technologies present a viable alternative to the use of methyl bromide in tobacco production in Argentina. The development of ODP substances´ policy is in hands of environment authorities in Argentina, while MB restrictions depend of Ministry of Agriculture decisions. This caused some issues during the project’s initial stages as MB importers lobbied authorities in the Ministry of Agriculture against elimination of MB in the sector. It was therefore, agreed that all future action in this sector would include full participation on the part of the Ministry of Agriculture in order to ensure it’s full political commitment to MB elimination.
Argentina | ARG/FUM/29/DEM/93 |  | Demonstration project for testing methyl bromide alternatives in post-harvest disinfestation for cotton and citrus (phase I) | FUM | DEM | IBRD | In these types of projects (testing of new treatment and technologies to replace some substances with other alternative methods in treatment of seasonal products) that are developed in specialized laboratories according to universally standardized working rules and protocols, there is need for more flexible implementation timeframes and no restrictions on the alternative methods to be used.
Argentina | ARG/FUM/30/INV/105 |  | Phase-out of methyl bromide in strawberry, protected vegetables and cut flower production | FUM | INV | UNIDO | 1) During the course of the project, there have been some difficulties in implementing the alternatives originally proposed. There were found problems with the efficiency of Metam sodium and the implementation of the practice of steaming. 2) Another chemical substitute considered was methyl iodide, also called iodomethane. This product was evaluated during the implementation of the project and has proven to be as effective as Methyl bromide. Unfortunately the manufacturer of Methyl iodide decided not to register the product in the country. 3) Organized farmers’ unions and association are important as they can assist not only in disseminating information among others in the region but also in pooling resoureces for the purchase of machinery and other imputs, reducing economic barriers, and improving accessibility to technology. 4) Farmers’ associations has been key for promoting adoption in Argentina.
Argentina | ARG/HAL/13/TAS/07 |  | Technical assistance to prepare a national halon programme | HAL | TAS | UNDP | For this type of activity which involves both data surveys and development of a sectoral phaseout plan, it is difficult to specify a time frame. According to local circumstances, activities usually take several years since they feed into Governmental policy decision-making process.
Argentina | ARG/HAL/26/TAS/80 |  | National halon management programme to help eliminate the use of halon-1301 in new applications and to manage recovered halon-1301 | HAL | TAS | IBRD | (1) From the beginning, the implementation process for the establishment of the Halon Bank encountered difficulties due to lack of experience regarding halon management options at the national level, including which would be the most appropriate laboratory equipment to procure and which mechanism would be the most expedient with which to achieve the sought after results. The assistance provided by an international expert hired by the World Bank (October 2000) helped to better define the components and build consensus in the sector. (2) In January 2004, the Halon Bank started to work through an Operator recognized by INTI. INTI played the role of the Halon Bank administrator agent and also managed and assessed its performance. The Halon Bank works in Argentina as a virtual bank, controlled by INTI, which is informed of each operation made in the market by the Operators and/or a Critical User, or for essential uses. Given that the market turned out to be smaller than initially expected, 3 firms out of the five initially identified as interested eventually registered as a Halon Bank Operator. (3) The Halon Bank was implemented at a lower cost than budgeted as it was determined that it was not necessary to purchase all the laboratory equipment initially calculated at design (i.e. analysis instruments) or furnish as many facilities with technical equipment (i.e. deposit tanks).
Argentina | ARG/REF/15/INV/15 |  | Conversion of the production of CFC-12 heat exchangers for MAC to HFC-134a refrigerant at Interclima, S.A. | REF | INV | IBRD | It is important to note that the MAC sector is directly linked to the automobile market. Whenever the car models that use CFC equipment are still produced in the country, the MAC projects will present delays as to the full completion of the project. The MAC manufacturing companies will always try to attend demand – and that includes CFC-12 units.
Argentina | ARG/REF/15/INV/16 |  | Conversion to non-CFC technology in the production of condensers for mobile air conditioning at Simon Cachan, S.A. | REF | INV | IBRD | The company is currently producing MAC units without CFC and the quality of its products has improved. Nonetheless, the company has had to respond to the adverse economic conditions in Argentina by posting lower production figures than originally expected.
Argentina | ARG/REF/15/INV/17 |  | Conversion of the production of CFC-12 hoses for MAC to HFC-134a refrigerant at Mirgor, S.A. | REF | INV | IBRD | The main lesson learned is that this project was dependent on the market demand for R-134a MAC units, and thus its completion did not occur until all automobile manufacturers ceased to design model with CFC-12 MAC units.
Argentina | ARG/REF/15/INV/19 |  | Helametal S.A. & Helemetal Catamarca. Conversion of a domestic refrigeration plant. replacement of CFC-11 used as blowing agent with cyclopentane and CFC-12 used as refrigerant with HFC-134a | REF | INV | IBRD | The company is currently producing refrigeration units without CFC and the quality of its products has improved. Nonetheless, due to economic and political conditions in the country, the company has posted lower production figures than originally expected.
Argentina | ARG/REF/15/INV/21 |  | Elimination of CFC in the domestic refrigerator manufacturing plant of McLean | REF | INV | IBRD | This project was executed without major problems. The company started production of refrigeration units in August 2000 using C-5 as the foaming agent and R-134 as the refrigerant.
Argentina | ARG/REF/16/DEM/22 |  | MAC servicing demonstration | REF | DEM | USA | Recovery/recycling equipment not only conserved refrigerant during preventive maintenance's well as during repair procedures but also saved considerable labor for some operation.
Argentina | ARG/REF/17/TAS/24 |  | Provision of training in leak reduction, emission control and recycling and management of non-CFC refrigerants in domestic and commercial refrigeration and air conditioning | REF | TAS | Australia | (1) A full report on the project - Phase 1: Assessment Teams Report Following Visit to Buenos Aires and Rosario November 3 to 19, 1995 - found that: "no useful purpose would be served by trying to set up a system for reclaim, recycling and/or destruction of ozone depleting refrigerants as exists in Australia because the infrastructure to support such a scheme does not exist". Three fields of activity were recommended for Argentina: training, pilot projects for recovery and recycling and awareness and information transfer. The Phase 1 report suggested that training schemes should "include reclaim and loss prevention technology as an integral part, because such a scheme would yield far greater economies in ODS consumption than would a formal reclaim scheme such as operates in Australia". (2) A much shorter document - Evaluation of the Technical Mission for the Phase 1 of the Project - reported that (sic) "some problems related with simultaneous translation needed for the workshops were solved by the local OPROZ in Buenos Aires and the cooperation of INTI in Rosario". It further suggested that future missions to Argentina should make funding provisions for translation services to INTI or OPROZ. Shorter missions were also preferred due to difficulties with INTI assigning a full-time coordinator to the mission. The Phase 1 report described how two different translation methods were used at each workshop, and found that "the larger the audience and the more general the topic, the better to use simultaneous translation, whilst the more technical the topic and the smaller the audience, sentence-by-sentence translation would seem to be more appropriate".
Argentina | ARG/REF/18/INV/37 |  | AUTOSAL, S.A. -- Elimination of CFCs in domestic refrigerator production plant. | REF | INV | IBRD | 1) The company is currently producing refrigeration units without CFC and the quality of its products has improved. Nonetheless, due to the economic and political situation in the country, the company has had to respond to the conditions by having lower production figures than originally expected. 2) Technology change has provided the company with new elements which will increase its productivity and will provide better competitive conditions to the open market the country is facing through Mercosur (regional trade agreement).
Argentina | ARG/REF/18/INV/38 |  | Elimination of CFC in the domestic refrigerator manufacturing plant of BRIKET, S.A. | REF | INV | IBRD | This project was executed without major problems. The company started production of refrigeration units in August 2001 using C-5 as the foaming agent and R-134 as the refrigerant.
Argentina | ARG/REF/18/INV/39 |  | Elimination of CFC in the manufacturing plant of domestic refrigerators of Neba, S.A. | REF | INV | IBRD | (1) Technical and administrative issues can be difficult to resolve when a company is also facing legal and financial issues. (2) Continued monitoring and reporting on the status of project implementation puts some pressure on all stakeholders to look for solutions to unblock implementation challenges.
Argentina | ARG/REF/18/INV/40 |  | Conversion to non-CFC technology in the production of mobile air conditioning systems at Sistemaire S.A. | REF | INV | IBRD | This project was completed successfully without any major problems. It is important to note that the company decided to invest a larger amount of counterpart funding in order to improve MAC production to very strict standards. All upgrades were financed by the company and the reduced MLF grant was used for eligible investments.
Argentina | ARG/REF/19/INV/44 |  | Elimination of CFCs in the manufacturing of domestic refrigerators of FRIMETAL, in Rosario, Argentina | REF | INV | IBRD | The company is currently producing refrigeration units without CFC and the quality of the products has improved; however, due to the economic and political situation in the country, the company has had to respond to the conditions by posting delays on its production delivery times.
Argentina | ARG/REF/19/INV/45 |  | Elimination of the use of CFCs in the manufacture of display cabinet and walk-in freezers at Disthel | REF | INV | UNDP | 1) Due to budget constraints, the project could not only finance the foam equipment. Therefore, the recipient company was expected and advised to invest the necessary funds for the refrigeration conversion. It has done so, without delaying the conversion of its refrigeration operation. 2) The recipient company has cooperated in a very pro-active and conscientious manner, investing own funds (see above) and also using the project for its own PR activities, creating environmental awareness and advertising such in its brochures and publications. The recipient company was commended for its cooperation and commitment to the CFC phaseout objective and may be highlighted for such in future reports if deemed useful.
Argentina | ARG/REF/19/TRA/46 |  | Technical assistance and training on safe designs of hydrocarbon based domestic and commercial refrigeration appliances | REF | TRA | Switzerland | 1) The NOU has gained a valuable experience to conduct communication with the different stakeholders, in order to ensure commitment and involvement. 2) The use of hydrocarbons as refrigerants will be incorporated in the normal curriculum of the Training Institution. 3) Training some mechanics of refrigeration companies, specially domestic refrigeration in ozone awareness. 4) The future activities will have to take special care in the provision of equipment and the necessary training and awareness. 5) Know-how and technology transfer from Europe and a similar Swiss-German sponsored project implemented in India proved successful as the learning process on hydrocarbon safety had later supported by equipment manufacturers and suppliers of compressors.
Argentina | ARG/REF/21/TRA/51 |  | National train the trainer programme on good practices in refrigeration | REF | TRA | UNEP | None.
Argentina | ARG/REF/22/INV/58 |  | Phasing out of CFCs in the manufacturing plant of Radio Victoria Catamarca S.A. (RVC). | REF | INV | UNIDO | Even if the companies looks very interedted by the project at the preparatory phase stage, an in deep commitement has to obtained from them. In this particular case the company was technically competent, however the share holders decided due to market considerations to close the factory and requested project cancellation without any other alternative.
Argentina | ARG/REF/23/INV/60 |  | Elimination of the use of CFCs in the manufacture of commercial refrigerators and display cabinets at Trevi (UNDP No. ARG/97/G69) | REF | INV | UNDP | Enterprises may choose to use a dispenser with lesser performance properties in the end product if the grant is severely limited. This is a choice that is acceptable, provided the enterprise understands the limitations of the equipment as compared to the recommended/approved selection. This choice is one that must be made on a case-by-case basis and is only to be made by the recipient enterprise when informed of all the facts.
Argentina | ARG/REF/23/INV/64 |  | Elimination of CFCs in the manufacturing plant of domestic refrigerators of FRARE S.A. (MP/ARG/97/185) | REF | INV | UNIDO | Frare owns a big experience in dealing with the production of refrigerators. This fact has been positively reflected in the implementation of the project. Excellent cooperation between counterpart and supplier PERROS INDUSTRIALE was basic to accomplish with success the project.
Argentina | ARG/REF/23/INV/66 |  | Elimination of the use of CFCs in the manufacture of display cabinets and polyurethane panels for cold stores and walk-in coolers at Eurofrio. | REF | INV | UNDP | Conversion of a panel manufacturing installation to pentane-based systems is a complex process requiring a great deal of dedication of the enterprises, as well as a significant amount of planning during the execution of the conversion. A two-year timeframe for this, and similar projects in Argentina, is challenging unless a significant amount of planning has been done during the project planning stage. While this zero-ODP technology is preferable from a technical standpoint, the expense and effort involved in the conversion is significantly greater than conversion to HCFC-141b as an interim step with a small residual ODP of 0.11. Enterprises need to be very aware of the commitment required before implementing this phaseout technology, and be prepared to continue the vigilant safety requirements and personnel training dictated by this technology.
Argentina | ARG/REF/23/INV/67 |  | Elimination of CFCs in the manufacturing plant of domestic refrigerators of BAMBI S.A. Santa Fe (MP/ARG/97/184) | REF | INV | UNIDO | Bambi owns considerable experience in dealing with the production of refrigerators. This fact has been positively reflected in the implementation of the project, and in the relationship with the contractor (PERROS Industriale).
Argentina | ARG/REF/23/INV/68 |  | Elimination of CFCs in 1 manufacturing plant of domestic refrigerators of enterprise Whirlpool Argentina S.A. | REF | INV | IBRD | 1) This project was executed without any major problems. The company is currently producing refrigeration units without CFC and the quality of its products has improved. Nonetheless, the company has had to respond to the adverse economic conditions in Argentina by posting lower production figures than originally expected. 2) An important consideration is related to the use of isobutane technology. The Project Document states that Whirlpool would adopt R-134a technology in the short run and that the company would later use its own resources to switch to isobutane. However, the lack of service centers and the overall inexperience with isobutane technology in Argentina has persuaded the company to postpone this change. At present, the company is using R-134a as a refrigerant and it has not been determined when the new isobutane-based technology will be adopted.
Argentina | ARG/REF/25/INV/77 |  | Substituting CFCs by HCFC-141b and HFC-134a in manufacturing of domestic and commercial refrigerators at El Dorado, S.A. | REF | INV | IBRD | - The grant agreement and the legal documents should be prepared in time in order to avoid any delays in the implementation of the subprojects. - The project was implemented successfully. No major problems were experienced and the company is satisfied with the new foam application and from using R-134a as a substitute refrigerant.
Argentina | ARG/REF/28/INV/92 |  | Phaseout of CFC-11 by conversion to HCFC-141b technology and of CFC-12 by conversion to HFC-134a in the manufacture of commercial refrigeration display cabinets and polyurethane panels for cold stores at Perito Moreno Ref. | REF | INV | UNDP | 1) The OMS technician needed 5 extra days for the installation of the dispensing equipment, because of equipment relocation desired by Perito Moreno. OMS charged the amount of US $3,000 to the recipient company. UNOPS reimbursed Perito Moreno for this charge, but Perito Moreno never paid OMS. 2) Follow-up by UNOPS was required to solve this problem. In the future, for issues related to payments due to suppliers from UNOPS, it may be more efficient to arrange direct payments rather than rely on the recipient enterprise to transfer the payment.
Argentina | ARG/REF/32/INV/116 |  | Replacement of CFC-11 by HCFC-141b in the manufacture of rigid polyurethane foam for domestic refrigerators and sandwich panels at MTH S.R.L. | REF | INV | IBRD | The company has improved the quality of its products using the new technology and the equipment provided by the project.
Argentina | ARG/REF/32/TRA/114 |  | Training of customs officers | REF | TRA | UNEP | 1) The practical sessions and group discussions were very appreciated, since participants had the chance to discuss issues regarding the implementation of the licensing system and effective prevention of ODS smuggling . Many of the workshop recommendations derived from these discussions. 2) A cooperative setting between institutions is critical for improved performance of the licensing system. Consequently, the workshop served as a platform to strengthen such supportive atmosphere. Indeed, the synergy created between the Customs Office (AFIP) and the National Ozone Unit (OPROZ) has allowed both parties to achieve greater results in carrying out their responsibilities. 3) The local executing agency (AFIP) had already developed a specific training structure with staff trained in the subject matter through the trainers course, held in India. However, it had little experience in managing international activities with external funding. Nevertheless, its commitment was evident from the onset, since the local team pushed several proposals to improve the overall design of the programme and carried out an efficient fund administration.
Argentina | ARG/REF/32/TRA/115 |  | Training programme for the refrigeration servicing sector (Phase III). | REF | TRA | UNEP | 1) During the summer and end-of-year seasons, the goals on training and certification are considerably affected by the availiability of technicians, which is the time of the year of highest demand for the refrigeration and air-conditioning servicing sectors. 2) It is highly recommendable that courses are outlined and structured for a short implementation period (two days maximum), since, the training itself is considered a trade off for most technicians, particularly during high demand seasons. 3) The consolidation of a specialized training network is an effort that inevitably takes time, particularly in a somewhat dispersed industry, such as the refrigeration and air conditioning sectors. Moreover, since no efforts had been carried out previously on this realm, the project implied to start from scratch the creation of such network, by incorporating relevant stakeholders in place and foster a friendly atmosphere for the project’s execution. In addition, it is important to take into account the size of the country which imposes considerable challenges when trying to replicate this effort in all provinces, in an attempt to cover the entire sector. 4) Having the agreements signed directly with the local executing agency allowed for a descentralization in the fund-transfer process, keeping the provision of funds expedite and safe from potential delays and interruptions derived from the involvement of 3rd parties. As such, this understanding was approved by the ruling authority in the country and it certainly eased project implementation.
Argentina | ARG/SEV/04/CPG/01 |  | Technical assistance for country programme preparation | SEV | CPG | UNDP | 1) In the early years of the MLF, getting agency legal and financial modalities established took quite some time. UNDP needed 6-9 months to do so, the World Bank needed 2-3 years. As a result joint UNDP/World bank activities suffered until such time as the World Bank could complete its legal agreements. 2) The Government decided to do the ODS survey on its own without outside assistance. This actually slowed down the process since the national experts could not rely on international experts for technical help. Had UNDP been allowed to provide the technical assistance in 1992/1993, the whole CP preparation process in Argentina would have been speeded up.
Argentina | ARG/SEV/30/TAS/104 |  | Policy assistance for the design and implementation of an ODS import/export licensing system | SEV | TAS | UNEP | 1) The National Ozone Unit (OPROZ) played an essential role in coordinating activities with other institutions such as the ministries of foreign affairs, industry, economics and trade. In addition, the links established with the private sector should be praised, since these facilitated the negotiation of the licensing system through dialogue with relevant stakeholders and certainly contributed to its institutional strength. 2) Monitoring the progress of local legislation processes requires the insight of a national player. As such, OPROZ did a remarkable follow up of the ODS legislation proposal and certainly helped UNEP to understand its singularities, when comparing to other legal systems in the region. Hence the joint approach between UNEP and local authorities is highly recommendable.
Argentina | ARG/SEV/45/TAS/144 |  | Assistance to carry out an HCFC survey | SEV | TAS | UNDP | (A) A summary of the findings from the survey - from the time the report was prepared - is provided below: (1) The use of HCFCs in Argentina can be divided into: (a) Primary Use: (i) Application - Manufacturing; Sector(s) - Aerosols, RAC, Foams; Amount (t) - 1,281. (ii) Application - Extinguishers/Cleaning/Aids/Solvent; Sector(s) - Cross Sectors; Amount (t) - 143. (b) Secondary Use: (i) Application - RAC Servicing; Sector(s) - RAC; Amount (t) - 2,155. (c ) Total - 3,579. (B) HCFCs are used in historical applications as well—in dramatically increased amounts—for CFC replacement. Because of the size of individual users and the limitations of technologies, it has not been possible to replace in all cases CFCs by non-ODS substances—even when financed by the MLF. (C) Considering the real 2005 volume of each HCFC, and using the growth for the different periods, the estimated 2015 consumption in metric tons is as follows: (1) 2005 actual: HCFC-22 - 3,004; HCFC-141b - 460; HCFC-123 - 34; HCFC-142b - 58; HCFC-124 - 23; Total - 3,579. (2) 2015 forecast: HCFC-22 - 6,400; HCFC-141b - 1,030; HCFC-123 - 60; HCFC-142b - 330; HCFC-124 - 130; Total - 7,950. (D) Pricing constitutes a major issue in favor of the use of HCFCs. In the case of HCFC-141b, investment costs are also an impediment, specifically in cases where replacement by hydrocarbons is considered. (E) The high operating costs of non-ODP technologies based on HFCs are another factor. There are currently no supply problems with HCFCs nor are any expected in the period through 2015. Prices have come down for virtually all HCFCs in the last ten years and are currently relatively stable. (F) Current alternatives are by enlarge the same as those for ODS-free CFC replacement. Exceptions are recently developed liquid HFCs for foams and HFC binary and ternary blends for refrigeration. (G) While the use of HCFCs in the servicing sector can be reduced through “best practices” approaches that are essentially the same as the currently used ones for servicing with CFCs, complete phaseout of its use can only be achieved through prior phaseout of the use in primary applications. (H) Argentina offers to prepare a HCFC management strategy before December 2007. The strategy could be used as a “pilot” one, e.g. as a base to develop formal, financial and technical criteria against which future HCFC phaseout projects could be approved. (I) An important part of the strategy will be the sequencing of projects with priorities for projects that offer sustainability by offering low operating costs—or even operating benefits. (J) The initial phase of a strategy (2008-2012) would be to “bend the trend”. Priority projects for this phase would be those who offer low operating costs—or even benefits. “Best Practices” and foam/refrigeration manufacturing projects—if based on HCs—would qualify as such. In addition, any pilot projects required to validate new technical approaches would be formulated and implemented. In this period, the upwards trend should be bend towards a flat one. (K) The second phase (2012-2015) would be to “keep the trend”. Follow-up projects on validated novel technical approaches as well as projects that are based on technologies that have become more cost-effective because of changed cost patterns. At the same time, regulatory measures to assure compliance with the freeze would be formulated. (L) The third and last phase (2016 – 2040) would be to “end the trend”. It would be based on enforcing the freeze while working towards complete phaseout of HCFCs. A regulatory umbrella will allow less emphasis on containment of operating costs. Co-financing will be emphasized. (M) The word will be to participate now or face enforcement later.
Argentina | ARG/SOL/28/INV/91 |  | Conversion from MCF used as solvent to aqua based cleaning at Argelite La Rioja, SA; CIMCAM, SA; Grimoldi, SA; Heliodino SAIC; Integral Metalurgica, SA; Orbis Mertig SAIC; Trosh, SA Unisol, SA and Buffalo, S.A. (umbrella) | SOL | INV | IBRD | N/A
Argentina | ARG/SOL/41/INV/137 |  | Plan for phase-out of ODS in the solvent sector | SOL | INV | UNIDO | N/A
Argentina | ARG/STE/27/INV/82 |  | Elimination of CFC in Sterilization via ETO at AISTHOS S.R.L. | STE | INV | IBRD | According to the company, incremental operating savings of $105,416.00 have been over-estimated, and operating costs are expected to be higher in the future due to changes in production factors (changes in prices of raw materials) and possible consumption constraints of the sterilization market in Argentina. Besides, due to the cut in the ICC, the company had to finance capital costs with an extra $241,365.00 from its own funds to complete the project. For future projects in which savings in IOC are feasible but difficult to predict, the MLF could better help the company by avoiding as much as possible cuts in capital costs.
Armenia | ARM/PHA/73/TAS/13 |  | Verification report for stage I of HCFC phase-out management plan | PHA | TAS | UNDP | This is a standard verification project and previously developed and utilized TORs were helpful in accelerating the preparedness to start the selection of verifiers. From the actual approval by the Executive Committee to the submission time of the formulated verification report, it took one calendar year including waiting time to receive funds by the IA, signature of the project document (legal arrangements) with the country, selection of independent reviewers/assessors and delivery and submission of the report to the MLF Secretariat.
Armenia | ARM/PHA/84/TAS/23 |  | Verification report on the implementation of the HCFC phase-out management plan | PHA | TAS | UNDP | 1) The MLF guidelines are useful in drafting the terms of reference for contracting persons or companies to undertake the verification. 2) Verification process involving all relevant stakeholders, e.g., customs, users of controlled substances, etc., allows to identify bottlenecks in data collection and can yield useful recommendations for improvements in the operation of the HCFC import licensing systems.
Armenia | ARM/SEV/74/TAS/16 |  | Survey of ODS alternatives at the national level | SEV | TAS | UNEP | 1) The collected data is limited in some extent due to aggregated record-keeping at the Custom Service of the Republic of Armenia — all amounts of imported ODS substitutes are aggregated under the few tariff headings (according to the customs codes of the Eurasian Economic Union), and an incomplete recordkeeping among importers and distributors during the requested time-series since no legally binding obligations are imposed by the legislation. Also, the response rates among companies involved in servicing the industrial and commercial refrigeration, respectively the mobile air conditioning and transport refrigeration equipment in place was very low. As result, we have faced certain data gaps that limit the predictive value of the compiled data. 2) In order to improve the situation with the record-keeping among some companies, it is recommended to set up an information system that could collect and forward the data from importers to the NOU automatically, once the importer clears the imports at the Custom Service. 3) To improve record-keeping, it is recommended that a chain-of-custody type scheme be implemented from importers to end users, with the condition that all technicians must be trained and obligatory certificated. This would be possible only after the training centers are established and become fully functioning. 4) With increasing focus on climate change low GWP refrigerants should be the preferred choice whenever possible; however, this will require extensive education of the industry and adaptation (harmonization) of national legislation. 5) The National Refrigeration Association is an important partner and acts as an advisory board to the Government, public bodies and other organizations in the Republic of Armenia, with the intention to promote the best interests of the refrigeration and air-conditioning sector. The Association serves also as the benchmark for technical expertise in the servicing sector and their work should be supported. 6) For ensuring the success of activity of monitoring and implementation of ODS alternatives in the country, it would be necessary to strengthen further the NOU efforts undertaken so far through capacity building.
Region: ASP | ASP/ARS/16/TRA/16 |  | Regional workshop on aerosol conversion for the SEAP region | ARS | TRA | UNEP | None.
Region: ASP | ASP/FOA/06/TRA/05 |  | Low-CFC foam training and demonstration programme in Asia | FOA | TRA | UNDP | Workshop participants congratulated UNDP on the clarity of presentation at the workshop. It resulted in a surge of requests for UNDP assistance in the foam sector in Asia, making the foam sector UNDP's largest sectoral activity. Having both government and industry representatives participate helped start the interaction between the two groups which facilitated the ODS phaseout process.
Region: ASP | ASP/FUM/17/TAS/19 |  | Methyl bromide data collection for Asia and the Pacific | FUM | TAS | UNDP | 1. In spite of the fact that due to local circumstances depending from each country, it is difficult to determine a time frame for data survey, the individual surveys were all completed within the original timeframe. 2. Doing the data surveys as a pre-requisite to the workshops run by UNEP was essential to enable the participating countries to discuss how they should proceed with the phase-out of methyl bromide and seek guidance from international experts on the available options and their costs. 3. UNDP ensured that each country had a national data team for the data collection and preliminary analysis of the collected data. All participating Governments expressed their appreciation to UNDP for it's efforts in developing a data survey and provided countries the opportunity to take a more active role in the formulation of policies to facilitate the development of future MeBr alternative demonstration and investment projects.
Region: ASP | ASP/FUM/17/TRA/18 |  | Regional workshop on methyl bromide for Asia and the Pacific | FUM | TRA | UNEP | None.
Region: ASP | ASP/FUM/34/TRA/43 |  | Regional Workshop on the Experiences of Use of Methyl Bromide Alternatives Evaluated Under the Multilateral Fund | FUM | TRA | UNEP | A) Lessons learned from "Regional Workshop on the Experiences of Use of Methyl Bromide Alternatives Evaluated under the Multilateral Fund": 1) Since the constant use of phosphine can result in insects becoming more resistant towards it and to see that the Phosphine-users do not revert back to using Methyle Bromide, more training on good fumigation practices and coordination between government regulatory agencies and fumigators is highly recommended. 2) The workshop recognises that phosphine is the most important alternative to methyl bromide in durable commodities and its broad use needs to be promoted through policy, legislation and education in countries in the region. 3) A study also needs to be undertaken to survey the extent of phosphine resistance on insects. 4) Training and awareness raising are essential components to the successful and sustained use of phosphine as an alternative fumigant. Phase out projects in countries need to include such components to support investment projects to support the "Phase in" of phosphine. B) Lesson Learned from "Regional workshop for Asia and the Pacific: Constraints and Solutions on the use of Phosphine as an Alternative for Durable Commodities": The sharing of experiences and lessons learnt by participants from various countries were found to be extremely useful in enhancing awareness of alternatives for methyle bromide. This approach has been found to be effective and can be replicated in other areas as well.
Region: ASP | ASP/HAL/08/TRA/07 |  | South-east Asia halon-1211 training workshop in Japan | HAL | TRA | USA | See attached halon report.
Region: ASP | ASP/HAL/30/TAS/36 |  | Halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen (jointly implemented with France) | HAL | TAS | Germany | 1) The regional steering committee made up of the Ozone officers agreed that only one recovery and recycling center should be purchased to be transported from one country to another, after it stayed in each country for a reasonable amount of time to effectively undertake recycling activities. 2) It was crucial to create a partnership between the Ozone Offices and the Fire Ffighting from the respective countries. A code of conduct was introduced to be voluntarily respected by the industry which would render the implementation of halon bank activities successful and sustainable. 3) The awareness seminars and campaigns that were implemented in the West Asia Countries paved the way for the introduction of recycling equipment. The armed forces in the countries were always invited to attend the seminars. This made them aware of the challenges of halon shortages they will be facing in the near future and take the necessary actions. 4) In some cases the operators apponted to undergo the training on the R&R equipment, did not have the necessary qualifications and background to benefit from the course. This necessitated additional training time. 5) The regional approach requires that the four participating countries take the full ownership and responsibility for sharing the mobile halon reclamation center. Finally, this approach was not viable as the ozone officers did not reach agreement on sharing the equipment.
Region: ASP | ASP/HAL/30/TAS/37 |  | Halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen (jointly implemented with France) | HAL | TAS | France | (1) The regional steering committee made up of the Ozone officers agreed that only one recovery and recycling center should be purchased to be transported from one country to another, after it stayed in each country for a reasonable amount of time to effectively undertake recycling activities. (2) It was crucial to create a partnership between the Ozone Offices and the Fire fighting industry from the respective countries. A code of conduct was introduced to be voluntarily respected by the industry which would render the implementation of halon bank activities successful and sustainable. (3) The awareness seminars and campaigns that were implemented in the West Asia Countries paved the way for the introduction of recycling equipment. The armed forces in the countries were always invited to attend the seminars. This made them aware of the challenges of halon shortages they will be facing in the near future and take the necessary actions. (4) In some cases the operators appointed to undergo the training on the R&R equipment, did not have the necessary qualifications and background to benefit from the course. This necessitated additional training time. (5) The regional approach requires that the four participating countries take the full ownership and responsibility for sharing the mobile halon reclamation center. Finally, this approach was not viable as the ozone officers did not reach agreement on sharing the equipment.
Region: ASP | ASP/HAL/30/TRA/38 |  | Workshop for halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen | HAL | TRA | UNEP | 1) UNEP required more technical support in Halon to better support the countries. 2) As subject was new, countries were not clear on how to raise their difficulties through the questionnaire circulated, but when met with experts of developed countries (GTZ, France, Japan, UK) directly in meetings, the same was explained better.
Region: ASP | ASP/REF/06/TRA/03 |  | Training and demonstration programme in CFC recycling in MAC in Asia | REF | TRA | UNDP | Delays occurred at all levels: at the level of the recruitment of the MAC consultant, at the level of involving the governments and determining how the logistics would be organized, and at the level of developing the agenda of the workshop. This was a consequence of working in a new subsector in which ExCom guidelines were still unclear. UNDP, therefore, did not want to convene the workshop until such time as ExCom policy was established since otherwise the instructors would have been unable to properly instruct workshop participants on ExCom guidelines and how the results of the programme would be evaluated by the respective Ozone Units.
Region: ASP | ASP/REF/09/TRA/09 |  | Refrigeration training workshop for Asia and the Pacific | REF | TRA | UNEP | None.
Region: ASP | ASP/REF/10/TRA/10 |  | Training and demonstration programme in commercial/industrial refrigeration in East Asia | REF | TRA | UNEP | 1) One training workshop is not enough 2) Gov't and industry must work more closely 3) Promote non-ODS technology
Region: ASP | ASP/REF/10/TRA/11 |  | Training and demonstration programme in commercial/industrial refrigeration in South Asia | REF | TRA | UNEP | 1) Gov't should come up with more specific policy statement 2) Should commit to ozone issue 3) Gov't should monitor CFC emission
Region: ASP | ASP/REF/12/TRA/14 |  | Support to participants to the regional workshop on refrigeration and air conditioning training programme | REF | TRA | Australia | Insufficient data
Region: ASP | ASP/REF/36/TAS/44 |  | Implementation of the PIC Strategy: three thematic meetings on issues related to the implementation of the strategy | REF | TAS | UNEP | As Small Island Developing States, the Pacific Island Countries have unique social, economic and environmental characteristics, including geographic isolation; small physical size; limited natural resources; small economies with low diversification; poorly-developed infrastructure and limited capacity; and paucity of human and financial resources. The extent to which these circumstances inhibit their development has been recognised by the international community in recent years: 1) The unique situation of small island developing states has been documented and acknowledged by the international community since this Project was designed (for example at the World Summit on Sustainable Development in 2002 and the International Meeting for the 10-year Review of the Barbados Programme of Action in January 2005). 2) In addition to their limited human capacity, PICs are vulnerable to environmental problems such as sea level rising and salt water intrusion; waste and pollution; land and soil degradation; and deforestation. 3) Because of the small size, isolation and small populations, other events of national import can impact on the ozone work and divert their limited resources elsewhere. To illustrate: a) The Solomon Islands has faced a period of civil unrest over the period of the Programme. A Regional Assistance Mission (RAMSI) has been deployed to assist with basic services of government (police, utilities, education etc); understandably, government attention has not been focused on the phase out of CFCs. To complicate the issue, the arrival of the expatriate RAMSI personnel has coincided with a reported increase in CFC consumption, perhaps due to expatriates' greater dependence on refrigeration and air conditioning. b) In Tonga the long term, poor health of the King, ending with his passing away on 10 September 2006, has had the nation preparing for an extended period of national mourning, during which time many normal activities are suspended. Little progress on ozone issues is expected during this time until the coronation of the new King in 2008. 4) Against this background the Strategy overall has achieved considerable success. However the pace of progress in enacting regulations to ensure the sustainability of phase-out has been slower than anticipated. This has been due to a generic lack of capacity, overlaid by specific national circumstances as illustrated above. 5) It is clear that the strategy underestimated the time and effort required to establish the ODS regulations. This has had consequential effects for the strategy in terms of the level of support required for the NCC staff to continue to maintain the profile for establishment of ODS regulations, and for project costs. 6) To explain in more detail; each PIC must follow its own regulation-making procedure involving reviewing existing Acts, vetting by Attorney General’s office, circulation among stakeholders for endorsement, and passing by the Parliament. a) Although model regulations have been prepared there have been delays with finalizing the drafts due to resource constraints with the appropriate legal authorities e.g. Attorney General’s office. In other cases, although the regulations have been finalized they have been queued for endorsement by the Parliament and passed over by other urgent bills, not related to environmental issues. b) The extended timeframes for establishing the regulations has resulted in the situation where resources available to the NCC staff are inadequate. This creates further difficulty in retaining, or attracting qualified staff to work on the ozone projects because of low resources, and uncertainties for future prospects. c) As the PICs are spread over a vast area and the distances amongst islands are vast there are very limited resources for UNEP and SPREP staff to travel to countries experiencing unexpected delays or difficulties to provide support.
Region: ASP | ASP/REF/36/TAS/45 |  | Implementation of the PIC Strategy: technical assistance for other countries not included in the strategy | REF | TAS | UNEP | As Small Island Developing States, the Pacific Island Countries have unique social, economic and environmental characteristics, including geographic isolation; small physical size; limited natural resources; small economies with low diversification; poorly-developed infrastructure and limited capacity; and paucity of human and financial resources. The extent to which these circumstances inhibit their development has been recognised by the international community in recent years: 1) The unique situation of small island developing states has been documented and acknowledged by the international community since this Project was designed (for example at the World Summit on Sustainable Development in 2002 and the International Meeting for the 10-year Review of the Barbados Programme of Action in January 2005). 2) In addition to their limited human capacity, PICs are vulnerable to environmental problems such as sea level rising and salt water intrusion; waste and pollution; land and soil degradation; and deforestation. 3) Because of the small size, isolation and small populations, other events of national import can impact on the ozone work and divert their limited resources elsewhere. To illustrate: a) The Solomon Islands has faced a period of civil unrest over the period of the Programme. A Regional Assistance Mission (RAMSI) has been deployed to assist with basic services of government (police, utilities, education etc); understandably, government attention has not been focused on the phase out of CFCs. To complicate the issue, the arrival of the expatriate RAMSI personnel has coincided with a reported increase in CFC consumption, perhaps due to expatriates' greater dependence on refrigeration and air conditioning. b) In Tonga the long term, poor health of the King, ending with his passing away on 10 September 2006, has had the nation preparing for an extended period of national mourning, during which time many normal activities are suspended. Little progress on ozone issues is expected during this time until the coronation of the new King in 2008. 4) Against this background the Strategy overall has achieved considerable success. However the pace of progress in enacting regulations to ensure the sustainability of phase-out has been slower than anticipated. This has been due to a generic lack of capacity, overlaid by specific national circumstances as illustrated above. 5) It is clear that the strategy underestimated the time and effort required to establish the ODS regulations. This has had consequential effects for the strategy in terms of the level of support required for the NCC staff to continue to maintain the profile for establishment of ODS regulations, and for project costs. 6) To explain in more detail; each PIC must follow its own regulation-making procedure involving reviewing existing Acts, vetting by Attorney General’s office, circulation among stakeholders for endorsement, and passing by the Parliament. a) Although model regulations have been prepared there have been delays with finalizing the drafts due to resource constraints with the appropriate legal authorities e.g. Attorney General’s office. In other cases, although the regulations have been finalized they have been queued for endorsement by the Parliament and passed over by other urgent bills, not related to environmental issues. b) The extended timeframes for establishing the regulations has resulted in the situation where resources available to the NCC staff are inadequate. This creates further difficulty in retaining, or attracting qualified staff to work on the ozone projects because of low resources, and uncertainties for future prospects. c) As the PICs are spread over a vast area and the distances amongst islands are vast there are very limited resources for UNEP and SPREP staff to travel to countries experiencing unexpected delays or difficulties to provide support.
Region: ASP | ASP/REF/36/TAS/46 |  | Implementation of the PIC Strategy: policy assistance and guidance to countries for development of regulations | REF | TAS | UNEP | As Small Island Developing States, the Pacific Island Countries have unique social, economic and environmental characteristics, including geographic isolation; small physical size; limited natural resources; small economies with low diversification; poorly-developed infrastructure and limited capacity; and paucity of human and financial resources. The extent to which these circumstances inhibit their development has been recognised by the international community in recent years: 1) The unique situation of small island developing states has been documented and acknowledged by the international community since this Project was designed (for example at the World Summit on Sustainable Development in 2002 and the International Meeting for the 10-year Review of the Barbados Programme of Action in January 2005). 2) In addition to their limited human capacity, PICs are vulnerable to environmental problems such as sea level rising and salt water intrusion; waste and pollution; land and soil degradation; and deforestation. 3) Because of the small size, isolation and small populations, other events of national import can impact on the ozone work and divert their limited resources elsewhere. To illustrate: a) The Solomon Islands has faced a period of civil unrest over the period of the Programme. A Regional Assistance Mission (RAMSI) has been deployed to assist with basic services of government (police, utilities, education etc); understandably, government attention has not been focused on the phase out of CFCs. To complicate the issue, the arrival of the expatriate RAMSI personnel has coincided with a reported increase in CFC consumption, perhaps due to expatriates' greater dependence on refrigeration and air conditioning. b) In Tonga the long term, poor health of the King, ending with his passing away on 10 September 2006, has had the nation preparing for an extended period of national mourning, during which time many normal activities are suspended. Little progress on ozone issues is expected during this time until the coronation of the new King in 2008. 4) Against this background the Strategy overall has achieved considerable success. However the pace of progress in enacting regulations to ensure the sustainability of phase-out has been slower than anticipated. This has been due to a generic lack of capacity, overlaid by specific national circumstances as illustrated above. 5) It is clear that the strategy underestimated the time and effort required to establish the ODS regulations. This has had consequential effects for the strategy in terms of the level of support required for the NCC staff to continue to maintain the profile for establishment of ODS regulations, and for project costs. 6) To explain in more detail; each PIC must follow its own regulation-making procedure involving reviewing existing Acts, vetting by Attorney General’s office, circulation among stakeholders for endorsement, and passing by the Parliament. a) Although model regulations have been prepared there have been delays with finalizing the drafts due to resource constraints with the appropriate legal authorities e.g. Attorney General’s office. In other cases, although the regulations have been finalized they have been queued for endorsement by the Parliament and passed over by other urgent bills, not related to environmental issues. b) The extended timeframes for establishing the regulations has resulted in the situation where resources available to the NCC staff are inadequate. This creates further difficulty in retaining, or attracting qualified staff to work on the ozone projects because of low resources, and uncertainties for future prospects. c) As the PICs are spread over a vast area and the distances amongst islands are vast there are very limited resources for UNEP and SPREP staff to travel to countries experiencing unexpected delays or difficulties to provide support.
Region: ASP | ASP/REF/36/TAS/47 |  | Implementation of the PIC Strategy: technical assistance to countries and monitoring the implementation of the strategy | REF | TAS | UNEP | As Small Island Developing States, the Pacific Island Countries have unique social, economic and environmental characteristics, including geographic isolation; small physical size; limited natural resources; small economies with low diversification; poorly-developed infrastructure and limited capacity; and paucity of human and financial resources. The extent to which these circumstances inhibit their development has been recognised by the international community in recent years: 1) The unique situation of small island developing states has been documented and acknowledged by the international community since this Project was designed (for example at the World Summit on Sustainable Development in 2002 and the International Meeting for the 10-year Review of the Barbados Programme of Action in January 2005). 2) In addition to their limited human capacity, PICs are vulnerable to environmental problems such as sea level rising and salt water intrusion; waste and pollution; land and soil degradation; and deforestation. 3) Because of the small size, isolation and small populations, other events of national import can impact on the ozone work and divert their limited resources elsewhere. To illustrate: a) The Solomon Islands has faced a period of civil unrest over the period of the Programme. A Regional Assistance Mission (RAMSI) has been deployed to assist with basic services of government (police, utilities, education etc); understandably, government attention has not been focused on the phase out of CFCs. To complicate the issue, the arrival of the expatriate RAMSI personnel has coincided with a reported increase in CFC consumption, perhaps due to expatriates' greater dependence on refrigeration and air conditioning. b) In Tonga the long term, poor health of the King, ending with his passing away on 10 September 2006, has had the nation preparing for an extended period of national mourning, during which time many normal activities are suspended. Little progress on ozone issues is expected during this time until the coronation of the new King in 2008. 4) Against this background the Strategy overall has achieved considerable success. However the pace of progress in enacting regulations to ensure the sustainability of phase-out has been slower than anticipated. This has been due to a generic lack of capacity, overlaid by specific national circumstances as illustrated above. 5) It is clear that the strategy underestimated the time and effort required to establish the ODS regulations. This has had consequential effects for the strategy in terms of the level of support required for the NCC staff to continue to maintain the profile for establishment of ODS regulations, and for project costs. 6) To explain in more detail; each PIC must follow its own regulation-making procedure involving reviewing existing Acts, vetting by Attorney General’s office, circulation among stakeholders for endorsement, and passing by the Parliament. a) Although model regulations have been prepared there have been delays with finalizing the drafts due to resource constraints with the appropriate legal authorities e.g. Attorney General’s office. In other cases, although the regulations have been finalized they have been queued for endorsement by the Parliament and passed over by other urgent bills, not related to environmental issues. b) The extended timeframes for establishing the regulations has resulted in the situation where resources available to the NCC staff are inadequate. This creates further difficulty in retaining, or attracting qualified staff to work on the ozone projects because of low resources, and uncertainties for future prospects. c) As the PICs are spread over a vast area and the distances amongst islands are vast there are very limited resources for UNEP and SPREP staff to travel to countries experiencing unexpected delays or difficulties to provide support.
Region: ASP | ASP/REF/44/TAS/51 |  | Implementation of the PIC strategy: technical assistance to countries and monitoring the implementation of the strategy | REF | TAS | UNEP | As Small Island Developing States, the Pacific Island Countries have unique social, economic and environmental characteristics, including geographic isolation; small physical size; limited natural resources; small economies with low diversification; poorly-developed infrastructure and limited capacity; and paucity of human and financial resources. The extent to which these circumstances inhibit their development has been recognised by the international community in recent years: 1) The unique situation of small island developing states has been documented and acknowledged by the international community since this Project was designed (for example at the World Summit on Sustainable Development in 2002 and the International Meeting for the 10-year Review of the Barbados Programme of Action in January 2005). 2) In addition to their limited human capacity, PICs are vulnerable to environmental problems such as sea level rising and salt water intrusion; waste and pollution; land and soil degradation; and deforestation. 3) Because of the small size, isolation and small populations, other events of national import can impact on the ozone work and divert their limited resources elsewhere. To illustrate: a) The Solomon Islands has faced a period of civil unrest over the period of the Programme. A Regional Assistance Mission (RAMSI) has been deployed to assist with basic services of government (police, utilities, education etc); understandably, government attention has not been focused on the phase out of CFCs. To complicate the issue, the arrival of the expatriate RAMSI personnel has coincided with a reported increase in CFC consumption, perhaps due to expatriates' greater dependence on refrigeration and air conditioning. b) In Tonga the long term, poor health of the King, ending with his passing away on 10 September 2006, has had the nation preparing for an extended period of national mourning, during which time many normal activities are suspended. Little progress on ozone issues is expected during this time until the coronation of the new King in 2008. 4) Against this background the Strategy overall has achieved considerable success. However the pace of progress in enacting regulations to ensure the sustainability of phase-out has been slower than anticipated. This has been due to a generic lack of capacity, overlaid by specific national circumstances as illustrated above. 5) It is clear that the strategy underestimated the time and effort required to establish the ODS regulations. This has had consequential effects for the strategy in terms of the level of support required for the NCC staff to continue to maintain the profile for establishment of ODS regulations, and for project costs. 6) To explain in more detail; each PIC must follow its own regulation-making procedure involving reviewing existing Acts, vetting by Attorney General’s office, circulation among stakeholders for endorsement, and passing by the Parliament. a) Although model regulations have been prepared there have been delays with finalizing the drafts due to resource constraints with the appropriate legal authorities e.g. Attorney General’s office. In other cases, although the regulations have been finalized they have been queued for endorsement by the Parliament and passed over by other urgent bills, not related to environmental issues. b) The extended timeframes for establishing the regulations has resulted in the situation where resources available to the NCC staff are inadequate. This creates further difficulty in retaining, or attracting qualified staff to work on the ozone projects because of low resources, and uncertainties for future prospects. c) As the PICs are spread over a vast area and the distances amongst islands are vast there are very limited resources for UNEP and SPREP staff to travel to countries experiencing unexpected delays or difficulties to provide support.
Region: ASP | ASP/REF/69/DEM/56 |  | Promoting low-global warming potential refrigerants for air-conditioning sectors in high-ambient temperature countries in West Asia | REF | DEM | UNEP | 1) There are potential alternatives that have close cooling capacity and energy efficiency performance to the baseline refrigerants, or even better in some cases, and that these are worth further investigation. With further engineering, these alternatives can be strong candidates for replacement of HCFC-22 as the main focus for phase-out activities in Article 5 countries. 2) There is a significant need to improve the R&D capacity at the local air-conditioning industry in high ambient temperature countries in terms of re-designing and optimizing products using low-GWP alternatives with their specifics; e.g. flammability; excess pressures; temperature glide; excess discharge temperature etc. 3) Economical and technology transfer barriers (IPRs) will continue to be issues for some time before the international and regional markets stabilize on a limited group of candidates that can continue in business compared to the current long list of options offered and being examined. 4) Due to the nature of future alternatives, a comprehensive risk assessment tailored to the need of A5 countries and the high ambient temperature conditions in particular. Such an assessment needs to address the dimensions of manufacturing, placing into market, servicing and the end of life of the equipment. 5) There is a lack of institutional programs that are addressing alternative technologies and reducing dependence on high-GWP alternatives in high ambient temperature countries. The market direction in going to the commercially available options is a reflection of such limited research. 6) The process of improving energy efficiency (EE) standards for air-conditioning application in high ambient temperature countries is progressing at a much quicker pace compared to assessing alternative refrigerants. Smart approach needs to be considered in addressing EE in conjunction with low-GWP alternatives in order to avoid promoting higher-GWP alternatives that are commercially available at this stage of time. 7) District cooling (DC) projects in high ambient countries are mostly using conventional technologies as DC technology providers or suppliers show reluctance to promote the use of low-GWP refrigerants or non-vapor compression technologies. The global move towards HFCs, in addition to energy efficiency pressure, provides an opportunity to start promoting such concepts.
Region: ASP | ASP/REF/69/DEM/57 |  | Promoting low-global warming potential refrigerants for air-conditioning sectors in high-ambient temperature countries in West Asia | REF | TAS | UNIDO | The key findings /conclusions of PRAHA I: 1) There are potential alternatives that have cooling capacities and energy efficiency performances close to the baseline refrigerants, or even better in some cases. These are worth further investigation. With further engineering, these alternatives can be strong candidates to replace HCFC-22 and the main focus for phase-out activities in Article 5 (developing) countries. 2) There is a need for significant improvement in the research and development capacity of the local air-conditioning industries in high-ambient temperature countries in terms of re-designing and optimising products using low-GWP alternatives with their specific characteristics, such as flammability, higher pressures, temperature glide, and excess discharge temperature. 3) Economic and technology transfer barriers such as intellectual property rights will continue to be an issue for some time before international and regional markets stabilise and focus on a limited group of alternative refrigerant candidates that can continue to be marketed, compared to the current long list of options currently being examined. 4) Due to the specific characteristics of the future alternatives, there is a need for comprehensive risk assessment tailored to the needs of Article 5 countries and high-ambient temperature conditions, in particular. Such an assessment should address the size of the industry, the markets, servicing and the end of life of the equipment. 5) There is a lack of institutional programmes that address alternative technologies and reduce dependence on high-GWP alternatives in high-ambient temperature countries. The continued marketing of available options reflects the limited research into alternatives. 6) The improvement in energy efficiency (EE) standards for air-conditioning applications in high-ambient temperature countries is progressing at a much quicker pace than the speed of assessing alternative refrigerants. A smart approach is needed in addressing energy efficiency in conjunction with low-GWP alternatives in order to avoid promotion of higher- GWP alternatives that are commercially available at present. 7) District cooling (DC) projects in high ambient countries are mostly using conventional technologies as DC technology providers are still preferred. The global move towards HFCs in addition to energy efficiency pressure will provide golden opportunity to expand the horizon for non-conventional DC plants.
Region: ASP | ASP/REF/76/DEM/59 |  | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | REF | DEM | UNEP | (A) In relation to support the process advancing the promotion and deployment of lower-GWP alternatives: 1) A tailored Risk Assessment is essential, not only for HAT countries, in better understanding safety implications associated with deploying alternative refrigerants, either A2L or A3, considering the specifics of different types of equipment and life stages. 2) Efforts in building risk assessment models should be exerted towards analyzing risks in the logistics side of the supply-chain i.e. Installation, In-door use, outdoor use, servicing and end of life (decommission); understanding the design and manufacturing risk assessment are covered by relevant international standards which should more or less apply to most countries. 3) The concept of risk assessment is quite similar worldwide, including methodologies in calculating and analyzing severity and frequency of risks. However, criteria for acceptable tolerance levels may differ depending on local considerations. Measures to mitigate risks would depend on type of exiting/operational standards and/or codes in each country noting. 4) Building a risk assessment model for the HAT countries that suits the climate and the service practices of the local technicians will help the HAT countries will set the foot of A5 countries, not only HAT, in understanding and establishing local risk assessment models hence adopting the needed regulations and training programs especially in relation to the logistics of lower-GWP based technologies i.e. installation, transportation, storage, servicing and decommissioning. (B) In relation to building capacities of local industry to better design with lower-GWP alternatives: 1) The optimization element of PRAHA-II also pointed out that components, especially compressors for the new refrigerants, are still not widely available. These and other limitations have to be dealt in order to help manufacturers make an informed decision on the way forward. 2) PRAHA capacity building activities have helped the PRAHA stakeholders in acquiring added knowledge about working with alternative lower-GWP refrigerants that are flammable. The study tours have exposed stakeholders to the latest in technology for both A2L and A3 refrigerants at global technology centers. The capacity building activities helped many manufacturers in HAT countries in building or engaging in other research projects. (C) In relation to maintaining sustainable technical platform to support PRAHA process and sharing knowledge about up-to-date technological developments amongst HAT countries: 1) The capacity building efforts have turned PRAHA into a global process that can be extended to all 35 HAT counties and not only the Gulf and Middle East countries that were engaged with PRAHA-I. 2) PRAHA-II events continued to attract global and regional participation in terms of government authorities, technology providers, manufacturers, and international/regional institutes. PRAHA presentations and knowledge sharing at networks of ozone officers and international conferences have become a fixture for exchanging experiences and knowledge about HAT technological related aspects. PRAHA-II has helped to spread the awareness of HAT challenges in optimization and risk assessment as well as opportunities.
Region: ASP | ASP/REF/76/DEM/60 |  | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | REF | TAS | UNIDO | PRAHA-II delivered tangible and beneficial results which can be summarized as follows:(1) Related design optimization: The original scope and schedule were modified during the project as new findings and challenges surfaced. The original baseline test data was used for comparison with tests done on the optimized units built according to the modeling work done even though the latter tests included measurements and metrics not typically performed in energy certification tests of the type done under PRAHA-I (see figure for system design framework in Annex). A resume of the conclusions: (a) For systems operating in considerably higher temperatures (greater than 46 °C), the resultant (b) impact on performance must be considered since performance will degrade as compared to operating under more temperate conditions. (c) The design assessment through modeling provided good insights on adequate component design and/or selection for proper system functioning when using novel refrigerants; (d) Rebuilt and tested units exhibited a considerable reduction in power consumption at the high ambient test condition (46 °C) as compared to the original test data. This indicates the importance of proper compressor selection; (d) Because of the differences in saturation curves from the simulation analysis, refrigerant with wider saturation curves tend to result in systems with higher efficiency and less charge when no modifications to the hardware are made. The results showed however, that by making appropriate component selection, such as compressors with larger displacement volumes and higher mass flow rate, the cooling capacities and overall performance of the other refrigerants were of the same order of magnitude; (e) Refrigerant fractionation as evidenced by the leak tests, does not appear to be a great concern since less than 2% change in cooling capacity was observed after the system’s re-charge. Table in Annex shows leak test summary for R-447B which exhibits the highest glide amongst the refrigerants evaluated under the project. (2) Related to capacity building: The capacity building element was successful in providing a platform of cooperation between governments, research institutes, industry associations, and the industry in general and became a process for the sharing of information and results among the different stakeholders. The experience of working on PRAHA-I gave UNIDO and UN Environment (UNEP) the confidence that international stakeholders support the goals of the project and that the outcome will be beneficial to all and beyond economic gains. (3) Related to risk assessment: The work on risk assessment required resources beyond the traditional RACHP expertise that is required for the balance of the project. The different usage and servicing practices used in the region needed to be considered in order to assess the risk of using flammable refrigerants. The initial concern about the effect of high ambient temperature on the increased risk of ignition was removed and the focus is on actual practices. The recommendation is for HAT countries to continue the risk assessment based on analyzing local situations and reduce the risk by implementing various measures that are verified such as minimizing ignition probability and advancing local codes/standards.
Region: ASP | ASP/SEV/04/TRA/01 |  | Regional workshop for Asia and the Pacific | SEV | TRA | UNEP | 1) Increase participation of gov't and industry representatives 2) Involve NGOs
Region: ASP | ASP/SEV/07/TRA/06 |  | Support for delegates from six Asian countries to participate in regional workshop on alternatives to CFC | SEV | TRA | Australia | Insufficient data.
Region: ASP | ASP/SEV/08/TRA/08 |  | Support to ASEAN regional conference on CFC and halons | SEV | TRA | Australia | Insufficient data
Region: ASP | ASP/SEV/12/TRA/13 |  | Workshop for small and medium size enterprises on management of ODS phase-out | SEV | TRA | UNEP | None.
Region: ASP | ASP/SEV/19/TRA/20 |  | Regional workshop on monitoring and control of ODS consumption for West Asia | SEV | TRA | UNEP | None.
Region: ASP | ASP/SEV/29/TRA/31 |  | Regional workshop on control and monitoring of ODS consumption for the South East Asia and the Pacific region | SEV | TRA | Sweden | See PCR.
Region: ASP | ASP/SEV/29/TRA/33 |  | Regional workshop on control and monitoring of ODS consumption for the South East Asia/Pacific region | SEV | TRA | Japan | While the workshop was successful overall, some important lessons were learned. These included: 1) It is important to put effort into getting the right participants to attend the workshop. It is essential that delegates are of a sufficiently high level to have an informed understanding of the relevant issues, and to be able to implement the measures decided on during the workshop. On the other hand it is also important that the customs officers present have actual experience of controlling ODS at the border, otherwise the practical advice needed to design efficient enforcement measures will be lost. This message should be emphasized in the invitation of the participants. 2) In selecting participants for the workshop good knowledge of the working language could be a requirement, albeit a less important one than the requirement of having persons from the right level as mentioned above. Language can be a barrier to good communication. In a region like the SEAP region it may be difficult to avoid this problem, as there is no common language for the region and the knowledge of English among participants is sometimes limited. At the present workshop the language problem was considered in the organization of working groups, where countries with similar languages were grouped together. Use was also made of the language abilities of individual participants who acted as translators for their colleagues in the working groups when needed. However, this type of arrangement is time consuming. The language barrier should be taken into account when the timeframe for the workshop is planned if it is suspected that language can be a problem in the region. 3) Several participants suggested that topics to be discussed at the workshop and in particular during working sessions could be sent out to the delegates before the workshop, to give them time to prepare better for the discussions. This is a measure that could also help abate the language problem. 4) Some Muslim participants complained about the time schedule not allowing them to conduct their prayers and about the fact that there was no halal food available at the workshop venue. In a region where participants have religious duties to observe the organizers should keep this in mind.
Region: ASP | ASP/SEV/29/TRA/34 |  | Regional Workshop on Control and Monitoring of ODS in the South | SEV | TRA | Japan | 1) It is important to put effort into getting the right participant to attend the workshop. It is essential that delegates are of a sufficiently high level to have an informed understanding of the relevant issues, and to be able to implement the meadures decided on during the workshop. On the other hand it is also important that the customs officers have actual experience of controlling ODS at the border, otherwise the practical advice needed to design efficient enforcement measures will be lost. This message should be emphasised in the invitation of the participants. 2) In selecting participants for the workshop good knowledge of the working language could be a requirement, albeit a less important one than the requirement of havingpersons from the right level as mentioned above. Language can be a barrier to good communication. In a region like the South Asia region it may be difficult to avoid this problem, as there is no common language for the region and the knowledge of English among participants is sometime limited. As the present workshop the language problem was considered in the organisation of working groups, where countries with similar languages were grouped toghether. Use was also made of the language abilities of individual participants who acted as translators for their colleagues in the working groups when needed. However, this type of arrangement is time consuming. The language barrier should be taken into account when the timeframe for the workshop is planned if it is suspected that language can be a problem in the region. 3) Several participants suggested that topics to be discussed at the workshop and in particular during working seessions could be sent to the delegates before the workshop, to give them time to prepare better for the discussions. This is a measure that could also help abate the language problem.
Region: ASP | ASP/SEV/30/TRA/35 |  | West Asia military ODS workshop (to be held in conjunction with a global military environmental conference) | SEV | TRA | UNEP | None.
Region: ASP | ASP/SEV/34/TAS/41 |  | Assistance for the implementation of strategic planning of the Multileteral Fund to promote compliance with the montreal Protocol in the Asia and the Pacific Region | SEV | TAS | Japan | 1) Preparation of a roadmap for the phase out of ODS which extensively covers all the ODS in all the relevant sectors is essential for an Article 5 countries in the compliance period. 2) Involment of as many stakeholders as possible including the private sector and the key government agencies other than the National Ozone Unit in the process of policy drafting is effective incollecting data, deepeningunderstanding and practical knowledge for ODS control and encouraging them to take due share responsibility. 3) Preparation of a policy implementation plan, whether Country Programme (Update), Refrigeration management Plan (Update) or National Compliance Action Plan, contributes to strengthening the management capability of an Article 5 country not only as a roadmap but also in the process of preparation, which can provide opportunities to strengthen coordination between the NOU and the government authorities. 4) In order to strengthen the management capability of an Article 5 country for the protection of the Ozone Layer, not only the institutional strengthening of the NOU itself but also the enhancement of coordination between the NOU and the relevant government authorities needs to be pursued, especially in an Article 5 country where other ODSs than CFC are consumed. 5) As many Article 5 countries are making steady progress in phasing out ODS consumption to the extent that some countries can aim at early phase-out, new issues such as illegal trade prevention and ODS disposal are getting more attention in Article 5 countries. 6) A recovery and Recycling programme is important as a supporting measure that an Article 5 country government can provide to end-users un the interim period between the termination of CFC import and the end of CFC demand. The programme should be re-evaluated for this perspective, not only from the performance achieved by the past projects.
Region: ASP | ASP/SEV/34/TAS/42 |  | Regional cooperation for monitoring and control of ODS consumption (SEAP) and Preventing illegal in the South Asia (SA) | SEV | TAS | Sweden | 1) On the delay: As requested by the countries, providing more time between workshops allowed countries to better follow-up and prepare their input to the subsequent meeting. Providing more time between workshops also meant that additional bilateral and small group meetings could be organised discussing specific problems between countries and this was perceived as very useful by the countries. At the same time, as Implementing Agency we had recommended more frequent meetings as this is believed to keep the participants more active and also minimize the risk of participants forgetting what was discussed at previous meeting or of participants changing their positions. The result turned out fine however. 2) On Project implementation: Project implementation resulted in many initiatives. However, there is a need for close follow-up in order to make them effective, which makes this type of project labour intensive. The planned activity on enforcement tools proved difficult to implement. This was partly due to countries being at different levels with regards to the amount of ODS being imported/exported and also their monitoring possibilities and capabilities. With regards to the initial ideas for setting-up of a website or a database, another reason why is what difficult was that long-term commitment and ownership is important in order to solve issues of credibility, maintenance and security and that this is difficult to arrange when the receipient and user is a network with a three year budget only. 3) On participation: a) One of the main pillars of the success of the project is the insistence on having the same officers attend all the workshops. This allowed for deeper understanding of the specific problems, created a big capacity building of those officers, allowed for a mutual search for solutions, with officers taking a very active role. The project did of course see a number of country participants being changed but on the whole the majority of the participants remained the same during the project period. b) Initially, the establishment of a project steering group was crucial to get the project set up accepted by some of the participating countries (for the SEAP-region in 2001). Especially one country made it clear that they were unwilling to meet within the proposed network and exchange information on trade data etc and other information that could be regarded as confidential. Even if we stressed the fact that the network had no intentions of requesting countries to provide sensitive data and that the aim was primarily on capacity building, one country was unwilling to attend. We therefore suggested the establishment of a steering committee (SC) with participants from two countries (rotating) – one LVC and one HVC – plus UNEP and Sida/SEI as implementing agencies and funder in order to increase the countries control over the project. The role of the SC would inter alia be to give comments on agendas, suggest suitable speakers and experts and help identify stakeholders and participants for the project meetings. After this proposed set-up, all countries agreed to participate. The establishment of the SC was also positive in that it increased countries active participation in the project. c) Before the start of this project, the majority of the countries did not have any formal or informal cooperation between the NOU and customs department and the awareness about illegal trade in ODS within the customs units was generally very low. One of the main objectives for the project was to establish a focal point at middle manager level (in order to be able to disseminate information within the organisation effectively) for ODS issues at the customs in each participating country. As a result of the project several countries did establish such formal or informal agreements between the NOU and the customs department on the cooperation of ODS trade and in many countries this collaboration proved to work very effectively. 4) On expertise: As the project worked closely on regional cooperation involving customs officers and international organisations, the assistance of a consultant with specific background in customs work, within the region has proven very effective in taking specific activities forward, such as the desk study, or the cooperation with RILO and other enforcement agencies. 5) On outreach: a) Outreach was not limited to national/regional implementation. The search of solutions on specific issues led countries to take the initiative to bring certain problems to the Meeting of the Parties. As an outcome of discussions on possibilities to track ODS trade at the meeting in Phuket 2003, Sri Lanka took the lead in drafting a CRP on this subject, which was first tabled at the 24th OEWG in July 2004. Sri Lanka and India eventually took the lead in drafting proposals for a MOP decision during meetings of the OEWG and MOP XV and XVI on behalf of the countries in the SA and SEAP networks, which ultimately led to the adoption of MOP Decision XVI/33. The ODS tracking workshop was organized by the Ozone Secretariat on request of the MOP on 3 April 2005 in Montreal on the development of specific areas and a conceptual framework of cooperation in preventing and combating illegal trade in controlled ozone-depleting substances. b) Following this, the participants of the 2005 Beijing Workshop recommended that the Ozone Secretariat might consider inviting the Ozone Officer of Sri Lanka to elaborate and explain the underlying concerns in the SA and SEAP Region. Eventually the 17th Meeting of the Parties in 2005 adopted Decision XVII/16: “Preventing illegal trade in controlled ozone-depleting”, which adopted the Terms of Reference for a study on the feasibility of developing an international system of monitoring the trans-boundary movement of controlled ozone-depleting substances between Parties. Chatham House and EIA prepared the study jointly, and it was discussed during the 18th MOP in October 2006. c) Informing other Regional networks worldwide about the activities of the project, led to a request by other regions to implement similar project. The Latin America Region are currently implementing a similar project in their Region (drafted by Sweden/SEI, taken over by Canada and implemented by UNEP). Some activities are being replicated such as cooperation with RILO offices in different Regions through formalised agreements, and encouragement of reporting through CEN. d) Other MEA secretariats also showed interest in being involved, while the participating countries also felt the need to extend the concept of cooperation between officers responsible for MEA implementation and customs to specifically the Rotterdam, Stockholm and Basel Conventions. This has now also been realised through the Sida funded extension of the project to include other MEAs. 6) On the role of other agencies: The project generated awareness raising within organisations, including Interpol and WCO, to put environmental crime on their agenda. However, awareness raising works both ways. The Environment side needs to have an understanding of what other organisations do, including specific tools they make available which could be useful in tackling environmental crime, such as the Ecomessage of Interpol and the Customs Enforcement Network (CEN) of RILO. Use of such tools for combating environmental crime will give a clear sign to those organisations about the importance that member countries attach to environmental crime. This in turn may lead those organisations to allocate more resources to environmental crime, giving it attention in their work programmes. 7) On the Scope: a) In order to strenghten the effective implementation in countries, it was suggested by some countries to raise awareness of the full enforcement chain, including prosecutors, judges, police, environmental inspectors, and investigators. This was also discussed at the start of the project but it was judged to make the scope to broad and hence this request was not met. b) Towards the end of the project, countries expressed a wish to broaden the scope of the regional cooperation to include other MEAs. There has during many years also been an increasing trend at various international negotiating fora to call for a coherent and coordinated implementation of chemicals related Multilateral Environmental Agreements (MEAs). One example is the Green Customs Initiative (GCI) launched in 2002 by the WCO and UNEP which aims to integrate training on different MEAs such as MP, Basel, Rotterdam and Stockholm Conventions to enhance synergies and linkages and increase the effectiveness of the training. These processes have been highlighted in the International Environmental Government/Governing Council of UNEP (IEG/GC) process as well. These ideas have now also been realised through the Sida funded extension of the project to include other MEAs as mentioned above. 8) Future Challenges: a) Environmental crime is one of the most profitable and fastest growing new areas of international criminal activity. Growing international environmental concerns have led to the proliferation of multilateral conventions and national laws and regulations to control pollutants that are health or environmental hazards, to prevent wanton exploitation of scarce natural resources, and to protect endangered plant and animal species. Criminal organizations around the world -- most notably in Italy, Russia, China, and Japan -- have taken advantage of the significantly greater costs for waste disposal, as well as the much-increased value of rare or precious natural resource commodities that are the subject of tight trade and sale restrictions, to earn substantial illicit income from circumventing environmental laws and regulations. b) Illegal trade in all categories of ODS will clearly remain a concern over the next 10 years at least, in particular for CFCs in developing countries and possibly for hydrochlorofluorocarbons (HCFCs) and halons in developed nations. c) At the same time, some may consider the Montreal Protocol as mostly done, and funding in coming years through the Multilateral Fund will probably decrease and ultimately end. This raises the issue of how to maintain the capacity built on Montreal Protocol issues within the national administrations, and how to maintain awareness about the control of ODS after 2010. One way of achieving this could be through integration of Ozone Depleting Substances in the hazardous chemicals policies of countries. A lot of capacity building has been generated within the Region working on the implementation and control of ODS trade and this should be made use of.
Region: ASP | ASP/SEV/38/TAS/49 |  | Assistance for the implementation of the strategic planning of the Multilateral Fund to promote compliance with the Montreal Protocol in the Asia and Pacific Region (Phase 2). | SEV | TAS | Japan | 1) Preparation of a roadmap for the phase out of ODS which extensively covers all the ODS in all the relevant sectors is essential for an Article 5 countries in the compliance period. 2) Involvement of as many stakeholders as possible including the private sector and the key government agencies other than the National Ozone Unit in the process of policy drafting is effective in collecting data, deeping understanding and practical knowledge for ODS control and encouraging them to take due share of responsibility. 3) Preparation of a policy implementation plan, whether Country Programme (Update), Refrigeration Management Plan (Update) or National Compliance Action Plan, contributes to strengthening the management capability of an Article 5 country not only as a road map but also in the process of preparation, which can provide opportunities to strengthen coordination between the NOU and the government authorities. 4) In order to strengthen the management capability of an Article 5 country for the protection of the Ozone Layer, not only the institutional strengthening of the NOU itself but also the enhancement of coordination between the NOU and the relevant government authorities needs to be pursued, especially in an Article 5 country where other ODSs than CFC are consumed. 5) In an Article 5 country which is a low volume consumer of ODS, the demand for illegal trade prevention is specially strong, foreboding that the similar tendency will prevail in other Article 5 countries as the ODS production and consumption are being phased out. 6) In a geographically large Article 5 countries, the roles of local governments are considered to become increasingly larger in ensuring the implementation and enforcement of national ODS phase-out policies.
Region: ASP | ASP/SEV/50/TAS/52 |  | Implementation of the PIC strategy: Thematic meetings, technical assistance and monitoring, assistance to PICs not part of the strategy, policy assistance and regulations, assistance for enforcing ODS regulations and training for customs officers and r... | SEV | TAS | Australia | As Small Island Developing States, the Pacific Island Countries have unique social, economic and environmental characteristics, including geographic isolation; small physical size; limited natural resources; small economies with low diversification; poorly-developed infrastructure and limited capacity; and paucity of human and financial resources. The extent to which these circumstances inhibit their development has been recognised by the international community in recent years: 1) The unique situation of small island developing states has been documented and acknowledged by the international community since this Project was designed (for example at the World Summit on Sustainable Development in 2002 and the International Meeting for the 10-year Review of the Barbados Programme of Action in January 2005). 2) In addition to their limited human capacity, PICs are vulnerable to environmental problems such as sea level rising and salt water intrusion; waste and pollution; land and soil degradation; and deforestation. 3) Because of the small size, isolation and small populations, other events of national import can impact on the ozone work and divert their limited resources elsewhere. To illustrate: a) The Solomon Islands has faced a period of civil unrest over the period of the Programme. A Regional Assistance Mission (RAMSI) has been deployed to assist with basic services of government (police, utilities, education etc); understandably, government attention has not been focused on the phase out of CFCs. To complicate the issue, the arrival of the expatriate RAMSI personnel has coincided with a reported increase in CFC consumption, perhaps due to expatriates' greater dependence on refrigeration and air conditioning. b) In Tonga the long term, poor health of the King, ending with his passing away on 10 September 2006, has had the nation preparing for an extended period of national mourning, during which time many normal activities are suspended. Little progress on ozone issues is expected during this time until the coronation of the new King in 2008. 4) Against this background the Strategy overall has achieved considerable success. However the pace of progress in enacting regulations to ensure the sustainability of phase-out has been slower than anticipated. This has been due to a generic lack of capacity, overlaid by specific national circumstances as illustrated above. 5) It is clear that the strategy underestimated the time and effort required to establish the ODS regulations. This has had consequential effects for the strategy in terms of the level of support required for the NCC staff to continue to maintain the profile for establishment of ODS regulations, and for project costs. 6) To explain in more detail; each PIC must follow its own regulation-making procedure involving reviewing existing Acts, vetting by Attorney General’s office, circulation among stakeholders for endorsement, and passing by the Parliament. (i) Although model regulations have been prepared there have been delays with finalizing the drafts due to resource constraints with the appropriate legal authorities e.g. Attorney General’s office. In other cases, although the regulations have been finalized they have been queued for endorsement by the Parliament and passed over by other urgent bills, not related to environmental issues. (ii) The extended timeframes for establishing the regulations has resulted in the situation where resources available to the NCC staff are inadequate. This creates further difficulty in retaining, or attracting qualified staff to work on the ozone projects because of low resources, and uncertainties for future prospects. (iii) As the PICs are spread over a vast area and the distances amongst islands are vast there are very limited resources for UNEP and SPREP staff to travel to countries experiencing unexpected delays or difficulties to provide support.
Bahrain | BAH/REF/22/TAS/04 |  | Implementation of a National Programme for Recovery and Recycling of Refrigerants (UNDP No. BAH/97/G61) | REF | TAS | UNDP | Generally, the lessons learnt are similar to the experience in other R & R projects. More specifically, these include: Requirement to incorporate more explicit implementation conditions into R&R Project Documents; Requirement to draw up and have signed pertinent completion documents (similar to investment project’s Certificate of Completion and Handover Protocol) and having each participant sign a related agreement, immediately after training and distribution has been carried out; By including provisions in the Project Document, as part of a specific Monitoring Project component, the need to contract a national consultant to carry out monitoring and evaluation of activities. It can be specified that such services are only to be remunerated upon receipt of requisite progress reports; Necessity of having appropriate policy and market mechanisms in place to support such programming. Such a requirement should be a key component of a management plan for the refrigeration sector, as a whole; Neccessity of having continuity in management of programme at national level in order to ensure continuity of all implementation-related activities and sense of national ownership of programming; and, Necessity of having open lines of communication amongst project partners in order that information requests may be properly channelled and feedback recorded.
Bahrain | BAH/REF/26/TRA/05 |  | Implementation of the RMP: train the trainers programme in the refrigeration sector | REF | TRA | UNEP | 1) Full coverage of opening session of Phase I training attended by approximately 50 invited guests from decision-making levels in Ministries and large companies, and the media. This contributed to raising public awareness and assisted in participation of technicians from various companies in the Phase II of the Programme; 2) Using the local trainers trained during Phase I has achieved optimum outputs and maximum results from the programme; 3) It would be more efficient to enhance the success of the programme if the country included certification of refrigeration technicians in the local legislation; 4) Practical training needs for Phae II would be better served with a well-equipped training centre.
Bahrain | BAH/REF/26/TRA/06 |  | Implementation of the RMP: customs training | REF | TRA | UNEP | 1) Full coverage of opening session of Phase I training attended by approximately 60 invited guests from decision making levels in Ministries and Large installation companies, and the media contributed to raise public awareness and assisted in participation of their technicians in the Phase II of the programme; 2) Using the local trainers trained by Phase I of the programme has achieved optimum outputs and maximum results from the programme; 3) Phase II was divided into Phase II-A and Phase II-B mentioned in the attached document, and the country managed to train over 200 technicians with limited fund; 4) There was a need for translation of the training materials "training Handbook" and a translator into Arabic during the training workshop; 5) Practical training "on site training" proved to be more efficient than the theoretical training; 6) Inviting the Director General of Customs in the opening ceremony and the closing ceremony has positive impacts on the cooperation form the Customs Directorate to implement Phase II. - Important Workshop Recommendation - 1) Government laboratory should be equipped with the standards for the gas chromatograph; 2) Explore alternatives for storage and destruction for seixed products; 3) Translation of the training materials into arabic is needed; 4) Future workshop to conducted in Arabic language, or similtaneous translation should be provided; 5) A unified GCC Import/export licensing should be put in place.
Bahrain | BAH/REF/29/INV/09 |  | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Jazira Cooling and Heating Factory | REF | INV | UNDP | The costs for trials and site preparation need to be realistically estimated and the eligible part funded accordingly.
Bahrain | BAH/REF/29/INV/10 |  | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Awal Refrigeration and Air Conditioning | REF | INV | UNDP | The scheduling of project activities needs full involvement of the beneficiary enterprise in order to prevent delays.
Bahrain | BAH/SOL/45/TAS/14 |  | Training and awareness workshop in the solvents and process agents (CTC and TCA) sector | SOL | TAS | UNIDO | None
Barbados | BAR/PHA/75/TAS/25 |  | Verification report on the implementation of the HCFC phase-out management plan | PHA | TAS | UNEP | 1) HCFC consumption verified by the consultant was different from the data provided by the country in Article 7. The difference in consumption quantities was attributed to an inadvertent omission of some import records by the DCCA. The NOU has accepted the verified consumption data confirmed by the consultant. 2) The NOU should provide additional capacity building to the DCCA officials so that recording errors are avoided in the future. Capacity building should emphasise the importance of maintaining proper records. A joint formal quarterly review system by DCCA and NOU officials should also be instituted wherein company data & DCCA data are compiled and reviewed for consistency. 3) Customs data on import & export, for any of the years covered under this verification report, was not available at the time of reporting. The formal communication channel between NOU and the Custom & Excise Department should be strengthened. The submission of customs data on imports and exports to the NOU on a routine basis would assist in eliminating the data inconsistencies. 4) The initial quota was set for HCFC-22 and HCFC-142b based on historical import records. However, in 2013 a small quantity of R-409a which contains HCFC124 was imported by a company and a one-time exception was made by NOU to allow that import. As a result, appropriate measures were implemented in order to track and account for HCFC-124 in this and any possible future import of this ODS. In addition, the country appropriately included the consumption of HCFC-124 in its submission of Article-7 data.
Barbados | BAR/REF/18/TAS/04 |  | CFC-recovery, recycling and training in refrigeration | TAS | TAS | UNIDO | The execution of CFC recovery, recycling and training projects in small countries is a highly efficient means to reduce the emission of CFCs.
Barbados | BAR/REF/43/TAS/10 |  | Implementation of the RMP: import-export licensing system and establishment of refrigeration and air-conditioning association | REF | TAS | UNEP | The process of drafting, discussing and approving of licensing system legislation took longer than planned, consequently delaying training related activities. However during the training sessions that were based on the draft text with the participation of brokers and distributors of refrigerant gases and equipment, suggestions were raised and considered for improving the draft, particularly to make the process more effective to all involved. Therefore, the enacted 2009 Order undertook an unforeseeable consultative process with stakeholders that make the final product more robust.
Barbados | BAR/REF/43/TAS/11 |  | Implementation of the RMP: technical assistance project to the MAC and end-users sectors | REF | TAS | UNDP | For MAC R&R units it is important to deliver equipment that can be retrofitted in the future to also work with HFC-134a, assuring the sustainability of the project. Also, MAC servicing shops operate differently from A/C servicing shops since many technicians are not formed in the refrigeration area, but in the mechanics, so more detailed training must be given.
Barbados | BAR/REF/43/TAS/12 |  | Implementation of the RMP: monitoring the activities in the RMP | REF | TAS | UNDP | For MAC R&R units it was important to deliver equipment that were possible to be retrofitted to also work with HFC-134a, assuring the sustainability of the project. Also, MAC servicing shops operate differently from A/C servicing shops since many technicians are not formed in the refrigeration area, but in the mechanics, so more detailed training was delivered.
Barbados | BAR/SEV/09/CPG/01 |  | Country programme preparation | SEV | CPG | UNEP | The accurate compilation of data and information is vital. If this is not done, phase out activities and possible projects are not properly identified.
Barbados | BAR/SEV/15/INS/03 |  | Establishment of the Ozone Unit | SEV | INS | UNEP | Change in ozone officer had its impact on the project towards the final stages. This resulted in delay in submission of final report on IS progress. This results in lack of accountability of ozone office
Burundi | BDI/ARS/35/INV/09 |  | Phase-out of CFC 11/12 mixture in the Manufacture of Insecticides by conversion to hydrocarbon propellant at FADI SA (Fabrication d'insecticides et de produits chimiques) | ARS | INV | UNDP | Some of the pneumatic tubing components for the propellant gassing unit were not in the responsibility of the equipment supplier. This caused some minor problems, because such technical components are not easily available in such land locked developing country like Burundi. By means of luck the enterprise and the equipment supplier managed to find suitable tubes and locally machined the missing pneumatic components. This situation could have been avoided by including the missing items in the specification of the internationally purchased equipment.
Burundi | BDI/FOA/35/INV/10 |  | Phasing out of CFC-11 in the Manufacture of Flexible Slabstock Foam at EXIM S.A by Conversion to Methylene Chloride | FOA | INV | UNDP | Good project design allowed very smooth conversion and those experiences can be replicated in similar projects in any other Article 5 counties.
Burundi | BDI/PHA/73/TAS/32 |  | Verification report on the implementation of the HCFC phase-out management plan | PHA | TAS | UNEP | Burundi has established a legal and institutional framework to implement Montreal Protocol. The licensing and quota system was revised and became operational on 1 January 2018. The monitoring system established by the NOU allows a good control on the import of HCFCs.
Burundi | BDI/REF/26/TAS/02 |  | Implementation of the RMP: monitoring the activities included in the RMP | REF | TAS | UNDP | A competent local consultant can be a valuable asset in monitoring the progress of an R&R program.
Burundi | BDI/REF/26/TAS/05 |  | Implementation of the RMP: implementation of a national programme for recovery and recycling of refrigerants | REF | TAS | UNDP | It is difficult to achieve the projected rates of recycling because of difficulties in transporting the recovered refrigerant to the recycling centers.
Burundi | BDI/REF/26/TRA/03 |  | Training for Customs officers | REF | TRA | UNEP
Burundi | BDI/REF/26/TRA/04 |  | Training Technicians in good management practices | REF | TRA | UNEP | Training equipment should not be purchased by another agency as part of their R&R project.
Burundi | BDI/REF/41/TAS/13 |  | Implementation of the RMP: supplementary training and spares to the national programme for recovery and recycling of refrigerants | REF | TAS | UNDP | LES FRIGORISTES ONT RENFORCE LEURS CONNAISSANCES DANS L’UTILISATION DE LA NOUVELLE TECHNOLOGIE DE RECUPERATION ET RECYCLAGE The beneficiaries have increased their knowledge in the use of a new technology in recovery/recycling
Burundi | BDI/REF/41/TAS/16 |  | Implementation of the RMP: monitoring the activities in the RMP | REF | TAS | UNDP | La maîtrise et le suivi de la récupération et du recyclage par les frigoristes, l’exploitation du système de licence The mastering of R&R practices by the Refrigeration technicians and the implementation of the licensing system.
Burundi | BDI/REF/41/TRA/14 |  | Implementation of the RMP: customs training programme (phase II) | REF | TRA | UNEP
Burundi | BDI/REF/41/TRA/15 |  | Implementation of the RMP: training of refrigeration technicians (phase II) | REF | TRA | UNEP
Burundi | BDI/SOL/45/TAS/19 |  | Training and awareness workshop in the process agents (TCA) sector | SOL | TAS | UNIDO | The project allowed the creation in the country of awareness on the use of CTC/TCA The execution of an awareness workshop was an important experience for SME and representatives of National institutions to become acquainted with solvent alternatives.
Benin | BEN/FOA/32/INV/12 |  | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Plastique Elastomeres du Benin (P.E.B.) | FOA | INV | UNDP | Based on previous flexible slabstock foam projects in other African nations, advance planning with the enterprise made certain that the project would be implemented as planned for in the project document. As a result, the project was able to be completed on schedule and within budget.
Benin | BEN/PHA/77/TAS/34 |  | Verification report on the implementation of the HCFC phase-out management plan | PHA | TAS | UNEP | Benin has established a legal and institutional framework to implement Montreal Protocol. The national regulations established licensing system on HCFC import. All economic operators importing HCFCs are known and subject to these regulations.
Benin | BEN/REF/22/TAS/04 |  | Refrigerant Recovery and Recycling Scheme | TAS | TAS | UNIDO | 1) The implementation of a Refrigerant Recovery-Recycling Scheme project (henceforth RMP) in LVCs is a very efficient means to reduce the emission of CFCs. However, the supply of equipment must absolutely be supported by specific training programmes for trainers and for technicians as well as by a training project for custom's officers in order to implement good refrigeration management practices and to efficiently monitor and control the import of ODS. 2) Project preparation, more specially the number of equipment to be supplied should be based on accurate data and information in order to avoid waste of time, delays or equipment shortfalls. 3) The issue of technical translation should be efficiently addressed by suppliers of equipment and training services and equipment inappropriate wording could lead to damage to the equipment. 4) During the preparation and the implementation of a such a project there is a need for: (a) close cooperation, active participation and full involvement of the local authorities in charge of the implementation of the Montreal Protocol, (b) thorough involvement of Ozone Office, (c) tight project management and monitoring by the project manager of the implementing agency.
Benin | BEN/REF/32/TAS/10 |  | Delopment of Code of Good Practice for technicians | REF | TAS | Canada | The project ensured that the country has an effective tool to promote good practice among the country's technicians.
Benin | BEN/REF/32/TRA/09 |  | Training of technicians in good refrigeration practice | REF | TRA | Canada | The 5-day Train-the-Trainer workshop benefitted from the presence of two trainers, one who with strong engineering and industry background, the other with more technical and operational experience.
Benin | BEN/REF/32/TRA/11 |  | Implementation of the RMP: training of environmental inspectors and investigators | REF | TRA | Canada | Much of the materials used for the training of customs officers can also be used to train environmental inspectors and investigators, although the emphasis with the latter group needs to be more technical in nature. In the case of a country like Benin which consumes CFCs only in refrigeration and air conditioning, it is important for environmental inspectors and investigators to understand where, why and how CFCs are used, and the basic fundamentals of good practices.
Bangladesh | BGD/ARS/17/INV/05 |  | Conversion to CFC-free technology in the manufacture of aerosol at Advanced Chemical Industries Ltd. (ACI) | ARS | INV | UNDP | The enterprise had problems in constructing the new factory and in the selection of HAP supplier.
Bangladesh | BGD/ARS/52/INV/26 |  | Phase-out of CFC consumption in the manufacture of aerosol MDIs (Beximco, Square Pharmaceutical and Acme Pharmaceutical) | ARS | INV | UNDP | For timely implementation, the Government should play an active role in completing contractual arrangements with the enterprises in a timely manner. Performance based payment modality is an efficient modality for project implementation.
Bangladesh | BGD/ARS/52/TAS/27 |  | Transition strategy for phasing out use of CFCs in the manufacturing of MDIs | ARS | TAS | UNEP | (1) The critical and regular monitoring of pharma grade CFC supply through campaign production allocations to Bangladesh and supplies from stockpiles. Quotas for control on quantities of CFC imports by the different manufacturers along with timing of ban on import of CFCs for MDI manufacturing. (2) Awareness activities are important for faster market adoption of non-CFC alternatives and phaseout of CFC MDIs. (3) Workshops for sensitizing the stakeholders on CFC MDI phaseout and adoption of CFC free alternatives played important key achievement in reaching the objectives of this project. (4) Developed awareness materials are very helpful in awareness campaign primarily stickers for use at the pharmaceutical outlets and clinics and posters for use at the pharmaceutical outlets, select medical centers treating respiratory diseases, hospitals etc.
Bangladesh | BGD/REF/29/TAS/10 |  | Implementation of the RMP: national recovery and recycling project | REF | TAS | UNDP | 1) Financial incentive is required to encourage R&R. 2) Awareness and constant monitoring are essential. 3) Small size electric recovery machine is better for recovery activities in developing countries.
Bangladesh | BGD/REF/29/TAS/12 |  | Implementation of the RMP: monitoring of the activities included in the RMP | REF | TAS | UNDP | 1) Financial incentive is required to encourage R&R. 2) Awareness and constant monitoring of project activities are essential. 3) Small size electric recovery machine is better for recovery activities in developing countries.
Bangladesh | BGD/REF/29/TRA/08 |  | Implementation of the RMP: Training programme for customs officers | REF | TRA | UNEP
Bangladesh | BGD/REF/29/TRA/11 |  | Implementation of the RMP: Training of trainiers in good refrigerant management practices and implementation of a national technicians training programme | REF | TRA | UNEP | (1) The project was delayed due to the signing of the MOU for various reasons including the budget, and the administration issues. After the signing of the MOU, the train-the-trainer workshop was further delayed as the Project Director (technical) was being changed. (2) The project training target should be more realistic in consideration of the proposed budget.
Bangladesh | BGD/REF/80/INV/01+ |  | Conversion of Domestic Refrigerator Manufacturing Facility from HFC-134a to Isobutane as a Refrigerant and Conversion of Compressor Manufacturing Facility from HFC-134a-Based Compressors to Isobutane based Compressors at Walton Hi Tech Industries Limited (“Walton”) | REF | INV | UNDP | 1) It is highly recommended that the MLF also consider parallel investments and interventions at the manufacturing and servicing sector to allow not only the industrial conversion of companies, but also the establishment of enabling activities on the ground to support the technology uptake (or deployment of the new technology). This can mitigate the perceptions of the public over risks on flammability and toxicity, high pressure and costs of the new product, assuring quick uptake and securing the sustainability of the project results. This is particularly relevant when future prospects of alternative refrigerants to high-GWP HFCs are usually flammable, mildly flammable and/or toxic refrigerants. 2) Successful conversion projects require proper project design, consideration of the necessary product modifications, and the proper allocation of the necessary resources (particularly co-funding and critical inter-institutional coordination). 3) Correspondingly, the selection of experienced experts to support the design, testing and trials phase, as well as experienced equipment/technologies suppliers is highly recommended. This requires proper consideration of re-designing costs, that are strongly recommended to be included in the capital cost components, as well as commissioning of the plants. 4) Considering the flammability of R-600a, we recommend the use of safety audits to verify the safety of the adoption of flammable refrigerants, as well as a budget prepared for it in similar projects. 5) The project also secured a network of service centers/technician with proper equipment, tools and knowledge who are able to service products based on HC-600a refrigerant. This is critical to avoid accidents in usage and maintenance, assuring that the quality of product is maintained, the brand of the manufacturer is protected, and the conversion of the refrigerators is sustained. 6) Safety criteria are critical for the selection of equipment, so it is also critical that the technical specifications take into consideration proper safety standards, certifications and commissioning services. It is important to consider the status of baseline equipment and the eventual needs to align current types and brands (for example, there might be the need for the new equipment to be harmonized with current installed capacities to assure full compatibility and safety systems integration). In this regard, certain level of flexibility on funding allocation can secure overall economies in the project. Moving away from itemization or budget lines, for example, could provide such flexibility. Above all, equipment certification against internationally established standards is fundamental to assure safety. 7) It is noted that the MLF does not have existing Policy(ies) on energy efficiency interventions while phasing-down HFCs. However, the project has clearly demonstrated that certain activities are feasible and will effectively provide larger energy efficiency gains, directly converted into GHG emissions reductions, representing real climate change mitigation opportunities. For example, the adoption of HC-600a inverter compressor in selected models has provided the double of the energy efficiency gains when compared to HC-600a optimized induction compressor. Therefore, further consideration of funding policies to encourage such technical upgrades by providing some incentives, like financial support on redesign of product, prototype production and testing as part of additional incremental costs, is recommended. 8) It is also very important to highlight the importance of inter-institutional relationship between the entities involved in the project. As a lesson learned, open and timely coordination was critical to assure the timeframe of 24 months to be met. A well-coordinated mechanism between the MOEF, UNDP and Walton have been put in place. 9) The Government of Bangladesh provided full support for the conversion, and Walton was able to manage its production schedule to allow the conversion of the lines in a manner that minimal production disruption happened. This stand-alone project increased the confidence of the stakeholders to implement the Kigali Amendment, since the Government is advancing in the ratification steps, sending clear signals to the market about future trend of HFCs phase-down, which granted the buy-in of the whole value chain.
Bangladesh | BGD/SEV/04/TAS/01 |  | Reconnaissance survey and training | SEV | TAS | UNDP | 1) The selection of national consulting firms to implement certain activities can lead to long delays when the fees requested exceed budget allocations. 2) A well done OS data survey is essential to the development of an accurate and realistic MP national Country Programme. 3) Participation at key regional and international meetings and conferences was instrumental in national officials understanding both the issues and the alternative technology options available thereby contributing to the effective formulation of a national Country Programme.
Bahamas | BHA/PHA/71/TAS/19 |  | Verification report on the implementation of the HCFC phase-out management plan | PHA | TAS | UNEP | 1) It is recommended that the NOU strictly follows quotas allocation to registered users (a process of which has been initiated for year 2017) and permits & licences should only be issued against these quotas rather than first come first serve method adopted earlier. 2) It is recommended that the NOU cross-checks their records with importing companies’ data on a regular basis (instead of the annual reconciliation of data based on the survey of the total annual imports per importer), to avoid the difference in consumption quantities coming from computational errors or because some imports are not being recorded. 3) The consultant discarded custom data for consumption verification due to various data discrepancies that were found in the old data provided by the BCED (use of wrong HS codes, different measurement units for quantities of shipments, non-availability of actual shipment dates, etc). 4) It is recommended that the NOU provide additional capacity building to the customs officials so that recording errors are avoided in the future. It is also recommended that a formal communication channel is developed between NOU and the BCED.
Bahamas | BHA/REF/23/TAS/05 |  | Implementation of a National Programme for Recovery and Recycling of Refrigerants (UNDP No. BHA/97/G61) | REF | TAS | UNDP | Generally, the lessons learnt are similar to the experience in other R & R projects. More specifically, these include: Requirement to incorporate more explicit implementation conditions into R&R Project Documents; Requirement to draw up and have signed pertinent completion documents (similar to investment project’s Certificate of Completion and Handover Protocol) and having each participant sign a related agreement, immediately after training and distribution has been carried out; By including provisions in the Project Document, as part of a specific Monitoring Project component, the need to contract a national consultant to carry out monitoring and evaluation of activities. It can be specified that such services are only to be remunerated upon receipt of requisite progress reports; Necessity of having appropriate policy and market mechanisms in place to support such programming. Such a requirement should be a key component of a management plan for the refrigeration sector, as a whole; Neccessity of having continuity in management of programme at national level in order to ensure continuity of all implementation-related activities and sense of national ownership of programming; and, Necessity of having open lines of communication amongst project partners in order that information requests may be properly channelled and feedback recorded.
Bahamas | BHA/REF/23/TRA/04 |  | IMPLEMENTATION OF THE RMP: TRAINING IN MONITORING AND CONTROLLING OF ODSS - Training of Customs Officers | REF | TRA | UNEP | 1) The active engagement of the National Ozone Unit at the regional and national levels is imperative in the successful completion of a RMP. 2) Direct and immediate support and follow-up are required. 3) Periodic letters to the line Minister on the status of implementation of the Montreal Protocol Activists is useful in keeping and maintaining political support. 4) The NOU will establish a monitoring mechanism to ensure that the objectives of the training programme are met and will produce a follow-up report on the status of implementation of the training programme. 5) The National Ozone Unit will consider and, as far as possible, implement the workshop recommendations as adopted by the workshop participants. 6) The recommendations will also be communicated to the relevant decision-makers and politicians, and requests will be made for their support. 7) Given the large numbers of International Sea Ports present in the Bahamas, the recommendation was made for additional refirgerant identifers. Under the Terminal Phase Out Management Plan (with the World Bank) this recommendation can be considered.
Bahamas | BHA/REF/23/TRA/06 |  | Implementation of the RMP: training the trainers of technicians in the refrigeration sector | REF | TRA | UNEP | 1) local weather conditions should be taken into account when planning workshops in the Caribbean region - just before the workshop a hurricane was passing by which had killed people in Nicaragua and Honduras; 2) There were difficulties to identify the training equipment at the customs because the airway bill number was corresponding to the flight to Miami, but not to the flight from Miami to Nassau; 3) the broker has also difficulties to identify the training materials (manuals) at the customs which were shipped well in advance with a direct flight from Paris to Nassau, even though the broker had the airway bill number, flight date and flight number; 4) the instructor of HRAI does not expect that refrigerant recovery bags are widely used when portable recovery and recycling equipment is available. Filled recovery bags are difficult to transport; 5) The instructor of HRAI mentioned that hand pumps for the recovery of refrigerant are not efficient and recommended the use of micron gauges.
Bahamas | BHA/SEV/11/CPG/01 |  | Country programme preparation | SEV | CPG | UNEP | The accurate compilation of data and information is vital. If this is not done, phase out activities and possible projects are not properly identified.
Ethiopia | ETH/REF/26/TAS/06 |  | Refrigerant management plan | REF | TAS | Germany | Regulations: Through the RMP for the 14 countries it has brought forward a view that where the NOU is based in the Meterological Department, it is a considerably greater struggle to get approval for ODS regulations primarily because the ODS regulations do form part of the overall environmental regulations of a country. If the Environment Ministry is not directly involved with the implementation of activities, it appears to be difficult to convince them on the importance of having approved ODS regulations.
Ethiopia | ETH/REF/30/TRA/09 |  | Implementation of a training programme for recovery and recycling of refrigerants | REF | TRA | UNEP | The recovery and recycling machines have been given to 11 institutions. The technicians association is trying to assemble the R&R machines locally.
Ethiopia | ETH/REF/44/TAS/14 |  | Implementation of the RMP update | REF | TAS | France | There were changes in the Ozone officer which also created some confusion and delay in work. The new officer had very limited information on the project activities and it took some time for him to understand how the ODS phase out activities worked. Also he had to work with little to no support from his department. Therefore for certain amount of progress to be made under phase out activities, the NOU has to be a person who has benefited from a proper handover from a previous officer if personnel changes are to take place. UNEP under its CAP programme should try and ensure that this is done so that the new officer is not left struggling.