## tbComment
Code | Secretariat's Comment | Agency's Response | Meeting of report
AFR/SEV/32/TAS/28 | This project is 30 months late and the project is still at a nascent stage, i.e., developing an action plan. With a balance of over US $120,000 left in this project, more harmonization might be done with the utilization of regional CAP staff to advise countries. | The balance is not really US$120 000 because a MoU is already signed with UEMOA and consequently a first payment of US $ 30,000 is done in September 2003. Another MoU between UNEP and CEMAC was signed with a first disbursement of US $ 30,000 in April 2004. | 43
AFR/SEV/32/TAS/28 | This project was approved in December 2000 with a total duration of ------- months. At the 40th Meeting, UNEP indicated that the planned completion date for this regional project was December 2003. At the 41st Meeting, UNEP reported that the MOU was signed and the first payment was made. However, the next meetings are not planned until April and June of 2004. It is not clear what the outcome of the meetings would be or how the project is going to be completed. Nevertheless, the following countries in French-speaking Africa network including Portuguese-speaking countries are in non-compliance with one or more controls: Cameroon, Cape Verde, Djibouti, Guinea-Bissau, Mali, Morocco, Sao Tome and Principe, and Sierra Leone. As no additional activities have been reported and the workshop has been delayed, please indicate if any activities have occurred since the last report or otherwise it appears that there has been no progress. | MOUs for both meetings have been signed and disbursed to the regional groups. Consultants have been hired by the regional groups to compile information on existing regulations and also make recommendations which will be discussed in the two meetings. | 42
AFR/SEV/32/TAS/28 | This project was approved just in 2000 and the first progress report indicates a 6 month delay. Please explain. | The Planned Date of completion in the database was not accurate. The implementation is ongoing as planned. Local consultants are presently being identified and engaged to undertake the implementation of the project. An implementation schedule was discussed and agreed by participating countries during the meeting of the Network Meeting of French-speaking African countries in April 2001. The Planned Date of Completion is June 2002. It is being changed in the database. | 34
AFR/SEV/45/TAS/33 | There does not appear to be any progress since the last report. Would UNEP agree with this statement? If not, why not? | YES | 62
AFR/SEV/45/TAS/33 | In light of the ExCom provision of approval, i.e. to complete the project in 18 months, when are the regulations going to be considered by the ministers to ECOWAS? | It is expected that the draft will be discussed by experts in July and submission to ECOWAS Council of Ministers expected by October. Meanwhile Harmonized ODS regulations have been enacted under this project for for CEMAC (6 Countries), COMESA (20 Countries) and UEMOA (8 Countries; the UEMOA countries are also part of ECOWAS). | 58Final
AFR/SEV/45/TAS/33 | The project was designed to build upon existing inter-regional trade ties within the EAC, ECOWAS and SADC. UNEP remarked to the 52nd meeting that a MOU has been signed with COMESA. COMESA was not referred to in the original project description. The date of completion for the project is June, 2007. Only US$ 70,000 of the US$ 140,000 in total funds approved had been disbursed. What is the status of discussion with the other regional groupings, and has the project been completed by its planned completion date? | COMESA was involved after some consultations and it was found that COMESA comprises SADC and some SACU countries. COMESA was also found to be more relevant as it deals more with trade issues. Discussions with ECOWAS has reached an advanced stage. There were some delays due to structural changes in ECOWAS Secretariat and now there is an officer responsible for environment and this will facilitate the project implementation. By June 2007, the COMESA ODS Regulations would have been approved but there will be a delay with ECOWAS ODS Regulations due to the problems experienced as mentioned above. | 52
AFR/SEV/45/TAS/33 | The ECOWAS Commission's approval was expected by the middle of the year. (a) Has it occurred? (b) If not when in terms of which month will it be approved? (c) What is UNEP's assessment of progress as we see no progress from the last meeting's report? | Approval has not yet occurred and it is espected by the middle of this year. Ministerial Meeting to brief the ECOWAS Ministers on the draft ECOWAS ODS Regulations is planned to be held during the AMCEN meeting. According to UNEP's assesment, there is some progress only that ECOWAS's procedures for approval are long. | 61Delays
AFR/SEV/45/TAS/33 | (a) At the 64th Meeting, UNEP reported that a High level meeting was planned to take place in May 2011 for approval of ODS Regulations. Were the regulations approved at this meeting? (b) Is the Council of Minister's another meeting different from the High level meeting? (c) If so, when is this meeting to take place? (d) If the implementation of project activities has been completed, then why should not the project be considered operationally completed and a date of operation completion provided? | High level meeting refers to Council of Ministers meeting and the meeting did not take place in May 2011. ECOWAS Commission is arranging for that meeting to take place and the dates are not yet known. The project should be considered operationaly completed in December 2010. | 65Delays
AFR/SEV/45/TAS/33 | 1) Is there any activity implemented between the 62nd and the 63rd Meeting? 2) The endorsement of ODS regulations by ECOWAS council of Ministers (not funded by MLF) still pending while all activites have been completed for this project. In this context, shouldn't we consider this project operationnally completed? If yes, what is the completion date? 3) Please specify the category of delay. | 1) No, except continuous reminders to the ECOWAS Secretariat regarding the approval of the ECOWAS ODS Regulation by the council of Ministers. 2) Yes, the project should be considered operationally completed as of December 2010. 3) External Delay | 63
AFR/SEV/45/TAS/33 | How did the implementation of activities begin when no funds were disbursed in 2005 for this 18 month project? | Some start-up activities were implemented as CAP services without necessarily requiring funding from the project. Such activities included compilation of data and relevant reference materials, identification of experts and discussion with ozone officers during network meetings on implementation logistics. The funds from the project will be used for the activities agreed upon during the initial stage described above. | 49
AFR/SEV/45/TAS/33 | We suggest an additional status report for this project to monitor when the ECOWAS Council of Ministers endorses the ODS regulations | ECOWAS Commision is organsing a meeting for Council of Ministers to take place within the 3rd Quarter of this year | 64
AFR/SEV/45/TAS/33 | UNEP reported last year that the agreement with ECOWAS was in its final stages. ECOWAS was part of the original project and we understood that the delay due to internal restructuring had been resolved. Please explain why last year we were near an agreement and this year we are still in negotiations. What is the nature of the current delay? | Efforts are still underway to engage the new Director responsible for Environmental Affairs in ECOWAS. The NOU from Nigeria is also assisting in consultations with ECOWAS Secretariat. A high level mission by UNEP is planned to finalise the process. | 55
AFR/SEV/45/TAS/33 | When was the project completed? | Previous response was related to Sub-regional project in French-speaking Africa. Project in English-speaking Africa is still ongoing. MOU for Harmonisation of regulations was completed in COMESA Region. ECOWAS has drafted the Regional ODS Regulations awaiting for validation by experts in October. The project to be completed by December, 2009. | 59
AFR/SEV/53/TAS/38 | What is left to be done for this project since the customs networks have been established and are operational? | Most activities are undertaken dire tly by UNEP have been implemented and what is remaining is the stregthening of the Focal Points in COMESA, CEMAC, ECOWAS/UEMOA Secretariat with funding received by France. | 58Final
COL/REF/15/INV/11 | The amount of funds disbursed for the INDUCOL refrigeration project in Colombia has been about the same since UNDP’s progress report to the 19th Meeting. At the 20th Meeting, this project was to be completed by 1st Quarter 1997. Then at the 22nd Meeting, completion by December 1997. At the 25th Meeting, completion by 1st Quarter 1998, now February 1999. Was this project completed in February? | Again, our understanding was the progress report was as of December 31st and anything after this date, if needed ExCom attention would be reported. For your information the COC was signed during the Jan 28-Feb 4 mission. | 28
COL/REF/17/TRA/18 | Please explain the reason for the additional 12 months delays. | Awaiting redesign of the project by the NOU in order to utilise the available fund in the most effective way. | 31
COL/REF/17/TRA/18 | This project is delayed by over 30 months, the status indicates the NOU is redesigning the project. Why is the project being redesigned since over US $110,000 of the US $149,100 budget has been disbursed, 3 workshops were completed in May 1996. R&R training took place in July 1996, and through July 1998, 1200 technicians were trained, legislation and licensing was under discussion? | In answer to the point raised the project is being redesigned by the NOU to ensure that the remaining funds (US$39,100) are used in the most effective way. | 31
COL/REF/19/INV/22 | UNDP reported that the Supernordioc refrigeration project in Colombia would be completed shortly after 1st Quarter 1998. Now the projection is for completion by October 1999 even though foam trials are expected to be completed in March 1999. Why will it take so long to complete this project after the foam trails in March since the foam equipment was delivered in 1998. Has the counterpart funding been resolved, yet? | Equipment was delivered but installation, commissioning, and training related to the new OMS high pressure foam machine is pending counterpart payment of a balance of US $ 10,500. UNOPS is negotiating with OMS to go down. Our consultant has planned mission scheduled for July. If this is resolved by then the project can be completed. | 28
COL/REF/19/INV/22 | The progress report indicated that the foam equipment was deliver in 1998, but now the update indicates that it was not installed until September 1999. The project was supposed to be completed in October, but now 1st quarter 2000. Please explain the progress claim. | The factory is forced to move because the Government is building a road through its land. Reallocation problems caused equipment installation delays. Foam machine was installed September 1999 which is why we claimed progress. Then the sensor on the injection head broke and tests could not be conducted. OMS has ordered from Italy the new part and we expect it to be replaced before end Oct-99. | 29
COL/REF/24/PRP/27 | Project preparation account are now classified as project with implementation delays. The project has no disbursement and no comments on what is going to be done with the funds, as well as no planned commitments. | Project information now included as appropriate. | 28
COL/REF/28/INV/34 | Moreover, delays in signing sub-grant agreements appear for more recent approvals in Colombia, this project that has already experienced delays but not 12 months yet according to the Bank's forecast. Please describe the sub-grant agreement signature problems in Colombia and what can be done to remedy this worsening situation. | Problems did not occur due to one issue (i.e. SGA signing), but depended, in some cases, on the enterprise and in some cases on ACCI. All problems have been resolved and we do not anticipate that this situation will continue. | 34
COL/REF/28/INV/44 | Moreover, delays in signing sub-grant agreements appear for more recent approvals in Colombia, this project that is now entering the list of projects with implementation delays. Please describe the sub-grant agreement signature problems in Colombia and what can be done to remedy this worsening situation. | Problems did not occur due to one issue (i.e. SGA signing), but depended, in some cases, on the enterprise and in some cases on ACCI. All problems have been resolved and we do not anticipate that this situation will continue. | 34
COL/REF/34/INV/51 | No remarks were provided for the US $1.3 million project for MAC systems in Colombia that was approved in July 2001. What is the status of the information requested by ExCom as a condition of approval, namely, that the project was approved on the understanding that the Government would indicate the dates by which production of CFC MAC compressors would cease in the country? | Subgrant agreement is been prepared, as well as bids. There are no MAC compressors produced in the country. | 37
COL/REF/35/TRA/52 | Project with Date Completed (Actual) in the 2007 Progress Report that is different from the Inventory (Date Actual). Please verify. | This was mistakenly reported in Canada’s 2005 Progress Reported as completed in June 2005. However, this was corrected to August 2006 in Canada’s 2006 Progress Report, with remarks indicating that one last activity was still ongoing until August 2006. The PCR submitted for this project also states a project completion date of August 2006. | 55
COL/REF/35/TRA/52 | Concerning the customs training project in Colombia, we note that US $67,500 of the US $106,150 budget has been disbursed and the remarks indicate that the project will begin in 2003. For what purpose have the funds been used through 2002? Also, we note that although a delay was indicated, the planned completion date or project duration has not changed. Should not the planned completion date also change? | UNEP is implementing the project in Colombia on behalf of Canada. The US $67,500 were transferred to UNEP in 2002, on the understanding that project activities would begin that year. However, for various reasons, including staffing difficulties within UNEP's Regional Office for Latin America and the Caribbean (ROLAC) and the fact that UNEP did not have a system in place to transfer funds to Colombia, no activities were actually undertaken. In the case of other projects which UNEP is implementing for Canada, our practice has been to report expenditures only when UNEP disburses the funds transferred to it. Therefore, if the Secretariat agrees with this practice, I propose to change the information pertaining to the expenditures for this project to indicate that in fact no money has yet been disbursed. This would provide a more realistic indicator of the status of the project, since a financial transfer from Canada to UNEP is not in itself a sign of progress. Please note also that UNEP has now informed us that within the next month, they will begin transferring funds to stakeholders in Colombia for the organization of the Train-the-Trainer workshop for customs officers. The date of completion has been changed to December 2004. | 40
COL/REF/38/INV/57 | Were the SGAs signed with the participating 17 enterprises commercial refrigeration project in Colombia during the first quarter of 2004? | There will be only one SGA with the executing enterprise, Cabarria. It will, in turn, sign agreements with the remaining 16 enterprises. The terms of reference and all other documents have been prepared in anticipation of the signing of the SGA. A World Bank mission is scheduled to meet with Cabarria the week of May 24-28. | 43
COL/REF/38/INV/57 | If the project is reduced in scope from 17 enterprises to 10 entetprises, might we expect a commensurate return of funds. | There will definitely be a significant return of funds upon project completion which is expected by the end of the year. | 47
COL/REF/38/INV/57 | Please provide the date completed. | Date of physical completion per Dec. 28/2: December 2005 | 48
COL/REF/47/DEM/65 | (a) UNDP's report to the 58th Meeting indicated that the cofiancing had been secured from the GEF through a PIF, it appears that the CEO approval never occurred and UNDP is attempting a different approach. Is my understanding correct? (b) Has the planned completion date of December 2010 changed? | a) We still expect the CEO approval to take place, several exchanges of information and clarifications have been given to the GEF during the final review phase for this project. In the meantime the Government is applying the tax reduction to the chillers owners to facilitate conversion and the National Ozone Unit with assistance from UNDP is calculating the corresponding amount and procuring official documentation from the government to demonstrate that this co-financing is taking place. This will help release funds to start the activities programmed for the project as it will allow release a portion of the approved funding (the Excom condition only allows disbursement in proportion with the cofinance procured). b) Due to the delay obtaining the cofinancing from GEF the completion date should be changed to December 2011. | 59
COL/REF/47/DEM/65 | When is the first disbursement expected or has it occurred to-date? | Jan-2010. | 64
COL/REF/47/DEM/65 | Please provide the most recent disbursment rate available. | To date, USD 51,389 were disbursed. | 66Status
COL/REF/47/DEM/65 | For several projects including this one, UNDP states that associated disbursement would be reflected in 2010. This is understandable for a project that might have been approved in November 2009 or even a project that was approved in April 2009 if the cost occurred in December 2009. However, in several cases when an activity is identified in the remarks on a project, there is usually a disbursement. In this case, no activity that would have been funded is identified in the remarks. Therefore, what is meant by the comment that the associated disbursement would be reflected in 2010, i.e. what would that associated activity that occurred in 2009 be, because any activity that took place in 2010 cannot be disbursed in 2009 anyway? Has the GEF project document been signed? | Excom Decision did not allow disbursement until co financing was procured. Cofinancing was finally obtained with GEF CEO Approval of the associated project for US 1M on October 7 2009. By the end of the year the project was just starting and there were no disbursements. We did not write in the remarks “associated disbursement would be reflected in 2010” because there were not activities for which disbursements should be done; we wrote instead: “GEF and MLF projects are starting implementation. Associated expenditures to take place in 2010” we referred to the expenditures associated to the starting implementation of the project. | 61
COL/REF/47/DEM/65 | Please report on the status of disbursement since the last progress report | The project is under implementation and some funds have been disbursed since the last progress report (US$ 9,500) as an international expert mission took place. | 65Status
COL/REF/47/DEM/65 | What is meant by MSP for the chiller project and since the GEF has approved its part, why has the project not begun? | MSP is the Medium Size Project that corresponds to an approval for less than US1M. The GEF has approved as of now only the PIF which means that the country can now prepare a project (the MSP). Having the PIF approved the cofinancing is secured, however it is not effective until the MSP is approved by the GEF. | 55
COL/REF/47/DEM/65 | What has delayed CEO approval as we note that the project is expected to be completed over a year late? | CEO approval is not delayed. The submission of the MSP took longer than expected as after formulation it had to receive several changes and improvements before submission to the GEF. | 58Final
COL/REF/47/DEM/65 | The decision asked for information on disbursement. Please indicate the estimated disbursement for the project now and explain the difference between the current estimated disbursement and that reported to the 67th meeting for the last reporting period. | Limited disbursement has taken place since the 67th ExCom since a company is being hired to evaluate climate and energy impacts of replaced chillers. The company profile is currently being reviewed and a contract is expected to be signed by November, entailing an obligation to be disbursed in coming months. | 68Status
COL/REF/47/DEM/65 | Please provide the estimated disbursement rate of approved funds. | Estimated amount disbursed and obligated: $205,845 out of 1,000,000 | 69Status
COL/REF/47/DEM/65 | What is the disbursement rate on this project? Has the agreeement been signed for any activities in the project? | No Response. | 71Status
COL/REF/75/DEM/97 | Progress satisfactory |  | 82
COL/SEV/45/TAS/62 | There is very little information provided about the HCFC surveys that were approved in April 2005. (a) No funds were disbursed for any of the surveys in 2005. (b) “Activities initiated” is not very forthcoming as it does not indicate what activities were initiated as is the case for Venezuela (VEN/SEV/45/TAS/102). (c) Consultants identified does not indicate if the consultants were contracted for example as is the case for Lebanon (LEB/SEV/45/TAS/60), Mexico (MEX/SEV/45/TAS/127), Sri Lanka (SRL/SEV/45/TAS/30) and Syria (SYR/SEV/45/TAS/90). (d) The surveys in Argentina (ARG/SEV/45/TAS/144), Brazil (BRA/SEV/45/TAS/271) and Colombia (COL/SEV/45/TAS/62) seems to be at the earliest stage of development or a late stage depending on what is meant by “preparatory work”. If “recruit consultants” means that they have been identified and a contract is being prepared, then this could be at a later stage. Please clarify. (e) There were those where the activities clearly identified such as Indonesia (IDS/SEV/45/TAS/169), India (IND/SEV/45/TAS/391), Iran (IRA/SEV/45/TAS/172) and Malaysia (MAL/SEV/45/TAS/155), but in all cases the surveys are still planned for completion in December 2006, which unfortunately will be after the last meeting of the year which will occur from 6 to 10 November 2006. In the light of this fact, it is likely that any of these surveys could be completed early, for example by 6 to 10 September 2006 so that a report could be provided to the 50th Meeting? | Activities initiated in 2005 included in the negotiations with NOUs and consultants of the TORs for the surveys and determining how the programme would be implemented and results pulled together in a harmonized way. This demanded a lot of consultation and design work of the type of surveys to be conducted and information to be gathered. CVs were collected in 2005 as well but no contracts were in fact issued in 2005. As of 18 May 2006, contracts have now been issued with the international consultants, and with the national consultants in ARG, BRA, COL, IND, MEX, SYR and VEN. Remaining contracts with National Consultants will be issued by the end of May for INS, IRA, LEB, MAL and SRI. Each study will consist of a desk study followed by the survey itself. Reports resulting from the desk studies were already received for ARG, BRA, COL, MEX, SYR and VEN. These were commented upon by the international consultant and the surveys themselves are now being initiated in these countries. UNDP would propose that a status report be prepared by the deadline for the 50th ExCom meeting on the progress in all these countries. However it is unlikely that any report will be final at that time (11 Sept) which is partially due to the very early date that the 49th ExCom meeting would be held. We will add this information in the narrative. | 49
COL/SEV/45/TAS/62 | Please indicate the date of completed. We do not need the date of financial completion, now. | Submitted to ExCom 51st Meeting. Technically completed in march 2007. Financial obligations being dealt with. Unobligated funds as of 31 Dec 2007 to be returned to MLF | 56
COL/SEV/45/TAS/62 | (a) Why should not the funds for the HCFC survey (about $42,000) be returned since the surveys were completed and submitted at 51st ExCom? (b) What is meant by data verification and additional stakeholder consultation pending? | 10 HCFC surveys delivered to 51sts meeting and 2 to the 52nd meeting. For the work done, the payments still pending will be liquidated in 2008. As far as the remaining unspent funds, UNDP at first thought of the possibility to use the balance for some additional stakeholder consultation and data verification for some countries where clarifications were needed. In view of the new guidelines approved for HPMP and the fact that detail sector information will be neededas well as stakeholder consultations, UNDP agrees the proposed above would be double counting . Therefore, UNDP will settle the account and return the unspent balance, as of 31st December 2007, to the MLF. | 55
COL/SEV/58/INS/73 | Please indicate if the relevant project document/MOU/grant agreement has been signed, if all reports have been provided, if any delays occurred in the transfer of funds, and if any delays occurred in planned activities. | Yes, ProDoc was signed and activities are being implemented according to the plan. | 64
COL/SEV/70/INS/83 | Please provide the estimated disbursement for the current year. | The estimated disbursement for this project in 2014 is $110,240. | 73
COL/SEV/74/INS/90 | Project delayed : (a) when is the project expected to be completed noting that planned completion should be by June 2017 (latest). | The project should be completed by Oct according to the title. There is always a 6 month overlap between two IS phases, and the same is the case here. | 82
COL/SEV/74/INS/90 | 2 ongoing projects | There was a small balance of the previous phase. | 77
COL/SEV/75/TAS/99 | The report was already submitted, will the balance be returned to the 80th meeting? | The final report was submitted and related budget completely disbursed. Therefore, no balance will be returned to the 80th meeting | 79
COL/SEV/79/INS/101 | (a) When is the first disbursement achieved. | The first disbursement took place in 2018. | 82
COL/SEV/79/INS/101 | In line with 84 Excom decision, balance funds need to be returned for the previous phase. | Most of the fund have been used, balance will be returned as existing policy. | 88
COL/SEV/80/TAS/01+ | Progress satisfactory - (a) what is the expected date of first disbursement. | The first activitiy of the Eas was a regional meeting in Panama that took place in May 2018. Funds from the Eas were used to cover the cost of participation of the country. | 82
COL/SEV/80/TAS/01+ | 1. Please confirm when the project can be completed. 2. If not please clarify if you need extension (to mm/yy) and what activities would be completed during this period. | The Government of Colombia would like to request and extension to June 2021; During the extension period it is planned to complete consultancies to collect the information on priority sectors for HFC phase down, to undertake consultation meetings with stakeholders to discuss the elements of the HFC phase down strategy. | 86
COL/SEV/80/TAS/01+ | Progress - please confirm if the project is complete | Project is completed. | 88
COL/SOL/31/INV/45 | Moreover, delays in signing sub-grant agreements appear for more recent approvals in Colombia, this project was approved in July 2000 that has already experienced delays but not 12 months yet according to the Bank's forecast. Please describe the sub-grant agreement signature problems in Colombia and what can be done to remedy this worsening situation. | Problems did not occur due to one issue (i.e. SGA signing), but depended, in some cases, on the enterprise and in some cases on ACCI. All problems have been resolved and we do not anticipate that this situation will continue. | 34
COL/SOL/31/INV/45 | Has the SGA been signed for this project? | The subgrant agreement with Rymco was signed on April 30, 2002 and became effective on June 11, 2002. | 40
COL/SOL/31/INV/45 | We agree with the designation of some progress for this project. | No comment. | 43
COL/SOL/31/INV/45 | No funds have been disbursed for this project that was approved in July 2000. The sub-grant agreement is now forecast to be completed in May, yet the planned date of completion is still December 2002. This seems understated since the project was supposed to be completed in 2 years. Please reassess this date as you know such dates determine if the project is delayed and requires additional monitoring. Therefore, accurate assessments are needed for this system to function properly. | Planned completion date revised. | 37
COS/FUM/29/PRP/21 | For the methyl bromide project preparation in Costa Rica, the project was approved in November 1999 but the remarks indicate that implementation modalities for the preparation of this project are still being discussed with FAO. Moreover, France's progress report database does not indicate any planned disbursement in 2001. Please clarify the difficulties with the implementation modalities because the planned completion date in the progress report (December 2000) has already passed. | Please note that, after one year of negotiation due to incompatibilities rules between FAO and AFD, the Agreement between FAO and AFD was signed only in April 2001. Under this contract, AFD will provide FAO with Euro 25,300 to for the formulation of the project. Therefore, this amount should be disbursed n 2001. Formulated project should be submitted in November 2001 or March 2002, the latest. | 34
COS/FUM/35/INV/25 | What milestones were achieved in the multi-year agreement MBR phase-out plan in Costa Rica. What milestones will be achieved between the 40th and 41st Meetings? | The milestones set for this multi-year project are annual in nature and clearly spelled out in the project's Agreed Conditions. As has been previously reported, both through the UNDP-MLF Secretariat channel, as well as directly to the ExCom, this project has not begun implementation in earnest (indeed, the project document remains unsigned) due to national political and economic considerations that surfaced post-project approval. UNDP HQ and Country Office have been working closely with the Government of Costa Rica and private sector stakeholders in order to work to resolve outstanding concerns. At the 39th Meeting of the ExCom, UNDP presented the MLF Secretariat with a letter from the Minister of the Environment of Costa Rica that reiterated the country's interest in this project and their commitment to their targets under the Montreal Protocol. It is expected that if the stalemate remains unresolved prior to the 41st meeting, a modification to the project structure, or perhaps cancellation, will be requested. | 40
COS/FUM/35/INV/25 | The first tranche was approved in December 2001. Although the project was delayed earlier due to concerns of participants, the project was launched in 2003. Only US $64,752 of the US $1.2 million approved for this project was disbursed through 2003. | Noted. Detailed information on the latest achievements is provided in the Progress Report submitted to the 43rd Executive Committee Meeting. | 43Final
COS/FUM/35/INV/25 | Newly approved therefore, there was no activity reported. What is the current status up to today? We note that Costa Rica's 2000 consumption was 390 ODP tonnes which was a reduction from its highest ever consumption of 455 ODP tonnes in 1999 The 2000 consumption is however below the baseline of 434 ODP tonnes. | The project was officially launched in early March 2002, a work programme was endorsed and terms of reference to engage the national project team were drafted. However, technical implementation has been delayed as a result of the following: 1) federal elections held in early April resulted in a change in Government that took office in early May. It is vital to the success of the project that the new Gov't endorse the project's objectives. UNDP/MPU and UNDP-Costa Rica are actively working with the NOU to bring the new Ministers of Environment and Agriculture on board. UNDP-Costa Rica's Resident Representative is playing an active role from a policy perspective by maintaining an open dialogue with senior gov't officials and key stakeholders from the agricultural sector. 2) Growers in the melon sector are being actively lobbied by US proponents advocating continued MeBr use, and have been informed by these lobbyists that Costa Rican competitiveness may be adversely affected should rumors in circulation come true that critical use exemptions expected for MeBr in 2003 will be actively sought by US growers. 3) In addition, concern has also been expressed by melon producers that other countries in the region, Costa Rica's competitors from a market perspective, have terminal MeBr investment projects under development whose reductions targets may not be as stringent as Costa Rica's. | 37
AFG/PHA/47/INV/06 | What is the status of the CTC awareness-raising workshop? | The only user of solvents is Toyota Service company which reduced its consumption from 220kg to 45 kg in due to import control from the government. Further discussions with the company convinced the company owner to stop further use of CTC and to switch over to water cleaning system. In this manner NOU already achieved complete phase out of the use of CTC in the country through Government action, without involvement of investment funds sanctioned for ODS phase out of Solvents. Hence, there is no further use of CTC in Afghanistan to be reported for the year 2007 onwards. | 55
AFG/PHA/47/TAS/05 | Are any halon activities planned as part of UNEP's NPP activities? | No halon phaseout activities are included as a part of UNEP's NPP activities. | 55
AFG/PHA/47/TAS/05 | Although several activities have been undertaken, please explain why the agreement is now expected to be completed 12 months later than expected in last year's progress report in terms of the reason for the delay. | The main reason for the delayed activities has been worsening of the security situation in the country in 2009 wherein the remaining workshops could be organized. For 2010, UNEP has collaborated with NEPA and Customs Department and the remaining training programmes are being planned for organization before the end of year. | 61MYA
AFG/PHA/48/INV/07 | How will halon be treated in terms of the NPP activities? | As the halon consumption was already very low at the time when the NPP proposal was written (19.2kg in 2004) and the projection was to decrease than to increase, activities for halon sector were not prioritized under the budget which was also for the R&R and foam sector. It is possible with that with the left budget – assuming NOU agrees – a training could be organized. | 55
AFG/PHA/48/INV/07 | Is there a particular reason why there have been more funds disbursed for the second tranche of the Afghanistan NPP (AFG/PHA/48/INV/07) than for the first tranche (AFG/PHA/48/INV/06)? | This development is due to the particular use of the funds: the 1st tranche is mainly used for technical assistance. The 2nd tranche is used mainly for equipment. A large equipment purchase and delivery has just been completed. | 52
AFG/PHA/55/PRP/09 | a) What is the status of the licensing system/regulations/legislation update for HCFCs? b) Please indicate when the legislation/regulation/licensing system will be updated. c) Was the HPMP completed in March 2010 as planned? d) Noting that the Prep project was approved in July 2008, kindly justify the delay. | a) The overall ODS national regulation covers HCFC, but the licensing system does not include HCFC yet. b) The country is currently working to revise the licensing system to cover HCFC. Timing of its completion will be by mid of 2010. c) It will be completed by mid of 2010 as the planned submission will be to the 62nd ExCom. d) Security situation in the country as well as the finding of foam production. | 61
AFG/PHA/63/INV/13 | The report does not address the issue raised in the request, i.e., low disbursement. Based on the report, it appears that there was no disbursement. Please indicate the estimated disbursement for the project now and explain the difference between the current estimated disbursement and that reported to the 67th meeting for the last reporting period. | The low disbursement is due to the specific travel restrictions in the project area that is crucial for the agreement with the beneficiary. However, preparatory works have been initiated and the NOU is very supportive in reaching the agreements. Part of the funding is already committed and will be disbursed until the end of 2012. Until now only advance payments for travel and work and miscellaneous costs of 5000 USD have been disbursed.. | 68Status
AFG/PHA/63/INV/13 | Please submit (a) the progress report, (b) IA assessment on project implementation "Progress, Some-Progress, No-Progress" and (c) the category of delay. | Since the last meeting procurement activities have been agreed and initiated. Selection of supplier and delivery of equipment is planned for mid 2013. A detailed progress report has been submitted to the 69 th meeting. | 69Status
AFG/PHA/63/INV/13 | Funds disbursed is less than 10% for this project approved more than a year ago. Please explain. | Activities completed: the local institutions were identified, draft documents were completed, documents were signed, the TOR for purchasing are completed, first disbursement has been initiated, the consumption target has been met. Because of the accessibility and travel restrictions to the project site the exchange with beneficiaries has delayed the project implementation. | 70
AFG/PHA/63/INV/13 | Could GIZ provide more details on reason for the delay and indicate whether or not this will impact the planned completion date? | Main reason for the delay is the difficult security situation in the country. For no security system is in place and funded by the MLF it is currently very difficult to send experts to Afghanistan. As an alternative, activities were planned in neighbouring Iran boarder regions which could not be implemented for lack of suitable nomination from the country. It is currently not possible to assess with certainty whether this delay will impact the completion date. | 73
AFG/PHA/63/INV/13 | (a) Is the transfer only related to the conversion of Qasr Yakh, or the entire Germany component including recovery and reclamation? (b) Is the transfer to UNEP? (c) How much funding will be transferred? | (a) The transfer is still under discussion. (b) The transfer is still under discussion. (c) Since no decision has been made when or if the project will be transferred, the exact amount can’t be determined at the moment. | 75
AFG/PHA/63/INV/13 | 1) Despite the fact there has been training and missions, the 2014 progress report indicated that discussions were to take place about a transfer at the 35 OEWG, what was the outcome of those discussions and why has not a transfer or cancellation been proposed as the project has been dormant for several meetings now? 2) Is it possible for Germany to purchase equipment and deliver to Afghanistan? 3) The project was originally approved as investment to assist the phase-out in refrigeration ans air-conditioning assembly enterprises. It involves enquipment purchase and training with design, installation, operation and maintenance. It would be difficult for UNEP to conduct this job. Therefore we suggest implementing according to what we agreed at the 72nd meeting, i.e. Germany to purchase the equipment and hire consultant who could be managed by UNEP in Afghanistan. Do you concur? | No Response. | 76Status
AFG/PHA/63/INV/13 | (a) When is the discussion expected to be completed and the project transferred? To which agency? (b) Will the project be completed by Nov 2016 as originally planned? If not, what is the updated planned completion date? (c) These discussions have continued for some time. Perhaps the project should be cancelled until such time that circumstances permit its implementation. | (a) Discussion is ongoing and NOU Afghanistan has not yet made its decision. Preliminary talks suggested UNEP should step in. However, it still needs to be clarified whether this INV project could be transferred to UNEP. (b) Transfer should be completed by November 2016 (ExCom 77). | 77
AFG/PHA/63/TAS/12 | For the “HCFC Phase Out Plan (Stage I)”, what specific activities are planned for 2012? | The specific activities for 2012 are; Stakeholder consultations for finalising draft quota system and strengthening licensing system;Consultation for registering and limiting the HCFC importers;ToT Workshop for Policy and Enforcement with the updated training manual; Procurement of Identifiers for Customs and relevant centers; Development of certification system by the NOU with the cooperation of relevant stakeholders and parties; Train the Trainers workshops for Service technicians with the updated training manual; Producing Print material (leaflets, pamphlets, booklets, etc) with Stakeholder Engagement/Workshops and Media Campaign;Capacity building programme in Refrigeration Union and providing knowledge support for developing good practices in Refrigetaion servicing sector,Capacity building in vocational training centers to integrate good practices training elements into their training programmes for refrigeration technicians | 67MYA
AFG/PHA/63/TAS/12 | Please provide reason for modifying planned completion date. | The country was unable to open a bank account to facilitate the transfer of funds. UNEP explored the possibilities to work with UNDP Kabul. UNEP is working with the country on an agreed UN approved mode of payment. | 75
AFG/PHA/72/INV/17 | Has the procurement of equipment started? If yes, please provide the status. If no, please provide reason for delay. | Procurement not yet started. We are awaiting results of the investigation of a company for replacement of Qasar Yak. | 75
AFG/PHA/72/INV/17 | 1) Despite the fact there has been training and missions, the 2014 progress report indicated that discussions were to take place about a transfer at the 35 OEWG, what was the outcome of those discussions and why has not a transfer or cancellation been proposed as the project has been dormant for several meetings now? 2) The project was originally approved as investment to assist the phase-out in refrigeration ans air-conditioning assembly enterprises. It involves enquipment purchase and training with design, installation, operation and maintenance. It would be difficult for UNEP to conduct this job. Therefore we suggest implementing according to what we agreed at the 72nd meeting, i.e. Germany to purchase the equipment and hire consultant who could be managed by UNEP in Afghanistan. Do you concur? | No Response. | 76Status
AFG/PHA/72/INV/17 | (a) When is the discussion expected to be completed and the project transferred? To which agency? (b) Will the project be completed by Nov 2016 as originally planned? If not, what is the updated planned completion date? (c) These discussions have continued for some time. Perhaps the project should be cancelled until such time that circumstance permit its implementation. | (a) Discussion is ongoing and NOU Afghanistan has not yet made its decision. Preliminary talks suggested UNEP should step in. However, it still needs to be clarified whether this INV project could be transferred to UNEP. (b) Transfer should be completed by November 2016 (ExCom 77). | 77
AFG/PHA/72/TAS/16 | Why is this not shown as "COM" given that project is completed. Why is there undibursed balances (about US $63000). | We cannot put COM because of the error in UMOJA. It is a technical problem in UMOJA made during the transition from IMIS. The first payments are shown as paid twice and the system does not allow to make the remaining payments due to overdraft. The problem | 82
AFG/PHA/72/TAS/16 | Why did UNEP need to review the modality for fund transfer? Is this review for all project or only for Afghanistan? Was this related to the security in Afghanistan? | (a) The country was unable to open a bank account to facilitate the transfer of funds. UNEP explored the possibilities to work with UNDP Kabul. UNEP is working with the country on an agreed UN approved mode of payment. (b) The mode of payment is being reviewed for Afghanistan at this stage. (c) Related to challenges of implementation of a project in a situation of limited institutional mechanisms for the management of a project of this kind that is country driven and applied through national procedures. | 75
AFG/PHA/72/TAS/16 | Please confirm that the bank account was opened to facilitate the transfer of funds | The country is not able to open the bank account. UNEP transfers funds through UNDP Kabul to the authorized official of the Ministry. The Ozone Officer is on extended sick leave and UNEP currently works with an interim officer. | 76Status
AFG/PHA/72/TAS/16 | (a) Any actions taken to have a new Ozone officer in place? (b) Will the project be completed by Nov 2016 as originally planned? If not, what is the updated planned completion date? | (a) Mr. Ahmad Samim Hoshmad, PMU coordinator is acting as an Ozone Officer for the last 5 months. NEPA is recruiting a PMU Coordinator at present. (b) HPMP tranche II SSFA is expiring in December 2017 and project will be completed based on new planned date of completion as reflected in PR. | 77
AFG/PHA/77/INV/20 | Progress seen but not adequate - limited disbursement in last 1 year after approval in Nov 2016: (1) when will the equipment be procured for the institutions. (2) when will the training programs and other activities relating to this project be completed. (month/year) | The MOU between National Environmental Protection Agency and the Ministry of Labor has been drafted and received by the Ministry. The signature on the MOU will allow the next step to furbish the designated Afghan-Korean Institute (AKI) for strengthening i | 82
AFG/PHA/77/INV/20 | Progress reported - why is the disbursement low? If it relates to payment for equipment/services, when is the payment expected (month/year)? | The equipment is almost to be shipped and the current estimated date of arrival is Nov 2019. Disbursements will be reflected upon delivery and installation. Funds are obligated. | 84
AFG/PHA/79/INV/22 | Project delayed. No disbursement in 6 months. Progress seen but not adequate - limited disbursement in last 1 year after approval in Nov 2016: (1) when will the equipment be procured for the institutions. (2) when will the training programs and other activities relating to this project be completed. (month/year) | The MOU between National Environmental Protection Agency and the Ministry of Labor has been drafted and received by the Ministry. The signature on the MOU will allow the next step to furbish the designated Afghan-Korean Institute (AKI) for strengthening i | 82
AFG/PHA/79/INV/22 | Progress reported - why is the disbursement low ? If it relates to payment for equipment/services, when is the payment expected (month/year)? | The government informally plan to establish a vocational center in another city, Herat. This budget is set aside to assist the center to be equipped with low GWP servicing equipment. | 84
AFG/PHA/79/INV/22 | Progress - stage I extension approved in 87th meeting upto Dec 2022 | Noted | 88
AFG/PHA/79/INV/22 | Project delayed - political sitatuion; to be discussed | Noted. | 91
AFG/PHA/79/TAS/21 | Progress - first disbursement made in June 2018 after SSFA signature (March 2018) | The first payment made in April 2018. | 82
AFG/PHA/82/PRP/25 | New project - what does the equipment procurement relate to as this is a PRP project? | The comment was given for the above Afghanistan project. PRP ToR has been drafted. NOU has posted job descriptions for national consultants for UNEP components. UNIDO will engage the same consultants if relevant for the project preparation. | 84
AFG/PHA/82/PRP/25 | When is the project expected to be financial completed - the stage II is already submitted. | Grant will be closed and funds returned, if any, in line with decision 77/8(f). | 88
AFG/PHA/85/INV/28 | Progress - stage I extension approved in 87th meeting; when is the first disbursement expected | The National Ozone Officer as well as the Director General of the National Environmental Protection Agency have left the country. The project will be on hold until UNIDO receives an official communication from the National Ozone Officer who will likely ne | 88
AFG/PHA/85/INV/28 | Project delayed - political sitatuion; to be discussed | Noted. | 91
AFG/PHA/85/INV/30 | Progress - stage I extension approved in 87th meeting; when is the first disbursement expected | First disbursement occurred in February 2021. | 88
AFG/PHA/85/INV/30 | Project delayed - political sitatuion; to be discussed | Noted. | 91
AFG/PHA/85/TAS/27 | Please provide information on funds transferred under the agreement. Extension given in 87th meeting | No Response | 88
AFG/PHA/85/TAS/27 | To be discussed - political situation challenging | As per the 87th ExCom, the completion date of the HPMP stage I for Afghanistan including this tranche was extended until 31 December 2022. Following lengthy complicated procedure of signing two legal agreements, SSFA with the government and UN2UN agreement with UNDP Afghanistan for fund transfer were signed. UNEP released the payment to UNDP Afghanistan on 14 May 2021. Following the fund transfer, the delayed payments to the PMU staff and contracted consultants under HPMP projects were partly covered and the NOU initiated some of the planned activities. However, all of the activities have been halted since August 2021 due to the political changes in the country. Both SSFA and the UN2UN agreement expired in December 2021 and could not be extended. The fund has been disbursed to UNDP Afghanistan under UN2UN Agreement. The balance will be returned by UNDP to UNEP, which will be further returned to MLF. UNEP is in the process of project closure and the return of balances from the UNDP Afghanistan Country Office. | 91
AFG/PHA/85/TAS/29 | When is the agreement (UN2UN) expected to be approved. | No Response | 88
AFG/PHA/85/TAS/29 | To be discussed - political situation challenging | Following the signing of both agreements, SSFA with the government and UN2UN agreement with UNDP Afghanistan, UNEP could release the payment to UNDP Afghanistan only in early August 2021 after the agreement had to be amended on 25 Jul 2021 due to change in Recipient Agency's bank details. Following the fund transfer, the delayed payments to the PMU staff and contracted consultants of HPMP projects were partly covered and the NOU was initiating some of the planned activities. However, all of the activities have been halted since August 2021 due to the political changes in the country. Technically the no-cost SSFA will expire in June 2023, however, UNDP Afghanistan informed UNEP on 07 February 2022 that the UN2UN agreement was terminated with immediate effect. UNEP is in the process of the return of remaining balances from the UNDP Afghanistan Country Office and UNEP will hold the funds until further notice. | 91
AFG/SEV/43/INS/01 | Please indicate if Afghanistan has provided outstanding base year data and baseline data per Decision XVI/18 and what is the status of the licensing system per Decision XVI/32? | Afghanistan has conducted the survey and is in the process of analyzing data collected. They will submit the baseline data subsequently. The draft licensing system has been prepared and is undergoing review process through various relevant Ministries. | 46
AFG/SEV/53/INS/08 | This is a critical year for institutional strengthening since the 1 January 2010 phase-out is quickly approaching. One of the major emphases of the review of this year's progress reports is INS. (a) Which institutional strengthening projects are not operational and what could the Executive Committee do to facilitate them becoming operational? (b) How can all of the funds have been disbursed as at 31 December 2008 if the planned completion date is November 2009? | Funds have been disbursed through a funding agreement. | 58Final
AFG/SEV/58/INS/10 | (a) Please indicate if all reports have been provided, if any delays occurred in the transfer of funds, and if any delays occurred in planned activities. | All reports provided in time, no delay for this project. | 64
AFG/SEV/74/INS/18 | Incorrect disbursement data | The SSFA is in place effective from 25 July 2016. The first payment was made. Please, kindly refer to the progress report 2016 version of 24 May 2017. Disbursements will only be reflected upon receipt and recording of expenditure report from the country. After the country sends the expenditure report to UN Environment, it will be recorded in UMOJA (this is new UMOJA system requirement). | 79
AFG/SEV/74/TAS/19 | Please provide submission date of the ODS alternatives survey. | May-17 | 79
AFG/SEV/74/TAS/19 | (a) What is the reason for the delay and has that issue been resolved since it has a September 2016 planned completion date? (b) Will it be possible to complete the project and submit the report to the 78th meeting? | (a) There was a delay in signing the SSFA. The SSFA is signed and the first payment has been released in September 2016. NOU has hired the consultant and first workshop is planned in October 2016. (b) The project report will be submitted as planned. | 77
AFG/SEV/80/INS/23 | Progress - Please provide details of funds disbursed in 2018 after SSFA signature. | 1st payment of 47,500 made and 2nd payment of 43,000 is currently being processed. The expenditure recorded in UMOJA is 42,965USD | 82
AFG/SEV/81/TAS/01+ | Please clarify if project activities can be completed by Jan 2021. | In light of the implementation time loss due to COVID-19, NOU is requesting 6 months exceptional extension (to 31st July 2021) to complete the project activities. | 86
AFG/SEV/81/TAS/01+ | Project complete |  | 91
AFG/SEV/87/INS/31 | To be discussed - political situation challenging | Approved at the 87th ExCom in July 2021. The political situation changed in August 2021. The SSFA could not be processed yet as there is no counterpart signer from the Afghanistan side. No SSFA and/or UN2UN Agreement initiated. The approved funding can be returned. | 91
AFR/DES/68/TAS/41 | Noting that the French bi-lateral contribution is implemented through UNIDO and that all funds have been released by France to UNIDO, could France provide its comment on the implementation progress of this project? | No Response. | 73
AFR/FUM/27/TRA/23 | Fumigation project with FAO: The comment is usually MOU with FAO and cash advance given to them but not financial reports have been received. Doesn't the MOU require progress reporting, if not, why not? | The text contained in the project is the following: "MOU with FAO agreed, cash advance given to them, but no financial reports have been received hence low disbursement. Work Plans have also already been agreed with FAO, and most of these activities will be implemented during the first quarter of the year. No progress reports received yet from FAO as MOU signed late in 1999." | 31
AFR/FUM/27/TRA/23 | Based on the remarks, it appears that there may be a project overrun, because of the US $80,000 approved for the project, US $10,000 has been disbursed and US $30,000 is planned to be committed and the remarks indicate what appears to be additional costs of US $75,000 from FAO. Please clarify. | No cost overruns are expected for this project. The cost indicated in the remarks column is that which has to be transferred to FAO (who is implementing the project jointly with UNEP). This cost is from the original US$ 80,000 and there are no additional costs. | 34
AFR/FUM/34/TRA/28 | One of the objectives of the workshop on methyl bromide activities in Africa is to assist countries to meet the 2002 freeze and the project had a completion date originally of 12 months from its July 2001 approval. The comments indicate that the implementation was rescheduled for 2003 due to transfer to regional MBR officer. This project was pre-CAP and funds from CAP are not to be used to implement the ongoing activities. The remarks last year indicated that the first disbursement was due in January 2002 so please explain that expectation without an MBR officer in place if that was the case. | Arrangement for organisation of the workshop started in 2002 by former OzonAction team and the RNC. Process for compiling necessary information on demonstration project started at that time. The process was slowed down with the appointment of OZAT staff in charge of the project to SEAP region as Methyl Bromide Officer. RNC is still in charge of the project in the region for 2003 but involvement of new CAP Methyl Bromide Officer is for training purposes for the Officer. Project will be completed in 2003. | 40
AFR/FUM/34/TRA/28 | This project has been delayed again until March 2004. At the 40th Meeting, the planned completion date was September 2003. At the 41st Meeting, the planned completion date was November 2003. One of the objectives of the study was to assist with the 2002 freeze. This project is critical to the compliance of low-volume consuming countries in French-speaking Africa including Cameroon that was found to be in non-compliance (Decision XV/32), and Cote D'Ivoire's latest reported consumption is about the freeze. As no additional activities have been reported and the workshop has been delayed, please indicate if any activities have occurred since the last report or otherwise, it appears that no progress has been achieved. | MOU was signed by the Government of Senegal on 13/02/04. Workshop for French-speaking Africa to be held as scheduled 8-10 March 2004 in Dakar, Senegal. | 42
AFR/FUM/34/TRA/28 | This project has experienced progress and should be removed from the list of projects with implementation delays. | Noted. | 43
AFR/FUM/38/TAS/32 | Given the number activities conducted for the regional phase-out strategies in methyl bromide in Africa, please explain the low level of disbursement for this project (US$18,356 of US $550,000) that was approved in November 2002. By contrast, the halon banking project in French-speaking Africa appears to be moving forward based on the level of disbursement and the activities underway (AFR/HAL/37/TAS/31) and all participating countries have signed contracts. | The low rate of disbursement is due to the fact the national contracts with the countries were still being finalized in late 2003 and will be signed in early 2004. The value of the contracts once signed will be over USD150,000. Technical survey missions in 2003 lead to equipment technical specifications and mission will occur in early 2003. Project on track. | 43Final
AFR/FUM/38/TAS/32 | With respect to the statement that efforts in Angola, Ethiopia and Somalia (and also Swaziland) have ceased and UNEP CAP has been advised in order that future needs may be addressed through CAP", is UNDP canceling this part of the project and will there be any return of funds? | UNDP is not cancelling this part of the project. Rather, the balance of funds that were expected to be associated with implementation of certain activities will, upon project completion be returned to the MLF. | 53
AFR/FUM/38/TAS/32 | Note: Since this project was approved over 3 years ago, the assessment must be some progress at best. | We agree with the MLFS recommendation of "some progress". | 57
AFR/FUM/38/TAS/32 | (a) Please provide the expected date of equipment delivery; (b) When will the project be completed? | (a) There is an on-going discussion with the supplier over their quote for an item. 6 units were requested and they claim they quoted only for one. This discussion has delayed the delivery. We estimate that the equipment will be delivered by mid 2012 the latest. (b) As soon as the equipment is delivered, as there are no activities planned any more. | 66Delays
AFR/FUM/38/TAS/32 | Regional methyl bromide project in Africa, in both last year’s progress report and this year’s progress report, UNDP has had a comment “For 20% A5” or “20% countries”. (a) Does this mean that 20% of the 24 countries have completed their surveys, completed their work plans, and received equipment? Also, we note that this 20% was reported to the 43rd Meeting. (b) Does this mean that the only additional progress since that meeting was activities in Swaziland and PR Congo and the agreement to a shift in execution strategy? | Of the 24 countries participating in the project, 5 must achieve a 20% phase-out reduction. Decision 38/26 of the ExCom approved the “Technical assistance for methyl bromide reductions and formulation of regional phase-out strategies for Low-Volume Consuming countries in Africa” with, inter alia, the following caveats: (c) The project will provide technical assistance to achieve methyl bromide reductions to meet the 20 per cent reduction step in Congo, Democratic Republic of Congo, Nigeria, Sudan and Swaziland, without further assistance from the Multilateral Fund for the said 20 per cent reduction; (d) The project would also provide assistance to countries to put in place appropriate mechanisms to reduce and eventually ban imports of methyl bromide; and, (e) UNDP would request all the governments participating in the project, except those in paragraph (c) above, to submit letters indicating their understanding that in accepting this project they would not return for further methyl bromide funding in future, as per the terms of the revised methyl bromide strategy and guidelines. As per Decision 46/16, a Progress Report was submitted to the 48th Meeting of the Executive Committee that outlines progress achieved during 2005. | 49
AFR/FUM/38/TAS/32 | (a) What is the status of the silo modification that was mentioned in the last status report on this project? (b) Is there an agreement with Sudan to substitute the silo modification for training materials? (c) What is the basis of UNDP's assessment of "No Progress"? | a) the silo has not been modified; b) no such agreement has been reached as of yet; c) in view of the above, UNDP was unable to assess the progress differently at this time. However our consultant informs that more detailed information will be available in a few weeks time, which we could share at ExCom if asked for. | 61Delays
AFR/FUM/38/TAS/32 | How can the project be completed by the end of 2011 if a contract has just been issued to implement activities that appear to be at initial stage of completion? | The activities scheduled are safety workshops, practical trainings and developing a technical brochure. Three locations have already been identified and the workshops are scheduled before year end. The practical trainings will take place at the same locations and the brochure will be distributed during these events. All this has been scheduled to be completed before year end. The only activity that might not be completed before year end is the delivery of some accessories for phosphine treatment. | 65Delays
AFR/FUM/38/TAS/32 | (a) This is the same report as was submitted to the 54th Meeting. Has there been any progress since this last report? (b) The remarks indicate that 5 of the LVCs had completed their stakeholder policy dialogues as at the end of 2007. Which countries are these and which countries have not yet responded? | 5 countries had completed their stakeholder policy dialogues at the end of 2007: Mauritania, Gambia, Comoros, Niger, Zambia And 3 countries have not yet finalised the legislation update activity (but all of them already received first payment and national consultants have been hired) : Benin, CAR and Djibouti. National survey has been organised in DRC to evaluate and locate the methyl bromide consumption and to identify the major users. | 55
AFR/FUM/38/TAS/32 | There is still a low rate of disbursement for this project (32% disbursed with only $20,000 obligated). It is not clear what progress was made in 2004 since the remarks for 2003 and 2004 are similar. Was the training mission different from the survey missions? What is the significance of technical experts being identified--what is next for these experts? MB alternatives were indicated as having been chosen both years. National contracts issued were also reported 2 times. What are the remaining technical missions and is there some breakdown on the status of each country in the event one falls into non-compliance? | Please note that full Progress Report on this project's implementation was submitted to the MLF Secretariat for consideration at ExCom 46. In response to specific questions: The survey missions helped the countries clarify where consumption existed and for what uses. The training mission involved preparation of equipment specifications and laid out a training programme. The technical experts identified have been contracted to prepare equipment specifications and conduct in-field trainer-the-trainers programmes, working in close cooperation with national agricultural experts. With regard to the last questions, implementation delays have been experienced, as explained in the aforementioned Progress Report. These have been due in large part to difficulties in communicating with partner countries (non-responsiveness) and in transferring funds for national contracts. | 46
AFR/FUM/38/TAS/32 | (a) All of UNDP's ongoing methyl bromide projects seem to be progressing based on the remarks in the progress reports including the regional project, with the exception of Fiji. Are there any issues with respect to the regional project or the Malaysian projects that could impact compliance? (b) Will the delay in the solar tent impact Fiji's compliance? | We have not been made aware of any MeBr compliance-related issues. | 58Final
AFR/FUM/38/TAS/32 | Please provide the category of delay. | The Category of delay is C | 68Delays
AFR/FUM/38/TAS/32 | Please provide completion date | Completed in December 2012 | 69Delays
AFR/FUM/54/DEM/40 | Large scale texts were planned for both countries (Algeria and Tunisia) in 2009 according to last year's progress report. This year's progress report indicates that results were received from the 2008 small scale tests but no mention of any large scale tests except that entomological tests are needed for further tests. (a) When are the large scale and final tests to begin? (b) Why has it taken so long for Tunisian partners to be selected? (c) How will the delay in the selection of Tunisian partners impact project completion? | Results from small-scale tests were discussed by representative from Algeria and Tunisia as well as international experts. Main outcome from the discussion was that the involvement of local expertise and experts is crucial for the correct understanding of the problems and selection of alternative technologies. While the selection of local counterpart in Algeria has been completed, in Tunisia the issue is still under consideration by the local authorities. Terms of Reference for the selection of the counterpart have been finalized and local companies/experts are expected to be selected soon. Large tests are planned to be executed in Algeria in the crop season 2010-2011. Similar tests will be conducted in Tunisia as soon as a local company is identified, however, not later than the crop season 2010-2011. The results will be discussed by Algeria and Tunisia and shared with other Parties and MBTOC. Considering that one more cropping season is needed for the execution of the tests, the project is expected to be completed with one year delay. | 61
AFR/FUM/54/DEM/40 | This project is now expected to be completed 20 months late. The planned completion date is December 2011, but the remarks indicate that the project is at an early stage of implementation where national experts have not been selected in Tunisia. (a) Why is this project at such an early stage and what is the reason for delay? (b) When will the tests begin? (c) Please reassess the planned completion date accordingly. | (a) Reason for the delay is the difficulties in selection of national experts. (b) Preliminary tests were conducted in 2008 on laboratory scale. Full tests foreseen in harvesting season 2011-2012. (c) Completion date moved to January 2013. | 64
AFR/FUM/54/DEM/40 | (i) Could UNIDO confirm that the consultant realised all the activities planned since the progress report indicated that the consultant report is expected to be received? (ii) Kindly indicate if the full tests foreseen in harvesting season 2011-2012 were released? (iii) What specific measures could be considered to speed up the project implementation since most of the milestones appear to be not achieved? (iv) What are the alternatives as regard to the selection of the national expert for Algeria? Will the difficulties in selected the national consultant for Algeria impact the planned completion date? | (i) National expert in Tunisia has not yet submitted the final report. Selection of other national experts (or national institution/laboratory/firm) in Tunisia and Algeria is still ongoing. (ii) No tests were conducted in the season 2011-2012, due to lack of national experts to follow on those. (iii) UNIDO field offices as well as HQ is supporting the NOUs in selecting national experts (or national institution/laboratory/firm) to plan and execute the tests in harvesting season 2012-2013. (iv) Selection of national experts (or national institution/laboratory/firm) in Algeria and Tunisia is key for the execution of the tests. | 67
AFR/FUM/54/DEM/40 | Will this project delay have any compliance issues for any of the countries involved? | Extensive discussions took place with the relevant authorities in the respective countries (i.e. NOU Tunisia and NOU Algeria) to explain the time constrains related to the approaching 2015 phase-out and consequence to compliance targets. UNIDO informed both NOUs about opportunities under the DEMO project as well as PRP grants recently approved by the ExCom (at its 71st meeting for Tunisia and 72nd meeting for Algeria). Both NOUs confirmed that the countries will do their utmost to ensure the phase-out, and preparation of a final phase-out project is under consideration. In the case of Tunisia, a project proposal for the phase-out of MB in the date sector will be submitted to the 73rd ExCom meeting. | 73
AFR/FUM/54/DEM/40 | Tunisia is completed, but Algeria continues to be delayed. Should be linked to Algeria MB phase-out project approved at the 73rd meeting | Some activities in Tunisia will be still implemented before the end of the year, to complete the full set of trials. Algeria will be still involved in the project implementation, with the view of facilitating the NOU in taking a decision on the best way forward. | 75
AFR/FUM/54/DEM/40 | Kindly indicated why a local expert for the Algeria component has not been identified and what UNIDO has done to address this matter, the status of implementation of the project, and how this project relates to the one approved for Algeria at the 73rd meeting. Kindly note that this project was approved at the 54th meeting in March 2008. | UNIDO has prepared a JD for the recruitment of a national expert to conduct the semi-industrial tests on MB alternatives. As per working arrangement with the NOU, the selection of any national experts should be supervised by the NOU and NOU is responsible to submit to UNIDO the CV of at least three potential candidates for further consideration. Though UNIDO suggested the NOU the name of some potential candidates, NOU asked the Ministry of Agriculture (authorities in charge for the overall palm date sector) to indicate potential candidates for the position. From the latest feedback received by UNIDO from NOU, the Ministry of Agriculture has not yet completed the internal procedure for the selection of candidates. UNIDO addressed the matter with several reminders to NOU. Results from the semi-industrial tests under the DEMO project should be the basis for the selection of alternatives for the follow-up project (PRP approved at the 73rd meeting). The Ministry of Agriculture has been consulted by the NOU on the opportunity/necessity to have a follow-up project in the same sector. Decision from the Ministry of Agriculture is pending (as per comments above). | 76Status
AFR/FUM/54/DEM/40 | Should the Algeria component be cancelled? | Government of Algeria was informed by UNIDO that any balance will be returned after the project completion, planned to occur before 31 December 2016. | 77
AFR/HAL/35/TAS/29 | Has the condition of approval for the ban of newly produced halon been put in place in all 7 regional countries? | Countries that have regulations have controls on halons imports but Botswana and Ethiopia have no regulations so no ban in place. | 55
AFR/HAL/35/TAS/29 | (a) What is the status of the Namibian tendering process and what are they tendering for (we note that Namibia is awaiting shipment to South Africa)? (b) I understand that the effort to move the halon from Zimbabwe was blocked, but has Zimbabwe decommissioned all halons as expected? (c) What is the status of the tendering process in Botswana and for what are they tendering? (d) We note that in your report to the last meeting, you have not had a response from Kenya, Ethiopia, Tanzania to verify that there are no remaining halons. What does that mean for example does it mean that you are assuming that Kenya, Ethiopia and Tanzania have in fact decomissioned halonshave not responded to repeated requests so it is assumed that there are no halons remaining. (e) As the condition of approval requires that there is a ban on the import of virgin halons, we asked before about the status. In your response, Germany indicated that regulations were in place except in Botswana and Ethiopia. Is that still the case and what has been done or will be done to attempt to achieve the needed ban? (f) Finally, we note that there was US $89,800 left in the project budget and the planned completion date was December 2009. How will the remaining budget be used and will the project be completed as planned in December 2009 or what is the new planned completion date? | (a) Zimbabwean fire fighting companies did not respond to the tender from Zimbabwe Power Company (ZPC) for they could not provide the required protection requested by the ZPC. Therefore Proklima forwarded the tender documents to Namibian companies. However, the the Namibian companies did not reply to the request except “Chubb”. Finally Chubb US based head office does not allow the company to tender for Zimbabwe. Thus far there was no official reply from ZPC despite the fact that the NOU informed ZPC about the difficulties and delays caused. Further efforts to find a suitable company for the task are undertaken. Namibia as a country has decommissioned halons at the fire department in Windhoek. These will be sent to South Africa for recycling before December 2009. (b)We are aware of halons being installed in Zimbabwe but unfortunately cannot decommission these because companies are not responding to the tenders to undertake the task. Further efforts to find a suitable company for the task are undertaken Matter to note, that the project only has limited funds, and is therefore only assisting with the process and would have contributed only a small amount towards the actual conversion. (c) In Botswana the Telecom company has 4 MT of halons installed. They are presently working on a decision on which alternative is most suited for their requirements. Botswana telecom is discussing with local companies on identifying suitable alternatives prior to tendering. They had tendered earlier and got varied options and so they cancelled that and want to do the process differently by first identifying the most suitable alternative and then tendering. The decision is expected in the next couple of weeks. (d) Tanzania has confirmed that they are not aware of any halons still in the country. Ethiopia has confirmed that small quantities of halons are in the airplanes owned by Ethiopian Airways. However, these are serviced in Europe and the airline company is currently not taking any action on halons. Kenya has indicated that there is installed capacity of Halon 1301 in the Ministry of Lands, however the Ministry has requested an assistance of USD 237,000 to convert their existing system to inert gas. Following discussions with the NOU, on the understanding that the regional project does not have sufficient funds to cover this request from the Ministry of Lands, it was agreed that maybe Kenya should approach one of the other implementing agencies to determine if a stand-alone project for Kenya could be developed. UNIDO was the identified agency. (e) The regulations banning import of halons are in place also in Botswana since Feb 2009. Despite numerous attempts from implementing agencies, MLF and Ozone Secretariats Ethiopia is the only country still lacking the relevant regulations. (f) All countries have been informed that the project will be closed in December 2009 and unused funds will be returned to the MF. | 59
AFR/HAL/35/TAS/29 | This is the first mention in the progress reports or any reports to the Executive Committee of the involvement of South Africa in the Eastern and Southern African Networks. Half of the funds have been disbursed and the equipment is located in a country that is not eligible to receive support from the Fund. This may be the subject of the evaluation, but it is not clear why a decision was taken in the light of the Parties views towards funding S. African projects. Moreover, please indicate what MOUs have been reached to make the project sustainable, what logistics have been decided, on what basis was a need for a mobile R&R decided? | RSA did not receive any funding from the MLF. The Halon Bank Manager Peter Devey provided free of charge essential input and information to the MLF-funded countries. In addition, the Johannesburg based company Afrox offered to host the mobile unit for the time being, which was accepted by the participating countries. Johannesburg is a strategic location with good roads to nearby Botswana, Lesotho, Namibia and Zimbabwe. Halon will be collected there and transported to the Johannesburg plant, as Afrox has operations in all these countries. Later the mobile unit will move to Ethiopia. The decision to put up a mobile unit was taken, as total funding does not allow to set up halon R&R centers for each country. General remark points 3 to 5 and 1: The majority of LCD conversions under the MLF are done by one or two major supplier. The supplier plays a crucial role in managing the progress, because in case of change of technical conditions or contributions of companies, clearance of suppliers is required. However, due to the large number of conversions under UN and bilateral projects, the capacities of the major suppliers to manage, visit and clear installations are reaching the upper limit. Therefore, effective time management and coordination of visits have become difficult to organize and realize and have generally delayed project implementation of those projects, especially if for various reasons recipients require specific, unforeseen modifications for final installation. | 43
AFR/HAL/35/TAS/29 | This project has the same remarks as were indicated in the 2001 progress report. Germany was requested to provide an update. Since no information was provided, the Executive Committee may wish to monitor these projects as projects with implementation delays: | Project agreements signed, national consultants contracted, national surveys done (except Namibia). The next milestones are installation and demonstration of mobile R&R unit and development of material and film on halon equipment. | 40
AFR/HAL/35/TAS/29 | (a) Please indicate if the reclamation equipment is operational in South Africa or still in the container. (b) Assuming the facility is operational, please indicate the amounts of halon reclaimed by the equipment and how much was transported from/to participating countries and at what price. (c) Please provide a copy of the updated plan that was circulated to the regional halon bank participating countries and the latest version of the plan if it has been subsequently updated. (d) We note that about $57,000 was spend on this project in 2004 and the remaining balance is about $24,000 with all of funds expected to be spent in 2005. What expenditures were incurred in 2004? | (a) The equipment is still in the container. (b) No halon has been reclaimed so far. (c) The draft plan is still under discussion with the concerned countries. (d) MLFS used erroneously the numbers from the excel line in the Progress Report above this project (ALG/HAL/35/TAS/51). Remaining balance as reported: $159.159. On the activities in 2004 we reported: National survey and workshop Zimbabwe, Lesotho; New contracts for legislation and PA; National promotion of halon bank in host countries; Evaluation: Comments on MF report; Steering committee meetings in Maputo in May 2004 and in Brazzaville in Sept 2004; Database established for Tanzania and Kenya; Dry Ice research; Communication with FAA South Africa; Safety guidelines provided. | 46
AFR/HAL/35/TAS/29 | The Secretariat would like to continue to monitor this project until the remaining 2 countries agree. | During the Africa-Network meeting last week, the last two countries, Tanzania and Ethiopia were present. Tanzania agreed fully with the new strategy. Ethiopia’s representative at the meeting was the newly appointed NOU. He stated that the strategy would be ok with him, if all other countries agreed (which is now the case). Since he is so new on the job, he however felt not very confident assessing the strategy himself and still would want to consult with his predecessor. I am submitting to the Secretariat, if his statement could, for the purpose of reporting to the ExCom, be counted as preliminary agreement by Ethiopia. | 47
AFR/HAL/35/TAS/29 | We have essentially the same questions as last year: (a) However, we understand that you are still in discussions with AFROX on the disposition of the equipment. Is then still correct that the equipment is still in South Africa in the container as you reported last year, not operational, and has not been used? (b) Last year all of the funds were expected to be disbursed. This year the completion date is slated for December 2007. The progress report remarks indicate that the MOU discussions are ongoing, but what else is to be completed with the remaining US $100,000? | The discussions with AFROX are stalled since early 2006 because AFROX would like to include the issue of contaminated halons resulting from the operations. AFROX would like to have an assurance that destruction costs for contaminated halons will be met by the owner of halons. However this is not agreeable to the countries and the project cannot cover these costs as well. AFROX is trying to determine other ways by which the issue of contaminated halons can be resolved. Since agreement has not yet been reached the halon recycling equipment is still in storage and not in use. The project activities however are progressing with countries individually working with local fire fighting companies towards encouraging the decommissioning of halons. Due to the delay in reaching agreement with AFROX the funds could not be dispersed as planned. The remaining funds are to assist the countries to decommission halons namely Halon 1301 and meet the transport costs for the halons to be sent from the country of origin to the recycling facility. | 49
AFR/HAL/35/TAS/29 | Despite the good progress indicated in the regional project at the country level, the regional halon bank through is still not operational and the equipment is still in storage, likley out of warranty, since AFROX has not agreed to be the bank due to the issue of the ownership of contaminated halons. Therefore, we suggest an additional status report to be submitted to the 51st meeting. | No Response | 50
AFR/HAL/35/TAS/29 | The regional halon project for Southern and Eastern Africa continues to have slow implementation of the halon banking part with AFROX. On this basis we suggest that there should be an additional status report presented to the 53rd Meeting. | Noted. | 52
AFR/HAL/35/TAS/29 | How will Germany determine when the project is completed? | Currently Botswana and Zimbabwe continue to have halons which need to be decommissioned. Botswana is already decommissioning the halons for shipment to the halon bank in South Africa. Zimbabwe has a problem because no local company is being able to provide an alternative. If Botswana's halons are transported to the halon bank and no progress is achieved with respect to Zimbabwe, the project will be judged as closed as other countries have all decommissioned their halons as per the available information. | 61
AFR/HAL/37/TAS/31 | UNDP's progress report submitted to the 49th Meeting indicated that the project would be completed by December 2006. This report indicates that the project will be completed in December 2007 and gives an assessment of progress. Please explain what has caused a now projected one year delay. | At the time of submission of the Progress Report to the 49th Meeting of the ExCom, it appeared that adoption of an agreed strategy (amongst the six countries) for completion of the project was imminent. However, despite the fact that agreement was reached, the forecast, in practical terms, has been reviewed as too optimistic in light of the reality of putting the final completion strategy in place – finalizing the last two countries national strategies and legislation (now both on the verge of completion, with drafts submitted and finalization of disbursement of national contracts imminent); and, designing a management plan for the excess halons through liaison with HRC in the US and UNEP’s Halon Trader. Perhaps a more appropriate assessment would be “some progress”. | 50
AFR/HAL/37/TAS/31 | With respect to the change in project design, a request would have to be made to the Executive Committee and given the nature of the proposal, it is unlikely that it would be approved without a business plan for managing the halon as this is a precedent in recent approvals. | We have written seperately to the MLFS to ask if flexibility may be applied in this programme. This does not seem to be the case, and in view of the difficulties to complete the project successfully, UNDP will inform the countries that the project will need to be canceled and return the remaining funds. | 56
AFR/HAL/37/TAS/31 | We agreed that there should be a formal report to the 49th meeting in the context of the implementation delays report, but the Secretariat did not include such a recommendation. It appears that there has not been any movement since the 48th Meeting when UNDP was still awaiting receipt form some countries of their national recycling plans and there is no signed MOU on using the halon facility in Nigeria. (a) Have there been any new activities? (b) I understand that 5 of the 6 participating countries do not now want to use the facility in Nigeria after having agreed before. Please clarify. (c) Should we now include a request for a formal report to be submitted to the 50th Meeting? | The MLFS is correct that UNDP is still awaiting receipt of national recycling plans from 2 of the 6 countries. An on-site visit by the 6 countries to the Nigerian halon facility - initiated by the technical expert engaged by the project – was organized in early 2005. However, there has not been any clear indication on the part of the countries, following the visit, as to whether they wish to proceed with establishment of a formal arrangement with the Nigerian facility and as a result, no service contracts have been signed. UNDP has therefore elected to present two options to the countries: 1) agree to service contracts with the Nigerian facility, contracts which will be prepared by UNDP on behalf of the countries; or 2) allow UNDP to put each of the countries in contact with the US Halon Bank and distribute the remainder of the project funding equally amongst the countries to support awareness/outreach activities with end users to promote the association with the US facility. The aim, in either case, is to bring the project to completion by end 2006. Yes, a formal request (through ExCom Decision) for submission of a progress report to ExCom 50 would assist UNDP in completing activities. | 49
AFR/HAL/37/TAS/31 | (a) In UNDP's report to the 53rd Meeting, it indicated that a proposal was pending for a US company to handle the surplus halon; what is the status of that proposal? (b) One of the conditions for approval was that each of these countries would ban the import of virgin halon. Which countries have legislation in place and does that imply they have licensing systems? | The contract with the US partner, as pre-established, would allow the organisation of the halons bottles collection, the documentation of the cylinders and the preparation of the import permits to the US plant for destruction. A local partner, to coordinate the legal work in the participating countries, has also been identified. | 55
AFR/HAL/37/TAS/31 | What is the status of halon activities in Cameroon? Can UNDP confirm that Cameroon's halon consumption was below 2.38 ODP tonnes in 2004? What is meant by national service contracts--what do they entail? Briefly describe what activities have been completed and those that are planned, by country, as this can be an Implementation Committee matter for some countries like Cameroon. | Please note that full Progress Report on this project's implementation was submitted to the MLF Secretariat for consideration at ExCom 46. In response to specific questions: The survey missions helped the countries clarify where consumption existed and for what uses. The training mission involved preparation of equipment specifications and laid out a training programme. The technical experts identified have been contracted to prepare equipment specifications and conduct in-field trainer-the-trainers programmes, working in close cooperation with national agricultural experts. With regard to the last questions, implementation delays have been experienced, as explained in the aforementioned Progress Report. These have been due in large part to difficulties in communicating with partner countries (non-responsiveness) and in transferring funds for national contracts. | 46
AFR/HAL/37/TAS/31 | We agree and will request a formal report. | No comment. | 48
AFR/REF/48/DEM/34 | (a) Most of the funds used to date have been for stakeholder meetings concluding the need for training in procurement practices; how much will be used for the purchase of equipment? (b) Could additional African countries, other than the 5 mentioned in the proposal, benefit from this project? | (a) Germany’s budget is rather small. It is only used for information management and capacity building. (b) Remaining funds will be used for outreach of the lessons learned and for multiplication of the experiences in the region. In this sense additional African countries will benefit from this project. UNIDO’s approved funding has been allocated to the 5 partner countries in relation to their chiller inventories. | 55
AFR/REF/48/DEM/35 | Funds disbursed very low for this project approved at the 48th Meeting. Please explain. | No Response. | 67
AFR/REF/48/DEM/35 | What activity is associated with the US $7392 bearing in mind that the ExCom provision for approval was that disbursement of the amounts approved would be dependent upon the availability of external resources as specified, to be confirmed by the Secretariat, based on the advice from the agency that external funding had been secured? | The expenditure relates to costs of travel for a Japanese expert to participate in a workshop related to the project. Funds from the French Global Environment Facility were approved in July 2008 and the Secretariat's advice on disbursement was sought accordingly. The expenditure took place after advice from the Secretariat that funding can be disbursed. | 61
AFR/REF/48/DEM/35 | (a) What are the issues delaying agreement with the Nigerian bank? (b) What was the US $8,319 in disbursements used for? | (a) The main obstacle in the negotiation with the Nigerian Bank is the co-financing aspect, as is required by donors. UNIDO, on behalf of Japan, will continue the negotiation. However, we envision that the implementation with the national banks will be completed by December 2012. The negotiations are currently ongoing, and the same co-financing modality is targeted as has been received in Egypt. (b) The expenditure refers to an international expert. | 64
AFR/REF/48/DEM/35 | The project implementation has not been assessed. Should this project received a "Some progress"? If not, kindly provide your assessment and the justifications? | No Response. | 67Status
AFR/REF/48/DEM/35 | Please justify/explain the revision of the planned completion date at this meeting where a delay over a year or more is expected. | Completion is pending upon receipt of remaining tranches of approved funds from French Development Agency and FFEM. Funds have been requested. | 70
AFR/REF/48/DEM/35 | Significant delays in the project as explained in the remarks. There appears to be some progress to ensure the project will be completed by December 2015 per ExCom decision. However, a relatively large remaining balance may be left over (over $200,000) that should be returned to the Fund after the project has been completed. | The MP part of the project is operationally completed as of December 2014 since the completion of the MLF-funded part was requested by the ExCom Decision 71/10. The extension of the bilaterally funded parts until December 2015 was granted by ExCom Decision 74/2. The activities were completed in all beneficiary countries except Sudan where procurement of five non-CFC chillers is planned to be financed from the combination of funds from AFR/REF/48/DEM/35 (Japan), AFR/REF/48/DEM/36 (France) and the extra budgetary contribution from the FFEM. The funds from the Japan and French bilateral contribution were obligated for this procurement at the beginning of 2015 but the progress in the procurement was halted by the late arrival of the last tranche of funds from the FFEM that arrived only in May 2015. In June-September 2015 UNIDO conducted the procurement and the Contract for delivery of five chillers in Sudan is expected to be awarded in early October 2015. Thus, funds will be obligated still this year and equipment will be purchased, but equipment may not arrive to and installed in Sudan during 2015. For this reason, we wonder whether a new ExCom decision would be required to complete the project by June 2016. | 75
AFR/REF/48/DEM/35 | What is the status of the chiller projects in Nigeria and Senegal? | No Response. | 76Status
AFR/REF/48/DEM/35 | (a) Has any information on cofinancing by the end-user and savings due to energy use been produced? (b) The Secretariat noted that the planned date of completion is revised from December 2015 to December 2016 since the installation and commissioning have not been completed due to the preparation of the site. Also, the financial data shows a balance of $242,917 as of 31 December 2015 while in the narrative section it is indicated that the remaining funds have been disbursed. Could you please clarify? | a) No such assessment has been made. b) Almost 100% of the balance was obligated before end 2015 to supply five non-CFC chillers for Sudan as the last substantive activity in the project. The TF funds were combined with the remaining TE funds (AdF). The chillers were delivered to the beneficiary in July 2016 and installed on place by the supplier's technicians. However, commissioning was not possible since the beneficiary has to adjust the AC infrastructure of the building for connection of the new chillers. A wokplan for the adjustment works has been agreed with the beneficiary. Since the adjustment work involves local tenders the completion is expected in 1 Q 2017 at the earliest, thus, the planned completion date has been revised to June 2017. | 77
AFR/REF/48/DEM/35 | Kindly note that project date of completion as per Excom decision 75/11(b)(ii) is June 2016. Any balance as of that date is to be returned to the Fund. | The grant validity expired in June 2016 in line with the ExCom decision and thus, no new expenditures beyond this date were done. However, at this moment we are not able to clear the remaining obligations since the chillers in Sudan have not been installed yet. Two payments are pending, which were obligated before June 2016. | 79
AFR/REF/48/DEM/36 | (a) The counterpart funding from the French GEF took 13 months to procure after the approval of the project. How could this have been expedited? (b) The remarks indicate that the counterpart funding was received in July 2007 and that negotiations were underway with UNIDO for an agreement. What is the nature of such negotiations and when is the agreement expected to be completed? | No Response | 55
AFR/REF/48/DEM/36 | (a) Given that France, through UNIDO as your consultant, has not negotiated a contract with the Nigerian Bank of Industry, is it still possible for France to achieve the planned July 2011 completion date? (b) What is the latest status of the negotiations? (c) Would not it take some time to implement the project after the Nigerian Bank of Industry agrees? | (a) The main obstacle in the negotiation with the Nigerian Bank is the co-financing aspect, as is required by donors. UNIDO will continue the negotiation, however, we invision that the implementation with the national banks will be completed by Dec. 2012. (b) The negotiations is still ongoing, UNIDO is aiming to achieve a same co-financing application as has been received in Egypt. (c) We invision that the implementation with the national banks will be completed by Dec. 2012. | 64
AFR/REF/48/DEM/36 | Since this funding is credited to France, a progress report on the activities that are covered by French funds should be provided only by France. Neither UNIDO or GTZ or UNEP provides us with progress reports on French activities because it is not a project number under their responsibility to the Multilateral Fund. | No Response. | 70
AFR/REF/48/DEM/37 | (a) No remarks were provided for this project. Please do so. (b) Those remarks should address the issue of low levels of disbursement in the regional CFC chiller in Africa. | The National Bank of Egypt and the Industrial Bank of Nigeria were identified to be the financial institutions to handle the financial mechanism for the replacement of the chillers. The agreements with the banks are under negotiation and funding will be partially disbursed every quarter to the banks to ensure completion of the chiller replacements prior to disbursement of funding. Detailed status report on the chiller projects was submitted to Mr. Sicars. | 62
AFR/REF/48/DEM/37 | (a) Please do not refer to the other report as this is not the correct procedure. There are different databases involved and different interests to meet ExCom decisions. These status reports should address progress since the last report. This is a different requirement than that for projects with specific reporting requirements. (b) Were the workshops held as planned for the other countries in February 2011 (Cameroon, Senegal and the Sudan)? | Nigeria; - Several barriers have been addressed with the National bank. However, due to the nature of the activities the bank does not have considerable experience in green investments, a mission was planned to take place to address last points of the Terms of reference, however due to the recent attacks on the UN, no mission could be fielded. In addition, negotiations for contract terms will be finalized once the financial mechanism is operational . Furthermore, UNIDO has organized a workshop which also had to be re-scheduled to the 4th quarter of 2011 due to the attack. Project steering committee has been established. Senegal / Sudan; - Technical specs of chillers will be collected; 2) co-financing opportunities have to be determined and discussed with counterpart. Cameroon; The NOU wishes that all the owners benefit from the fund therefore local banks are being contacted to check options for establishment of a revolving fund to cover all remaining beneficiaries. This activity is still ongoing. Egypt Agreement has been concluded with the National Bank and the activities are planned to go ahead as described in the TOR of the bank and the steering committee. | 65Status
AFR/REF/48/DEM/37 | 1) The Secretariat assessed this project with "No Progress" suggesting the need for an additional status report. Do you agree with MLF assessment? If not, kindly provide justifications. What is the reason why the negociation with the Nigerian Bank of Industry could not be finilized? 2) Please specify the category of delay. | 1) Eligibility requirements; and operation and grant/loan portions of the revolving fund still have to be negotiated with the Nigerian Bank of Industry. 2) Please note that in the case of additional status reports, historically, the fields "Assessment" and "Category of Delays" are not applicable. | 63
AFR/REF/48/DEM/37 | The overall servicing sector plan has been approved and there remain a significant amount of funds left to be disbursed. In the light of the decision on NPPs and TPMPs how will these funds be used by the November 2010 completion date or will they be incorporated into HPMPs. | In countries where a fund for the replacement of the chillers is being established, the fund is being incorporated into the HPMP. | 61
AFR/REF/48/DEM/37 | (a) Did national workshops occur in all countries in February 2011? If not, why not? (b) What is the cause for the delay in the negotiations with the Nigerian Bank of Industry? (c) What efforts have been taken to conclude the negotiations? (d) This project is already projected to be completed 27 months late. The project is also at a very early stage of initiation in all companies with national workshops having just started this year. On what basis are you projecting a December 2011 completion and should not this planned completion date be reassessed? (e) Is it correct that co-financing has not been obtained for any of the countries? | (a) Due to the polictial situation in the region, it was not possible to arrange for the work shops to take place. However, UNIDO plans to move forward in organizing workshops to take place in the areas where there are significant amount of chillers, such as Egypt, Nigeria and possibly Cameroon. (b) and (c) The main reason for the delay's in all countries including Egypt is the negotiations with local authorities and the Banks to identify a suitable co-financing system, as requested in the bilateral agreements. (d) Please take note that the resources of the project including the bilateral agreements have been received by UNIDO later than expected. UNIDO will make every effort to undertake the necessary activities by December 2011. (e) Co-financing bas been obtained for Egypt through an agreement singed between UNIDO and the National bank of Egypt. The co-financing agreement covers approximately 60 chillers. Currently UNIDO is ongoing with negotiations with the Nigerian National bank, hoping to achieve a similar co-financing agreement, as been done in Egypt. | 64
AFR/REF/48/DEM/37 | We suggest an additional status report on the completion of negotiations with the Nigerian bank for the chiller project in Nigeria | Additional status report will be provided at the 65th ExCom meeting. | 64Delays
AFR/REF/48/DEM/37 | Submission of an additional status report was requested to the 67thMeeting on the completion of the Agreement with the Nigerian Bank of Industry. Based on UNIDO comment, progress has been made for Nigeria but it is not clear whether the agreement with the Nigerian Bank of Industry has been completed. Please clarify. | Agreement with the Nigeria Bank of Industry has not yet been completed. | 67
AFR/REF/48/DEM/37 | The project implementation has not been assessed. Should this project received a "Some Progress"? If not, kindly provide your assessment and the justifications? | This is a project for which a status report was requested on a specific issues and it is not a project under implementation delays. Until now, assessment of no progress, some progress or progress was only requested for projects under implementation delays. Furthermore, no changes to this practice was agreed upon in the IA coordination meeting on streamlining reporting requirements. | 67Status
AFR/REF/48/DEM/37 | The report does not address any of the items requested. The decision requests information (a) on the completion of the agreement with Nigerian bank of Industry; (b) to monitor the resolution of the financial mechanism and co-financing issues for Nigeria, Senegal and the Sudan by the 68th meeting as a milestone for achievement in order to avoid consideration of possible cancellation in those countries. Please address these items and proposel a milestone for achievement for Sudan as no progress was reported for Sudan. | After the technical expert's visit to the Nigerian Bank of Industry at the beginning of October, the agreement with the NBI is under consideration. The completinon of the agreement is pending on the update of the list of chiller owners in Nigeria eligible for assistance from the project, which is being consolidated and updated by the NOU after the technical expert mission. In Senegal, the NOU is also currently updating the list of chiller owners elibible for assistance from the project and mission of technical experts will be fielded upon receipt of the updated information (tentatively scheduled for November/December 2012). Decision on the financial mechanism/co-financing will depend on the results of the mission. A special effort is being made to get response from the NOU Sudan regarding the continuation of the project in Sudan and milestone of 31 December 2012 is proposed to establish next steps for Sudan. | 68Status
AFR/REF/48/DEM/37 | Why is this CFC related projects not expected to be completed until 2014? | Completion is pending upon receipt of remaining tranches of approved funds from French Development Agency and FFEM. Funds have been requested. | 70
AFR/SEV/16/TAS/20 | This project is listed with overruns. Overruns are not allowed per Decision 17/22. Please explain. | The Funds Disbursed was corrected in the project mentioned. The figure is in the final table submitted on 15 May 2000. Percentage of Funds Disbursed: 100% | 31
AFR/SEV/23/TAS/21 | There are 4 projects that are classified as financially completed and there remains an unutilized balance of US $93,343. Aside from AFR/SEV/23/TAS/21, which is in the Adjustments Table of UNEP's progress report (Annex III), is UNEP returning these funds for the other projects to the 34th Meeting? If any funds have been returned and when? | Balance of US $21,369 returned to 30th meeting | 34
AFR/SEV/26/TAS/22 | There are 4 projects that are classified as financially completed and there remains an unutilized balance of US $93,343. Aside from AFR/SEV/23/TAS/21, which is in the Adjustments Table of UNEP's progress report (Annex III), is UNEP returning these funds for the other projects to the 34th Meeting? If any funds have been returned and when? | Balance of US $14,398 to be returned to 34th meeting | 34
AFR/SEV/29/TAS/25 | Concerning this project, while most of its objectives were achieved, we note that: a) Although countries attended meetings, it appears that only one of eight countries became a Party (Angola); b) UNEP indicates that "ministerial agenda are crowded and little time is available for Montreal Protocol" while our experience with the highest level of representation from the Fund indicates that ministerial agendas can be arranged to address the Montreal Protocol in a substantive manner; c) NOUs do not appear to have been empowered by dialogues with highest level officials as UNEP indicates that "some NOUs do not have good support in their governments'. | UNEP notes that the comments you have provided for the Africa network relate to remarks in the column called "Problems and Difficulties". In this column, we have tried to indicate some of the problems and difficulties we and the networks encountered during 2000 in implementing the planned networking activities. Indication of a problem should not be taken as meaning that the activity was totally unsuccessful or that the objective was not achieved. We have simply tried to indicate what problems exist and that we are working hard to find ways round them. Some additional comments are: a) Of the non-Parties in Africa, Angola, Cap Verde, Rwanda and Sao Tome attended network meetings during 2000. Largely as a result of contacts with the RNC and network members, Angola ratified the Vienna Convention and the Montreal Protocol on 17 May 2000. As the progress report states, the other non-Parties in the region have been contacted by the RNC and invited to network meetings. Cap Verde, Rwanda and Sao Tome attended the joint meeting in Mali in August 2000 and were encouraged to begin the process of ratification. The other non-Party countries did not attend the network meetings in 2000. b) UNEP agrees that it is possible to arrange for the agenda of ministerial meetings to address the Montreal Protocol in a substantive manner. This has been our experience during 2000 in Africa, Caribbean, Latin America and West Asia. However, we are also aware that the agenda of such meetings are crowded and it may be a challenge in future to ensure that ministers continue to spend a significant amount of time considering the Montreal Protocol at each of their meetings. Nevertheless, a good start has been made and the networks will continue to enhance high level political awareness in the regions. c) While it is true that "some NOUs do not have good support in their governments", many NOUs do enjoy strong support from their ministers and senior officials. As stated, the network, in line with recent ExCom initiatives under the Institutional Strengthening projects, has worked to strengthen the links between NOUs and their governments. The fact that some NOUs do not yet have the necessary support is not a basis for implying that NOUs in general have not been empowered. | 34
AFR/SEV/32/TAS/28 | 1) Please provide the category of delay for this project. 2) Please provide your proposed assessment of each project in future reports, i.e., progress, some progress, no progress, completed. This helps the Secretariat in determining if its assessment corresponds with your assessment. | No Response. | 45
AFR/SEV/32/TAS/28 | Concerning the harmonization of legislation project in Africa, the 2000 progress report response to questions indicated that local consultants were being identified and engaged and there were consultative meetings during the network meeting. Last year the progress was reported as contracts processed for a regional consultant and two local consultants. This year 2 contracts with regional agencies were reported. The project is now projected to be completed 18 months late in December 2003. Are there any more contacts to be signed since one would assume that this was a priority project given the time it takes to change legislation and regulations knowing that Fund projects are being implemented before the legislation/regulations are harmonized? | At least one Sub-regional Agency promised that harmonization mechanism will be adopted by end of 2003. Only 2 countries in both regions do not have regulations in place as of now. | 40
COS/FUM/43/INV/33 | What is the nature of the technical problem for the methyl bromide project in Costa Rica that will not enable Costa Rica to achieve its 2006 phase-out target and what is being done to address the technical problem? | The term ‘technical’ problem referred more precisely to ‘consideration of specific requirements for adoption of alternatives and transfer of technology’, since reporting under the MYA table of the Progress Report was understood to be a very brief overview of activities in light of the fact that detailed progress reports, reviewed and endorsed by the MLFS are also submitted for the project. MeBr users in Costa Rica differ drastically between and within sectors (a small amount of producers / large farms / high technology / high consumption of MeBr vs. numerous producers / small farms / minimum technology / low utilization of MeBr). The necessary steps for reduction of MeBr (outreach, scheduling, equipment, training and technology transfer) require singular approaches. This "tailor made" approach is slow and time consuming. Difficulties or constraints to the commercial adoption of alternatives are being addressed by the project and solutions are being sought. Often for example, it is not a question of a particular product not working but of using the correct application method to guarantee proper distribution of the product and thus an optimum level of efficiency. Factors such as this one are essential for adequate commercial adoption to take place and as a consequence, for the sustainability of MB phase-out to be ensured. | 49
COS/FUM/59/INV/43 | Please provide further details on the challenges with the alternatives faced by farmers. | The project will be completed by July 2014. All use of MB has been phased out as per the agreement with the ExCom (end of 2012). The current harvest (2013-14) is the first season with zero consumption of MB. The project team has carefully monitored the activities and provided Technical Assistance when needed in order to assure that no MB is being used. Costa Rica is mainly using Biological alternatives in some cases combined with chemical alternatives to substitute the use of MB. | 73
COS/KIP/87/PRP/63 | Progress - when is the KIP expected to be submitted | Probably to the second meeting of 2023 | 91
COS/PHA/55/PRP/39 | Any work on legislation? If all funds are to be disbursed in 2009, will there be funds available for activities in 2010? | Current legislation is currently being evaluated, and a new decree that will include HCFCs in the licensing system is expected to be approved later this year. Most funds are programmed for 2009. | 58Final
COS/PHA/55/PRP/39 | a) What is the status of the licensing system/regulations/legislation update for HCFCs? b) Please indicate when the legislation/regulation/licensing system will be updated. c) When will the HCFC survey be completed? d) When will HPMP be completed? e) We note that UNDP indicated in last year's progress report that the legislation was being evaluated and a new decree that would include HCFCs in the licensing system was expected to be approved by the end of 2009: i) Did this happen? ii) This project appears to be at an early stage of development while the planned completion date is now September 2010. This seems contradictory but the level of disbursement of US $2702 of the US $150,000 attests to a possible early stage of development. Please clarify. iii) What has caused the apparent slow development of this HPMP? f) Is September 2010 a possible date of submission given the stage of development? | a) Licensing system has been updated and HCFCs are included. Regulations/legislation is under review. b) See a). c) The HCFC survey is expected to be finished by August, 2010. d) The HPMP will be submitted to ExCom 63. e) i) Yes, it did happen, ii) Most of the funds have been committed and we expect them to be disbursed before the end of the year. iii) No specific reason. f) It will either be submitted for the 62nd or 63rd meeting of the ExCom. It could potentially be ready for a September submission. | 61
COS/PHA/58/INV/42 | Please return the remaining US $23,531 as ODS destruction is not covered by the TPMP. | All ODS destruction activities have been covered by non-MLF funds. MLF funds have been used for training and to support the R&R structure that is related to the ODS destruction throughout the supply chain. | 67MYA
COS/PHA/64/INV/46 | Was there any delay in implementing 2012 activities? If yes, please specify the concerned activity and provide the reasons. | No delays. Everything is on track and project will be completed by July 2013. | 70
COS/PHA/70/INV/48 | Is the Agreement signed? | Yes, the agreement was signed. | 73
COS/PHA/74/INV/50 | Progress saatisfactory. |  | 82
COS/PHA/75/TAS/54 | No issue. Tranche due in 2017 by which time verification report will be submitted |  | 77
COS/PHA/80/INV/57 | (a) What activities are proposed (please provide a brief overview - e.g., training of technicians, etc.). (b) When is the first disbursement (month/year) expected. | All activities were listed in the tranche request that was approved at ExCom 80. Training of technicians is an important part of the HPMP. The first disbursement took place in April 2018. | 82
COS/PHA/81/PRP/58 | (a) Please advise why the balance is nil given that stage II is submitted. | The financial data is from 2018. Disbursement from 2019 is not recorded in the PR. Funds have been spent for the preparation of the stage II HPMP and will be reported in next years PR. | 84
COS/PHA/81/PRP/58 | When will the project be completed and balances be returned noting that stage II is already submitted to the 84th meeting? | The project will be completed before the end of 2021 as per the agreement. | 86
COS/PHA/83/INV/59 | When is the first disbursement expected? | Tranches is seen as cash flow and funds from 5th tranche will be disbursed once the full 4th tranche has been completed. | 86
COS/PHA/84/INV/60 | When was the project document signed; why is the disbursement nil - please provide a brief explanation. | The ProDoc was signed in 2021 and that is why no expenditures were recorded in 2020. | 88
COS/PHA/84/INV/60 | Progress - when is the first disbursement expected. | UNDP is working closely with the company to initiate the reconversion process, as reported in the recent tranche request. | 91
COS/PHA/84/INV/61 | When was the project document signed; why is the disbursement nil - please provide a brief explanation. | The ProDoc was signed in 2021 and that is why no expenditures were recorded in 2020. | 88
COS/REF/27/INV/20 | The remarks indicate that the company went bankrupt. It also notes that "the government is formulating a proposal on how best to handle the stiuation and has asked not to close the project. The Executive Committee has decided that projects where companies have gone bankrupt cannot not be resubmitted. Please indicate the nature of the proposal from the government. | It was the Government's intention to use the remaining balance to provide assistance to small manufacturers of refrigeration equipment. Preparation of the RMP is underway and UNDP is working with the Government to identify small refrigeration manufacturers. The Government has agreed to close the project and return the remaining balance, provided that there is future possibility that remaining consumption in the refrigeration manufacturing sector can be addressed under the auspices of a national CFC phase-out plan. | 37
COS/REF/32/TAS/23 | There does not seem to be a reason to move this project down the road to cancellation when the payment issue seems to be one of the responsibility of UNDP. Please indicate why the payment cannot be made. | Project is operationally completed and this can be reflected in the report on projects with implementation delays. UNDP will carry out final payments before year-end. | 44
COS/REF/32/TAS/23 | When was the project completed? | The project was completed in September 2005. Final invoices still pending. | 47
COS/REF/41/TAS/27 | How many beneficiaries have been identified for the project in Costa Rica and what is the amount of each incentive and the amount of associated CFC? Were there any conversions without incentive support based on the operation of the demonstrations? | Four boats were selected for a pilot conversion. As of today, the first conversion was completed and two more are ongoing. The incentives system was established in a way that the boats owners do not receive cash, but instead they receive the materials for the conversion, the technical assistance provided by a local expert recruited by the NOU and UNDP. The four pilot conversions are useful to determine more accurate costs and to show the results to other owners and motivate them to convert. 12 additional boats are identified for a second phase that will start during the second half of 2005 | 46
COS/REF/41/TAS/28 | As with the other RMP update project in Costa Rica, less than 1% was disbursed and no funds were obligated but the remarks indicate that the RMP is ongoing satisfactorily. What is planned for 2005 for specifically the refrigeration servicing sector because the remarks for this RMP component are essentially the same as for the other components? | Local consultants is identifying additional MAC workshops and to do a diagnosis of the status of R&R equipment distributed in previous project. Withthis information the MAC R&R network will be reactivated. | 46
COS/REF/41/TAS/31 | Please describe what activities were undertaken by the Monitoring component of the RMP in Costa Rica that resulted in disbursements of US $15,436 of the US $60,000 approved for the project. | The local consultant that is coordinating RMP update in Costa Rica has been partially funded by the Monitoring Component, since he is also in charge of all the Monitoring and Evaluation of all the activities of the RMP update. | 49
COS/REF/41/TRA/29 | Only 10% of the funds have been disbursed for the technician training component of the RMP in Costa Rica that was approved in December 2003. What will most of the remaining funds be used for? | It has been very difficult to establish the MOU with the institution that will be in charge of the general training in Costa Rica. The low disbursement reflects this. Direct training has been given to the technicians in e.g. Punta-arenas, because it has been a necessary condition in order to execute the activities in the fishery sector. Once the MOU with the National Learning Institute (INA) is well functioning, the disbursement is expected to increase significantly. | 49
COS/REF/41/TRA/29 | What training activities were conducted for technical assistance for certification and licensing of refrigeration technicians in 2004 and what is planned for 2005? | National consultant started contacts with INA (Instituto Nacional de Aprendizaje) to include good practices module in refrigeration courses. | 46
COS/REF/41/TRA/30 | What has caused the 12 month delays for the customs officer training in Costa Rica? | The Project execution was delayed almost 12 months after it got approved in 2003. The project team that is implementing the whole RMP in Costa Rica has focused its activities in the sectors with the highest consumption of CFCs, in order to comply with the reduction targets of CFC. In 2005 the whole program of Custom training has been planned and it will be executed during 2006. | 49
COS/REF/41/TRA/30 | What training activities were conducted for customs officers in 2004 and what is planned for 2005? | As of the moment, the custom component of the RMP is being implemented in coordination with the custom activities under the Methyl Bromide Plan. The information system of COGO will be integrated to the custom system, however as of now there have not been concrete outputs. | 46
COS/REF/57/PRP/41 | (a) Why are balances for stage I PRP funding left over for Costa Rica. (b) Under what decision will the proposed foam project be submitted. | The decsion on preblended poliols allows Costa Rica to submit the Foam proposal at any point it time. MABE Costa Rica was approved in 2011, and the remaining balance is for the foam sector plan when low GWP alternatives are available at SH level in countr | 82
COS/REF/57/PRP/41 | (a) Please clarify if the project has been prepared and submitted. | Financial data is from 2018. The Investment project for MABE was approved in 2011, and one investment project has been submitted to this ExCom. | 84
COS/REF/57/PRP/41 | Since no activities were identified in the remarks and no disbursement was recorded, and a 10-month delay is forecasted, we assume that no activities occurred in 2009 for this project. What has caused the delay in the HPMP preparation? | HPMP preparation process is delayed and preparation of investment projects will commence soon. | 61
COS/REF/57/PRP/41 | Could you please confirm that the project is part of the HPMP submitted to the 64th ExCom meeting? | The investment project for MABE Costa Rica was presented to ExCom 64. | 64
COS/REF/57/PRP/41 | Secretariat's Category: HPMP approved - 100% use of funds planned - Investment project for the remaining part of the companies to be submitted when low GWP alternatives are available for SMEs. | The MLFS’s categorization is correct. | 70
COS/REF/57/PRP/41 | if refrigeration sector projects cannot be prepared because of lack of technologies, funds should be returned, and preparation could be part of stage II unless country justifies need for these funds now (note current completion date of 2017, stage II PRP would be due at the same time) COS stage I is until 2020. Additional information on status of technology discussion and options | Funds have been kept to prepare Foam Sector plan, which will be presented in 2016 in line with decision 63/15. | 75
COS/REF/57/PRP/41 | (a) Explain zero disbursement; preparation funds should be returned if no project is forthcoming, and could be requested again for stage III if still required; (b) What actions are being taken to resolve this delay noting that the project is one of the oldest project preparation accounts and delayed by almost 7 years. What actions could ExCom take? | Project will be submitted at the 78th meeting, preliminary information has been collected. | 77
COS/REF/74/PRP/51 | (a) Explain why zero disbursement; demo project approved at 76th Meeting, balances of PRP should be returned; (b) The remarks do not indicate any delay, but the tranche has a planned completion date 13 months later than indicated in the 2014 report. Kindly indicate the delay, the actions taken to address it and what actions ExCom might take to address this matter. | There are pending invoices that need to be settled. Expenditures will show up in 2016 Progress Report. | 77
COS/SEV/21/INS/10 | UNDP provided detailed information about several of its INS projects that indicated in detail the activities of the ozone units. However, in the following cases, the same level of detail was not provided. Since INS is no longer monitored as implementation delays, we would appreciate similar detailed information for the following projects: | In addition to the efforts undertaken in cooperation with UNDP for the finalization and approval of the MBr elimination project at the 35th ExCom, the NOU is putting great efforts to ratify the Montreal Amendment and results are expected in 2002. NOU is also implementing the CFC import control system in place. Training on CFC recycling machines was organized in 2001 and MB public awareness campaign was carried out. The NOU is working with UNDP in the implementation of the MBr project approved as well as the formulation of the RMP. | 37
COS/SEV/35/INS/26 | UNDP is also implementing the institutional strengthening project in Costa Rica that has conducted public awareness activities. However, only about $52,000 of the US $108,000 approved for this project was disbursed through 2003 while institutional strengthening was renewed in December 2003 in the amount of US $140,513. Please clarify. | This project was approved in December 2001 and started activities in February 2002 once the project document was signed. While activities and disbursements have been completed as planned, as of December 2003 they had not been totally registered in the system but they are introduced in the system now. As of Today all the funds of the project have been disbursed, however, there will be expenditure in the system up to May 2004. The funds for the renewal were requested in December 2003, which is no more than 6 months in advance (according to decision 19/29) as the new phase has already started. | 43Final
COS/SEV/53/INS/38 | This is a critical year for institutional strengthening since the 1 January 2010 phase-out is quickly approaching. One of the major emphases of the review of this year's progress reports is INS. (a) Which institutional strengthening projects are not operational and what could the Executive Committee do to facilitate them becoming operational as we note that based on UNDP's progress report it appears that all of UNDP's NOUs are operating well? (b) Please provide more information on 2008 activities along the lines of the report on Argentina's or Malaysia's 2008 activities. | Costa Rica has an active Public awareness programme. Costa Rica is in the process of evaluating their current ODS system in order to include HCFCs in a revised licensing system. The ozone unit supports the implementation of the MB project, TPMP and HPMP preparation. | 58Final
COS/SEV/59/INS/44 | Please indicate if the relevant project document/MOU/grant agreement has been signed, if all reports have been provided, if any delays occurred in the transfer of funds, and if any delays occurred in planned activities. | Yes, ProDoc was signed and activities are being implemented according to the plan. | 64
COS/SEV/65/INS/47 | (a) Please provide additional information on the activities implemented in 2012 to enable the Secretariat assessing progress made. (b) Was there any delay in implementing 2012 activities? If Yes, please specify the concerned activity and provide the reasons. | (a) The NOU performs the standard IS activities such as Project oversight, Data collection and reporting, staying permanently in contact with all stakeholders, implementation of public awareness campaing, keeping the licensing and quota system up to date, etc. (b) No, we are not aware of any delays. | 70
COS/SEV/71/INS/49 | Disbursement 33 percent and no obligations. IS renewal expected at 75th meeting | IS will be requested at ExCom 75. | 75
COS/SEV/74/TAS/52 | Confirm whether survey report will be submitted by January 2017 | Results are expected at the end of 2016. | 77
COS/SEV/75/INS/53 | Progress satisfactory |  | 82
COS/SEV/80/INS/56 | Progress satisfactory. (a) Please provide estimated date of first disbursement. | Mar-18 | 82
COS/SEV/80/TAS/01+ | Progress satisfactory - (a) what is the expected date of first disbursement. | The first activitiy of the Eas was a regional meeting in Panama that took place in May 2018. Funds from the Eas were used to cover the cost of participation of the country. | 82
COS/SEV/80/TAS/01+ | Progress reported. Given that the country has ratified Kigali Amendment, what changes in the plans are incorporated especially relating to activities relating to data monitoring and reporting and introduction of low-GWP alternatives. | The country is working with the customs office to adopt new tariff code for HFC; also reviewing the national coordination mechanism for the implementation of the Montreal Protocol, including the Kigali Amendment. The country is updating its survey of ODS alternatives and this includes low GWP alternatives. The country has a functioning HFC licensing system. | 84
CPR/ARS/07/INV/23 | This project has a difference between information provided about the date completed in the individual project completion reports and the information provided in the progress report. This can be very significant because for example, one of the performance indicators for non-investment projects is the number of projects completed during the business planning year. If a non-investment project was classified as completed in 1997 it counted against that performance indicator. It cannot now be counted against the same indicator for projects to be completed in 1998. | There appear to be a number of factors at play in causing the discrepancies on completion dates. First, per ExCom decision, project completion reports are due 6 months after physical completion. Therefore, the date included as completion in the PCR should be the date of physical completion. There may, however, be confusion on the part of financial agents and task managers on which date to provide, especially on back-logged projects which were already financially complete. We are investigating this. In addition, you can see that this confusion is possible given that your own table included in Attachment I lists both FIN and COM dates in the status column. For the information required this should only include COM dates. Comparison should be made between COM dates in the Progress Report and physical completion dates in the PCRs. We are currently checking: (1) COM dates per PCR dates and (2) whether the date provided in the PCR is financial or physical completion. Once these issues are resolved we will make the final changes to the PCR and PR. | 28
CPR/ARS/24/INV/244 | This project was supposed to be completed in 25 months but it is now expected to be completed over two years late (51 months). This project has a huge impact on the ozone layer (1224 ODP tonnes), but only 13 per cent of the US $547,675 budget has been disbursed. This project now enters the list of projects with implementation delays both because of slow disbursement (over 18 months to 1st disbursement and 12-month project delay). What is meant by splitting the project into three components and what is an "FA" and how long did it take to select one and why so long? Was the selection of the FA the cause of the delay or were there other reasons? | Delay caused by the change in financial agent from CIB, which was liquidated, to CEB after project approval. Umbrella project consists of two subprojects and technical assistance (three components total). Fujian Jintong Fine Chemical Co.: Infrastructure construction completed. LPG storage station built and safety facilities for storage, such as a water pool and air-pressure station are approaching completion. Procurement for the LCD alarm facility, semi-automatic filling machine and testing instrument is underway. Expected completion is August 2001. Fujian Light Industrial Co.: Safety training for enterprise managers, technicans, testing staff, workshop leaders and technical workers is underway. Nine aerosol factories closed and five converted. Shanghai Perfume Research Institute: Safety specification was approved by the Light Industry Association. There have been four sample tests to be passed and 3 have already passed. | 34
CPR/ARS/24/INV/244 | The response does not address the question highlighted in red in the column to the right | This condition was satisfied years ago with a document from the Financial Agent which has the list of baseline equipment to be destroyed | 37
CPR/ARS/24/INV/244 | The condition of approval for this project was that "Project implementation should not go forward until a list of equipment to be destroyed or made unusable has been prepared, and an undertaking given by the enterprise concerned that the dismantling or destruction will be carried out." Has such a list been compiled and if so, please provide to fulfill the condition. We note that 18 per cent of the project budget has been disbursed. | Two hand-operated filling machines dismantled. For disbursement, as of May 2002, 60% of the total grant has been disbursed. | 37
CPR/ARS/43/PRP/415 | Since China is preparing the MDI sector plan, is not the mode of payment retroactive payments (code: D) instead of disbursement during implementation (code: I)? | The mode of payment for the project preparation of the MDI sector plan is disbursement during implementation. The country took time to select a consultant as reported. Once the consultant was selected, work could commence and disbursement could start. The disbursement consequently started in February 2006 but this could not be recorded for the 2005 reporting period. | 49
CPR/ARS/44/PRP/422 | Please clarify how UNIDO claimed that this project was ready for submission to the 50th Meeting when we were considering in January 2006 whether this should be deferred until 2007. Since no funds were used in 2005, should not the remaining funds be returned since the projects have already been prepared? | The plan is under preparation in cooperation with SEPA and the State Food and Drug Administration of China. Contract was signed last year and US$69,000 were obligated in 2005. According to the contract, the report should be ready in July/August 2006, however, due to the recent decision of the ExCom, activities have slowed down and the work is now planned to be completed in the fourth quarter of 2006. | 49
CPR/ARS/44/PRP/422 | UNIDO reported that the preparation of a MDI sector plan will be ready by mid-2007 for submission to the Executive Committee. The project is planned for completion by July 2007. At the time of reporting, only US$ 43 had been spent, since December 2004, and only US$ 69,000 was reported as obligated, which is the same amount that had been reported obligated in 2005. Is this project now expected for submission to the 53rd Meeting? | A contract was signed with a national consultancy company already last year. The work is progressing. | 52
CPR/ARS/51/INV/447 | The report provided at the 65th and 66th Meetings are quite similar and the new information is the completion of the 2 out of 14 TA activities. In this regard, kindly confirm the 2 TA were completed after le 65th Meeting to justify a "Some progress". | The reason for indicating “some progress” is that the two technical assistance activities were completed and because a number of the enterprises are awaiting approval of their registered alternative pharmaceutical applications with the FDA which are estimated to take two years. Thus, one can consider that the project is moving forward with the FDA’s ongoing process of review and approval. | 66Delays
CPR/ARS/51/INV/447 | (a) How has the Bank ensured that intellectual property rights are protected in development of alternatives? (b) What impact does the failure of alternatives have on the completion of the project, for example, does this mean that the Bank will have to continue to seek alternatives until one is found to work according to some definition of success of alternatives? | (a) Protection of intellectual property rights is the domain of the Government of China and beyond the scope of this project. Iin terms of Chinese law, for the registration of new formulas, an enterprise is to observe Article 18 of the Drug Registration Regulation translated as: “Regarding the drug or its formula, production process, indication etc., the applicant shall submit documents explaining the China patent status and ownership rights. If another party holds a patent in China, the applicant shall submit a letter stating that the drug will not infringe on the patent rights of others. Upon acceptance of the application, drug administration authorities should publicly disclose the statement submitted by applicant”. (b) The project is aimed at finding substitute excipients used in pharmaceutical aerosols and entails the change to the substitute up through registration of the CFC-free aerosol application/drug with the State Food and Drug Association (SFDA). When this is done for all beneficiary enterprises that have developed substitutes and wish to register their products, the project will be completed. | 65Delays
CPR/ARS/51/INV/447 | Please provide a status report on project progress | A total number of 37 applications out of 49 applications have been submitted by pharmaceutical aerosol manufacturers. SFDA has completed review of 19 applications. A remaining 18 applications are pending. Since the new regulation issued in 2007 and which became effective recently requires all future review of applications be done based on the national standards, instead of enterprises' own standards, the 18 pending applications may have to wait until the new standards are issued in early 2013. In the meantime, SFDA continues to review these pending applications in order to be able to finalize its review as soon as the new standards become available. There are 12 applications that have not been submitted for SFDA's review. Consultant contracts to undertake development of quality standards for HFC-134a, HFC-227, CO2, HC-600a will be granted by FECO by October. Tasks are expected to be completed in 2013. | 68Delays
CPR/ARS/51/INV/447 | It is reported that the project will be completed in September 2014. On this basis, the Secretariat would like to remind IBRD that as per decision 70/7, this project should be completed in 2013 and funds balances returned by 31 December 2014. | Decision 70/7(b)(ii) states, “not to incur any new commitments and to return, by the end of 2013, the fund balances for the following projects approved before 2009,” and goes on to identify the projects in question in the following subparagraph (a.), which are “the projects indicated in Table 1 of Annex VII” to the 71st meeting report. The project CPR/ARS/51/INV/447 is not listed in Annex VII of the meeting report. Moreover, our understanding was that this part of the decision applied to tranches of ongoing national or terminal phaseout management plans. The China pharmaceutical aerosol project was approved as a “one-off” phaseout project. | 71Delays
CPR/ARS/51/INV/447 | (a) Why was the project kept open after the expected closing in June 2013, (moreover, the project was not completed as at 31 December 2013 as mentioned at the Inter-agency Coordination Meeting in February 2014) with additional payments in 2014 and possibly more until the end of 2014? (b) Why should funds not be returned until the end of 2015? (c) We note that there are US $1.1 million that has been disbursed to China but not returned as at the end of 2013 according to the column on disbursements from FECO. Was the US $1.1 million balance including the US $900,000 disbursement in the first quarter of 2014 or was the US $1.1 million after the US $900,000 disbursement? | (a) The project faced delay since a number of companies are still in the process of securing SFDA registration for their products using the new formulations. The project has been extended to the end of 2014 to allow the enterprises to secure the registration and to allow disbursement for all activities to be completed. (b) It is not stated anywhere in the report that the funds would be returned at the end of 2015. The remarks indicate that the project would end in 2014 and the balance would be returned in 2015. We believe that it will only take several months for financial completion after the project is physically completed. c) The US$1.1 million is after the US$993,821 disbursement from our understanding. In fact, $993,821 is the cumulative disbursement for TA under the project as of the end of 2013. The revised remarks reflect this understanding. | 73
CPR/ARS/51/INV/447 | Please provie completion date | Jun-15 | 76Delays
CPR/ARS/56/INV/473 | Progress not satisfactory - (a) what are the pending activities under this project. (b) what is the plan for completing these activities. | Main pending activities are: 1) Finalization of the conversion of MDI manufacture with non-ODS alternatives pending registration of products; 2) cancel the production license of CFC based MDI which enterprise will not put into production; 3) regular on-si | 82
CPR/ARS/56/INV/473 | Project should have been completed by the 83rd meeting - (a) Have all activities been completed by 83rd meeting (as per previous decision)? (b) when will the balances be returned? | The project has been completed in June 2019 and all activities of phase-out contracts have been completed. Financial completion is expected within 1 year, i.e. by June 2020 and thus, remaining balances will be returned to the 86th Meeting of the Executive | 84
CPR/ARS/56/INV/473 | It was agreed that the financial completion of the project would be Dec-16. Kindly inform the meeting to which the balance of US $321,729 will be returned to the Fund. | There is no ExCom decision on the closure of this project and the planned completion date of February 2018 has been reported in the 2015 and also in the 2016 Progress and Financial Reports. The project is ongoing. After operational completion, UNIDO will do its utmost to financially close the project ASAP. | 79
CPR/ARS/56/INV/473 | (a) Why is this project already planned to be completed 2 years later than originally planned? (b) There is no mention of any conversions of the 15 production lines, what is the status? | The National Transition Strategy for the Phase-ot of CFCs use in MDI, together with Nomination of the Aerosol MDI as an essential use for 2011 were prepared and submitted to the Secretariat on 30 January 2010. The revision of the draft contract template is underway based on the first term of consultation with enterprises in March 2010. CFC substitution in MDI sector is an issue of technology innovation which rests with many factors including the status of IPR, the production equipment, as well as the development of relevant standards. Most of MDI manufacturers in China have started R&D of salbutamol non-CFC MDI formulations. Two companies have submitted applications for alternative MDIs. However, constrained by many factors such as lengthy clinical trials and expensive equipment for industrial production, the R&D activities are still in pre-clinical stage. Based on the average pace of drug research and approval in China, the alternative products are expected to be approved earliest by the end of 2013 and entering the market not before 2015. As soon as policy and regulations for essential use of CFC are put in place, MEP and SFDA will proceed with awarding contracts based on their implementation work plan. | 61
CPR/ARS/56/INV/473 | Why is this project now planned to be completed in December 2015 with a 23-month delay? | The implementation plan needed to be agreed by UNIDO, SFDA, and MEP/FECO and the coordination required time. CFC substitution in MDI is an innovation of technology, a bypass of intellectual property rights, an update of production equipment and an improvement of standards and product quality. Most MDI manufacturers in China have started the research and development of salbutamol non-CFC MDI formulations. However, these efforts are limited by many factors such as lengthy clinical trials and expensive equipment for industrial production, thus, these research and development projects are still in pre-clinical stage. Considering the average pace of drug research and approval in China, the earliest that alternative products can be approved would be by the end of 2015. | 64
CPR/ARS/56/INV/473 | Kindly note that the Remarks column includes activities to be achieved in 2013. Please indicate if these activities occurred in 2013. | In 2013, the Special Working Group for the MDI project in China modified the work plan based on progress in project implementation in the previous year. According to the new work plan, ToRs were prepared for site supervision of CFC users and manufacturers, as well as ToRs for non-CFC MDI patent analysis. The monitoring and information system was set in place, and the research on the establishment of quality standards for HFC-134a was undertaken. The remaining companies were contacted regarding the contracts, which will be signed in 2014. Arrangements were made to organize the MTOC meeting in Beijing and undertake the inspection on MDI companies by the experts team. | 73
CPR/ARS/56/INV/473 | (a) If 98% of the funds have been disbursed and most of the activities have been completed, why is the planned date of completion Feb-18? (b) As there is limited funds obligated and since the project has already been delayed by 5 years, why can it not be considered completed now? | Final activities need to be reported. Despite those are limited, are substantial in assessing the success of the project. In particular, final report is expected to be submitted, with information company by company on their CFC phase-out for MDI purposes. Though the finalization of the project is before the end of year 2017, we indicated Feb 2018 as completion date to be sure that no more extension will be required. Should the project be completed earlier, UNIDO will communicate it to MLFS without further delay. | 77
CPR/ARS/56/INV/473 | Delayed project - should have been completed by June 2020; no update is available. Please confirm and return balances to the 86th meeting. | A total of 32 ODS Phase-out contracts has been signed with 25 enterprises, whose CFCs consumption composed 99.45% of the consumption in the baseline year 2007, out of which 17 are conversion contracts (including 42 product licenses) and 15 are cancellation contracts (including 27 product licenses). Project has been completed by June 2020. Financial closure is being initiated. | 86
CPR/ARS/62/TAS/505 | (a) The first step for new approvals is the submission of the project document/MOU/grant agreement for signature. Did this occur by the end of 2010? (b) Has this occurred to-date, if not why not? (c) What is the status of the action plan? (d) Have any activities been implemented. | (a) This activity falls under the ODS IV umbrella grant agreement between the World Bank and China, hence there was no need for any new agreement. (b) Not required. (c) There is no action plan. The purpose of the activity is to conduct a verification of CFC production and sales, purchase records at FECO and of selected MDI manufacturers, and of CFC export and import. A summary of existing regulations and policies related to CFC production, use, export/import and MDI use will also be a deliverable. (d) Activities have commenced in 2011. The verification of CFC production for the agreed essential use exemption will be conducted by May 2011. | 64
CPR/DES/59/PRP/494 | This demonstration was supposed to provide information upon which ODS waste could be addressed in China. Based on the remarks, the demonstration has not yet been prepared and is not expected to be prepared until the end of the year. This would reduce its viability. Please indicate what specifically has been achieved with this preparation to-date. | The demonstration project is expected to be submitted to the 65th ExCom Meeting. A survey was undertaken in various cities and provinces on the ODS collected, the available collection and destruction facilities and processes etc. The survey is being assessed by the local experts, after which the financial scheme will be worked out. | 64
CPR/DES/67/DEM/520 | Please explain why this project cannot yet be considered as completed, when disbursement is 100 per cent | The project includes two components, including a bilateral project from Japan. The two components are implemented in close coordination and the activities will be declared completed once all activities on both grants are completed. | 79
CPR/DES/67/DEM/520 | Why is this ODS project not expected to be completed until 2015? | Project duration is 30 months. Since the project is also co-financed by Japan and the funds for the Japanese component was received end December 2012, implementation of the project could only be initiated in 2013. | 70
CPR/DES/67/DEM/520 | Please provide the reason for delay. | During UNIDO's mission to China (March 2014), UNIDO had the opportunity to discuss specifics of the most suitable project implementation modality with the Foreign Economic Cooperation Office of the Ministry of Environmental Protection of the Government of China (FECO/MEP). Such discussion took place due to the challenges found when trying to coordinate the Environmental Protection Bureaus (EPBs) of the provinces participating in the project. An agreement was reached to adapt the project's Implementation Plan in view of these challenges; the updated Implementation Plan was submitted to the EPBs in April for their comments. Comments from EPBs have already been collected, and the revised version of the Implementation Plan including such comments is currently in the process of internal approval at FECO/MEP. Although this procedure requires additional time, both FECO/MEP and UNIDO agree that the additional step ensures a more robust approach to project implementation. As per the updated Implementation Plan, EPBs and not destruction facilities will apply for destruction funding to FECO/MEP once they have signed a destruction agreement with the eligible destruction facilities. With this procedure, project implementation gets aligned with the regulatory framework for waste management in the various provinces where the project is being implemented. In parallel to the administrative project to have the updated Implementation Plan approved, trials for ODS waste destruction have been done at one of the facilities considered for project implementation (plasma facility in Shenzhen). | 73
CPR/DES/67/DEM/520 | why are planned dates for completion different for the 2 componets (UNIDO and Japan) for same project? | Different completion dates are the result of an error; due to internal procedures related to funds management at the time when project implementation was initiated, UNIDO's component shows high disbursement while Japan's component shows very low disbursement. Notwithstanding this, project completion date should reflect the latest date out of the two components, June 2017. | 75
CPR/DES/67/DEM/520 | Explain why project completion was moved to 2018, and why the completion date for the Japan component is 2017. | We agree to move both completion date to December 2017. | 77
CPR/DES/67/DEM/521 | Please provide a brief description of the activities implemented during the first quarter of the year 2014 in the Remarks column (latest information). | During UNIDO's mission to China (March 2014), UNIDO had the opportunity to discuss specifics of the most suitable project implementation modality with the Foreign Economic Cooperation Office of the Ministry of Environmental Protection of the Government of China (FECO/MEP). Such discussion took place due to the challenges found when trying to coordinate the Environmental Protection Bureaus (EPBs) of the provinces participating in the project. An agreement was reached to adapt the project's Implementation Plan in view of these challenges; the updated Implementation Plan was submitted to the EPBs in April for their comments. Comments from EPBs have already been collected, and the revised version of the Implementation Plan including such comments is currently in the process of internal approval at FECO/MEP. Although this procedure requires additional time, both FECO/MEP and UNIDO agree that the additional step ensures a more robust approach to project implementation. As per the updated Implementation Plan, EPBs and not destruction facilities will apply for destruction funding to FECO/MEP once they have signed a destruction agreement with the eligible destruction facilities. With this procedure, project implementation gets aligned with the regulatory framework for waste management in the various provinces where the project is being implemented. In parallel to the administrative project to have the updated Implementation Plan approved, trials for ODS waste destruction have been done at one of the facilities considered for project implementation (plasma facility in Shenzhen). | 73
CPR/DES/67/DEM/521 | (a) Why are planned dates for completion different for the 2 components (UNIDO and Japan) for the same project? | Different completion dates are the result of an error; due to internal procedures related to funds management at the time when project implementation was initiated, UNIDO's component shows high disbursement while Japan's component shows very low disbursement. Notwithstanding this, project completion date should reflect the latest date out of the two components, June 2017. | 75
CPR/DES/67/DEM/521 | 1) All of the funds from the UNIDO MLF component of the destruction project were disbursed as at 31 December 2015, but the remarks indicate that disbursement of the Japanese MLF component was structured not to begin until after the funds were disbursed by UNIDO. Kindly explain. Also, the UNIDO component indicated that ODS had been destroyed at several plants. Will the Japanese component continue to use the same facilities or different facilities. If different facilities kindly indicate why the disbursement of funds for the Japanese component had to wait the completion of the UNIDO component. Kindly note that the planned completion for the Japanese component (June 2016) is before the planned completion date of the UNIDO component (June 2017). Kindly indicate how the Japanese component can be completed before the UNIDO component. This project was originally intended to be completed by January 2015, but it does not appear to have begun implementation. Should not this project be cancelled and funds returned if no projects have been identified since the project was approved in July 2012? 2) Kindly indicate when the project will be completed. | No Response. | 76Status
CPR/DES/67/DEM/521 | (a) Please explain why there is very low disbursement; (b) Why is the completion date different from the UNIDO component for the same project? (c) When will the final report on this project be issued? | a) Low disbursement reflected as funds from both the TF and MP grants were combined in one contract. Disbursements were first made from the MP grant; b) The completion dates have both been adjusted to December 2017; c) The final report on this project will be issued within 6 months after project completion. | 77
CPR/DES/67/DEM/521 | Kindly explain low disbursement, and confirm project completion by the end of 2017 as revised. | The DEMO project for the disposal of unwanted ODSs in China has two components: one funded by MLF and one from Japan as bilateral activity. From the implementation point of view, both components are considered fully integrated in one single project and one single sub-contract to the executing agency (FECO). However, from the contractual point of view, payments have been first booked on the MLF component. The disbursement on the Japanese project component will be reflected in the coming months, according to IPSAS requirements. Expected completion date remain as indicated (i.e. 31 Dec 2017). | 79
CPR/FOA/07/INV/16 | Project with Approved Funding that are not equal to the FUND_ALLOCATED1 in the Inventory. Please correct. | This was a lumpsum amount of contingency funding for nine 50% reduced CFC foam projects (the nine shown below). | 34
CPR/FOA/07/INV/16 | This project is listed with overruns. When the funds authorized by the Committee? If funds have not been authorized, is the Bank asking for these funds at the 34th Meeting or has it assumed the debt from it own resources? | The Bank has absorbed this overrun with its administrative fees. The database has been adjusted. | 34
CPR/FOA/09/TAS/22 | Project with Approved Funding that is different from the FUND_ALLOCATED in the Inventory. Could this be because there was a subsequent adjustment, if so please so indicate? | As discussed, we shifted the budget from "Approved Funding" to "Adjustments" since they were transferred funds from the World Bank. | 34
CPR/FOA/10/INV/42 | Project with Approved Funding that are not equal to the FUND_ALLOCATED1 in the Inventory. Please correct. | The savings shown are, in fact, part of the contingency funds from the $645,000 lumpsum. | 34
CPR/FOA/10/INV/43 | Project with Approved Funding that are not equal to the FUND_ALLOCATED1 in the Inventory. Please correct. | The savings shown are, in fact, part of the contingency funds from the $645,000 lumpsum. | 34
CPR/FOA/10/INV/44 | Project with Approved Funding that are not equal to the FUND_ALLOCATED1 in the Inventory. Please correct. | The savings shown are, in fact, part of the contingency funds from the $645,000 lumpsum. | 34
CPR/FOA/10/INV/44 | This project has a difference between information provided about the amount ODP phased out in the individual project completion reports and the information provided in the progress report. These numbers must be exactly the same. Whichever report is in error (be it the progress report or the project completion report), should be corrected. | We have done a preliminary review of the discrepancies reported in Attachment II. In some cases this appears to relate to confusion in how final ODP should be calculated, including indirect phaseout. This is an issue given that in some cases the inventory includes indirect phaseout and in others not. We are currently checking the original project documents in all reported cases as well as checking with task managers and financial agents. | 28
CPR/FOA/10/INV/45 | Project with Approved Funding that are not equal to the FUND_ALLOCATED1 in the Inventory. Please correct. | The savings shown are, in fact, part of the contingency funds from the $645,000 lumpsum. | 34
CPR/FOA/10/INV/46 | Project with Approved Funding that are not equal to the FUND_ALLOCATED1 in the Inventory. Please correct. | Project transferred to UNDP. Funding $443,000 credited to the MLF at the 17th Meeting. | 34
CPR/FOA/10/INV/47 | Project with Approved Funding that are not equal to the FUND_ALLOCATED1 in the Inventory. Please correct. | The savings shown are, in fact, part of the contingency funds from the $645,000 lumpsum. | 34
CPR/FOA/10/INV/47 | This project has a difference between information provided about the amount ODP phased out in the individual project completion reports and the information provided in the progress report. These numbers must be exactly the same. Whichever report is in error (be it the progress report or the project completion report), should be corrected. | We have done a preliminary review of the discrepancies reported in Attachment II. In some cases this appears to relate to confusion in how final ODP should be calculated, including indirect phaseout. This is an issue given that in some cases the inventory includes indirect phaseout and in others not. We are currently checking the original project documents in all reported cases as well as checking with task managers and financial agents. | 28
CPR/FOA/10/INV/48 | Project with Approved Funding that are not equal to the FUND_ALLOCATED1 in the Inventory. Please correct. | The savings shown are, in fact, part of the contingency funds from the $645,000 lumpsum. | 34
CPR/FOA/10/INV/48 | This project has a difference between information provided about the amount ODP phased out in the individual project completion reports and the information provided in the progress report. These numbers must be exactly the same. Whichever report is in error (be it the progress report or the project completion report), should be corrected. | We have done a preliminary review of the discrepancies reported in Attachment II. In some cases this appears to relate to confusion in how final ODP should be calculated, including indirect phaseout. This is an issue given that in some cases the inventory includes indirect phaseout and in others not. We are currently checking the original project documents in all reported cases as well as checking with task managers and financial agents. | 28
CPR/FOA/10/INV/49 | Project with Approved Funding that are not equal to the FUND_ALLOCATED1 in the Inventory. Please correct. | The savings shown are, in fact, part of the contingency funds from the $645,000 lumpsum. | 34
CPR/FOA/10/INV/49 | This project has a difference between information provided about the date completed in the individual project completion reports and the information provided in the progress report. This can be very significant because for example, one of the performance indicators for non-investment projects is the number of projects completed during the business planning year. If a non-investment project was classified as completed in 1997 it counted against that performance indicator. It cannot now be counted against the same indicator for projects to be completed in 1998. | There appear to be a number of factors at play in causing the discrepancies on completion dates. First, per ExCom decision, project completion reports are due 6 months after physical completion. Therefore, the date included as completion in the PCR should be the date of physical completion. There may, however, be confusion on the part of financial agents and task managers on which date to provide, especially on back-logged projects which were already financially complete. We are investigating this. In addition, you can see that this confusion is possible given that your own table included in Attachment I lists both FIN and COM dates in the status column. For the information required this should only include COM dates. Comparison should be made between COM dates in the Progress Report and physical completion dates in the PCRs. We are currently checking: (1) COM dates per PCR dates and (2) whether the date provided in the PCR is financial or physical completion. Once these issues are resolved we will make the final changes to the PCR and PR. | 28
CPR/FOA/10/INV/49 | This project has a difference between information provided about the amount ODP phased out in the individual project completion reports and the information provided in the progress report. These numbers must be exactly the same. Whichever report is in error (be it the progress report or the project completion report), should be corrected. | We have done a preliminary review of the discrepancies reported in Attachment II. In some cases this appears to relate to confusion in how final ODP should be calculated, including indirect phaseout. This is an issue given that in some cases the inventory includes indirect phaseout and in others not. We are currently checking the original project documents in all reported cases as well as checking with task managers and financial agents. | 28