## tbProgress
meeting_of_report | code | status | Latest Status | Assessment of Progress | Latest Progress | agency | project_title | multi-year/one-off phaseout/individual/rmp/rmp update | region | country | sector | mtg | type | num | a_n | o_t | irdx | chemical | consumption_odp_out_proposal | consumption_odp_out_actual | production_odp_out_proposal | production_odp_out_actual | date_approved | date_first_disbursement | date_comp_proposal | date_comp_plan | date_comp_actual | date_comp_financial | funds_approved | funds_adjustment | funds_net | funds_disbursed | percent_disbursed | balance | funds_obligated | funds_current_year | support_approved | support_adjustment | support_disbursed | support_balance | support_obligated | support_returned(37only) | year_approved | months_first_disbursement | months_comp_proposal | months_comp_plan | months_comp_actual | remarks_1 | remarks_2 | year_of_contribution | date_comp_plan_22 | date_comp_plan_28 | date_comp_plan_31 | date_comp_plan_34 | date_comp_plan_37 | date_comp_plan_40 | date_comp_plan_43 | date_comp_plan_46 | date_comp_plan_49 | date_comp_plan_52 | date_comp_plan_55 | Latest_Planned_Date | BP_Year | BP_Allocation | Disbursements made to final beneficiaries from FECO/ MEP | MY_consumption_performance_target | MY_actual_consumption | MY_production_performance_target | MY_actual_production | MY_annual_target_met | MY_verification_completed | MY_verification_report
73Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
75 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
75Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
77 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
77Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
79 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
79Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
82 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
82Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
84 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
84Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
86 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
86Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
88 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
88Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
91 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
91Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
31 | COS/FUM/27/DEM/15 | ONG | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers |  | LAC | COS | FUM | 27 | DEM | 15 | N | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 2000-10-01 | 2000-10-01 |  |  | 193500 | 0 | 193500 | 7295 | 0.0377 | 186205 |  | 87624.3303 | [6 empty] | 1999 | 8 | 19 | 19 |  | MeBr projects presented at " Annual Int.Research Conf.on MeBr and Emission Reductions", San Diego (USA),Nov 99.Workshop with the participation of users and international experts planned for April-00.
34 | COS/FUM/27/DEM/15 | ONG | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers |  | LAC | COS | FUM | 27 | DEM | 15 | N | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 2000-10-01 | 2001-12-01 |  |  | 193500 | 0 | 193500 | 117184 | 0.6056 | 76316 |  | 60219.81 | [6 empty] | 1999 | 8 | 19 | 33 |  | MeBr projects presented at " Annual Int.Research Conf.on MeBr and Emission Reductions", Florida (USA),Nov 00.Workshop with the participation of users and international experts in April-00.
34Final | COS/FUM/27/DEM/15 | ONG | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers |  | LAC | COS | FUM | 27 | DEM | 15 | N | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 2000-10-01 | 2001-12-01 |  |  | 193500 | 0 | 193500 | 117184 | 0.6056 | 76316 |  | 57740 | [6 empty] | 1999 | 8 | 19 | 33 |  | MeBr projects presented at " Annual Int.Research Conf.on MeBr and Emission Reductions", Florida (USA),Nov 00.Workshop with the participation of users and international experts in April-00.
35 | COS/FUM/27/DEM/15 |  | FIN | Completed |  | UNDP | [41 empty] | Project Completed. Final project workshops were held with all stakeholders in May and June 2001. Demonstration results have been analysed and final report will be submitted together with Investment Project Proposal to the 35th ExCom Meeting.
37 | COS/FUM/27/DEM/15 | COM | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers |  | LAC | COS | FUM | 27 | DEM | 15 | N | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 |  | 193500 | 0 | 193500 | 187863.06 | 0.97087 | 5636.94 |  | 3972.2815 | 25155 |  | 24422.1978 |  |  | 0 | 1999 | 8 | 19 |  | 33 | Completed in 2001. Results used to prepare inv project (approved at 35th ExCom) to eliminate MB consumption in soil furmigation | [14 empty] | 1999 | Investment
37Final | COS/FUM/27/DEM/15 | COM | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers |  | LAC | COS | FUM | 27 | DEM | 15 | N | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 |  | 193500 | 0 | 193500 | 187863.06 | 0.97087 | 5636.94 |  | 3739.7663 | 25155 |  | 24422.1978 |  |  | 0 | 1999 | 8 | 19 |  | 33 | Completed in 2001. Results used to prepare inv project (approved at 35th ExCom) to eliminate MB consumption in soil furmigation | [14 empty] | 1999 | Investment
40 | COS/FUM/27/DEM/15 | COM | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-03-01 |  | 193500 | 0 | 193500 | 193383 | 0.9994 | 117 | 0 | 63.8741 | 25155 | 0 | 25139.79 | 15.21 | 25139.79 | 0 | 1999 | 8 | 19 | 0 | 24 | Completed in 2001. | [14 empty] | 1999 | Investment
40Final | COS/FUM/27/DEM/15 | COM | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 |  | 193500 | 0 | 193500 | 193383 | 0.9994 | 117 | 0 | 64 | 25155 | 0 | 25139.79 | 15.21 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. | [14 empty] | 1999 | Investment
43Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 25140 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Operationally completed in 2001. PCR submitted in 2003. Financially completed in 2003. | [14 empty] | 1999 | Investment
46 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 25140 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
46Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 25140 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
49 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 25140 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
49Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 25140 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
52 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 25140 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
52Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 25140 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
55 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 100 | 0 | 0 | 0 | 25155 | -15 | 25140 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
55Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 25140 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
58Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0 |  | 0 | 0 | 1999 | 8 | 19 |  | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
61 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
61Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
64 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15.21 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
64Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
67 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15.21 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
67Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15.21 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
70 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
70Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
73 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0.21 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
73Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0.21 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
75 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15.21 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
75Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0.21 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
77 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0.21 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
77Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0.21 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
79 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15.21 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
79Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15.21 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
82 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0.21 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
82Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15.21 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
84 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15.21 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
84Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15.21 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
86 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0.21 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
86Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0.21 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
88 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0.21 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
88Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0.21 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
91 | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0.21 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
91Final | COS/FUM/27/DEM/15 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 1 | 0 | 0 | 0 | 25155 | -15 | 0.21 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
31 | COS/FUM/29/PRP/21 | ONG | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I | [5 empty] | 1999-11-01 |  | 2000-12-01 | 2000-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0 | 30000 | [8 empty] | 1999 | 0 | 13 | 13 | 0 | projet nouvellement approuvé |  | 1999
34 | COS/FUM/29/PRP/21 | ONG | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I | [5 empty] | 1999-11-01 |  | 2000-12-01 | 2000-12-01 |  |  | 30000 | 0 | 30000 |  | 0 | 30000 | [8 empty] | 1999 | 0 | 13 | 13 | 0 | les modalités de coopération entre le FFEM et la FAO sont en cours de discussion |  | 1999
34 | COL/SOL/31/INV/45 | ONG | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco |  | LAC | COL | SOL | 31 | INV | 45 | N | O | I |  | 7.6 |  |  |  | 2000-07-01 |  | 2002-08-01 | 2002-12-01 |  |  | 81579 | 0 | 81579 | 0 | 0 | 81579 |  | 24473.7 | [6 empty] | 2000 |  | 25 | 29 |  | The enterprise is preparing the documentation for the Bank approval of the technical proposal to built the new equipment. Delays in signing of subgrant agreement. The subgrant agreement is expected to be signed in May 2001.
34Final | COL/SOL/31/INV/45 | ONG | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco |  | LAC | COL | SOL | 31 | INV | 45 | N | O | I |  | 7.6 |  |  |  | 2000-07-01 |  | 2002-08-01 | 2002-12-01 |  |  | 81579 | 0 | 81579 | 0 | 0 | 81579 |  | 40790 | [6 empty] | 2000 | 0 | 25 | 29 | 0 | The enterprise is preparing the documentation for the Bank approval of the technical proposal to built the new equipment. Delays in signing of subgrant agreement. The subgrant agreement is expected to be signed in May 2001.
37 | COL/SOL/31/INV/45 | ONG | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco |  | LAC | COL | SOL | 31 | INV | 45 | N | O | I |  | 7.6 | 0 |  |  | 2000-07-01 |  | 2002-08-01 | 2002-12-01 |  |  | 81579 | 0 | 81579 | 0 | 0 | 81579 |  | 50000 | 10605.27 |  | 0 |  |  | 0 | 2000 | 0 | 25 | 29 | 0 | As the technology is tailor-made according to the enterprise's special circumstances, delayed occurred in planning of technical component. Technical specifications for equipment ready. The SGA is expected to be signed by May 2002. | [14 empty] | INV | 2000
37Final | COL/SOL/31/INV/45 | ONG | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco |  | LAC | COL | SOL | 31 | INV | 45 | N | O | I |  | 7.6 | 0 |  |  | 2000-07-01 |  | 2002-08-01 | 2003-05-01 |  |  | 81579 | 0 | 81579 | 0 | 0 | 81579 |  | 50000 | 10605.27 |  | 0 |  |  | 0 | 2000 | 0 | 25 | 34 | 0 | As the technology is tailor-made according to the enterprise's special circumstances, delayed occurred in planning of technical component. Technical specifications for equipment ready. The SGA is expected to be signed by May 2002. | [14 empty] | 2000 | INV
40 | COL/SOL/31/INV/45 | ONG | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 0 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 | 2003-10-01 |  |  | 81579 | 0 | 81579 | 49000 | 0.60064 | 32579 | 32579 | 32579 | 10605.27 | 0 | 6369.99 | 4235.28 | 4235.28 | 0 | 2000 | 29 | 25 | 39 | 0 | Change in expected completion date due to delays in completion of designs of new production line, performed specifically for the enterprise by a specialized consultant. Designs have been completed. Construction works to remodel existing plant facilities to start Jan. 03. Manufacturing of new equipment is expected to be completed by the 3rd trimester of 2003. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
40Final | COL/SOL/31/INV/45 | ONG | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 0 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 | 2003-10-01 |  |  | 81579 | 0 | 81579 | 49000 | 0.60064 | 32579 | 32579 | 32579 | 10605.27 | 0 | 6369.99 | 4235.28 | 4235.28 | 0 | 2000 | 29 | 25 | 39 | 0 | Change in expected completion date due to delays in completion of designs of new production line, performed specifically for the enterprise by a specialized consultant. Designs have been completed. Construction works to remodel existing plant facilities to start Jan. 03. Manufacturing of new equipment is expected to be completed by the 3rd trimester of 2003. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
41 | COL/SOL/31/INV/45 |  | FIN | Progress |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | [29 empty] | 0 |  | 0 |  |  | 0 | [5 empty] | Phase I of the project, the upgrade of plant facilities, has been completed. Phase II, equipment development and installation, is currently underway. Providers have been selected and contracts have been awarded. Delivery of all new equipment is expected before the end of 2003.
42 | COL/SOL/31/INV/45 |  | FIN | Some Progress |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | [29 empty] | 0 |  | 0 |  |  | 0 | [5 empty] | Phase II of the project, equipment development and installation, has been completed. Phase III, trials runs and personnel training, is currently underway. A few delays were experienced to begin Phase III due to problems with the selection of providers. Project is expected to be completed during the first quarter of 2004.
43 | COL/SOL/31/INV/45 | ONG | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 0 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 | 2004-05-01 |  |  | 81579 | 0 | 81579 | 72000 | 88.25 | 9579 | 9579 | 9579 | 10605.27 | 0 | 9360 | 1245.27 | 1245.27 | 0 | 2000 | 29 | 25 | 46 | 0 | Phase II of the project, equipment development and installation, completed. Phase III, trial runs and personnel training, currently underway. A few delays were experienced to begin Phase III due to problems with the selection of contractors. Project is expected to be physically and financially completed during Q1 2004. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
43Delays | COL/SOL/31/INV/45 |  | FIN | Some Progress |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | [29 empty] | 0 |  | 0 |  |  | 0 | [5 empty] | Phase III, the final phase of the project - training - has been completed. The project will close by mid-2004.
43Final | COL/SOL/31/INV/45 | ONG | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 0 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 | 2004-05-01 |  |  | 81579 | 0 | 81579 | 72000 | 0.88258 | 9579 | 9579 | 9579 | 10605.27 | 0 | 9360 | 1245.27 | 1245.27 | 0 | 2000 | 29 | 25 | 46 | 0 | Phase II of the project, equipment development and installation, completed. Phase III, trial runs and personnel training, currently underway. A few delays were experienced to begin Phase III due to problems with the selection of contractors. Project is expected to be physically and financially completed during Q1 2004. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
44 | COL/SOL/31/INV/45 |  | FIN | Completed |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | [29 empty] | 0 |  | 0 |  |  | 0 | [5 empty] | Project has been physically completed: full ODS-free production, at full capacity, started in July 2004. No equipment disposal was required, as per project proposal, but silicone-based coating equipment was retrofitted.
46 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 10605.27 | 0 | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
46Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 10605.27 | 0 | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
49 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 10605.27 | 0 | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
49Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 10605.27 | 0 | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
52 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 10605.27 | 0 | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
52Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 10605.27 | 0 | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
55 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 10605.27 | 0 | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
55Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 10605.27 | 0 | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
58Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
61 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [14 empty] | 6/22/1905 | INV |  | 0 | 0 | 0 | 0
61Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
64 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
64Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [14 empty] | 2000 | INV |  | 0 | 0 | 0 | 0
67 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV
67Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV
70 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV
70Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV
73 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV
73Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV
75 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV | 0
75Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV | 0
77 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV | 0
77Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV | 0
79 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV | 0
79Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605.27 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV | 0
82 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV | 0
82Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 |  | 10605 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV | 0
84 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 | 0 | 10605 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV | 0
84Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 | 0 | 10605 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV | 0
86 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 | 0 | 10605 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV | 0
86Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 | 0 | 10605 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV | 0
88 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 | 0 | 10605 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV | 0
88Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 | 0 | 10605 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. | [15 empty] | INV | 0
91 | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 | 0 | 10605 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. |  | 2000 | [13 empty] | INV | 0
91Final | COL/SOL/31/INV/45 | FIN | FIN |  |  | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N |  | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 1 | 0 | 0 | 0 | 10605 | 0 | 0 |  | 0 | 0 | 2000 | 29 | 25 | 0 | 53 | Project is physically and financially completed. |  | 2000 | [13 empty] | INV | 0
40 | COL/SOL/36/PRP/53 | ONG | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 | 2003-04-01 |  |  | 20000 | 0 | 20000 | 8000 | 0.4 | 12000 | 12000 | 12000 | 2600 | 0 | 1040 | 1560 | 1560 | 0 | 2002 | 9 | 13 | 13 | 0 | Project preparation is ongoing. Primary consumer of CTC in Colombia has been contacted and has expressed interest in participating in project. Preliminary information related to its conversion to non-ODS technologies has been obtained. Survey of remaining CTC consumption will be commissioned in order to prepare CTC sector phase-out project. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
40Final | COL/SOL/36/PRP/53 | ONG | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 | 2003-04-01 |  |  | 20000 | 0 | 20000 | 8000 | 0.4 | 12000 | 12000 | 12000 | 2600 | 0 | 1040 | 1560 | 1560 | 0 | 2002 | 9 | 13 | 13 | 0 | Project preparation is ongoing. Primary consumer of CTC in Colombia has been contacted and has expressed interest in participating in project. Preliminary information related to its conversion to non-ODS technologies has been obtained. Survey of remaining CTC consumption will be commissioned in order to prepare CTC sector phase-out project. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
43 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | 0 | 20000 | 8000 | 40 | 12000 | 12000 | 0 | 2600 | 0 | 1040 | 1560 | 1560 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
43Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | 0 | 20000 | 8000 | 0.4 | 12000 | 0 |  | 2600 | 0 | 1040 | 1560 | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
46 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 1040 | 0 | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
46Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 1040 | 0 | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
49 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 1040 | 0 | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
49Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 1040 | 0 | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
52 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 1040 | 0 | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
52Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 1040 | 0 | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
55 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 1040 | 0 | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
55Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 1040 | 0 | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
58Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
61 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [14 empty] | 6/24/1905 | Non-INV |  | 0 | 0 | 0 | 0
61Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
64 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
64Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [14 empty] | 2002 | Non-INV |  | 0 | 0 | 0 | 0
67 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV
67Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV
70 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV
70Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV
73 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV
73Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV
75 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV | 0
75Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV | 0
77 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV | 0
77Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV | 0
79 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV | 0
79Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV | 0
82 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV | 0
82Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 |  | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV | 0
84 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 | 0 | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV | 0
84Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 | 0 | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV | 0
86 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 | 0 | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV | 0
86Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 | 0 | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV | 0
88 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 | 0 | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV | 0
88Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 | 0 | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [15 empty] | Non-INV | 0
91 | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 | 0 | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. |  | 2002 | [13 empty] | Non-INV | 0
91Final | COL/SOL/36/PRP/53 | FIN | FIN |  |  | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A |  | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 1 | 0 | 0 | 0 | 2600 | -1560 | 0 |  | 0 | 0 | 2002 | 9 | 13 | 0 | 10 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. |  | 2002 | [13 empty] | Non-INV | 0
13 | COS/FOA/08/TRA/05 |  | FIN |  |  | UNDP | Seminar/Workshop in the foam sector |  | LAC | COS | FOA | 8 | TRA | 5 | [33 empty] | Activity is part of UNDP project number COS/92/G63 which was signed in May 94 and is nationally executed. Activities will be implemented from June 1994 onwards tied to project preparation activities. Funds will be disbursed as per budget
15 | COS/FOA/08/TRA/05 |  | FIN |  |  | UNDP | Seminar/Workshop in the foam sector |  | LAC | COS | FOA | 8 | TRA | 5 | [33 empty] | Project document signed in May 94 and is nationally executed. Activities are being implemented tied to project preparation activities. Funds disbursed as per budget schedule.
17 | COS/FOA/08/TRA/05 |  | FIN |  |  | UNDP | Seminar/Workshop in the foam sector |  | LAC | COS | FOA | 8 | TRA | 5 | [33 empty] | Ongoing. Project document signed in May 94 and is nationally executed. Activities are being implemented tied to project preparation activities. Funds disbursed as per budget schedule.
18 | COS/FOA/08/TRA/05 |  | FIN |  |  | UNDP | Seminar/Workshop in the foam sector |  | LAC | COS | FOA | 8 | TRA | 5 | [33 empty] | Despite efforts by UNDP to accelerate implementation, no Govt. action to date. By end-95, UNDP may either revise project with firm workplan, or close project and revert funds.
19 | COS/FOA/08/TRA/05 | ONG | FIN |  |  | UNDP | Seminar/Workshop in the foam sector |  | LAC | COS | FOA | 8 | TRA | 5 |  |  |  |  | 0 |  |  |  | 1992-10-01 |  | 1994-09-01 |  | 1996-07-01 |  | 21120 | 0 |  | 6770 | 0.32055 | 0 | [13 empty] | Despite efforts by UNDP to accelerate implementation, very little Govt. action to date. UNDP is seeking Govt concurrence to closing the project or transforming it. | Delay--1 year 2 months. UNDP considering closing in dec/95.
20 | COS/FOA/08/TRA/05 | ONG | FIN |  |  | UNDP | Seminar/Workshop in the foam sector |  | LAC | COS | FOA | 8 | TRA | 5 | N | O | I |  | 0 | 0 |  |  | 1992-10-01 |  | 1994-09-01 | 1996-12-01 |  |  | 21120 | 0 | 21120 | 0 | 0 | 21120 |  | 21120 | [7 empty] | 0 | 23 | 50 | 0 | After visit by UNDP staff in May 96, government counterpart proposes to hold workshop in fall 1996. Arrangements being finalized.
22 | COS/FOA/08/TRA/05 | ONG | FIN |  |  | UNDP | Seminar/Workshop in the foam sector** |  | LAC | COS | FOA | 8 | TRA | 5 | N | O | I |  | 0 | 0 |  |  | 1992-10-01 | 0 | 1995-10-01 | 1997-05-01 |  |  | 21120 | 0 | 21120 | 0 | 0 | 21120 |  | 8610 | [6 empty] | 1993 | 0 | 36 | 55 | 0 | Workshops dates proposed for April/May 97. Two international consultants will participate at workshop, one in flexible and one in rigid foam.
25 | COS/FOA/08/TRA/05 | COM | FIN |  |  | UNDP | Seminar/Workshop in the foam sector |  | LAC | COS | FOA | 8 | TRA | 5 | N | O | I |  | 0 | 0 |  |  | 1992-10-01 | 1997-04-01 | 1995-10-01 |  | 1997-04-01 |  | 21120 | 0 | 21120 | 13635 | 0.6456 | 7485 |  | 6737 | [6 empty] | 1992 | 54 | 36 |  | 54 | Completed. Workshops with participation of two international consultants, one in flexible and one in rigid foam took place in April 1997, completing this activity. |  |  | 1997-05-01
28 | COS/FOA/08/TRA/05 | COM | FIN |  |  | UNDP | Seminar/Workshop in the foam sector |  | LAC | COS | FOA | 8 | TRA | 5 | N | O | I |  | 0 | 0 |  |  | 1992-10-01 | 1997-04-01 | 1995-10-01 |  | 1997-04-01 |  | 21120 | 0 | 21120 | 18923 | 0.9 | 2197 |  | 1098.5 | [6 empty] | 1992 | 54 | 36 |  | 54 | Completed. |  |  | 1997-05-01
31 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/Workshop in the foam sector |  | LAC | COS | FOA | 8 | TRA | 5 | N | O | I |  | 0 | 0 |  |  | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 1999-12-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 |  | 0 | [6 empty] | 1992 | 49 | 36 |  | 49 | Completed in 1996. Financially closed.
34 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/Workshop in the foam sector |  | LAC | COS | FOA | 8 | TRA | 5 | N | O | I |  | 0 | 0 |  |  | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 1999-12-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 |  | 0 | [6 empty] | 1992 | 49 | 36 |  | 49 | Completed in 1996. Financially closed.
34Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/Workshop in the foam sector |  | LAC | COS | FOA | 8 | TRA | 5 | N | O | I |  | 0 | 0 |  |  | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 1999-12-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 |  | 0 | [6 empty] | 1992 | 49 | 36 |  | 49 | Completed in 1996. Financially closed.
37 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/Workshop in the foam sector |  | LAC | COS | FOA | 8 | TRA | 5 | N | O | I |  | 0 | 0 |  |  | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 1999-12-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 |  | 0 | 2746 |  | 2746 |  |  | 0 | 1992 | 49 | 36 |  | 49 | Completed in 1996. Financially completed. | [14 empty] | 1992 | Non-Investment
37Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/Workshop in the foam sector |  | LAC | COS | FOA | 8 | TRA | 5 | N | O | I |  | 0 | 0 |  |  | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 1999-12-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 |  | 0 | 2746 |  | 2746 |  |  | 0 | 1992 | 49 | 36 |  | 49 | Completed in 1996. Financially completed. | [14 empty] | 1992 | Non-Investment
40 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 1999-12-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 2746 | 0 | 2746 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 1999. PCR submitted in Jan-2000. | [14 empty] | 1992 | Non-Investment
40Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 1999-12-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 2746 | 0 | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 1999. PCR submitted in Jan-2000. | [14 empty] | 1992 | Non-Investment
43Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 2746 | 0 | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Operationally completed in 1996. PCR submitted in 2000. Financially completed in 2003. | [14 empty] | 1992 | Non-Investment
46 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 2746 | 0 | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. | [14 empty] | 1992 | Non-Investment
46Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 2746 | 0 | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. | [14 empty] | 1992 | Non-Investment
49 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 2746 | 0 | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. | [14 empty] | 1992 | Non-Investment
49Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 2746 | 0 | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. | [14 empty] | 1992 | Non-Investment
52 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 2746 | 0 | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. | [14 empty] | 1992 | Non-Investment
52Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 2746 | 0 | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. | [14 empty] | 1992 | Non-Investment
55 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 100 | 0 | 0 | 0 | 2746 | 0 | 2746 | 0 | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. | [14 empty] | 1992 | Non-Investment
55Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 2746 | 0 | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. | [14 empty] | 1992 | Non-Investment
58Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0 |  | 0 | 0 | 1992 | 49 | 36 |  | 49 | Completed in 1996. Financially completed in 2003. | [14 empty] | 1992 | Non-Investment
61 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. | [14 empty] | 1992 | Non-Investment
61Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. | [14 empty] | 1992 | Non-Investment
64 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2745.6 | 0 | 0 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. | [14 empty] | 1992 | Non-Investment
64Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2745.6 | 0.4 | 0 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. | [14 empty] | 1992 | Non-Investment
67 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2745.6 | 0 | 0 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
67Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2745.6 | 0 | 0 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
70 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
70Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
73 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0.4 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
73Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0.4 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
75 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2745.6 | 0 | 0 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
75Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0.4 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
77 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0.4 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
77Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0.4 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
79 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2745.6 | 0 | 0 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
79Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2745.6 | 0 | 0 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
82 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0.4 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
82Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0.4 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
84 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2745.6 | 0 | 0 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
84Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2745.6 | 0 | 0 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
86 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0.4 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
86Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0.4 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
88 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 |  |  | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0.4 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
88Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 |  |  | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0.4 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
91 | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0.4 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
91Final | COS/FOA/08/TRA/05 | FIN | FIN |  |  | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 8 | TRA | 5 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 1 | 0 | 0 | 0 | 2746 | 0 | 0.4 |  | 0 | 0 | 1992 | 49 | 36 | 0 | 49 | Completed in 1996. Financially completed in 2003. |  | 1992 | [13 empty] | Non-Investment
28 | COS/FUM/24/PRP/12 | COM | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects |  | LAC | COS | FUM | 24 | PRP | 12 | N | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 |  | 40000 | 0 | 40000 | 1500 | 0.0375 | 38500 |  | 22950 | [6 empty] | 1998 | 1 | 9 |  | 9 | Completed. National expert was hired. Two missions to Costa Rica. International consultants to be paid. Two projects: melons and cut flowers prepared for subm. to the 27th ExCom in March 1999.
31 | COS/FUM/24/PRP/12 | COM | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects |  | LAC | COS | FUM | 24 | PRP | 12 | N | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 |  | 40000 | 0 | 40000 | 11375 | 0.28438 | 28625 |  | 22900 | [6 empty] | 1998 | 1 | 9 |  | 9 | Completed in 1998. Final budget revision was not issued due to delays resulting from programme management and financial system conversions. Unspent balance could be returned as soon as accounts can be closed.
34 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects |  | LAC | COS | FUM | 24 | PRP | 12 | N | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 |  | 0 | [6 empty] | 1998 | 1 | 9 |  | 9 | Completed in 1998. Financially closed in December 2000.
34Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects |  | LAC | COS | FUM | 24 | PRP | 12 | N | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 |  | 0 | [6 empty] | 1998 | 1 | 9 |  | 9 | Completed in 1998. Financially closed in December 2000.
37 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects |  | LAC | COS | FUM | 24 | PRP | 12 | N | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 |  | 0 | 5200 |  | 5200 |  |  | 0 | 1998 | 1 | 9 |  | 9 | Completed in 1998. Financially completed. | [14 empty] | 1998 | Investment
37Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects |  | LAC | COS | FUM | 24 | PRP | 12 | N | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 |  | 0 | 5200 |  | 5200 |  |  | 0 | 1998 | 1 | 9 |  | 9 | Completed in 1998. Financially completed. | [14 empty] | 1998 | Investment
40 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 5200 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. | [14 empty] | 1998 | Investment
40Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. | [14 empty] | 1998 | Investment
43Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Operationally completed in 1998. Financially completed in 2000. Remaining financial issues under investigation. | [14 empty] | 1998 | Investment
46 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. | [14 empty] | 1998 | Investment
46Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. | [14 empty] | 1998 | Investment
49 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. | [14 empty] | 1998 | Investment
49Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. | [14 empty] | 1998 | Investment
52 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. | [14 empty] | 1998 | Investment
52Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. | [14 empty] | 1998 | Investment
55 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100 | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. | [14 empty] | 1998 | Investment
55Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. | [14 empty] | 1998 | Investment
58Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 |  | 9 | Completed in 1998. Financially completed in 2000. | [14 empty] | 1998 | Investment
61 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. | [14 empty] | 1998 | Investment
61Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. | [14 empty] | 1998 | Investment
64 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. | [14 empty] | 1998 | Investment
64Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. | [14 empty] | 1998 | Investment
67 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
67Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
70 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
70Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
73 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
73Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
75 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
75Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
77 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
77Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
79 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
79Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
82 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
82Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
84 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
84Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
86 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
86Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
88 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
88Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
91 | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
91Final | COS/FUM/24/PRP/12 | FIN | FIN |  |  | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N |  | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 1 | 0 | 0 | 0 | 5200 | 0 | 0 |  | 0 | 0 | 1998 | 1 | 9 | 0 | 9 | Completed in 1998. Financially completed in 2000. |  | 1998 | [13 empty] | Investment
31 | COS/FUM/27/DEM/14 | ONG | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons |  | LAC | COS | FUM | 27 | DEM | 14 | N | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 2000-10-01 | 2000-10-01 |  |  | 180500 | 0 | 180500 | 19889 | 0.11019 | 160611 |  | 75580.3083 | [6 empty] | 1999 | 8 | 19 | 19 |  | MeBr projects presented at " Annual Int.Research Conf.on MeBr and Emission Reductions", San Diego (USA),Nov 99.Workshop with participation of users and international experts held Nov99.
34 | COS/FUM/27/DEM/14 | ONG | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons |  | LAC | COS | FUM | 27 | DEM | 14 | N | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 2000-10-01 | 2001-12-01 |  |  | 180500 | 0 | 180500 | 117798 | 0.65262 | 62702 |  | 49477.2 | [6 empty] | 1999 | 8 | 19 | 33 |  | Evaluation alternatives on going. Video on alternatives in Melons/flowers. Awareness meetings with importers/ farmers. Preliminary project results discussed at Int. Research Conf. on MeBr and Emission Reductions, Florida, Nov. 00.
34Final | COS/FUM/27/DEM/14 | ONG | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons |  | LAC | COS | FUM | 27 | DEM | 14 | N | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 2000-10-01 | 2001-12-01 |  |  | 180500 | 0 | 180500 | 117798 | 0.65262 | 62702 |  | 47440 | [6 empty] | 1999 | 8 | 19 | 33 |  | Evaluation alternatives on going. Video on alternatives in Melons/flowers. Awareness meetings with importers/ farmers. Preliminary project results discussed at Int. Research Conf. on MeBr and Emission Reductions, Florida, Nov. 00.
35 | COS/FUM/27/DEM/14 |  | FIN | Completed |  | UNDP | [41 empty] | Project Completed. Final project workshops were held with all stakeholders in May and June 2001. Demonstration results have been analysed and final report will be submitted together with Investment Project Proposal to the 35th ExCom Meeting.
37 | COS/FUM/27/DEM/14 | COM | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons |  | LAC | COS | FUM | 27 | DEM | 14 | N | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 |  | 180500 | 0 | 180500 | 178771.19 | 0.99042 | 1728.81 |  | 1218.2709 | 23465 |  | 23240.2547 |  |  | 0 | 1999 | 8 | 19 |  | 33 | Completed in 2001. Results used to prepare inv project (approved at 35th ExCom) to eliminate MB consumption in soil furmigation | [14 empty] | 1999 | Investment
37Final | COS/FUM/27/DEM/14 | COM | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons |  | LAC | COS | FUM | 27 | DEM | 14 | N | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 |  | 180500 | 0 | 180500 | 178771.19 | 0.99042 | 1728.81 |  | 1146.9601 | 23465 |  | 23240.2547 |  |  | 0 | 1999 | 8 | 19 |  | 33 | Completed in 2001. Results used to prepare inv project (approved at 35th ExCom) to eliminate MB consumption in soil furmigation | [14 empty] | 1999 | Investment
40 | COS/FUM/27/DEM/14 | COM | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-03-01 |  | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 23465 | 0 | 1999 | 8 | 19 | 0 | 24 | Completed in 2001. | [14 empty] | 1999 | Investment
40Final | COS/FUM/27/DEM/14 | COM | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 |  | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. | [14 empty] | 1999 | Investment
43Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Operationally completed in 2001. PCR submitted in 2003. Financially completed in 2003. | [14 empty] | 1999 | Investment
46 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
46Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
49 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
49Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
52 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
52Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
55 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 100 | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
55Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
58Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 |  | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
61 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
61Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
64 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
64Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. | [14 empty] | 1999 | Investment
67 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
67Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
70 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
70Final | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
73 | COS/FUM/27/DEM/14 | FIN | FIN |  |  | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N |  | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 1 | 0 | 0 | 0 | 23465 | 0 | 0 |  | 0 | 0 | 1999 | 8 | 19 | 0 | 33 | Completed in 2001. Financially completed in 2003. |  | 1999 | [13 empty] | Investment
34Final | COS/FUM/29/PRP/21 | ONG | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I | [5 empty] | 1999-11-01 |  | 2000-12-01 | 2000-12-01 |  |  | 30000 | 0 | 30000 |  | 0 | 30000 | [8 empty] | 1999 | 0 | 13 | 13 | 0 | les modalités de coopération entre le FFEM et la FAO sont en cours de discussion |  | 1999
37 | COS/FUM/29/PRP/21 | CLO | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I | [5 empty] | 1999-11-01 |  | 2000-12-01 |  |  |  | 30000 | -19256.9002 | 10743.0998 | 10743.0998 | 0.3581 | 0 | [8 empty] | 1999 | 23 | 13 | 0 | 23 | une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
37Final | COS/FUM/29/PRP/21 | COM | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  |  |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 |  | 30000 | -19256.9002 | 10743.0998 | 10743.0998 | 1 | 0 |  | 0 | [6 empty] | 1999 | 23 | 13 | 0 | 23 | une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
40 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I | [5 empty] | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | -19256.9002 | 10743.0998 | 10743.0998 | 0.3581 | 0 |  | 0 | [5 empty] | 0 | 1999 | 23 | 13 | 0 | 23 | une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
40Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I | [5 empty] | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 |  | 30000 | 10743.0998 | 0.3581 | 19256.9002 |  | 0 | 1500 |  | 537.155 | 962.845 |  | 0 | 1999 | 23 | 13 | 0 | 23 | une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
43Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I | [5 empty] | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | -19257 | 10743 | 10743.0998 | 0.3581 | -0.0998 |  | 0 | 1500 |  | 537.155 | 962.845 |  | 0 | 1999 | 23 | 13 | 0 | 23 | une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
46 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | 0 | 30000 | 10743.0998 | 0.3581 | 19256.9002 |  | 0 | 1500 | 0 | 537.155 | 962.845 |  | 0 | 1999 | 23 | 13 | 0 | 23 | une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
46Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | 0 | 30000 | 10743.0998 | 0.3581 | 19256.9002 |  | 0 | 1500 | 0 | 537.155 | 962.845 |  | 0 | 1999 | 23 | 13 | 0 | 23 | une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
49 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | 0 | 30000 | 10743.0998 | 0.3581 | 19256.9002 |  | 0 | 1500 | 0 | 537.155 | 962.845 |  | 0 | 1999 | 23 | 13 | 0 | 23 | une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
49Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | -19257 | 10743 | 10743.0998 | 0.3581 | -0.0998 |  | 0 | 1500 | 0 | 537.155 | 962.845 |  | 0 | 1999 | 23 | 13 | 0 | 23 | une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
52 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | -19257 | 10743 | 10743.0998 | 0.3581 | -0.0998 |  | 0 | 1500 | 0 | 537.155 | 962.845 |  | 0 | 1999 | 23 | 13 | 0 | 23 | une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
52Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | -19257 | 10743 | 10743.0998 | 0.3581 | -0.0998 |  | 0 | 1500 | 0 | 537.155 | 962.845 |  | 0 | 1999 | 23 | 13 | 0 | 23 | une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
55 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | -19257 | 10743 | 10743.0998 | 1 | -0.0998 |  | 0 | 1500 | 0 | 537.155 | 962.845 |  | 0 | 1999 | 23 | 13 | 0 | 23 | une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
55Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | -19257 | 10743 | 10743.0998 | 1 | -0.0998 |  | 0 | 1500 | 0 | 537.155 | 962.845 |  | 0 | 1999 | 23 | 13 | 0 | 23 | une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
58Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | -19257 | 10743 | 10743.0998 | 1 | -0.0998 |  | 0 | 1500 | -963 | -0.155 |  |  | 0 | 1999 | 23 | 13 | 0 | 23 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
61 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | -19257 | 10743 | 10743.0998 | 1 | -0.0998 |  | 0 | 1500 | -963 | 0 |  |  | 0 |  | 23 | 13 | 0 | 23 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
61Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | -19257 | 10743 | 10743.0998 | 1 | -0.0998 |  | 0 | 1500 | -963 | 0 |  |  | 0 |  | 23 | 13 | 0 | 23 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
64 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | -19257 | 10743 | 10743.0998 | 1 | -0.0998 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 23 | 13 | 0 | 23 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
64Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | -19257 | 10743 | 10743.0998 | 1 | -0.0998 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 23 | 13 | 0 | 23 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
67 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
67Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
25 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam |  | ASP | CPR | FOA | 6 | TAS | 3 | A | T | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 |  | 0 | [6 empty] | 1992 | 17 | 16 |  | 34 | Completed. |  |  | 1994-12-01
28 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam |  | ASP | CPR | FOA | 6 | TAS | 3 | A | T | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 |  | 0 | [6 empty] | 1992 | 17 | 16 |  | 34 | Completed.
31 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam |  | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 |  | 0 | [6 empty] | 1992 | 17 | 16 |  | 34 | Completed in 1994. Financially closed.
34 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam |  | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 |  | 0 | [6 empty] | 1992 | 17 | 16 |  | 34 | Completed in 1994. Financially closed.
34Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam |  | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 |  | 0 | [6 empty] | 1992 | 17 | 16 |  | 34 | Completed in 1994. Financially closed.
37 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam |  | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 |  | 0 | 9100 |  | 9100 |  |  | 0 | 1992 | 17 | 16 |  | 34 | Completed in 1994. Financially completed. | [14 empty] | 1992 | Non-Investment
37Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam |  | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 |  | 0 | 9100 |  | 9100 |  |  | 0 | 1992 | 17 | 16 |  | 34 | Completed in 1994. Financially completed. | [14 empty] | 1992 | Non-Investment
40 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 9100 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. PCR submitted in Jun-2000. | [14 empty] | 1992 | Non-Investment
40Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. PCR submitted in Jun-2000. | [14 empty] | 1992 | Non-Investment
43Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Operationally completed in 1994. PCR submitted in 2000. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
46 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
46Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
49 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
49Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
52 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
52Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
55 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100 | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
55Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
58Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 |  | 34 | Completed in 1994. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
61 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
61Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
70 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
70Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
73 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
73Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
75 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
75Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
77Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
79 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
79Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
82 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
82Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
84 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
84Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
86 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
86Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
88 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
88Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
91 | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
91Final | COS/FUM/29/PRP/21 | FIN | FIN |  |  | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A |  | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 1 | 0 |  | 0 | 1500 | -963 | 0 |  |  | 0 | 1999 | 22 | 13 | 0 | 22 | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
34 | COS/FUM/30/TAS/22 | ONG | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication |  | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-11-01 | 2001-03-01 | 2001-03-01 |  |  | 25000 | 0 | 25000 | 2000 | 0.08 | 23000 |  | 23000 | [6 empty] | 2000 | 8 | 12 | 12 | 0 | PAN identified as project coordinator, NGOs identified, awaiting confirmation from NOUs. Workshop of NGOs planned in Paris in Fenruary 2001
34Final | COS/FUM/30/TAS/22 | ONG | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication |  | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-11-01 | 2001-03-01 | 2001-03-01 |  |  | 25000 | 0 | 25000 | 2000 | 0.08 | 23000 |  | 23000 | [6 empty] | 2000 | 8 | 12 | 12 | 0 | PAN identified as project coordinator, NGOs identified, awaiting confirmation from NOUs. Workshop of NGOs planned in Paris in Fenruary 2001
37 | COS/FUM/30/TAS/22 | COM | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication |  | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 |  | 25000 | 0 | 25000 | 13000 | 0.52 | 12000 |  | 12000 | 3250 |  | 1690 |  |  | 0 | 2000 | 8 | 12 | 0 | 21 | activities completed by NGO, final reports including financial reports have been submitted, only final workshop needs to be done | [14 empty] | 2000
37Final | COS/FUM/30/TAS/22 | COM | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication |  | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 |  | 25000 | 0 | 25000 | 13000 | 0.52 | 12000 |  | 12000 | 3250 |  | 1690 |  |  | 0 | 2000 | 8 | 12 | 0 | 21 | activities completed by NGO, final reports including financial reports have been submitted, only final workshop needs to be done | [14 empty] | 2000
37Narrative | COS/FUM/30/TAS/22 | COM | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | [29 empty] | 0 |  | 0 |  |  | 0 | [5 empty] | PAN identified as project coordinator. NGOs identified, awaiting confirmation from NOUs. Workshop of NGOs planned in Paris in February 2001.
40 | COS/FUM/30/TAS/22 | COM | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 |  | 25000 | 0 | 25000 | 15608 | 0.62432 | 9392 |  | 9392 | 3250 | 0 | 2029.04 | 1220.96 |  | 0 | 2000 | 8 | 12 | 0 | 21 | PCR prepared October 2002. PCR submitted November 2002 | [14 empty] | 2000 | Non Investment
40Final | COS/FUM/30/TAS/22 | COM | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 |  | 25000 | 0 | 25000 | 15608 | 0.62432 | 9392 |  | 9392 | 3250 | 0 | 2029.04 | 1220.96 |  | 0 | 2000 | 8 | 12 | 0 | 21 | Project completed in December 2001. PCR submitted in November 2002. | [14 empty] | 2000 | Non Investment
43 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 |  | 0 | 3250 | -1253.07 | 1996.93 | 0 |  | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | [14 empty] | 2000 | Non Investment
43Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 |  | 0 | 3250 | -1253.07 | 1996.93 | 0 |  | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | $9639 plus $1253 PSC returned ExCom 41 | [13 empty] | 2000 | Non Investment
46 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 |  |  | 3250 | -1253.07 | 1996.93 | 0 |  | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | $9639 plus $1253 PSC returned ExCom 41 | [13 empty] | 2000 | Non Investment
46Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 |  |  | 3250 | -1253.07 | 1996.93 | 0 |  | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | $9639 plus $1253 PSC returned ExCom 41 | [13 empty] | 2000 | Non Investment
49 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 |  |  | 3250 | -1253.07 | 1996.93 | 0 |  | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | $9639 plus $1253 PSC returned ExCom 41 | [13 empty] | 2000 | Non Investment
49Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 |  |  | 3250 | -1253.07 | 1996.93 | 0 |  | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | $9639 plus $1253 PSC returned ExCom 41 | [13 empty] | 2000 | Non Investment
52 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 |  |  | 3250 | -1253.07 | 1996.93 | 0 | 0 | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | $9639 plus $1253 PSC returned ExCom 41 | [13 empty] | 2000 | Non Investment
52Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 |  |  | 3250 | -1253.07 | 1996.93 | 0 | 0 | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | $9639 plus $1253 PSC returned ExCom 41 | [13 empty] | Jun-05 | Non Investment
55 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 1996.93 | 0 | 0 | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | $9639 plus $1253 PSC returned ExCom 41 | [13 empty] | 2000 | Non Investment
55Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 1996.93 | 0 | 0 | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | $9639 plus $1253 PSC returned ExCom 41 | [13 empty] | 2000 | Non Investment
58Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 2506.14 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | $9,639 plus $1,253 PSC returned ExCom 41 | [13 empty] | 2000 | Non Investment
61 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | $9,639 plus $1,253 PSC returned ExCom 41 | [13 empty] | 2000 | Non Investment
61Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | $9,639 plus $1,253 PSC returned ExCom 41 | [13 empty] | 2000 | Non Investment
64 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 2506.14 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | $9,639 plus $1,253 PSC returned ExCom 41 | [13 empty] | 2000 | Non Investment
64Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | $9,639 plus $1,253 PSC returned ExCom 41 | [13 empty] | 2000 | Non Investment
67 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | [15 empty] | Non Investment
67Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | [15 empty] | Non Investment
70 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | [15 empty] | Non Investment
70Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed. | [15 empty] | Non Investment
73 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed.
73Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21 | Project financially completed.
75 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 |  | 3250 | -1253 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21 |  | Project financially completed.
75Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 |  | 3250 | -1253 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21 |  | Project financially completed.
77 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | -0.07 |  |  | 0 | 2000 | 8 | 12 | 0 | 21
77Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | -0.07 |  |  | 0 | 2000 | 8 | 12 | 0 | 21
79 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 |  | 0 | 3250 | -1253.07 | -0.07 |  |  | 0 | 2000 | 8 | 12 | 0 | 21
79Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 |  | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21
82 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 |  | 3250 | -1253.07 | -0.07 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21
82Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 |  | 3250 | -1253.07 | -0.07 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21
83 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 |  | 8 | 12 | 0 | 21
84 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21
84Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21
61Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 0 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
64 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -647.53 | 0 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
64Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 0 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
67 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -647.53 | 0 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
67Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -647.53 | 0 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
70 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 0 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
70Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 0 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
73 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | -0.47 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
73Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | -0.47 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
75 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -647.53 | 0 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
75Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | -0.47 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
77 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | -0.47 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
86 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21
86Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21
88 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21
88Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21
91 | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21
91Final | COS/FUM/30/TAS/22 | FIN | FIN |  |  | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A |  | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 1 | 0 | 0 | 0 | 3250 | -1253.07 | 0 |  | 0 | 0 | 2000 | 8 | 12 | 0 | 21
70 | CPR/DES/67/DEM/520 | ONG | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 |  |  | 2012-07-01 |  | 2015-01-31 | 2015-09-01 |  |  | 1227885 | 0 | 1227885 | 0 | 0 | 1227885 | 0 | 425577 | 85952 | 0 | 85952 |  | 0 | 0 | 2012 | 0 | 31 | 38 | 0 | The project was approved in 2012. Detailed work plan for implementation prepared and agreed upon between FECO and UNIDO. | .- Technical validation of the four facilities where destruction activities will take place; .- Development of training contents and organization of initial training courses; .- First batched of ODS waste destroyed in two of the four facilities | [14 empty] | INV
70Final | CPR/DES/67/DEM/520 | ONG | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 |  |  | 2012-07-01 |  | 2015-01-31 | 2015-09-01 |  |  | 1227885 | 0 | 1227885 | 0 | 0 | 1227885 | 0 | 425577 | 85952 | 0 | 85952 |  | 0 | 0 | 2012 | 0 | 31 | 38 | 0 | The project was approved in 2012. Detailed work plan for implementation prepared and agreed upon between FECO and UNIDO. Project duration is 30 months. Since the project is also co-financed by Japan and the funds for the Japanese component was received end December 2012, implementation of the project could only be initiated in 2013. | .- Technical validation of the four facilities where destruction activities will take place; .- Development of training contents and organization of initial training courses; .- First batched of ODS waste destroyed in two of the four facilities | [14 empty] | INV
73 | CPR/DES/67/DEM/520 | ONG | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 |  |  | 2012-07-01 |  | 2015-01-31 | 2016-06-01 |  |  | 1227885 | 0 | 1227885 | 0 | 0 | 1227885 | 1227885 | 851154 | 85952 | 0 | 85952 |  | 85951.95 | 0 | 2012 | 0 | 31 | 47 | 0 | Environmental authorities of the participating provinces have initiated preparatory work to ensure project implementation as per project document requirements. The second phase of capacity building in local environmental authorities was launched at the end of 2013 and included a component on ODS waste management. | A mission has been organized in the last week of March to discuss progress in project implementation and have a meeting with stakeholders in one of the provinces participating in the project. | [14 empty] | INV
73Final | CPR/DES/67/DEM/520 | ONG | FIN | To request the submission of additional status report to the 73rd meeting to monitor the status of disbursement for the ODS disposal demonstration project, pursuant to decision 70/23(b)(viii)c.. |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 |  |  | 2012-07-01 |  | 2015-01-31 | 2016-06-01 |  |  | 1227885 | 0 | 1227885 | 0 | 0 | 1227885 | 1227885 | 851154 | 85952 | 0 | 85952 |  | 85951.95 | 0 | 2012 | 0 | 31 | 47 | 0 | Environmental authorities of the participating provinces have initiated preparatory work to ensure project implementation as per project document requirements. The second phase of capacity building in local environmental authorities was launched at the end of 2013 and included a component on ODS waste management. | A mission has been organized in the last week of March to discuss progress in project implementation and have a meeting with stakeholders in one of the provinces participating in the project. | [14 empty] | INV
73Status | CPR/DES/67/DEM/520 |  | FIN | To request the submission of additional status report to the 74th meeting - Reason: Low disbursement rates of approved funds |  | UNIDO | Pilot demonstration project on ODS waste management and disposal |  |  | CPR |  |  | DEM | [23 empty] | 0 |  | 0 |  |  | 0 | [5 empty] | Figures regarding disbursement as provided by our reporting system are not aligned with real project disbursement due to a technical problem. As of 25 August 2014, disbursement should reflect an amount of 425,577 US$. By 31 December 2014, it is planned that additional 851,154 US$ will be disbursed, in line with the current Implementation Plan agreed upon between FECO and UNIDO. It is important to note that this project receives funding from the MLF and bilateral funding from Japan. Disbursement estimates as of end of 2014 take both funding components into consideration.
74Status | CPR/DES/67/DEM/520 |  | FIN | No additional status report required. |  | UNIDO | Pilot demonstration project on ODS waste management and disposal |  |  | CPR |  |  | DEM | [23 empty] | 0 |  | 0 |  |  | 0 | [5 empty] | In line with what was reported at the 73rd ExCom, end-of-the-year disbursement figures are in line with the extent of implementation of the project, taking into account that this project receives funding from the MLF and bilateral funding from Japan. In this regard, it is worth noting that procedural issues at the time of establishing the funds allocation from both sources of funding prevented UNIDO from utilizing funds from both sources simultaneously, thus resulting in funds from the MLF-funded component being used in the first place.
75 | CPR/DES/67/DEM/520 | ONG | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 |  |  | 2012-07-01 | 2014-10-01 | 2015-01-31 | 2017-06-01 |  |  | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 |  | 85952 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 31 | 59 | 0 | In March, 2014, FECO and UNIDO held a meeting at FECO office. FECO briefed UNIDO team of the progress and next step work plan. Based on surveys to several companies and meetings with relevant EPBs, it was decided that part of the funding will be allocated to the EPBs for organizing and management of the project. UNIDO agrees with the plan and asked FECO to make sure payment of fund from UNIDO is sufficient to support current spending. - In April 2014, FECO organized a meeting with relevant provincial EPBs in Beijing. At the meeting, the EPBs introduced the information they have collected and discussed how to proceed with the project. A total of 5 contracts have been signed between local EPBs and FECO. Milestones achieved: Milestone 1: Yes - Preparation of a revised Implementation Plan Milestone 2: Yes - Contracts signed with 5 participating EPBs Milestone 2: Yes - 1st batch of 800 kg. of CFC-12 destroyed Actions towards next goals: (-) EPBs to submit Progress Report and province-specific Implementation Plans; (-) Visits to provinces to check progress in implementation. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Delays in signature of contracts between FECO and local EPBs (solved). Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | In April 2015, an additional contract has been signed between a local EPB and FECO. - In July 2015, a follow-up meeting was organized between FECO and UNIDO. Milestones achieved: Milestone 1: Yes - Contract signed with 6th EPB. Actions towards next goals: (-) Progress Reports to be submitted by local EPBs by end of August 2015; (-) Meeting of local EPBs, FECO and UNIDO scheduled in September 2015. Was there any delay during the reporting year? No, but to ensure successful completion of the project, completion date was revised to June 2017. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | [14 empty] | INV
75Final | CPR/DES/67/DEM/520 | ONG | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 |  |  | 2012-07-01 | 2014-10-01 | 2015-01-31 | 2017-06-01 |  |  | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 |  | 85952 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 31 | 59 | 0 | - In March, 2014, FECO and UNIDO held a meeting at FECO office. FECO briefed UNIDO team of the progress and next step work plan. Based on surveys to several companies and meetings with relevant EPBs, it was decided that part of the funding will be allocated to the EPBs for organizing and management of the project. UNIDO agrees with the plan and asked FECO to make sure payment of fund from UNIDO is sufficient to support current spending. - In April 2014, FECO organized a meeting with relevant provincial EPBs in Beijing. At the meeting, the EPBs introduced the information they have collected and discussed how to proceed with the project. A total of 5 contracts have been signed between local EPBs and FECO. Milestones achieved: Milestone 1: Yes - Preparation of a revised Implementation Plan Milestone 2: Yes - Contracts signed with 5 participating EPBs Milestone 2: Yes - 1st batch of 800 kg. of CFC-12 destroyed Actions towards next goals: (-) EPBs to submit Progress Report and province-specific Implementation Plans; (-) Visits to provinces to check progress in implementation. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Delays in signature of contracts between FECO and local EPBs (solved). Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - In April 2015, an additional contract has been signed between a local EPB and FECO. - In July 2015, a follow-up meeting was organized between FECO and UNIDO. Milestones achieved: Milestone 1: Yes - Contract signed with 6th EPB. Actions towards next goals: (-) Progress Reports to be submitted by local EPBs by end of August 2015; (-) Meeting of local EPBs, FECO and UNIDO scheduled in September 2015. Was there any delay during the reporting year? No, but to ensure successful completion of the project, completion date was revised to June 2017. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | [14 empty] | INV
77 | CPR/DES/67/DEM/520 | ONG | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 |  |  | 2012-07-01 | 2014-10-01 | 2015-01-31 | 2018-03-01 |  |  | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 |  | 85952 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 31 | 68 | 0 | - In April 2015, an additional contract has been signed between a local EPB and FECO. - In July 2015, a follow-up meeting was organized between FECO and UNIDO. Milestones achieved: Milestone 1: Yes - Contract signed with 6th EPB. Milestone 2: Yes - Meeting of local EPBs, FECO and UNIDO. Actions towards next goals: (-) Progress Reports to be submitted by local EPBs; Was there any delay during the reporting year? Yes, Progress Reports by local EPBs were not submitted when expected. UNIDO and FECO are currently working to obtain these reports as soon as possible. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - In March 2016, a meeting was held between FECO and EPBs on the progress of activities. - The provinces of Shangai and Chongqing disposed first batches of ODS. Shangai: 819.5 kg in 2015 and 1,308 kg in 2016. Chongqing: 5,144 kg in 2016. - In Jiangsu and Guangdong, the EPB has targeted a disposal company. Actions towards next goals: (-) Progress Reports to be submitted by local EPBs; Was there any delay during the reporting year? Yes, Progress Reports by local EPBs were not submitted when expected. UNIDO and FECO are currently working to obtain these reports as soon as possible. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | [14 empty] | INV
77Final | CPR/DES/67/DEM/520 | ONG | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 |  |  | 2012-07-01 | 2014-10-01 | 2015-01-31 | 2017-12-01 |  |  | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 |  | 85952 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 31 | 65 | 0 | - In April 2015, an additional contract has been signed between a local EPB and FECO. - In July 2015, a follow-up meeting was organized between FECO and UNIDO. Milestones achieved: Milestone 1: Yes - Contract signed with 6th EPB. Milestone 2: Yes - Meeting of local EPBs, FECO and UNIDO. Actions towards next goals: (-) Progress Reports to be submitted by local EPBs; Was there any delay during the reporting year? Yes, Progress Reports by local EPBs were not submitted when expected. UNIDO and FECO are currently working to obtain these reports as soon as possible. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - In March 2016, a meeting was held between FECO and EPBs on the progress of activities. - The provinces of Shangai and Chongqing disposed first batches of ODS. Shangai: 819.5 kg in 2015 and 1,308 kg in 2016. Chongqing: 5,144 kg in 2016. - In Jiangsu and Guangdong, the EPB has targeted a disposal company. Actions towards next goals: (-) Progress Reports to be submitted by local EPBs; Was there any delay during the reporting year? Yes, Progress Reports by local EPBs were not submitted when expected. UNIDO and FECO are currently working to obtain these reports as soon as possible. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | [14 empty] | INV
79 | CPR/DES/67/DEM/520 | ONG | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 |  |  | 2012-07-01 | 2014-10-01 | 2015-01-31 | 2017-12-01 |  |  | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 |  | 85952 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 31 | 65 | 0 | - In March 2016, a meeting was held between FECO and EPBs on the progress of activities. - The provinces of Shangai and Chongqing disposed first batches of ODS. Shanghai: 819.5 kg in 2015 and 1,308 kg in 2016. Chongqing: 5,144 kg in 2016. - In Jiangsu and Guangdong, the EPB has targeted a disposal company. - UNIDO organized a meeting to China in October to monitor project progressed. Out of the planned 192t, it was indicated that 18t have been disposed by the meeting date. - The municipality of Shanghai certified disposal of 12t of CFC11 and 0.87t of CFC12 in the year 2015. Furthermore, additional 12t of CFC11 and 0.4t of CFC11 were disposed as of October. - The city of Shandong planned to dispose a total of 20t in 2016 and progresses are encouraging: three centers for the disposal of appliances have been identified and agreement was reached with them to proceed with the ODS disposal from the refrigeration part as well as from the foam. The province of Tianjin completed the survey and could not start with the disposal activities. - FECO organized a meeting with the relevant municipalities and provinces to agree on a plan of action before the end of the year 2016. Actions towards next goals: (-) Receive latest progress Reports to be submitted by local EPBs (continuous monitoring); Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO discussed with FECO on project development and agreed to place a monitoring visit to the relevant municipalities/provinces in the first half of 2017. - The project will be completed in 2017. | [14 empty] | INV
79Final | CPR/DES/67/DEM/520 | ONG | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 |  |  | 2012-07-01 | 2014-10-01 | 2015-01-31 | 2017-12-01 |  |  | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 |  | 85952 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 31 | 65 | 0 | - In March 2016, a meeting was held between FECO and EPBs on the progress of activities. - The provinces of Shangai and Chongqing disposed first batches of ODS. Shanghai: 819.5 kg in 2015 and 1,308 kg in 2016. Chongqing: 5,144 kg in 2016. - In Jiangsu and Guangdong, the EPB has targeted a disposal company. - UNIDO organized a meeting to China in October to monitor project progressed. Out of the planned 192t, it was indicated that 18t have been disposed by the meeting date. - The municipality of Shanghai certified disposal of 12t of CFC11 and 0.87t of CFC12 in the year 2015. Furthermore, additional 12t of CFC11 and 0.4t of CFC11 were disposed as of October. - The city of Shandong planned to dispose a total of 20t in 2016 and progresses are encouraging: three centers for the disposal of appliances have been identified and agreement was reached with them to proceed with the ODS disposal from the refrigeration part as well as from the foam. The province of Tianjin completed the survey and could not start with the disposal activities. - FECO organized a meeting with the relevant municipalities and provinces to agree on a plan of action before the end of the year 2016. Actions towards next goals: (-) Receive latest progress Reports to be submitted by local EPBs (continuous monitoring); Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO discussed with FECO on project development and agreed to place a monitoring visit to the relevant municipalities/provinces in the first half of 2017. - The project will be completed in 2017. | [14 empty] | INV
82 | CPR/DES/67/DEM/520 | COM | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-31 |  | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 | 0 | 85952 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 66 | Activities were completed as planned in 2017. Final report submitted to ExCom. | The Project was financially closed. | [14 empty] | INV
82Final | CPR/DES/67/DEM/520 | COM | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-31 |  | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 | 0 | 85952 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 66 | Activities were completed as planned in 2017. Final report submitted to ExCom. | The Project was financially closed. | [14 empty] | INV
84 | CPR/DES/67/DEM/520 | FIN | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-31 | 2018-04-01 | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 | 0 | 85952 | 0 | 0.05 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 66 | Project was financially completed in April 2018. Fund balances were returned at 81st ExCom in June 2018. | N/A | [14 empty] | INV
84Final | CPR/DES/67/DEM/520 | FIN | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-31 | 2018-04-01 | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 | 0 | 85952 | 0 | 0.05 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 66 | Project was financially completed in April 2018. Fund balances were returned at 81st ExCom in June 2018. | N/A | [14 empty] | INV
86 | CPR/DES/67/DEM/520 | FIN | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 | 2018-04-01 | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 |  | 85952 | 0 | 0.05 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 65 | [16 empty] | INV
86Final | CPR/DES/67/DEM/520 | FIN | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 | 2018-04-01 | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 |  | 85952 | 0 | 0.05 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 65 | [16 empty] | INV
88 | CPR/DES/67/DEM/520 | FIN | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 | 2018-04-01 | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 |  | 85952 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 65 | [16 empty] | INV
88Final | CPR/DES/67/DEM/520 | FIN | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 | 2018-04-01 | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 |  | 85952 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 65 | [16 empty] | INV
91 | CPR/DES/67/DEM/520 | FIN | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 | 2018-04-01 | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 |  | 85952 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 65 | [16 empty] | INV
91Final | CPR/DES/67/DEM/520 | FIN | FIN |  |  | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 | 2018-04-01 | 1227885 | 0 | 1227885 | 1227885 | 1 | 0 | 0 |  | 85952 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 65 | [16 empty] | INV
70 | CPR/DES/67/DEM/521 | ONG | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal |  | ASP | CPR | DES | 67 | DEM | 521 |  |  |  |  | 0 |  | 0 |  | 2012-07-01 |  | 2015-01-01 |  |  |  | 900000 | 0 | 900000 |  | 0 | 900000 |  |  | 109000 | 0 | 109000 |  |  | 0 | 2012 | 0 | 30 | 0 | 0
70Final | CPR/DES/67/DEM/521 | ONG | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal |  | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 |  | 0 |  | 2012-07-01 |  | 2015-01-01 |  |  |  | 900000 | 0 | 900000 |  | 0 | 900000 |  |  | 109000 | 0 | 109000 |  |  | 0 | 2012 | 0 | 30 | 0 | 0
73 | CPR/DES/67/DEM/521 | ONG | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal |  | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 |  | 0 |  | 2012-07-01 |  | 2015-01-01 | 2015-01-01 |  |  | 900000 | 0 | 900000 |  | 0 | 900000 | 48846 | 40000 | 109000 | 0 | 109000 |  | 5915.7933 | 0 | 2012 | 0 | 30 | 30 | 0 | Contract was issued for the complete project fund. | Payments will be done in the years 2014 and 2015 respectively. | 2013 | [13 empty] | Investmen t
73Final | CPR/DES/67/DEM/521 | ONG | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal |  | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 |  | 0 |  | 2012-07-01 |  | 2015-01-01 | 2015-01-01 |  |  | 900000 | 0 | 900000 |  | 0 | 900000 | 48846 | 40000 | 109000 | 0 | 109000 |  | 5915.7933 | 0 | 2012 | 0 | 30 | 30 | 0 | Contract was issued for the complete project fund. | Payments will be done in the years 2014 and 2015 respectively. | 2013 | [13 empty] | Investmen t
75 | CPR/DES/67/DEM/521 | ONG | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 |  | 0 |  | 2012-07-01 | 2014-10-01 | 2015-01-01 | 2016-06-01 |  |  | 900000 | 0 | 900000 | 48846 | 0.054273 | 851154 | 638365.5 | 300000 | 109000 | 0 | 103084.2067 |  | 77313.155 | 0 | 2012 | 27 | 30 | 47 | 0 | In March, 2014, FECO and UNIDO held a meeting at FECO office. FECO briefed UNIDO team of the progress and next step work plan. Based on surveys to several companies and meetings with relevant EBPs, it was decided that part of the funding will be allocated to the EBPs for organizing and management of the project. UNIDO agrees with the plan and asked FECO to make sure payment of fund from UNIDO is sufficient to support current spending. In April 2014, FECO organized a meeting with relevant provincial EBPs in Beijing. At the meeting, the EPBs introduced the information they have collected and discussed how to proceed with the project. A total of 5 contracts have been signed between local EPBs and FECO. | In April 2015, an additional contract has been signed between a local EPB and FECO. In July 2015, a follow-up meeting was organized between FECO and UNIDO. | 2013 | [13 empty] | Investment
75Final | CPR/DES/67/DEM/521 | ONG | FIN | To request the submission of additional status report to the 76th meeting - Reason: The amount of ODS destroyed by the project due to the low rates of disbursement of approved funds. |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 |  | 0 |  | 2012-07-01 | 2014-10-01 | 2015-01-01 | 2016-06-01 |  |  | 900000 | 0 | 900000 | 48846 | 0.054273 | 851154 | 638365.5 | 300000 | 109000 | 0 | 103084.2067 |  | 77313.155 | 0 | 2012 | 27 | 30 | 47 | 0 | In March, 2014, FECO and UNIDO held a meeting at FECO office. FECO briefed UNIDO team of the progress and next step work plan. Based on surveys to several companies and meetings with relevant EBPs, it was decided that part of the funding will be allocated to the EBPs for organizing and management of the project. UNIDO agrees with the plan and asked FECO to make sure payment of fund from UNIDO is sufficient to support current spending. In April 2014, FECO organized a meeting with relevant provincial EBPs in Beijing. At the meeting, the EPBs introduced the information they have collected and discussed how to proceed with the project. A total of 5 contracts have been signed between local EPBs and FECO. | In April 2015, an additional contract has been signed between a local EPB and FECO. In July 2015, a follow-up meeting was organized between FECO and UNIDO. | 2013 | [13 empty] | Investment
76Status | CPR/DES/67/DEM/521 |  | FIN | No additional status report needed |  | Japan | Pilot demonstration project on ODS waste management and disposal |  |  | CPR |  |  | DEM | [23 empty] | 0 |  | 0 |  |  | 0 | [5 empty] | Until now, the disbursement rate of Japan's bilateral contribution to the project has been very low due to the fact that the contractual agreements necessary for the execution of the project were made in a way that project activities would initially be funded from the MLF contribution to the project, and only once the MLF-related grant had been used, funding from the bilateral contribution would be applied. Disbursements to date have been linked to the necessary subcontracts that FECO has signed with the Environmental Protection Bureaus of the participating provinces and cities. However, future payments are performance-based and proportional to the amounts of ODS waste disposed of. As EPBs are encountering some difficulties to operationalize the project (as discussed during the workshop held by FECO and UNIDO in September 2015, with participation of local EPBs), therefore disbursement rates remain low despite progress in the implementation of the project.
77 | CPR/DES/67/DEM/521 | ONG | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 |  | 0 |  | 2012-07-01 | 2014-10-01 | 2015-01-01 | 2017-12-01 |  |  | 900000 | 0 | 900000 | 48846 | 0.054273 | 851154 | 851154 | 300000 | 109000 | 0 | 103084 |  | 103084.2067 | 0 | 2012 | 27 | 30 | 65 | 0 | - In April 2015, an additional contract has been signed between a local EPB and FECO. - In July 2015, a follow-up meeting was organized between FECO and UNIDO. Milestones achieved: Milestone 1: Yes - Contract signed with 6th EPB. Milestone 2: Yes - Meeting of local EPBs, FECO and UNIDO. Actions towards next goals: (-) Progress Reports to be submitted by local EPBs; Was there any delay during the reporting year? Yes, Progress Reports by local EPBs were not submitted when expected. UNIDO and FECO are currently working to obtain these reports as soon as possible. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - In March 2016, a meeting was held between FECO and EPBs on the progress of activities. - The provinces of Shangai and Chongqing disposed first batches of ODS. Shangai: 819.5 kg in 2015 and 1,308 kg in 2016. Chongqing: 5,144 kg in 2016. - In Jiangsu and Guangdong, the EPB has targeted a disposal company. Actions towards next goals: (-) Progress Reports to be submitted by local EPBs; Was there any delay during the reporting year? Yes, Progress Reports by local EPBs were not submitted when expected. UNIDO and FECO are currently working to obtain these reports as soon as possible. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | 2013 | [13 empty] | Investment
77Final | CPR/DES/67/DEM/521 | ONG | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 |  | 0 |  | 2012-07-01 | 2014-10-01 | 2015-01-01 | 2017-12-01 |  |  | 900000 | 0 | 900000 | 48846 | 0.054273 | 851154 | 851154 | 300000 | 109000 | 0 | 103084 |  | 103084.2067 | 0 | 2012 | 27 | 30 | 65 | 0 | - In April 2015, an additional contract has been signed between a local EPB and FECO. - In July 2015, a follow-up meeting was organized between FECO and UNIDO. Milestones achieved: Milestone 1: Yes - Contract signed with 6th EPB. Milestone 2: Yes - Meeting of local EPBs, FECO and UNIDO. Actions towards next goals: (-) Progress Reports to be submitted by local EPBs; Was there any delay during the reporting year? Yes, Progress Reports by local EPBs were not submitted when expected. UNIDO and FECO are currently working to obtain these reports as soon as possible. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - In March 2016, a meeting was held between FECO and EPBs on the progress of activities. - The provinces of Shangai and Chongqing disposed first batches of ODS. Shangai: 819.5 kg in 2015 and 1,308 kg in 2016. Chongqing: 5,144 kg in 2016. - In Jiangsu and Guangdong, the EPB has targeted a disposal company. Actions towards next goals: (-) Progress Reports to be submitted by local EPBs; Was there any delay during the reporting year? Yes, Progress Reports by local EPBs were not submitted when expected. UNIDO and FECO are currently working to obtain these reports as soon as possible. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | 2013 | [13 empty] | Investment
79 | CPR/DES/67/DEM/521 | ONG | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 |  | 0 |  | 2012-07-01 | 2014-10-01 | 2015-01-01 | 2017-12-01 |  |  | 900000 | 0 | 900000 | 48846 | 0.054273 | 851154 | 851154 | 851154 | 109000 | 0 | 103084 |  | 103084 | 0 | 2012 | 27 | 30 | 65 | 0 | - In March 2016, a meeting was held between FECO and EPBs on the progress of activities. - The provinces of Shangai and Chongqing disposed first batches of ODS. Shangai: 819.5 kg in 2015 and 1,308 kg in 2016. Chongqing: 5,144 kg in 2016. - In Jiangsu and Guangdong, the EPB has targeted a disposal company. - UNIDO organised a meeting to China in October to monitor project progressed. Out of the planned 192t, it was indicated that 18t have been disposed by the meeting date. - The municipality of Shanghai certified disposal of 12t of CFC11 and 0.87t of CFC12 in the year 2015. Furthermore, additional 12t of CFC11 and 0.4t of CFC11 were disposed as of October 2016. - The city of Shandong planned to dispose a total of 20t in 2016 and progresses are encouraging: three centres for the disposal of appliances have been identified and agreement was reached with them to proceed with the ODS disposal from the refrigeration part as well as from the foam. - The province of Tianjin completed the survey, but could not start with the disposal activities. - FECO organised a meeting with the relevant municipalities and provinces to agree on a plan of action before the end of the year 2016. Actions towards next goals: - Receive latest progress Reports to be submitted by local EPBs (continuous monitoring); - Disposal activities to get started in the province of Tianjin. Was there any delay during the reporting year? Yes Reason for the delay: Disposal activities in the province of Tianjin could not start yet. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO discussed with FECO on project development and agreed to place a monitoring visit to the relevant municipalities/provinces in the first half of 2017. - Disposal activities in the province of Tianjin start in 2017. - The project is planned to be completed before the end of 2017. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | 2013 | [13 empty] | Investment
79Final | CPR/DES/67/DEM/521 | ONG | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 |  | 0 |  | 2012-07-01 | 2014-10-01 | 2015-01-01 | 2017-12-01 |  |  | 900000 | 0 | 900000 | 48846 | 0.054273 | 851154 | 851154 | 851154 | 109000 | 0 | 103084 |  | 103084 | 0 | 2012 | 27 | 30 | 65 | 0 | - In March 2016, a meeting was held between FECO and EPBs on the progress of activities. - The provinces of Shangai and Chongqing disposed first batches of ODS. Shangai: 819.5 kg in 2015 and 1,308 kg in 2016. Chongqing: 5,144 kg in 2016. - In Jiangsu and Guangdong, the EPB has targeted a disposal company. - UNIDO organised a meeting to China in October to monitor project progressed. Out of the planned 192t, it was indicated that 18t have been disposed by the meeting date. - The municipality of Shanghai certified disposal of 12t of CFC11 and 0.87t of CFC12 in the year 2015. Furthermore, additional 12t of CFC11 and 0.4t of CFC11 were disposed as of October 2016. - The city of Shandong planned to dispose a total of 20t in 2016 and progresses are encouraging: three centres for the disposal of appliances have been identified and agreement was reached with them to proceed with the ODS disposal from the refrigeration part as well as from the foam. - The province of Tianjin completed the survey, but could not start with the disposal activities. - FECO organised a meeting with the relevant municipalities and provinces to agree on a plan of action before the end of the year 2016. Actions towards next goals: - Receive latest progress Reports to be submitted by local EPBs (continuous monitoring); - Disposal activities to get started in the province of Tianjin. Was there any delay during the reporting year? Yes Reason for the delay: Disposal activities in the province of Tianjin could not start yet. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO discussed with FECO on project development and agreed to place a monitoring visit to the relevant municipalities/provinces in the first half of 2017. - Disposal activities in the province of Tianjin start in 2017. - The project is planned to be completed before the end of 2017. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | 2013 | [13 empty] | Investment
82 | CPR/DES/67/DEM/521 | COM | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 |  | 900000 | 0 | 900000 | 687211.5 | 0.76357 | 212788.5 | 212788.5 | 212789 | 109000 | 0 | 25771.0517 |  | 25771.0517 | 0 | 2012 | 27 | 30 | 0 | 65 | The project was completed as planned in 2017. | The remaining obligations are being liquidated and the financial closure is in process. | 2013 | [13 empty] | Investment
82Final | CPR/DES/67/DEM/521 | COM | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 |  | 900000 | 0 | 900000 | 687211.5 | 0.76357 | 212788.5 | 212788.5 | 212789 | 109000 | 0 | 25771.0517 |  | 25771.0517 | 0 | 2012 | 27 | 30 | 0 | 65 | The project was completed as planned in 2017. | The remaining obligations are being liquidated and the financial closure is in process. | 2013 | [13 empty] | Investment
84 | CPR/DES/67/DEM/521 | COM | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 |  | 900000 | 0 | 900000 | 900000 | 1 | 0 | 0 | 0 | 109000 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 65 | The project was completed as planned in 2017. The financial closure of the project was initiated. | The project was financially closed in March 2019. | 2013 | [13 empty] | Investment
84Final | CPR/DES/67/DEM/521 | COM | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 |  | 900000 | 0 | 900000 | 900000 | 1 | 0 | 0 | 0 | 109000 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 65 | The project was completed as planned in 2017. The financial closure of the project was initiated. | The project was financially closed in March 2019. | 2013 | [13 empty] | Investment
86 | CPR/DES/67/DEM/521 | FIN | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 |  | 900000 | 0 | 900000 | 900000 | 1 | 0 | 0 | 0 | 109000 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 65 | The project was completed as planned in 2017. The financial closure of the project was initiated. | The project was financially closed in March 2019. | 2013 | [13 empty] | Investment
86Final | CPR/DES/67/DEM/521 | FIN | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 | 2019-03-21 | 900000 | 0 | 900000 | 900000 | 1 | 0 | 0 | 0 | 109000 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 65 | The project was completed as planned in 2017. The financial closure of the project was initiated. | The project was financially closed in March 2019. | 2013 | [13 empty] | Investment
88 | CPR/DES/67/DEM/521 | FIN | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 | 2019-03-01 | 900000 | 0 | 900000 | 900000 | 1 | 0 | 0 | 0 | 109000 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 65 | The project was completed as planned in 2017. The financial closure of the project was initiated. | The project was financially closed in March 2019. | 2013 | [13 empty] | Investment
88Final | CPR/DES/67/DEM/521 | FIN | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 | 2019-03-01 | 900000 | 0 | 900000 | 900000 | 1 | 0 | 0 | 0 | 109000 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 65 | The project was completed as planned in 2017. The financial closure of the project was initiated. | The project was financially closed in March 2019. | 2013 | [13 empty] | Investment
91 | CPR/DES/67/DEM/521 | FIN | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 | 2019-03-01 | 900000 | 0 | 900000 | 900000 | 1 | 0 | 0 | 0 | 109000 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 65 | The project was completed as planned in 2017. The financial closure of the project was initiated. | The project was financially closed in March 2019. | 2013 | [13 empty] | Investment
91Final | CPR/DES/67/DEM/521 | FIN | FIN |  |  | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A |  | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-10-01 | 2015-01-01 |  | 2017-12-01 | 2019-03-01 | 900000 | 0 | 900000 | 900000 | 1 | 0 | 0 | 0 | 109000 | 0 | 0 |  | 0 | 0 | 2012 | 27 | 30 | 0 | 65 | The project was completed as planned in 2017. The financial closure of the project was initiated. | The project was financially closed in March 2019. | 2013 | [13 empty] | Investment
13 | CPR/FOA/06/TAS/03 |  | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam |  | ASP | CPR | FOA | 6 | TAS | 3 | [33 empty] | Two technology assessment visits completed in 1993, the first covering flexible foams and the second covering polystyrene and polyethylene foams. The approved $1.08 million Tianjin flexible foam project was one result and a pipeline of upto
15 | CPR/FOA/06/TAS/03 |  | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam |  | ASP | CPR | FOA | 6 | TAS | 3 | [33 empty] | Additional technical assistance will be provided in 4Q94 to complete this project.
17 | CPR/FOA/06/TAS/03 |  | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam |  | ASP | CPR | FOA | 6 | TAS | 3 | [33 empty] | Ongoing. Additional technical assistance will be provided in 4Q94 to complete this project.
18 | CPR/FOA/06/TAS/03 |  | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam |  | ASP | CPR | FOA | 6 | TAS | 3 | [33 empty] | Operationally completed. Awaiting closure of financial accounts.
19 | CPR/FOA/06/TAS/03 | ONG | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam |  | ASP | CPR | FOA | 6 | TAS | 3 |  |  |  |  | 0 |  |  |  | 1992-02-01 |  | 1992-12-01 |  | 1994-12-01 |  | 70000 | 0 |  | 65000 | 0.92857 | 5000 | [13 empty] | Operationally completed. Awaiting closure of financial accounts.
20 | CPR/FOA/06/TAS/03 | COM | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam |  | ASP | CPR | FOA | 6 | TAS | 3 | A | T | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-07-01 | 1992-12-01 |  | 1994-12-01 |  | 70000 | 0 | 70000 | 65000 | 0.92857 | 5000 |  | 5000 | [7 empty] | 17 | 10 | 0 | 34 | Completed.
22 | CPR/FOA/06/TAS/03 | COM | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam** |  | ASP | CPR | FOA | 6 | TAS | 3 | A | T | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 |  | 70000 | 0 | 70000 | 70000 | 1 | 0 |  | 0 | [6 empty] | 1993 | 17 | 16 | 0 | 34 | Completed.
64 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
64Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
67 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
67Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
70 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
70Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
73 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
73Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
75 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
75Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
77 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
77Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
79 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
79Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
82 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
82Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
84 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
84Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
86 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
86Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
88 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 |  |  | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
88Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 |  |  | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
91 | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
91Final | CPR/FOA/06/TAS/03 | FIN | FIN |  |  | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 6 | TAS | 3 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 1 | 0 | 0 | 0 | 9100 | 0 | 0 |  | 0 | 0 | 1992 | 17 | 16 | 0 | 34 | Completed in 1994. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
13 | CPR/FOA/06/TAS/07 |  | FIN |  |  | UNDP | Quality control testing on CFC-11 substitute technology in a production line for home refrigerators |  | ASP | CPR | FOA | 6 | TAS | 7 | [33 empty] | Completed. Technologies used in the US and Japan were evaluated for relevance in China. The result of this technical assistance has been to significantly boost the ODS phaseout investment programme in the refrigerator sector.
17 | CPR/FOA/06/TAS/07 |  | FIN |  |  | UNDP | Quality control testing on CFC-11 substitute technology in a production line for home refrigerators |  | ASP | CPR | FOA | 6 | TAS | 7 | [33 empty] | Completed. Technologies used in the US and Japan were evaluated for relevance in China. The result of this technical assistance has been to significantly boost the ODS phaseout investment programme in the refrigerator sector.
18 | CPR/FOA/06/TAS/07 |  | FIN |  |  | UNDP | Quality control testing on CFC-11 substitute technology in a production line for home refrigerators |  | ASP | CPR | FOA | 6 | TAS | 7 | [33 empty] | Completed.
19 | CPR/FOA/06/TAS/07 | COM | FIN |  |  | UNDP | Quality control testing on CFC-11 substitute technology in a production line for home refrigerators |  | ASP | CPR | FOA | 6 | TAS | 7 |  |  |  |  | 0 |  |  |  | 1992-02-01 |  |  | 1995-07-01 | 1993-09-01 | 1900-02-23 | 65000 | -4981 |  | 60019 | 0.92337 | -4981 | [13 empty] | Completed
20 | CPR/FOA/06/TAS/07 | COM | FIN |  |  | UNDP | Quality control testing on CFC-11 substitute technology in a production line for home refrigerators |  | ASP | CPR | FOA | 6 | TAS | 7 | A | T | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-06-01 | 1992-12-01 |  | 1993-09-01 |  | 65000 | -4981 | 60019 | 60019 | 1 | 0 |  | 0 | [7 empty] | 16 | 10 | 0 | 19 | Completed. 17th ExCom approved Amendment.
22 | CPR/FOA/06/TAS/07 | COM | FIN |  |  | UNDP | Quality control testing on CFC-11 substitute technology in a production line for home refrigerators** |  | ASP | CPR | FOA | 6 | TAS | 7 | A | T | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 |  | 65000 | -4981 | 60019 | 60019 | 1 | 0 |  | 0 | [6 empty] | 1993 | 16 | 19 | 0 | 19 | Completed. 17th ExCom approved Amendment.
25 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on CFC-11 substitute technology in a production line for home refrigerators |  | ASP | CPR | FOA | 6 | TAS | 7 | A | T | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 0.92337 | 0 |  | 0 | [6 empty] | 1992 | 16 | 19 |  | 19 | Completed. 17th ExCom approved Amendment. |  |  | 1993-09-01
28 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on CFC-11 substitute technology in a production line for home refrigerators |  | ASP | CPR | FOA | 6 | TAS | 7 | A | T | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 |  | 0 | [6 empty] | 1992 | 16 | 19 |  | 19 | Completed. 17th ExCom approved Amendment.
31 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on CFC-11 substitute technology in a production line for home refrigerators |  | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 |  | 0 | [6 empty] | 1992 | 16 | 19 |  | 19 | Completed in 1993. Financially closed.
34 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on CFC-11 substitute technology in a production line for home refrigerators |  | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 |  | 0 | [6 empty] | 1992 | 16 | 19 |  | 19 | Completed in 1993. Financially closed.
34Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on CFC-11 substitute technology in a production line for home refrigerators |  | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 |  | 0 | [6 empty] | 1992 | 16 | 19 |  | 19 | Completed in 1993. Financially closed.
37 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on CFC-11 substitute technology in a production line for home refrigerators |  | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 |  | 0 | 8450 |  | 7802 |  |  | -648 | 1992 | 16 | 19 |  | 19 | Completed in 1993. Financially completed. | [14 empty] | 1992 | Non-Investment
37Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on CFC-11 substitute technology in a production line for home refrigerators |  | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I |  | 0 | 0 |  |  | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 |  | 0 | 8450 |  | 7802 |  |  | 648 | 1992 | 16 | 19 |  | 19 | Completed in 1993. Financially completed. | [14 empty] | 1992 | Non-Investment
40 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 7802 | 0 | 7802 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. PCR submitted in Jun-2000. | [14 empty] | 1992 | Non-Investment
40Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 7802 | 0 | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. PCR submitted in Jun-2000. | [14 empty] | 1992 | Non-Investment
43Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 7802 | 0 | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Operationally completed in 1993. PCR submitted in 2000. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
46 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 7802 | 0 | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
46Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 7802 | 0 | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
49 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 7802 | 0 | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
49Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 7802 | 0 | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
52 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 7802 | 0 | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
52Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 7802 | 0 | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
55 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 100 | 0 | 0 | 0 | 8450 | -648 | 7802 | 0 | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
55Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 7802 | 0 | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
58Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 0 |  | 0 | 0 | 1992 | 16 | 19 |  | 19 | Completed in 1993. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
61 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | 0 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. | [14 empty] | 1992 | Non-Investment
77Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | -0.47 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
79 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -647.53 | 0 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
79Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -647.53 | 0 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
82 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | -0.47 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
82Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -647.53 | 0 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
84 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -647.53 | 0 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
84Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -647.53 | 0 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
86 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | -0.47 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
86Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | -0.47 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
88 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 |  |  | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | -0.47 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
88Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 |  |  | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | -0.47 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
91 | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | -0.47 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment
91Final | CPR/FOA/06/TAS/07 | FIN | FIN |  |  | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 6 | TAS | 7 | A |  | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 1 | 0 | 0 | 0 | 8450 | -648 | -0.47 |  | 0 | 0 | 1992 | 16 | 19 | 0 | 19 | Completed in 1993. Financially completed in 1997. |  | 1992 | [13 empty] | Non-Investment