## Consolidated_Progress
CODE | status | agency | project_title | multi-year/one-off phaseout/individual/rmp/rmp update | imp_char | PROJECT_DESCRIPTION | ExCom_Provision | funds_net | funds_disbursed | consumption_odp_out_proposal | funds_obligated | estimated_funds_in_current_year | production_odp_out_proposal | consumption_odp_out | production_odp_out | date_approved | first_disbursement_date | date_compl_per_proposal | duration_baseline | date_comp_plan | duration_plan | date_completed | date_financial_completion | delay_msg | country | num | countryname | sector | Disbursements made to final beneficiaries from FECO/ MEP
AFG/PHA/47/INV/06 | FIN | Germany | National phase-out plan (1st tranche) | Multi-Year | A,I | Conversion of two flexible foam manufacturing plants (Mille Sponge Factory in Kabul and Arya Foam Industry in Heart) to methylene chloride; establishment of a CFC recovery and recycling network; and technical assistance for phasing out the use of CTC awareness programmes, and technical and financial support for the users of CTC to convert to viable alternatives. | Approved in accordance with the Agreement between the Government and the Executive Committee. | 118438 | 118438 | 28 | 0 | 0 | 0 | 28 |  | 2005-11-01 | 2016-05-01 | 2007-12-01 | 25 |  | 0 | 2008-08-01 | 2010-08-01 |  | AFG | 6 | Afghanistan | PHA
AFG/PHA/47/TAS/05 | FIN | UNEP | National phase-out plan (1st tranche) | Multi-year | A,I | To provide, inter alia, assistance for developing ODS regulations and codes of good practice in refrigeration and their enforcement and monitoring; training in good refrigeration practices to some 400 technicians, and establishment of seven training centers; and training to customs officers on issues related to ozone depletion and the Montreal Protocol, policy and regulations with respect to ODS, illegal trade and methods of tracking and controlling, recording imports of ODS and ODS-based equipment, and enforcement of a licensing system for ODS. It is also includes the establishment of the project management unit. | Approved in accordance with the Agreement between the Government and the Executive Committee. | 305000 | 305000 | 0 | 0 | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2009-12-01 | 49 |  | 0 | 2010-12-01 | 2011-12-01 |  | AFG | 5 | Afghanistan | PHA
AFG/PHA/48/INV/07 | FIN | Germany | National phase-out plan (2nd tranche) | Multi-Year | A,I | Last tranche of the phase-out plan approved at the 47th Meeting of the Executive Committee, to be implemented in accordance with the agreement between the Government and the Committee. |  | 642368 | 642368 | 151.8 | 0 | 0 | 0 | 151.8 |  | 2006-04-01 | 2006-05-01 | 2009-12-01 | 44 |  | 0 | 2009-12-01 | 2011-11-01 |  | AFG | 7 | Afghanistan | PHA
AFG/PHA/55/PRP/09 | FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | A,I | Preparation of the HPMP including assistance for policy and legislation; survey of HCFC use and analysis of data; and development and finalization of the full HPMP including consultations. |  | 85000 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2009-07-01 | 12 |  | 0 | 2010-12-01 | 2011-12-01 |  | AFG | 9 | Afghanistan | PHA
AFG/PHA/60/PRP/11 | FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | A,I | Preparation of an investment project in the refrigeration sector at Qasr Yakh. The company produces all types of standalone refrigeration systems like commercial size refrigerators, water coolers, ice-cream freezers, ice makers, bottle coolers, fresh food display cabinets and small commercial freezers. |  | 30000 | 30000 | 0 | 0 | 0 | 0 |  |  | 2010-04-01 | 2010-04-01 | 2011-04-01 | 12 |  | 0 | 2011-03-01 | 2013-03-01 |  | AFG | 11 | Afghanistan | PHA
AFG/PHA/63/INV/13 | TRF | Germany | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | A,I | It includes the establishment of refrigerant reclaim centres, technical support for the conversion of an assembly enterprise (Qasr Yakh) to phase out 757 kg of HCFC-22, including a refrigerant storage tank, HC refrigerant evacuation and charging unit and safety related equipment. Jointly implemented with UNEP. | Approved in accordance with the Agreement between the Government and the Executive Committee. Noted that the Government had agreed to establish an estimated baseline of 23.3 ODP tonnes as its starting point for sustained aggregate reduction in HCFC consumption, calculated using actual consumption of 22.2 ODP tonnes reported for 2009 and consumption of 24.4 ODP tonnes estimated for 2010. The Secretariat was requested, once the baseline data were known, to update Appendix 2-A to the Agreement to include the figures for maximum allowable consumption, and to notify the Executive Committee of the resulting levels of maximum allowable consumption and of any potential related impact on the eligible funding level, with any adjustments needed being made when the next tranche was submitted. | 31787 | 31787 | 0 | 0 | 0 | 0 | 0 |  | 2011-04-01 | 2011-10-01 | 2012-03-01 | 11 |  | 0 |  | 2016-12-01 |  | AFG | 13 | Afghanistan | PHA
AFG/PHA/63/TAS/12 | FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | A,I | It includes policy amendments, quota system development, and enforcement officers training; capability certifications and servicing technicians licensing; enhanced awareness and outreach programmes; training of technicians, provision of tools and equipment, and technical assistance for refrigerant recovery and recycling; project coordination and management. Jointly implemented with Germany. | Approved in accordance with the Agreement between the Government and the Executive Committee. Noted that the Government had agreed to establish an estimated baseline of 23.3 ODP tonnes as its starting point for sustained aggregate reduction in HCFC consumption, calculated using actual consumption of 22.2 ODP tonnes reported for 2009 and consumption of 24.4 ODP tonnes estimated for 2010. The Secretariat was requested, once the baseline data were known, to update Appendix 2-A to the Agreement to include the figures for maximum allowable consumption, and to notify the Executive Committee of the resulting levels of maximum allowable consumption and of any potential related impact on the eligible funding level, with any adjustments needed being made when the next tranche was submitted. | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2012-03-01 | 11 |  | 0 | 2015-12-01 | 2019-12-01 |  | AFG | 12 | Afghanistan | PHA
AFG/PHA/72/INV/17 | TRF | Germany | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | A,I | Project transferred to UNIDO at the 77th meeting | Approved on the understanding that the approved funds would not be transferred to the Government of Germany and UNEP until the Secretariat had received a verification report confirming that in 2013 the Government of Afghanistan was in compliance with the Montreal Protocol and the Agreement between the Government and the Executive Committee. Noted that the Agreement was updated based on the established HCFC baseline for compliance, and that the revised starting point for sustained aggregate reduction in HCFC consumption was 23.8 ODP tonnes, calculated using the average of 22.2 ODP tonnes of consumption for 2009 and 25.4 ODP tonnes of consumption (consisting of 24.9 ODP tonnes of virgin HCFC-22 and 0.5 ODP tonnes of recycled HCFC-22) for 2010, reported under Article 7 of the Montreal Protocol. | 0 | 0 | 1 | 0 | 0 | 0 |  |  | 2014-05-01 | 2014-09-01 | 2017-05-01 | 36 |  | 0 |  | 2016-12-01 |  | AFG | 17 | Afghanistan | PHA
AFG/PHA/72/TAS/16 | FIN | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | A,I | Continuation of enforcement of the licensing and quota system, two training workshops for 60 customs officers and provision of five refrigerant identifiers; four training workshops for 160 technicians on good servicing practices and provision of two sets of tools and recovery and recycling equipment; development and distribution of awareness material and conducting outreach activities; and project monitoring and co-ordination and verification of achievements for 2013. Jointly implemented with Germany. | Approved on the understanding that the approved funds would not be transferred to the Government of Germany and UNEP until the Secretariat had received a verification report confirming that in 2013 the Government of Afghanistan was in compliance with the Montreal Protocol and the Agreement between the Government and the Executive Committee. Noted that the Agreement was updated based on the established HCFC baseline for compliance, and that the revised starting point for sustained aggregate reduction in HCFC consumption was 23.8 ODP tonnes, calculated using the average of 22.2 ODP tonnes of consumption for 2009 and 25.4 ODP tonnes of consumption (consisting of 24.9 ODP tonnes of virgin HCFC-22 and 0.5 ODP tonnes of recycled HCFC-22) for 2010, reported under Article 7 of the Montreal Protocol. | 114131.07 | 114131 | 1.4 | 0 | 0 | 0 | 1.4 |  | 2014-05-01 | 2015-11-01 | 2017-05-01 | 36 |  | 0 | 2018-12-01 | 2019-12-01 |  | AFG | 16 | Afghanistan | PHA
AFG/PHA/77/INV/20 | FIN | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | A,I | It includes establishment of the National Refrigerant Management Competence Centre on refrigerant reclamation including provision of equipment and training in refrigerant recovery and reclamation; and training and demonstration for conversion of manufacturing of refrigeration equipment. Jointly implemented with UNEP. |  | 131938 | 131426.51 | 1 | 0 |  | 0 | 1 | 0 | 2016-12-01 | 2017-07-01 | 2019-12-01 | 36 |  | 0 | 2021-09-01 | 2021-09-07 | No Progress - Continued Monitoring | AFG | 20 | Afghanistan | PHA
AFG/PHA/79/INV/22 | ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | A,I | Establish a national refrigeration management competence centre on reclamation, containment and best practices; provide technical assistance to three enterprises (including Jahan Sarmayesh) in the commercial refrigeration manufacturing sector. Jointly implemented with UNEP. | Noted that the Agreement has been updated based on the HCFC consumption baseline under Article 7 data and the transfer of Germany’s component to UNIDO in accordance with decision 77/16. | 83000 | 11914.48 | 2.5 | 0 | 1 | 0 | 0.2 | 0 | 2017-07-01 | 2021-02-01 | 2020-07-01 | 36 | 2022-12-31 | 66 |  |  | No Progress - Continued Monitoring | AFG | 22 | Afghanistan | PHA
AFG/PHA/79/TAS/21 | COM | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | A,I | Complete the amendment of the Ozone Regulation and introduce the ban on HCFC-based equipment starting from 1 January 2018; conduct: two courses to train 40 officers in ODS imports control, two workshops to disseminate the amended regulation, one workshop for 15 trainers, two workshops for 60 technicians in good servicing practices, four courses for 100 servicing technicians in good practices and in servicing equipment with alternatives including flammables; implement the certification system for servicing workshops and technicians; raise awareness through outreach to small-quantity importers on HCFC import control, translating relevant materials into local-language, one workshop for media on HCFC phase out; and project co-ordination, monitoring and reporting. Jointly implemented with UNIDO. | Noted that the Agreement has been updated based on the HCFC consumption baseline under Article 7 data and the transfer of Germany’s component to UNIDO in accordance with decision 77/16. | 120000 | 108626 | 3.5 | 5000.41 | 11374 | 0 |  |  | 2017-07-01 | 2018-12-01 | 2020-07-01 | 36 |  | 0 | 2021-12-31 |  |  | AFG | 21 | Afghanistan | PHA
AFG/PHA/82/PRP/24 | FIN | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Individual | A,I |  |  | 39727 | 39727 | 0 | 0 | 0 | 0 |  |  | 2018-12-01 | 2019-06-01 | 2019-12-01 | 12 |  | 0 | 2020-09-30 | 2020-12-01 |  | AFG | 24 | Afghanistan | PHA
AFG/PHA/82/PRP/25 | FIN | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | A,I |  |  | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-12-01 | 2019-12-01 | 2019-12-01 | 12 |  | 0 | 2021-01-01 | 2021-09-17 |  | AFG | 25 | Afghanistan | PHA
AFG/PHA/85/INV/28 | ONG | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) | Multi-Year | A,I | Purchase equipment for training institutes (six refrigerant identifiers (three for training institutes and three for Customs), five R-290 air conditioners and two reclamation units); and initiate upgrading of two institutes for technicians. Jointly implemented with UNEP. |  | 28276 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2020-06-01 |  | 2021-12-01 | 18 | 2022-12-31 | 31 |  |  | To request UNIDO to provide a status report to the 91st meeting on implementation progress | AFG | 28 | Afghanistan | PHA
AFG/PHA/85/INV/30 | ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) | Multi-Year | A,I | Provide equipment and tools to upgrade training facilities in two provinces (tools for servicing, tools for handling flammable refrigerants and equipment for refrigerant recovery and recharge); provide support for the participation of female students (at least four) in the training programmes, and provide servicing tools for servicing workshops as needed. Jointly implemented with UNEP. | Approved in accordance with the Agreement between the Government and the Executive Committee for the period 2020 to 2025 to reduce HCFC consumption by 67.5 per cent of the country’s baseline; deducted 7.67 ODP tonnes of HCFCs from the remaining HCFC consumption eligible for funding. | 90000 | 2873.12 | 0 | 0 | 1 | 0 | 0 | 0 | 2020-06-01 | 2021-02-01 | 2023-12-01 | 42 | 2026-12-01 | 78 |  |  | No Progress - Continued Monitoring | AFG | 30 | Afghanistan | PHA
AFG/PHA/85/TAS/27 | ONG | UNEP | HCFC phase-out management plan (stage I, fourth tranche) | Multi-Year | A,I | Organize three stakeholder consultations and information dissemination to strengthen enforcement of the licensing and quota system and implementation of ban on HCFC-based equipment; train 90 customs officers (four workshops); develop a certification system for good RAC servicing practices, including training curriculum and an evaluation system for certification; train 90 technicians (three workshops) on good servicing practices, safety in handling flammable refrigerants and improving energy efficiency of RAC units; implement awareness-raising activities to disseminate information on ODS policies and alternative technologies; and manage, coordinate and report on the HPMP. Jointly implemented with UNIDO. |  | 40825 | 0 | 0 | 40824 | 20412.5 | 0 |  |  | 2020-06-01 |  | 2021-12-01 | 18 | 2022-12-01 | 30 |  |  | To request UNEP to provide a status report to the 91st meeting on the national ozone unit (NOU) operations and implementation progress | AFG | 27 | Afghanistan | PHA
AFG/PHA/85/TAS/29 | ONG | UNEP | HCFC phase-out management plan (stage II, first tranche) | Multi-Year | A,I | Update ODS regulations (changes to procedures for licensing and quota system to cover registration of importers, mandatory reporting by importers, and continuous monitoring and data collection); develop an online licensing and quota system; enforce a ban on HCFC-based equipment import; build importers’ capacity to improve record-keeping and data reporting. Mainstreaming the HPMP into sector policies to inhibit new HCFC demand in the foam sector in building construction and cold chain food processing sub-sectors; develop seven policy briefs/information notes; conduct sensitization events for stakeholders in these sub-sectors; promote ODS alternatives and energy-efficient equipment through the public procurement policy; train 180 customs and enforcement officers, conduct border dialogues with neighbouring countries, participate in regional training activities and iPIC systems; legalize market monitoring through inspections; train 150 technicians in good servicing practices (i.e. refrigerant leakage control and containment in industrial applications); pilot technician certification system (e.g. development and rolling out of the mechanism for recognition of prior learning, accreditation process and training of assessors; and developing a database of trained technicians); distribute awareness raising materials, and update communication strategy for stakeholders; and coordinate HPMP activities and prepare progress reports. Jointly implemented with UNIDO. | Approved in accordance with the Agreement between the Government and the Executive Committee for the period 2020 to 2025 to reduce HCFC consumption by 67.5 per cent of the country’s baseline; deducted 7.67 ODP tonnes of HCFCs from the remaining HCFC consumption eligible for funding. | 229567 | 0 | 0 | 189567 | 114783.5 | 0 |  |  | 2020-06-01 |  | 2023-06-01 | 36 | 2023-06-01 | 36 |  |  | To request UNEP to provide a status report to the 91st meeting on the NOU operations and implementation progress | AFG | 29 | Afghanistan | PHA
AFG/SEV/43/CPG/02 | FIN | UNEP | Preparation of the country programme/RMP project | Individual | A,I | Assist with the development of the country programme and RMP in accordance with Executive Committee guidelines. |  | 41845 | 41845 | 0 | 0 | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2005-03-01 | 8 |  | 0 | 2005-10-01 | 2011-12-01 |  | AFG | 2 | Afghanistan | SEV
AFG/SEV/43/INS/01 | FIN | UNEP | Institutional strengthening project (phase I, start-up) | Individual | A,I | Start-up costs to assist in data collection and preparation of the country programme/RMP project proposal. |  | 39987 | 39987 | 0 | 0 | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2005-07-01 | 12 |  | 0 | 2005-07-01 | 2007-04-01 |  | AFG | 1 | Afghanistan | SEV
AFG/SEV/46/INS/03 | FIN | UNEP | Start up of institutional strengthening project | Individual | A,I | Additional start-up funding | Approved, on an exceptional basis, as an advance on funding for phase I of the institutional strengthening project. | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-08-01 | 2005-12-01 | 5 |  | 0 | 2005-10-01 | 2006-10-01 |  | AFG | 3 | Afghanistan | SEV
AFG/SEV/47/INS/04 | FIN | UNEP | Establishment of national ozone unit for implementing the phase-out of ODS (institutional strengthening) | Individual | A,I | To provide information on the Montreal Protocol, phase-out schedules, regulations and general information to enable Afghanistan to achieve the phase-out goals as presented in the country programme; to develop and implement specific capacity building and awareness programmes; to submit annual reports on the ODS consumption to the Fund and Ozone Secretariats as per relevant decisions by the Parties and the Executive Committee; assisting in the development of legislative system to control ODS and ODS-based equipment including a licensing and quota system, and facilitating implementation of regulations on ODSs; and to monitor implementation of the RMP and other phase-out activities. |  | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 | 25 |  | 0 | 2007-11-01 | 2007-12-01 |  | AFG | 4 | Afghanistan | SEV
AFG/SEV/53/INS/08 | FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | A,I | To strengthening coordination with customs officers to ensure enforcement of ODS legislations; dissemination of information on new technologies and ODS substitutes through various workshops; implementation of a certification system for refrigeration technicians; monitoring of the implementation of the TPMP including verification of ODS data; and data reporting. The country would need to maintain momentum of the existing phase-out measures and complete implementation of project activities under the phase-out plan to ensure achievement of future targets and sustaining compliance. |  | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-11-01 | 24 |  | 0 | 2009-11-01 | 2009-11-01 |  | AFG | 8 | Afghanistan | SEV
AFG/SEV/58/INS/10 | FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | A,I | To maintain momentum of ODS phase-out activities through implementation of activities in the phase-out plan; to initiate HPMP activities; to continue the implementation of the ODS monitoring and control regulatory framework including licensing and quota systems and strengthen regulations to control HCFC imports; to submit data reporting to the Fund and Ozone Secretariats. | In line with decision 58/16 approving institutional strengthening renewals up to 31 December 2010. Additional funding approved at the 61st Meeting in line with decision 59/47. | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2011-11-01 | 28 |  | 0 | 2011-12-01 | 2012-12-01 |  | AFG | 10 | Afghanistan | SEV
AFG/SEV/64/INS/14 | FIN | UNEP | Extension of institutional strengthening project (phase V: 12/2011-11/2013) | Individual | A,I | Public awareness activities to increase knowledge among stakeholders; implementation ODS monitoring and control regulatory framework including licensing and quota systems; strengthening regulations to implement HCFC phase-out (HS codes for HCFCs, HCFC import licensing and quota systems); implementation of HPMP; timely submission of data reporting to the Fund and Ozone Fund Secretariats and other agencies. |  | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2013-11-01 | 28 |  | 0 | 2013-12-01 | 2014-12-01 |  | AFG | 14 | Afghanistan | SEV
AFG/SEV/70/INS/15 | FIN | UNEP | Extension of institutional strengthening project (phase VI: 12/2013-11/2015) | Individual | A,I | To assist the country in complying with the 10 percent reduction of HCFCs by 2015; and data reporting to the Fund and Ozone Secretariats. |  | 150000 | 150000 | 0 | 0 | 0 | 0 |  |  | 2013-07-01 | 2014-04-01 | 2015-11-01 | 28 |  | 0 | 2016-12-01 | 2018-06-01 |  | AFG | 15 | Afghanistan | SEV
AFG/SEV/74/INS/18 | FIN | UNEP | Extension of institutional strengthening project (phase VII: 12/2015-11/2017) | Individual | A,I | Consultations on the HCFC-based equipment ban; twice yearly meetings with the Custom Department on data collection, field surveys and visits, customs officers training, and an awareness campaign; training in good practices; and awareness activities. |  | 150000 | 150000 | 0 | 0 | 0 | 0 |  |  | 2015-05-01 | 2016-08-01 | 2017-11-01 | 30 |  | 0 | 2017-12-01 | 2018-12-01 |  | AFG | 18 | Afghanistan | SEV
AFG/SEV/74/TAS/19 | FIN | UNEP | Survey of ODS alternatives at the national level | Individual | A,I | To obtain information including data (where available) and estimates of ODS alternatives currently in use by sector and subsector, and forecasts of ODS alternatives most commonly used. |  | 59742.07 | 59742 | 0 | 0 | 0 | 0 |  |  | 2015-05-01 | 2016-10-01 | 2016-05-01 | 12 |  | 0 | 2017-08-01 | 2019-12-01 |  | AFG | 19 | Afghanistan | SEV
AFG/SEV/80/INS/23 | FIN | UNEP | Extension of institutional strengthening project (phase VIII: 1/2018-12/2019) | Individual | A,I | Consult on the HCFC-based equipment ban; hold meetings with customs department on data collection, field surveys and visits; raise awareness among stakeholders of the forthcoming ban on HCFC-based equipment; continue training in good practices and strengthen its cooperation with the customs department, ministries and industry associations; and start preparatory work on enabling activities to facilitate Kigali Amendment ratification. |  | 186246 | 186246 | 0 | 0 | 0 | 0 |  |  | 2017-11-01 | 2018-11-01 | 2019-12-01 | 25 |  | 0 | 2019-12-31 | 2020-12-01 |  | AFG | 23 | Afghanistan | SEV
AFG/SEV/81/TAS/01+ | ONG | UNEP | Enabling activities for HFC phase-down | Individual | A,I | Facilitate early ratification (ozone, climate and energy policy/legislation analysis, draft legislation preparation, stakeholder consultations, and cost benefit analysis of the ratification impacts); build capacity for introducing HFC alternatives (training needs assessments in the servicing sector and meetings with technicians on safe handling); develop regulatory framework for import/export licensing systems for HFC and HFC alternatives (review of methodologies for monitoring and recording of individual HFC/alternative imports/exports); prepare a national strategy for implementation (framework, HFC production and consumption information, sector profile and analysis, estimated baseline, growth prediction, alternative technology mapping, HCFC phase out linkage, potential priority areas for phase-down); and raise awareness. | Funded from the additional voluntary contributions of non-Article 5 countries. | 150000 | 130965.35 | 0 | 16362.16 | 9517.325 |  |  |  | 2018-06-01 | 2019-03-01 | 2020-01-01 | 19 | 2022-06-01 | 48 |  |  |  | AFG | 1 | Afghanistan | SEV
AFG/SEV/83/INS/26 | COM | UNEP | Extension of institutional strengthening project (phase IX: 1/2020-12/2021) | Individual | A,I | Implement the ban on HCFC-based equipment and other policy measures; conduct regular consultations, capacity building for customs officers, field visits; monitor, and coordinate with neighbouring countries to prevent illegal trade; train technicians in good practices with industry associations, implement enabling activities to facilitate the ratification of the Kigali Amendment. |  | 192000 | 80598 | 0 | 111401.62 | 111402 | 0 |  |  | 2019-05-01 | 2020-12-01 | 2021-12-01 | 31 |  | 0 | 2021-12-31 |  |  | AFG | 26 | Afghanistan | SEV
AFG/SEV/87/INS/31 | ONG | UNEP | Extension of institutional strengthening project (phase X: 1/2022-12/2023) | Individual | A,I | Cooperate with customs organization on the Montreal Protocol issues including the assignment of individual codes for HFCs and blends under the 2022 HS code; conduct regular trainings for customs authorities; conduct good practices trainings for RAC technicians; carry out field surveys and market inspection; coordinate with enforcement authorities to better implement the HPMP; ensure the timely submission of consumption data under Article 7 of the Montreal Protocol and country programme data reports, and gender mainstreaming will be integrated into the implementation of the upcoming phase. |  | 192000 | 0 | 0 | 0 | 48000 | 0 |  |  | 2021-07-01 |  | 2023-12-01 | 29 | 2023-12-31 | 30 |  |  |  | AFG | 31 | Afghanistan | SEV
AFR/DES/68/TAS/41 | FIN | France | Strategy for disposal and destruction of ODS for five low-volume-consuming Central African countries (Burundi, Cameroon, Central African Republic, Congo and Guinea) | Individual | A,I | It includes data collection in the 6 participating countries on non reusable and unwanted ODS stockpiles; analysis of the existing legal framework for the sound disposal of unwanted ODS from a regional perspective; assessment of the economic aspects of the collection and disposal options for non reusable and unwanted ODS; preparation of a report containing options to dispose of, and destroy non-reusable and unwanted ODS in LVC countries in Africa; and dissemination of the report and the overall strategy to other countries in the African region. Jointly implemented with UNIDO. | Approved in line with decision 67/38 and on the understanding that: the technical assistance should focus on the following activities: data collection on non-reusable and unwanted ODS amounts; verification of the existing legal framework for the sound disposal of ODS stockpiles; awareness-raising and dissemination; and development of a strategy. UNIDO and the Government of France were encouraged to ensure that the final report and strategy included the following information: the methodology adopted for the collection and verification of ODS waste data, taking into account challenges faced and lessons learned; an analysis of the existing situation in the participating countries with regard to their capacity to recover, recycle and reclaim ODS taking into account projects for CFC phase-out already approved; synergies with other conventions dealing with chemicals (Stockholm Convention on Persistent Organic Pollutants). The strategy would be developed in such a way that it could be extended to all countries in the African region, as well as other LVC countries; and no other funding would be made available for new activities related to ODS disposal and destruction in the absence of a new relevant decision of the Meeting of the Parties. | 66872 | 66872 | 0 | 0 | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-05-01 | 2013-12-01 | 12 |  | 0 | 2017-11-01 | 2017-11-01 |  | AFR | 41 | Region: AFR | DES
AFR/FUM/16/TRA/10 | FIN | UNEP | Regional workshop on methyl bromide for English-speaking African countries | Individual | A,I | To raise awareness concerning the role of methyl bromide in ozone layer depletion, control measures and definitions, implications of control measures, current methods to control emissions, and alternative uses. |  | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 | 12 |  | 0 | 1995-09-01 | 1999-04-01 |  | AFR | 10 | Region: AFR | FUM
AFR/FUM/17/TAS/14 | FIN | Australia | Replacement of methyl bromide with non-ozone depleting alternative in grain storage | Individual | A,D | To demonstrate commodity fumigation techniques that are not dependent on methyl bromide. It will include the transfer of the improved and permanent sheeting systems of disinfection and protection of bagged grain to Southern Africa. Target countries for the demonstration activity are Kenya, Malawi, Zambia and Zimbabwe. |  | 38896 | 38896 | 0 | 0 | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 | 6 |  | 0 | 1995-10-01 | 1995-11-01 |  | AFR | 14 | Region: AFR | FUM
AFR/FUM/17/TAS/15 | FIN | UNDP | Methyl bromide data collection for Africa | Individual | A,I | Investigate and determine the exact usage of methyl bromide and develop regional and/or country-specific plans that outline cost-effective substitution possibilities that could be used to reduce use of methyl bromide. |  | 179850 | 179850 | 0 | 0 | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-01-01 | 6 |  | 0 | 1998-04-01 | 2000-12-01 |  | AFR | 15 | Region: AFR | FUM
AFR/FUM/21/TRA/18 | FIN | UNEP | Regional survey and workshop on methyl bromide for French-speaking African countries | Individual | A,I | The workshop will focus on the following aspects: related control measures and definitions under the Montreal Protocol, and their implications for the region; methodologies to control emissions into the atmosphere from the various current uses of methyl bromide; alternatives to methyl bromide uses (fumigation of soils, perishables, and structures); and cost effectiveness of the different alternatives. |  | 275000 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-02-01 | 12 |  | 0 | 1998-04-01 | 1999-03-01 |  | AFR | 18 | Region: AFR | FUM
AFR/FUM/27/TRA/23 | FIN | UNEP | Regional training of trainer courses for extension workers | Individual | A,I | UNEP/FAO will implement a regional training course for extension workers through 4-week courses focused on building facilitation skills and group dynamic/group building methods, methods for participatory approach, farmer-to-farmer methods, cultural sensitivity, and communication, including increased coordination and systems training. It will use the manuals for extension workers developed as part of this programme. Trainers will come from experienced extension staff working in FAO’s Farmer Field Schools, local experts, cooperatives, farmers' organizations or NGOs in the country that have skills and experience in interactive learning. |  | 63956 | 63956 | 0 | 0 | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 | 31 |  | 0 | 2001-12-01 | 2006-02-01 |  | AFR | 23 | Region: AFR | FUM
AFR/FUM/27/TRA/24 | FIN | UNEP | Regional training workshops on policy development | Individual | A,I | To provide countries with tools and information necessary to develop short and long term policies for meeting the 2002 freeze, reductions and phase out and to promote the use of alternatives; encourage countries to develop action plans for methyl bromide phase out that will ensure a coordinated and effective approach for replacing methyl bromide; and raise awareness among policymakers in ozone units, agricultural ministries and pesticide control authorities about the importance of developing strong national policies to phase out methyl bromide and implement effective alternatives. |  | 130000 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-01 | 2000-03-01 | 12 |  | 0 | 1999-12-01 | 2001-12-01 |  | AFR | 24 | Region: AFR | FUM
AFR/FUM/34/TRA/28 | FIN | UNEP | Regional workshop on the experiences of use of methyl bromide alternatives evaluated under the Multilateral Fund | Individual | A,I | Regional workshop on the experiences of use of MB alternatives evaluation under the Fund to exchange experiences and lessons learned from demonstration projects in one country to other countries in the region; promote the adoption of MB alternatives that have been identified in the demonstration projects to enable countries to meet the 2002 freeze and 20 per cent reduction by 2005 and to prevent future usage; identify new or unrecognized barriers to the rapid adoption of alternative technologies and develop strategies for addressing these barriers; raise awareness about effective alternatives to MB; promote ratification of the Copenhagen Amendment in countries that have not done so; and clarify definition of quarantine and pre-shipment applications as outlined in the Montreal Protocol to assist countries in accurately reporting MB consumption data. |  | 55823 | 55823 | 0 | 0 | 0 | 0 | 0 | 0 | 2001-07-01 | 2003-08-01 | 2002-07-01 | 12 |  | 0 | 2004-03-01 | 2009-07-01 |  | AFR | 28 | Region: AFR | FUM
AFR/FUM/38/TAS/32 | FIN | UNDP | Technical assistance for methyl bromide reductions and formulation of regional phase-out strategies for low-volume consuming countries | Individual | A,I | The project is to provide technical assistance to achieve MB reductions to meet the 20 per cent reduction step in Congo, Congo DR, Nigeria, Sudan, Swaziland. It will begin by developing national and regional strategies which will identify the most effective activities, timetables for action steps, and responsible organizations. The project will also provide assistance to 24 countries that have no reported MB consumption to prevent the introduction and use of MB (Angola, Benin, Burkina Faso, Burundi, Central African Republic, Chad, Comoros, Djibouti, Eritrea, Gabon, Gambia, Guinea, Mali, Mauritania, Mozambique, Niger, Rwanda, Sao Tomé and Principe, Seychelles, Sierra Leone, Somalia, Tanzania and Togo) | Approved on the understanding that: (a) Botswana and Cameroon would not be included in the project proposal since the demonstration projects previously approved for UNIDO would result in the complete phase-out of methyl bromide consumption in those countries; (b) because UNIDO had been requested by the Governments of Ethiopia and Zambia to formulate investment projects once ratification of the Copenhagen Amendment had been finalized, the project would include those two countries only insofar as policy support was required to allow for the ratification of the Copenhagen Agreement and that any future investment work post-ratification, as deemed necessary, would be undertaken with UNIDO; (c) the project will provide technical assistance to achieve methyl bromide reductions to meet the 20 per cent reduction step in Congo, Democratic Republic of Congo, Nigeria, Sudan and Swaziland, without further assistance from the Multilateral Fund; (d) the project will also provide assistance to countries to put in place appropriate mechanisms to reduce and eventually ban imports of methyl bromide; (e) UNDP would request all the governments participating in the project, except those in paragraph c above, to submit letters indicating their understanding that in accepting this project they would not return for further methyl bromide funding in future, as per the terms of the revised methyl bromide strategy and guidelines; and (f) UNDP agreed to report to the Executive Committee on progress achieved on an annual basis | 547888 | 547888 | 1.5 | 0 | 0 | 0 | 1.5 | 0 | 2002-11-01 | 2003-02-01 | 2006-02-01 | 39 |  | 0 | 2011-12-01 | 2014-02-01 |  | AFR | 32 | Region: AFR | FUM
AFR/FUM/54/DEM/40 | FIN | UNIDO | Regional demonstration project on alternatives to the use of methyl bromide for treatment of high moisture dates (Algeria and Tunisia) | Individual | A,I | To demonstrate the technical and economic feasibility of the following alternatives for disinfestation of high moisture palm dates: modified atmosphere; heating treatment; and alternative chemicals, including ethyl formate in combination with CO2, phosphine in combination with CO2, sulphur dioxide and sulphuryl fluoride, incorporated within an IPM programme. It will be implemented in four phases: a technical evaluation based on a small-scale test of the alternatives; an expert discussion of results obtained from the first year of activity, aimed at selecting the most promising alternatives and compiling results of the trials performed under commercial conditions in varieties with different levels of humidity; a full-scale commercial evaluation including economic evaluation of the technically feasible alternatives; and a final workshop to demonstrate the results obtained during the two years of trials with alternatives. |  | 269358.81 | 269359 | 0 | 0 |  | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2010-03-01 | 23 |  | 0 | 2016-12-01 | 2017-09-01 |  | AFR | 40 | Region: AFR | FUM
AFR/HAL/35/TAS/29 | FIN | Germany | Establishment of a regional halon bank for Eastern and Southern African countries (Botswana, Ethiopia, Kenya, Lesotho, Namibia, Tanzania and Zimbabwe) | Halon banking | A,I | Establishment of a regional halon bank for East Africa to ensure that the countries meet their obligations under the Montreal Protocol. It will provide halon banking, promotion of recovery and recycling of halons, recovery services for halons in the case of maintenance of a fire protection system, storage of halon recovered and recycled, a system of distribution of halons for essential uses, provisions for the trade of recycled halons, and regional co-ordination of activities. It will be developed by a team of international and national halon bank experts. Each country will ban the importation of new produced halons with the establishment of the halon bank, except for essential uses as decided by the Parties to the Protocol. | Approved on the condition that this would be the final project in the halon sector for the participating countries. | 350000 | 350000 | 27 | 0 | 0 | 0 | 27 |  | 2001-12-01 | 2002-08-01 | 2005-01-01 | 37 |  | 0 | 2010-12-01 | 2012-12-01 |  | AFR | 29 | Region: AFR | HAL
AFR/HAL/37/TAS/31 | CLO | UNDP | Sectoral phase out programme: establishing a regional halon bank for West and Central Africa (Benin, Burkina Faso, Cameroon, Congo, Congo DR, and Guinea) | Individual | A,I | It includes formulation of national halon banking strategies, provision of recovery and recycling, storage and quality control equipment, training program to recovery and recycling personnel, the identification of international trade opportunities, development of halon regulations, a database and promotion All participating countries are active members of the African regional network. The network meetings of ozone officers will provide co-ordination activities for knowledge exchange of halons and information regarding use of alternatives. Each country will ban the importation of new produced halons at the time of the establishment of the halon bank |  | 218481 | 218481 | 61 | 0 | 0 | 0 | 44.2 | 0 | 2002-07-01 | 2003-02-01 | 2005-08-01 | 37 |  | 0 |  | 2008-11-01 |  | AFR | 31 | Region: AFR | HAL
AFR/REF/06/TRA/02 | TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in West Africa (French) | Individual | A,I | NOTE: Transferred to UNEP work programme in Jun 1993. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 | 12 |  | 0 |  | 1993-06-01 |  | AFR | 2 | Region: AFR | REF
AFR/REF/06/TRA/03 | TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in Africa (English-speaking countries) | Individual | A,I | NOTE: Transferred from UNDP work programme in Jun 1993. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 | 12 |  | 0 |  | 1993-06-01 |  | AFR | 3 | Region: AFR | REF
AFR/REF/06/TRA/04 | FIN | UNEP | Regional training course on refrigeration for Africa | Individual | A,I |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-12-01 | 1992-12-01 | 10 |  | 0 | 1992-12-01 | 1993-12-01 |  | AFR | 4 | Region: AFR | REF
AFR/REF/10/TRA/05 | FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in West Africa (French) | Individual | A,I | NOTE: Transferred from UNDP work programme in Jun 1993. |  | 43400 | 43400 | 0 | 0 | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-05-01 | 11 |  | 0 | 1995-07-01 | 1995-12-01 |  | AFR | 5 | Region: AFR | REF
AFR/REF/10/TRA/06 | FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in Africa (English-speaking countries) | Individual | A,I | NOTE: Transferred to UNEP work programme in Jun 1993. |  | 43400 | 43400 | 0 | 0 | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-05-01 | 11 |  | 0 | 1994-09-01 | 1994-12-01 |  | AFR | 6 | Region: AFR | REF
AFR/REF/17/PRP/12 | FIN | UNIDO | Preparation of a recovery and recycling project in Benin, Botswana, Burkina Faso, Gambia, Guinea, Namibia, and Senegal | Individual | A,I |  |  | 43881 | 43881 | 0 | 0 |  | 0 | 0 | 0 | 1995-07-01 | 1996-04-01 | 1996-01-01 | 6 |  | 0 | 1997-09-01 | 1999-08-01 |  | AFR | 12 | Region: AFR | REF
AFR/REF/32/TAS/26 | FIN | France | Refrigeration and global environment evaluation of equipment modernization study |  | A,I | To carry out a study in countries of a sub-regional economically integrated organization of the West Africa (UEMO) with the following goals: evaluation of the contribution of the refrigeration sector on ozone depletion and greenhouse effect, identification of the necessary actions in order to integrate these environmental aspects in the development of this very important sector, propose an equipment modernization investment programme, with new equipment using less energy and ODS-free refrigerant. The expected results are: formulation of a strategic plan for the ODS phase out and reduction of greenhouse gases emissions in the commercial and industrial refrigeration in UEMOA countries through 2010; identification of incentives (funding, taxes, regulations) for early modernization of the existing equipment; establishment of an investment programme aimed at reducing the consumption of ODS and emission of greenhouse gases; setting up an innovative funding process including GEF, Multilateral Fund and other funding sources to ensure the sustainability of the refrigeration sub-sectors with respect to the global environment | The resources would be used only for ozone-related issues; the results of the study would be made available to the Committee as well as to the countries involved; and no further funding would be requested from the Multilateral Fund as a result of the study, unless such requests were fully consistent with decision 31/48 an all other Executive Committee requirements | 15000 | 15000 | 0 |  | 0 | 0 |  |  | 2000-12-01 | 2001-07-01 | 2002-07-01 | 19 |  | 0 | 2002-12-01 | 2002-11-01 |  | AFR | 26 | Region: AFR | REF
AFR/REF/48/DEM/34 | FIN | Germany | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | A,I | It will provide a valuable contribution of innovative strategic elements for implementation of complete CFC phase out in the region (jointly implemented with UNIDO as the lead agency and the Governments of France and Japan). | Approved on the understanding that external resources of US $477,876 for the whole project were to be used only for activities considered to be part of the project costs; disbursement of the amounts approved would be dependent upon the availability of external resources as specified, to be confirmed by the Secretariat, based on the advice from the agency that external funding had been secured. The ratio between the maximum amount of Fund resources that could be disbursed and the external resources confirmed by the Secretariat should be equal to the ratio between the amount approved and the corresponding amount of associated external resources; additional countries in Africa could receive support for phase-out in the chiller sector under the project, provided that funding under the project was available, and that all other conditions established by the Executive Committee in its respective decisions regarding chiller demonstration projects were being met. UNIDO and the bilateral agencies involved would inform the Secretariat on an annual basis, and in time for the last Meeting of the Executive Committee, in every year of project implementation as well as in the year of completion, on progress in terms of implementation, main experiences and additional external resources acquired for the chiller phase-out and major market transformations observed. | 192500 | 192500 | 0 | 0 | 0 | 0 |  |  | 2006-04-01 | 2006-09-01 | 2009-09-01 | 41 |  | 0 | 2010-12-01 | 2011-12-01 |  | AFR | 34 | Region: AFR | REF
AFR/REF/48/DEM/35 | FIN | Japan | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | A,I | It will provide a valuable contribution of innovative strategic elements for implementation of complete CFC phase out in the region (jointly implemented with UNIDO as the lead agency and the Governments of France and Germany). | Approved on the understanding that external resources of US $477,876 for the whole project were to be used only for activities considered to be part of the project costs; disbursement of the amounts approved would be dependent upon the availability of external resources as specified, to be confirmed by the Secretariat, based on the advice from the agency that external funding had been secured. The ratio between the maximum amount of Fund resources that could be disbursed and the external resources confirmed by the Secretariat should be equal to the ratio between the amount approved and the corresponding amount of associated external resources; additional countries in Africa could receive support for phase-out in the chiller sector under the project, provided that funding under the project was available, and that all other conditions established by the Executive Committee in its respective decisions regarding chiller demonstration projects were being met. UNIDO and the bilateral agencies involved would inform the Secretariat on an annual basis, and in time for the last Meeting of the Executive Committee, in every year of project implementation as well as in the year of completion, on progress in terms of implementation, main experiences and additional external resources acquired for the chiller phase-out and major market transformations observed. | 699946.75 | 699947 | 0 | 0 | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-06-01 | 2009-09-01 | 41 |  | 0 | 2017-12-01 | 2018-12-01 |  | AFR | 35 | Region: AFR | REF
AFR/REF/48/DEM/36 | FIN | France | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | A,I | It will provide a valuable contribution of innovative strategic elements for implementation of complete CFC phase out in the region (jointly implemented with UNIDO as the lead agency and the Government of Germany). | Approved on the understanding that external resources of US $477,876 for the whole project were to be used only for activities considered to be part of the project costs; disbursement of the amounts approved would be dependent upon the availability of external resources as specified, to be confirmed by the Secretariat, based on the advice from the agency that external funding had been secured. The ratio between the maximum amount of Fund resources that could be disbursed and the external resources confirmed by the Secretariat should be equal to the ratio between the amount approved and the corresponding amount of associated external resources; additional countries in Africa could receive support for phase-out in the chiller sector under the project, provided that funding under the project was available, and that all other conditions established by the Executive Committee in its respective decisions regarding chiller demonstration projects were being met. UNIDO and the bilateral agencies involved would inform the Secretariat on an annual basis, and in time for the last Meeting of the Executive Committee, in every year of project implementation as well as in the year of completion, on progress in terms of implementation, main experiences and additional external resources acquired for the chiller phase-out and major market transformations observed. | 261396 | 261396 | 0 | 0 | 0 | 0 | 0 | 0 | 2006-04-01 | 2010-12-01 | 2009-09-01 | 41 |  | 0 | 2017-12-01 | 2019-07-01 |  | AFR | 36 | Region: AFR | REF
AFR/REF/48/DEM/37 | FIN | UNIDO | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | A,I | It proposes to develop strategies to handle the existing and future demand of CFCs for the entire CFC chiller sub-sector; assess the potential for managing CFC chiller servicing through stock piles after 2010; identify applications of strategic importance for accelerated replacement and thus contribute to the compliance with the national phase out targets; initiate accelerated replacement of CFC chillers and support for innovative financial acquisition; demonstrate benefits of investments in CFC free chiller technologies among investors, governments and financial institutions and increase awareness; establish a strategy for managing the entire CFC chiller sub-sector; and increase public awareness of the impending phase out and options that may be available for dealing with chillers. Utilization of external funding from the French Global Environment Facility is being proposed (implemented jointly with the Governments of France, Germany and Japan). | Approved on the understanding that external resources of US $477,876 for the whole project were to be used only for activities considered to be part of the project costs; disbursement of the amounts approved would be dependent upon the availability of external resources as specified, to be confirmed by the Secretariat, based on the advice from the agency that external funding had been secured. The ratio between the maximum amount of Fund resources that could be disbursed and the external resources confirmed by the Secretariat should be equal to the ratio between the amount approved and the corresponding amount of associated external resources; additional countries in Africa could receive support for phase-out in the chiller sector under the project, provided that funding under the project was available, and that all other conditions established by the Executive Committee in its respective decisions regarding chiller demonstration projects were being met. UNIDO and the bilateral agencies involved would inform the Secretariat on an annual basis, and in time for the last Meeting of the Executive Committee, in every year of project implementation as well as in the year of completion, on progress in terms of implementation, main experiences and additional external resources acquired for the chiller phase-out and major market transformations observed. | 693381.5 | 693381.5 | 0 | 0 |  | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2009-09-01 | 41 |  | 0 | 2014-12-01 | 2017-08-01 |  | AFR | 37 | Region: AFR | REF
AFR/SEV/06/TRA/01 | FIN | UNEP | Regional workshop for Africa | Individual | A,I | Designed to provide government and industry decision-makers with basic information on ODS control policies and strategies and the latest information about replacement technologies and products relating to the controlled substances. |  | 210000 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 | 12 |  | 0 | 1992-12-01 | 1993-12-01 |  | AFR | 1 | Region: AFR | SEV
AFR/SEV/11/TRA/07 | FIN | South Africa | Industry workshop on the practical implementation of the Protocol for English-speaking countries |  | A,D | To provide maintenance, repair and manufacturing industry technical managers from several African countries with information on complying with the Montreal Protocol. |  | 30000 | 30000 | 0 | [5 empty] | 1993-11-01 |  | 1995-11-01 | 24 | 1994-09-01 | 10 | 1994-09-01 | 1994-09-01 |  | AFR | 7 | Region: AFR | SEV
AFR/SEV/12/TAS/09 | FIN | UNEP | Support to regional network for ODS officers in Africa (1994) | Individual | A,I | To establish co-operation among ODS officers in a sub-region with developed countries, and to strengthen the capacity of the ozone units to design and implement effective strategies, well-adapted to local conditions, leading to ODS phase-out at the earliest possible date. An ODSONET in Africa will be divided into one network for English-speaking countries (ODSONET/AF-E) and one for French-speaking countries (ODSONET/AF-Fr). |  | 180000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 | 12 |  | 0 | 1996-03-01 | 2000-03-01 |  | AFR | 9 | Region: AFR | SEV
AFR/SEV/12/TRA/08 | FIN | UNEP | Follow-up on prior regional workshop and training activities | Individual | A,I | Ensure that the Regional Workshop for Africa on the Implementation of the Montreal Protocol (Nairobi, Dec 1992), and the Training Courses on Good Practices in Refrigeration (Ghana, Oct 1993 and Kenya, Dec 1993), have led to concrete ODS-phase-out actions. |  | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 | 12 |  | 0 | 1997-06-01 | 1999-04-01 |  | AFR | 8 | Region: AFR | SEV
AFR/SEV/16/TAS/20 | FIN | UNEP | Support to regional network for ODS officers in Africa (1995) | Individual | A,I | To establish co-operation among ODS officers in a sub-region with developed countries, and to strengthen the capacity of the ozone units to design and implement effective strategies, well-adapted to local conditions, leading to ODS phase-out at the earliest possible date. An ODSONET in Africa will be divided into one network for English-speaking countries (ODSONET/AF-E) and one for French-speaking countries (ODSONET/AF-Fr). |  | 232200 | 232200 | 0 | 0 | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-01 | 1996-03-01 | 12 |  | 0 | 1996-03-01 | 1999-01-01 |  | AFR | 20 | Region: AFR | SEV
AFR/SEV/17/TRA/11 | FIN | France | Technology transfer workshop for African countries on practical implementation of the Montreal Protocol |  | A,D | To assist African countries (Algeria, Benin, Burkina Faso, Cameroon, Central African Republic, Chad, Comoros, Congo, Cote D'Ivoire, Egypt, Gabon, Guinea, Mali, Mauritania, Niger, Senegal, Togo, Tunisia, Zaire) in ODS phase out activities by providing for interaction and cooperation between Government and industries in developed and developing countries. |  | 120000 | 120000 | 0 |  |  | 0 |  |  | 1995-07-01 | 1995-12-01 | 1996-01-01 | 6 |  | 0 | 1996-02-01 | 1996-02-01 |  | AFR | 11 | Region: AFR | SEV
AFR/SEV/19/TAS/17 | FIN | UNEP | African Network (1996) | Individual | A,I |  |  | 299400 | 299400 | 0 | 0 | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 | 12 |  | 0 | 1996-12-01 | 1999-12-01 |  | AFR | 17 | Region: AFR | SEV
AFR/SEV/19/TRA/16 | FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for English-speaking Africa | Individual | A,I |  |  | 85000 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 | 12 |  | 0 | 1997-07-01 | 1999-01-01 |  | AFR | 16 | Region: AFR | SEV
AFR/SEV/21/TAS/19 | FIN | UNEP | African Region Network (1997) | Individual | A,I | Activities towards expediting the implementation of approved activities, and additional countries will be integrated into the networks. Two networks one for English-speaking countries and one for all French-speaking countries are operating. The English-speaking African Network includes Botswana, Egypt, Ethiopia, Gambia, Ghana, Kenya, Lesotho, Libya, Malawi, Mauritius, Mozambique, Namibia, Nigeria, Seychelles, Sudan, Swaziland, Tanzania, Uganda, Zambia and Zimbabwe (developed country members are Denmark and South Africa). The French-speaking African Network. includes Algeria, Benin, Burkina Faso, Cameroon, Central African Republic, Chad, Congo, Comoros, Cote d'Ivoire, Gabon, Guinea, Mali, Mauritania, Morocco, Niger, Senegal, Togo, Tunisia and Zaire. Developed country members are France and Switzerland. |  | 377656 | 377656 | 0 | 0 | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 | 10 |  | 0 | 1997-12-01 | 1999-12-01 |  | AFR | 19 | Region: AFR | SEV
AFR/SEV/23/TAS/21 | FIN | UNEP | African regional networks for French-speaking and English-speaking countries (1998) | Individual | A,I | Development of team building in the region and sharing of experiences between the countries given the diversity of participating countries at different stages of phase out. |  | 409631 | 409631 | 0 | 0 | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-01-01 | 2 |  | 0 | 1998-12-01 | 2000-03-01 |  | AFR | 21 | Region: AFR | SEV
AFR/SEV/26/TAS/22 | FIN | UNEP | Africa Region Network (French-speaking and English-speaking) | Individual | A,I | Members of the English-speaking Network are Botswana, Egypt, Ethiopia, Gambia, Ghana, Kenya, Lesotho, Libya, Malawi, Mauritius, Mozambique, Namibia, Nigeria, Seychelles, Sudan, Swaziland, Tanzania, Uganda, Zambia and Zimbabwe, Denmark and South Africa. Members of the French-speaking African Network are Algeria, Benin, Burkina Faso, Burundi, Cameroon, Central African Republic, Chad, Congo, Comoros, Cote d'Ivoire, Gabon, Guinea, Mali, Mauritania, Morocco, Niger, Senegal, Togo, Tunisia and Zaire, France and Switzerland. |  | 416602 | 416602 | 0 | 0 | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 | 13 |  | 0 | 1999-12-01 | 2000-12-01 |  | AFR | 22 | Region: AFR | SEV
AFR/SEV/29/TAS/25 | FIN | UNEP | African regional network (French-and English-speaking countries) (2000) | Individual | A,I | There are 2 African Networks (English-speaking and French-speaking countries). There are 21 country members of the English-speaking network (Botswana, Egypt, Ethiopia, The Gambia, Ghana, Kenya, Lesotho, Liberia, Libya, Malawi, Mauritius, Mozambique, Namibia, Nigeria, Seychelles, Sudan, Swaziland, Tanzania, Uganda, Zambia, Zimbabwe) and 2 developed country members (Germany, South Africa). There are 22 developing country members of the French-speaking network (Algeria, Benin, Burkina Faso, Burundi, Cameroon, Central African Republic, Chad, Congo, Comoros, Congo Dem. Rep., Cote d'Ivoire, Gabon, Guinea, Madagascar, Mali, Mauritania, Morocco, Niger, Senegal, Togo, Tunisia, Zaire) and 2 developed country members (France, Switzerland). |  | 422296 | 422296 | 0 | 0 | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 | 13 |  | 0 | 2000-12-01 | 2005-01-01 |  | AFR | 25 | Region: AFR | SEV
AFR/SEV/32/TAS/27 | FIN | UNEP | African regional network (French-speaking, English-speaking) (2001) | Individual | A,I | Assist ozone officers to design and implement policies so that their countries meet Montreal Protocol control measures; encourage countries to adopt regional approaches and to co-operate to assist each other in achieving compliance; develop greater ownership of the phase out and compliance process by the NOUs to promote country-driven strategic planning; and assist ozone officers to review, verify, correct and report data to Fund Secretariat and under Article 7. English speaking countries: Botswana, Egypt, Ethiopia, The Gambia, Ghana, Kenya, Lesotho, Liberia, Libya, Malawi, Mauritius, Mozambique, Namibia, Nigeria, Seychelles, South Africa, Sudan, Swaziland, Tanzania, Uganda, Zambia, Zimbabwe. French speaking countries: Algeria, Benin, Burkina Faso, Burundi, Cameroon, Central African Republic, Chad, Congo, Comoros, DR Congo, Côte d'Ivoire, Gabon, Guinea, Madagascar, Mali, Mauritania, Morocco, Niger, Senegal, Togo, Tunisia, Zaire |  | 427137 | 427137 | 0 | 0 | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 | 12 |  | 0 | 2001-12-01 | 2003-06-01 |  | AFR | 27 | Region: AFR | SEV
AFR/SEV/32/TAS/28 | FIN | UNEP | Harmonization of legislative and regulatory mechanisms to improve monitoring and control of ODS consumption in French-speaking African countries | Individual | A,I | Assist French-speaking African countries in developing, adopting and implementing harmonized sub-regional legislative and regulatory mechanisms for ODS imports, as well as customs training curricula; fostering regional cooperation amongst national regulatory and customs authorities; encouraging the adoption of local solutions; and enhancing enforcement and compliance with the control measures contained in the Montreal Protocol. It will be implemented in cooperation with the sub-regional economic and trade organizations of Western and Central Africa, l’Union Économique et Monétaire de l’Ouest Afrique, and the Communauté Économique et Monétaire de l’Afrique Centrale |  | 129415 | 129415 | 0 | 0 | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-06-01 | 18 |  | 0 | 2004-11-01 | 2007-12-01 |  | AFR | 28 | Region: AFR | SEV
AFR/SEV/36/TAS/30 | FIN | UNDP | Regional surveys in halon and methyl bromide sector | Individual | A,I |  |  | 29854 | 29854 | 0 | 0 | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 | 13 |  | 0 | 2002-11-01 | 2005-10-01 |  | AFR | 30 | Region: AFR | SEV
AFR/SEV/45/TAS/33 | FIN | UNEP | Sub-regional project on harmonization of legislative and regulatory mechanisms to improve monitoring and control of ODS consumption in English-speaking Africa | Individual | A,I | Assist English speaking African countries, in cooperation with the sub-regional economic and trade organizations of Eastern, Western and Southern Africa, (Eastern Africa Community (EAC), Economic Community of West African States (ECOWAS) and the Southern Africa Development Co-operation (SADC)), to develop, adopt and implement harmonized sub-regional legislative and regulatory mechanisms for ODS imports and customs training programmes. It aims to foster regional cooperation amongst national regulatory and customs authorities, encourage the adoption of local solutions and, enhance compliance with the control measures contained in the Montreal Protocol by building upon existing inter-regional trade ties within the EAC, ECOWAS and SADC. | UNEP was requested to complete the project within 18 months and to provide a completion report by the end of 2006. | 140000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2006-12-01 | 20 |  | 0 | 2011-06-01 | 2011-12-01 |  | AFR | 33 | Region: AFR | SEV
AFR/SEV/53/TAS/38 | FIN | UNEP | African customs enforcement networks for preventing illegal trade of ODS in the African sub-regional trade organizations (CEMAC, COMESA, SACU and UEMOA) | Individual | A,I | To prevent illegal trade in ODS by strengthening cooperation between enforcement officers and the African sub-regional trade organizations (CEMAC, COMESA, SACU and UEMOA) within the framework of the ODSONET/Africa; and to encourage cooperation among customs officers, other enforcement officers, and the ozone focal points in the region (jointly implemented with the Government of France). | Approved on the understanding that: it was without prejudice to future funding approvals for the remaining year proposed for this project; that disbursement would take place only when UNEP had provided the Secretariat with letters from the 38 countries signifying the interest and commitment of their governments and customs representatives to this network; and UNEP and the Government of France would prepare a joint report on the outputs of the network’s first year of operation, with an emphasis on making its operations sustainable into the future. | 157316 | 157316 | 0 | 0 | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 | 24 |  | 0 | 2009-07-01 | 2013-12-01 |  | AFR | 38 | Region: AFR | SEV
AFR/SEV/53/TAS/39 | CLO | France | African customs enforcement networks for preventing illegal trade of ODS in the African sub-regional trade organizations (CEMAC, COMESA, SACU and UEMOA) | Individual | A,I | To prevent illegal trade in ODS by strengthening cooperation between enforcement officers and the African sub-regional trade organizations (CEMAC, COMESA, SACU and UEMOA) within the framework of the ODSONET/Africa; and to encourage cooperation among customs officers, other enforcement officers, and the ozone focal points in the region (jointly implemented with UNEP). | Approved on the understanding that: it was without prejudice to future funding approvals for the remaining year proposed for this project; that disbursement would take place only when UNEP had provided the Secretariat with letters from the 38 countries signifying the interest and commitment of their governments and customs representatives to this network; and UNEP and the Government of France would prepare a joint report on the outputs of the network’s first year of operation, with an emphasis on making its operations sustainable into the future. | 0 | 0 | 0 |  | 0 | 0 |  |  | 2007-11-01 |  | 2009-11-01 | 24 |  | 0 |  | 2014-12-01 |  | AFR | 39 | Region: AFR | SEV
ALB/KIP/87/PRP/43 | ONG | UNIDO | Preparation of Kigali HFC implementation plan | Individual | A,I | Stakeholder consultations (e.g., interviews and meetings); development of HFC phase down strategy, including assessment of needs to develop/update trainings and certification scheme on use of flammable refrigerants, and for enhancing training programs on recovery, recycling and destruction; preparation of a comprehensive communication and outreach plan focusing on technology and policy awareness raising; capacity building activities related to RAC sector activities and enforcement; and validation of the overarching strategy. |  | 85000 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 2021-07-01 |  | 2023-08-01 | 25 | 2023-08-31 | 26 |  |  |  | ALB | 43 | Albania | KIP
ALB/KIP/87/PRP/44 | ONG | UNEP | Preparation of Kigali HFC implementation plan | Individual | A,I | Stakeholder consultations (e.g., interviews and meetings); development of HFC phase down strategy, including assessment of needs to develop/update trainings and certification scheme on use of flammable refrigerants, and for enhancing training programs on recovery, recycling and destruction; preparation of a comprehensive communication and outreach plan focusing on technology and policy awareness raising; capacity building activities related to RAC sector activities and enforcement; and validation of the overarching strategy. |  | 45000 | 0 | 0 | 10000 | 11250 | 0 |  |  | 2021-07-01 |  | 2023-08-01 | 25 | 2023-08-01 | 25 |  |  |  | ALB | 44 | Albania | KIP
ALB/PHA/36/PRP/03 | FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | A,I |  | Approved with the understanding that: (a) the national ODS phase-out plan will be submitted together with the Albania country programme, and will address all ODSs used in the country, including the refrigeration servicing sector; (b) implementation of the projects and activities identified in the national ODS phase-out plan will be co-ordinated with UNEP; (c) no additional funding will be requested from the Multilateral Fund for the preparation of project proposals. | 39542 | 39542 | 0 | 0 |  | 0 | 0 | 0 | 2002-03-01 | 2002-06-01 | 2003-07-01 | 16 |  | 0 | 2003-12-01 | 2004-12-01 |  | ALB | 3 | Albania | PHA
ALB/PHA/39/INV/10 | FIN | UNIDO | National ozone depleting substances phase-out plan: conversion of cleaning installations from carbon tetrachloride (CTC) to tetrachloroethylene (PER) at Energy Combinat Ltd., Elbasan | Multi-Year | A,I | It includes installation of a distillation unit, activated carbon absorbers, catch trays and a suction hood. Counterpart contribution is provided since the enterprise uses hand cleaning in the baseline, with no production or safety equipment installed. |  | 44808 | 44808 | 2.3 | 0 |  | 0 | 2.3 | 0 | 2003-04-01 | 2005-09-01 | 2005-04-01 | 24 |  | 0 | 2005-12-01 | 2007-09-01 |  | ALB | 10 | Albania | PHA
ALB/PHA/39/TAS/05 | FIN | UNIDO | National ODS phase-out plan: refrigerant recovery and recycling network | Multi-Year | A,I | To establish a network of recovery and recycling machines and ancillary equipment for servicing commercial and industrial refrigeration equipment and provide basic tooling to workshops for servicing domestic refrigerators. | The sub-project should not commence until the legislation controlling CFC imports is in place and measures have been taken to ensure that the local market prices of CFCs and non-ODS refrigerants are similar. Also, the subproject is approved without prejudice to the operation of the Montreal Protocol’s mechanisms dealing with non-compliance issues. | 100000 | 100000 | 6.8 | 0 |  | 0 | 6.8 | 0 | 2003-04-01 | 2004-12-01 | 2006-04-01 | 36 |  | 0 | 2007-12-01 | 2008-09-01 |  | ALB | 5 | Albania | PHA
ALB/PHA/39/TAS/08 | FIN | UNIDO | National ODS phase-out plan: awareness workshop to prevent the introduction of methyl bromide | Multi-Year | A,I | To raise awareness among farmers and other stakeholders to prevent the re-introduction of methyl bromide since it has been reported smuggling of methyl bromide due to recent economic growth experienced in the country. | Approved without prejudice to the operation of the Montreal Protocol’s mechanisms dealing with non-compliance issues. | 19681 | 19681 | 0 | 0 |  | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2004-04-01 | 12 |  | 0 | 2004-07-01 | 2005-09-01 |  | ALB | 8 | Albania | PHA
ALB/PHA/39/TAS/09 | FIN | UNIDO | National ODS phase-out plan: programme management and auditing | Multi-Year | A,I | Assist in the implementation and monitoring of the ODS phase out projects and activities proposed in the national plan. | Approved without prejudice to the operation of the Montreal Protocol’s mechanisms dealing with non-compliance issues. | 16068 | 16068 | 0 | 0 |  | 0 | 0 | 0 | 2003-04-01 | 2005-04-01 | 2009-12-01 | 80 |  | 0 | 2007-12-01 | 2008-07-01 |  | ALB | 9 | Albania | PHA
ALB/PHA/39/TRA/06 | FIN | UNEP | National ODS phase-out plan: training of customs officers in monitoring of ODS | Multi-year | A,I | To improve the control of imports/exports of ODS and ODS-based equipment; to establish a database of ODS importers and users; and to improve the reliability of reporting data under the Montreal Protocol. | Approved without prejudice to the operation of the Montreal Protocol’s mechanisms dealing with non-compliance issues. | 35422 | 35422 | 0 | 0 | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 | 12 |  | 0 | 2005-08-01 | 2007-04-01 |  | ALB | 6 | Albania | PHA
ALB/PHA/39/TRA/07 | FIN | UNEP | National ODS phase-out plan: training of trainers in good practices of refrigeration | Multi-year | A,I | To increase awareness of 300 service technicians on issues related to the ozone depletion and to enhance their technical skills to avoid emission of refrigerant into the atmosphere during the maintenance and repair of equipment. | Approved without prejudice to the operation of the Montreal Protocol’s mechanisms dealing with non-compliance issues. | 72262 | 72262 | 0 | 0 | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 | 12 |  | 0 | 2006-07-01 | 2010-12-01 |  | ALB | 7 | Albania | PHA
ALB/PHA/46/INV/11 | FIN | UNIDO | National ODS phase out plan (2nd tranche) | Multi-Year | A,I | Training of approximately 300 technicians, strengthening of vocational schools, a workshop on the use of alternative drop-in refrigerants; the completion of the CTC phase-out sub-project; phase I of a recovery and recycling project to establish 3 recovery and recycling centres and the strengthening of the ODS monitoring and reporting system; approval of the legal act on ozone layer protection, establish a licensing system and an import/export quota system and the approval of the Council of Ministers on ozone layer protection. | Approved on the understanding that the licensing and quota system would be implemented with the utmost urgency, and without prejudice to the operation of the Montreal Protocol’s mechanism for addressing non-compliance. | 172322 | 172322 | 25 | 0 |  | 0 | 25 | 0 | 2005-07-01 | 2006-08-01 | 2006-07-01 | 12 |  | 0 | 2008-04-01 | 2010-12-01 |  | ALB | 11 | Albania | PHA
ALB/PHA/50/INV/14 | FIN | UNIDO | National ODS phase out plan (3rd tranche) | Multi-Year | A,I | Strengthening of vocational schools through updating of materials and hardware and training of trainers; implementation of a workshop on the use of alternative drop-in refrigerants and phase I of the recovery and recycling project; strengthening of the ODS monitoring and reporting system; ban production and import of ODS-containing equipment by January 2007; enforce penalties for illegal trade; and strengthen the co-operation between the ozone Unit and customs authorities and between the Ozone Unit and those of neighboring countries. |  | 72322 | 72322 | 21 | 0 |  | 0 | 21 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 | 12 |  | 0 | 2009-12-01 | 2010-12-01 |  | ALB | 14 | Albania | PHA
ALB/PHA/54/INV/15 | FIN | UNIDO | National ODS phase out plan (fourth and fifth tranches) | Multi-Year | A,I | Update existing training materials, undertake a training workshop; development of end-user programme, including training workshops and preparation of demonstration projects; identify additional refrigeration tools for service workshops and drop-in refrigerant; recovery and recycling of CFCs, reduction of venting and reduction in CFC consumption; strengthening of ODS monitoring and reporting system through data collection, upgrade of database and data verification audit; enforcement of import ban of ODS-containing equipment, enforcement of legislation by penalties of ODS illegal trade, continue the cooperation with NOUs in neighboring countries and public awareness activities. |  | 64627.39 | 64627 | 13 | 0 |  | 0 | 13 | 0 | 2008-04-01 | 2008-12-01 | 2009-03-01 | 11 |  | 0 | 2011-01-01 | 2012-05-01 |  | ALB | 15 | Albania | PHA
ALB/PHA/55/PRP/17 | FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | A,I | Preparation of the HPMP including assistance for policy and legislation; survey of HCFC use and analysis of data; and development and finalization of the full HPMP including consultations. |  | 29926.15 | 29926 | 0 | 0 |  | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2009-07-01 | 12 |  | 0 | 2011-06-01 | 2011-12-01 |  | ALB | 17 | Albania | PHA
ALB/PHA/57/PRP/18 | FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | A,I | Additional funding for the preparation of the HPMP |  | 54102.72 | 54103 | 0 | 0 |  | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-03-01 | 11 |  | 0 | 2011-06-01 | 2012-10-01 |  | ALB | 18 | Albania | PHA
ALB/PHA/58/INV/19 | FIN | UNIDO | National ODS phase out plan (sixth tranche) | Multi-Year | A,I | Implementation of training programmes and procurement of demonstration equipment for vocational; implementation of the end-user programme to support retrofitting of 2 to 5 air conditioning and refrigeration systems; continue with project assessment and monitoring. |  | 21883.81 | 21884 | 2.2 | 0 |  | 0 | 2.2 | 0 | 2009-07-01 | 2010-12-01 | 2010-07-01 | 12 |  | 0 | 2012-05-01 | 2012-12-01 |  | ALB | 19 | Albania | PHA
ALB/PHA/58/INV/20 | FIN | UNIDO | National ODS phase out plan (seventh tranche) | Multi-Year | A,I | Implementation of training programmes and procurement of demonstration equipment for vocational; project assessment and monitoring. |  | 21454.56 | 21455 | 0 | 0 |  | 0 | 0 | 0 | 2009-07-01 | 2010-12-01 | 2010-07-01 | 12 |  | 0 | 2012-09-01 | 2013-10-01 |  | ALB | 20 | Albania | PHA
ALB/PHA/64/INV/22 | FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | A,I | Provision of equipment and tools for technicians, strengthening refrigerant recovery, reuse and recycling; and project management, monitoring and coordination. Jointly implemented with UNEP. | Approved in accordance with the Agreement between the Government and the Executive Committee for the period 2011 to 2020 to meet the 35 per cent reduction in HCFC consumption. Noted that the Government had agreed to establish as its starting point for sustained aggregate reduction in HCFC consumption an estimated baseline of 5.9 ODP tonnes, calculated using actual consumption of 5.4 ODP tonnes reported for 2009 and consumption of 6.5 ODP tonnes estimated for 2010. The Secretariat was requested, once the baseline data were known, to update Appendix 2-A to the Agreement to include the figures for maximum allowable consumption, and to notify the Executive Committee of the resulting change in the levels of maximum allowable consumption and of any potential related impact on the eligible funding level, with any adjustments needed being made when the next tranche was submitted. UNIDO, UNEP and the Government were requested to deduct 2.1 ODP tonnes of HCFCs from the starting point for sustained aggregate reduction in HCFC consumption. | 44011 | 44011 | 0 | 0 |  | 0 | 0 | 0 | 2011-07-01 | 2012-03-01 | 2013-07-01 | 24 |  | 0 | 2015-03-01 | 2016-10-01 |  | ALB | 22 | Albania | PHA
ALB/PHA/64/TAS/23 | FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | A,I | Training and certification of technicians in workshops on policies, regulations and code of practice; reviewing and updating course curriculum for technicians; training of customs officers (trainers) and environmental inspectors on legislations, licensing and quota system, labeling of containers. Jointly implemented with UNIDO. | Approved in accordance with the Agreement between the Government and the Executive Committee for the period 2011 to 2020 to meet the 35 per cent reduction in HCFC consumption. Noted that the Government had agreed to establish as its starting point for sustained aggregate reduction in HCFC consumption an estimated baseline of 5.9 ODP tonnes, calculated using actual consumption of 5.4 ODP tonnes reported for 2009 and consumption of 6.5 ODP tonnes estimated for 2010. The Secretariat was requested, once the baseline data were known, to update Appendix 2-A to the Agreement to include the figures for maximum allowable consumption, and to notify the Executive Committee of the resulting change in the levels of maximum allowable consumption and of any potential related impact on the eligible funding level, with any adjustments needed being made when the next tranche was submitted. UNIDO, UNEP and the Government were requested to deduct 2.1 ODP tonnes of HCFCs from the starting point for sustained aggregate reduction in HCFC consumption. | 24954 | 24954 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-01-01 | 2013-07-01 | 24 |  | 0 | 2013-07-01 | 2014-07-01 |  | ALB | 23 | Albania | PHA
ALB/PHA/70/INV/25 | FIN | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | A,I | Training of refrigeration servicing technicians including upgrading the manuals, training/certifying up to 60 technicians, refrigerants recovery and recycling, retrofitting to non-HCFC equipment; distributing 60 sets of recovery and recycling equipment and tools to certified technicians; and monitoring and evaluation, including preparing an annual performance audit, an independent verification if required, and an annual progress report and implementation plan. Jointly implemented with UNEP. | Noted that the Agreement was updated based on the established HCFC baseline for compliance, and that the revised starting point for sustained aggregate reduction in HCFC consumption was 6.0 ODP tonnes, calculated using consumption of 5.4 ODP tonnes and 6.5 ODP tonnes reported for 2009 and 2010, respectively, under Article 7 of the Montreal Protocol. | 92000 | 92000 | 0.4 | 0 |  | 0 | 0.4 | 0 | 2013-07-01 | 2015-05-01 | 2015-07-01 | 24 |  | 0 | 2017-06-01 | 2018-10-01 |  | ALB | 25 | Albania | PHA
ALB/PHA/70/TAS/26 | FIN | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | A,I | Training of 20 customs officers on implementing the HCFC licensing and quota system, and on identification of HCFC refrigerants and blends; conducting 2 workshops for technicians and other stakeholders on HCFC phase-out and promoting legislation and HCFC alternatives; and developing a guide on good practices in refrigeration servicing and a practical manual for customs officers in managing refrigerants. Jointly implemented with UNIDO. | Noted that the Agreement was updated based on the established HCFC baseline for compliance, and that the revised starting point for sustained aggregate reduction in HCFC consumption was 6.0 ODP tonnes, calculated using consumption of 5.4 ODP tonnes and 6.5 ODP tonnes reported for 2009 and 2010, respectively, under Article 7 of the Montreal Protocol. | 20000 | 20000 | 0.2 | 0 | 0 | 0 |  |  | 2013-07-01 | 2014-01-01 | 2015-07-01 | 24 |  | 0 | 2014-12-01 | 2017-12-01 |  | ALB | 26 | Albania | PHA
ALB/PHA/71/TAS/27 | FIN | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | A,I |  | Approved on the understanding that the verification report should be submitted at least 60 days prior to the applicable Executive Committee meeting where the next funding tranche for its HPMP is being sought, in accordance with paragraph 5(b) of the agreement between Albania and the Executive Committee for the reduction of consumption of HCFCs. | 30000 | 30000 | 0 | 0 |  | 0 | 0 | 0 | 2013-12-01 | 2014-05-01 | 2015-05-01 | 17 |  | 0 | 2017-06-01 | 2018-10-01 |  | ALB | 27 | Albania | PHA
ALB/PHA/75/INV/30 | FIN | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | A,I | Continue the consultation process for final adoption of the new legislation and assist in its implementation in 2016; implement the technician certification programme following the new legislation, support training institutions, and enhance refrigerant recovery following the EU model; and monitor and coordinate HPMP activities to ensure efficient implementation. Jointly implemented with UNEP. |  | 39969 | 39969 | 0 | 0 |  | 0 | 0 | 0 | 2015-11-01 | 2018-07-01 | 2018-12-01 | 37 |  | 0 | 2018-12-01 | 2019-06-01 |  | ALB | 30 | Albania | PHA
ALB/PHA/75/TAS/31 | FIN | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | A,I | Train 30 enforcement officers and environmental inspectors in control of HCFCs; and update training materials and train 40 technicians in good servicing practices, refrigerant recovery, recycling and reclamation, and the use of natural refrigerants. Jointly implemented with UNIDO. |  | 22379 | 22378.6 | 0 | 0 | 0 | 0 |  |  | 2015-11-01 | 2016-03-01 | 2018-12-01 | 37 |  | 0 | 2018-05-01 | 2019-12-01 |  | ALB | 31 | Albania | PHA
ALB/PHA/81/INV/34 | FIN | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) | Multi-Year | A,I | Continue the review and consultation process on the legislative framework, and enforce it upon its approval; consult nationally to provide technical support and train servicing technicians to assist with refrigerant recovery, good practices and emission prevention in the servicing sector; and monitor and coordinate activities to ensure efficient implementation. Jointly implemented with UNEP. |  | 30000 | 30000 | 1.1 | 0 | 0 | 0 | 1.1 | 0 | 2018-06-01 | 2018-12-01 | 2021-07-01 | 37 |  | 0 | 2020-06-01 | 2021-03-09 |  | ALB | 34 | Albania | PHA
ALB/PHA/81/PRP/36 | FIN | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | A,I |  |  | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-06-01 | 2019-11-01 | 2020-07-01 | 25 |  | 0 | 2021-01-01 | 2021-07-12 |  | ALB | 36 | Albania | PHA
ALB/PHA/81/TAS/35 | FIN | UNEP | HCFC phase-out management plan (stage I, fourth tranche) | Multi-Year | A,I | Conduct two workshops to train 30 technicians in good servicing practices, refrigerant recovery, recycling and reuse. Jointly implemented with UNIDO. |  | 8500 | 8499.79 | 0.4 | 0 | 0 | 0 |  |  | 2018-06-01 | 2019-04-01 | 2020-07-01 | 25 |  | 0 | 2019-07-01 | 2019-12-01 |  | ALB | 35 | Albania | PHA
ALB/PHA/82/TAS/37 | FIN | UNIDO | Verification report on the implementation of the HCFC phase-out management plan | Individual | A,I |  | Approved on the understanding that the verification report should be submitted at least 60 days prior to the applicable Executive Committee meeting where the next funding tranche for its HPMP is being sought. | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-12-01 | 2019-03-01 | 2020-12-01 | 24 |  | 0 | 2020-12-31 | 2021-03-09 |  | ALB | 37 | Albania | PHA
ALB/PHA/85/INV/39 | COM | UNIDO | HCFC phase-out management plan (stage I, fifth tranche) | Multi-Year | A,I | Follow up approval of the legal acts on leakage control, data reporting on the use of ODS and ODS-based equipment, and training procedures, evaluation and certification of servicing technicians; update the legislation on private sector involvement in certification, and on refrigerant RRR; integrate certification requirements into training materials for servicing technicians; develop a data format for registration of servicing workshops integrating gender aspects; disseminate the data format to workshops on a trial basis; and manage, monitor and report on HPMP progress including recruitment of consultants to assist the NOU in following up on legal and technical aspects of activities. Jointly implemented with UNEP. |  | 23000 | 17540 | 0 | 5460 | 5400 | 0 | 0 | 0 | 2020-06-01 | 2020-09-01 | 2021-12-01 | 18 |  | 0 | 2021-12-31 |  |  | ALB | 39 | Albania | PHA
ALB/PHA/85/INV/41 | ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) | Multi-Year | A,I | Update the ODS regulation on the use of ODS alternatives (i.e. energy efficiency, standards and gender aspects); implement the certification scheme for servicing technicians; conduct a survey on the technical capacity of servicing workshops; train 60 technicians on refrigerant recovery, recycling and reuse operations; organize training sessions on RRR inviting female technicians; select site for a feasibility study to assess non-conventional cooling options for the building sector, stakeholder consultations, develop terms of reference and hire consultant for feasibility study; and manage, coordinate, monitor and report on HPMP including collecting data and preparing progress reports. Jointly implemented with UNEP. | Approved in accordance with the Agreement between the Government and the Executive Committee for the period 2020 to 2025 to reduce HCFC consumption by 67.5 per cent of the country’s baseline; deducted 1.95 ODP tonnes of HCFCs from the remaining HCFC consumption eligible for funding. | 88000 | 239.27 | 0 | 180 | 30000 | 0 | 0 | 0 | 2020-06-01 | 2021-05-01 | 2023-06-01 | 36 | 2023-06-30 | 37 |  |  | Some Progress - Continued Monitoring | ALB | 41 | Albania | PHA
ALB/PHA/85/TAS/40 | FIN | UNEP | HCFC phase-out management plan (stage I, fifth tranche) | Multi-Year | A,I | Update training materials and train 30 servicing technicians in good servicing practice and refrigerant containment, including practices for leakage control, certification requirements, HCFC alternatives, energy efficiency, safety standards and risk management; and support the customs authorities to integrate ODS-related issues into the curriculum of the regular and mandatory training for customs officers. Jointly implemented with UNIDO. |  | 8500 | 8350.02 | 0 | 0 | 0 | 0 |  |  | 2020-06-01 | 2020-09-01 | 2021-12-01 | 18 |  | 0 | 2021-12-01 | 2021-12-01 |  | ALB | 40 | Albania | PHA
ALB/PHA/85/TAS/42 | ONG | UNEP | HCFC phase-out management plan (stage II, first tranche) | Multi-Year | A,I | Update training materials and train 40 customs officers and environmental inspectors in the prevention of illegal trade, mislabelling refrigerant cylinders and monitoring and reporting of ODS data. Update training materials and conduct four workshops for 80 technicians in good servicing practices, leakage detection and control, R&R, and proper handling of flammable and toxic refrigerants. Jointly implemented with UNIDO. | Approved in accordance with the Agreement between the Government and the Executive Committee for the period 2020 to 2025 to reduce HCFC consumption by 67.5 per cent of the country’s baseline; deducted 1.95 ODP tonnes of HCFCs from the remaining HCFC consumption eligible for funding. | 39500 | 9000 | 0 | 30500 | 15250 | 0 |  |  | 2020-06-01 | 2020-09-01 | 2023-06-01 | 36 | 2023-06-01 | 36 |  |  |  | ALB | 42 | Albania | PHA
ALB/PHA/88/TAS/46 | ONG | UNIDO | Verification report on the implementation of stage II of the HCFC phase-out management plan | Individual | A,I |  | Approved on the understanding that the verification report should be submitted at least 10 weeks prior to the applicable Executive Committee meeting where the next funding tranche for the HPMP is being sought. | 30000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 2021-11-01 |  | 2023-12-01 | 25 | 2023-12-31 | 26 |  |  |  | ALB | 46 | Albania | PHA
ALB/SEV/30/CPG/01 | FIN | UNEP | Preparation of country programme | Individual | A,I | The Government of Albania is fully conscious of being in non-compliance with the Montreal Protocol and is committed to urgently undertake all necessary steps to minimize the extent and duration of non-compliance and to completely phase out ODSs by 2009. Institutional development, implementation of a legal framework including the introduction of import restrictions, capacity building to ensure data collection and monitoring of consumption of ODSs, implementation of projects and activities in the refrigeration servicing and solvent sectors, awareness raising, and training are the main components of the Government’s phase out strategy. |  | 31000 | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-04-01 | 2001-06-01 | 15 |  | 0 | 2002-06-01 | 2005-12-01 |  | ALB | 1 | Albania | SEV
ALB/SEV/35/INS/02 | FIN | UNEP | Establishment of the Ozone Unit | Individual | A,I | Co-ordinating all actions identified in the national phase-out plan and monitoring their implementation; co-ordinating all activities of RMP project; developing a monitoring system for ODS imports in order to comply with reporting requirements of the Montreal Protocol and tracking progress of ODS phase-out; establishing a legal and regulatory system (including a licensing system for ODS import and use, imposing custom taxes on ODS, certifying refrigeration technicians, banning imports of equipment using or containing ODS); developing and introducing relevant regulatory acts and a quota system for control of imports of ODS; developing public awareness campaigns and awareness raising activities; providing training to governmental authorities NGOs and representatives from the business sector on general issues of the protection of the ozone layer; reporting annually to both the Multilateral Fund Secretariat and Ozone Secretariat on the ODS consumption. | Approved for one year in order to review the ODS consumption data for the completion of the country programme and RMP project. | 42000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2002-12-01 | 12 |  | 0 | 2002-12-01 | 2004-01-01 |  | ALB | 2 | Albania | SEV
ALB/SEV/38/INS/04 | FIN | UNEP | Establishment of the Ozone Unit (second year) | Individual | A,I | Approved for an additional one year until non-compliance issues are resolved. | Approved for an additional one year on the understanding that the decision was without prejudice to the operation of the Montreal Protocol’s mechanisms dealing with non-compliance issues | 54600 | 54600 | 0 | 0 | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2003-12-01 | 13 |  | 0 | 2005-07-01 | 2007-06-01 |  | ALB | 4 | Albania | SEV
ALB/SEV/46/INS/12 | FIN | UNEP | Renewal of institutional strengthening project (phase I, year 3) | Individual | A,I | By the end of 2006 the phase-out of CFCs and reduction of ODS imports to levels consistent with Montreal Protocol control measures for CFCs will be achieved; 3 recycling centres in the country are planned and end-users will be assisted in the final stage of ODS phase out; measures to counteract illegal trade will be reinforced and ODS trade will be controlled; the second phase of customs training is envisaged, cooperation with the General Customs Authority will be strengthened, and seminars for customs inspectors on legislation regarding ODS and import licensing system are planned; an educational programme on Ozone Layer Protection will be introduced in high schools and universities. | Approved without prejudice to the operation of the Montreal Protocol’s mechanism for addressing non-compliance. The Executive Committee urged Albania to implement its licensing and quota system with the utmost urgency. | 54600 | 54600 | 0 | 0 | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2007-07-01 | 24 |  | 0 | 2006-07-01 | 2008-03-01 |  | ALB | 12 | Albania | SEV
ALB/SEV/49/INS/13 | FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | A,I | Phase-out of CFCs and the reduction of ODS imports and to be in compliance with the quota system; promote the increased use of non-CFC equipment and technology as well as CFC-free refrigerants; an inventory of ODS-using equipment is carried out every year to identify and assist end-users in the final stage of ODS phase-out; implementation of workshops in the refrigeration and air-conditioning sector; and preparation of a booklet for recovery, recycling and retrofitting. |  | 109200 | 109200 | 0 | 0 | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-08-01 | 2008-06-01 | 23 |  | 0 | 2008-06-01 | 2010-12-01 |  | ALB | 13 | Albania | SEV
ALB/SEV/54/INS/16 | FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | A,I | Continue activities regarding recovery and recycle of CFCs, improve ODS legislation to include HCFCs, to further raise public awareness, coordinate the overall efforts to enable compliance to the Montreal Protocol, and data reporting to the Fund and Ozone Secretariats. |  | 109137 | 109137 | 0 | 0 | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-06-01 | 26 |  | 0 | 2011-06-01 | 2012-06-01 |  | ALB | 16 | Albania | SEV
ALB/SEV/61/INS/21 | FIN | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | A,I | Continuing ODS monitoring and management activities to sustain zero CFCs consumption beyond 2010; developing and initiating implementation of the HPMP; improve and update the regulatory system to include HCFC in the regulatory framework and establish a quota system for HCFs; monitor the recovery, recycling and reclamation scheme; work with other related MEAs to continue the public awareness activities; and data reporting. | Approved in accordance with decisions 61/20 and 61/43. | 109200 | 109200 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2012-06-01 | 23 |  | 0 | 2012-12-01 | 2013-12-01 |  | ALB | 21 | Albania | SEV
ALB/SEV/66/INS/24 | FIN | UNEP | Renewal of institutional strengthening project (phase V: 7/2012-6/2014) | Individual | A,I | To ensure compliance with the Protocol by enforcing the HCFC quota system; further develop legislative measures to control HCFC consumption and decrease emissions; introduce a ban of importing and placing on the market of non–refillable containers, and require the mandatory recovery of HCFCs from containers, from equipment and from products; to harmonize the legislation with European Union directives; ensure implementation of the HPMP activities; public awareness activities; and data reporting to the Fund and Ozone Secretariats. |  | 109200 | 109200 | 0 | 0 | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-06-01 | 26 |  | 0 | 2014-06-01 | 2016-12-01 |  | ALB | 24 | Albania | SEV
ALB/SEV/72/INS/28 | FIN | UNEP | Renewal of institutional strengthening project (phase VI: 7/2014-6/2016) | Individual | A,I | Continue development of national capacities for the implementation of the commitments under the MP, strengthening the existing legal framework, strict control of HCFCs and facilitating access and use of new alternatives and technologies to HCFCs; continue partnerships and synergies with public and private stakeholders to achieve HCFC phase-out goals; continue public awareness campaigns; and data reporting to the Fund and Ozone Secretariats. |  | 108000 | 108000 | 0 | 0 | 0 | 0 |  |  | 2014-05-01 | 2014-10-01 | 2016-06-01 | 25 |  | 0 | 2017-02-01 | 2019-12-01 |  | ALB | 28 | Albania | SEV
ALB/SEV/74/TAS/29 | FIN | UNIDO | Survey of ODS alternatives at the national level | Individual | A,I | To obtain information including data (where available) and estimates of ODS alternatives currently in use by sector and subsector, and forecasts of ODS alternatives most commonly used. |  | 40000 | 40000 | 0 | 0 |  | 0 | 0 | 0 | 2015-05-01 | 2016-07-01 | 2016-05-01 | 12 |  | 0 | 2017-06-01 | 2017-12-01 |  | ALB | 29 | Albania | SEV
ALB/SEV/76/INS/32 | FIN | UNEP | Renewal of institutional strengthening project (phase VII: 7/2016-6/2018) | Individual | A,I | Work towards the approval and adoption of the legal acts and implement the new ODS legislation; develop national capacities to allow MP implementation; monitor and control imports and use of HCFCs; facilitate access to and use of ODS alternatives and technologies; train servicing technicians, customs officers and environment inspectors; foster partnerships with public and private sector stakeholders; and implement public awareness campaigns. |  | 138966 | 138965.73 | 0 | 0 | 0 | 0 |  |  | 2016-05-01 | 2016-09-01 | 2018-06-01 | 25 |  | 0 | 2018-06-01 | 2019-12-01 |  | ALB | 32 | Albania | SEV
ALB/SEV/80/INS/33 | FIN | UNEP | Renewal of institutional strengthening project (phase VIII: 7/2018-6/2020) | Individual | A,I | Continue activities to ensure approval and adoption of the legal acts; implement the new ODS legislation, develop capacities to promote Montreal Protocol implementation, monitoring and control of HCFC imports and use, and facilitate access to and use of new alternatives and technologies; continue training of RAC technicians in servicing, customs officers and environment inspectors; foster partnership with stakeholders; continue public awareness campaigns; and prepare for Kigali Amendment ratification and implement enabling activities for HFC phase-down. |  | 139776 | 139776 | 0 | 0 | 0 | 0 |  |  | 2017-11-01 | 2018-06-01 | 2020-06-01 | 31 |  | 0 | 2020-06-01 | 2020-12-01 |  | ALB | 33 | Albania | SEV
ALB/SEV/80/TAS/01+ | FIN | UNIDO | Enabling activities for HFC phase-down | Individual | A,I | Support the early ratification including stakeholder consultation, support the development of national ratification instruments; raise awareness on HFC phase-down and energy efficiency improvement; review codes and standards for the efficient use of HFCs and ODS alternatives in the value chain; prepare harmonized tariff codes according to HFC commitments including blends; review national mechanisms used for ODS reporting to include HFCs consumption; prepare a national strategy including assessment of the RAC servicing sector, inventory of RAC equipment, and policy, institutional and management framework to facilitate phase-down and introduction of low-GWP alternative technologies. | Funded from the additional voluntary contributions of non-Article 5 countries. | 94978 | 94978 | 0 | 0 | 0 |  | 0 |  | 2017-11-01 | 2018-02-01 | 2019-06-01 | 19 |  | 0 | 2019-06-01 | 2019-09-01 |  | ALB | 1 | Albania | SEV
ALB/SEV/84/INS/38 | ONG | UNEP | Renewal of institutional strengthening project (phase IX: 7/2020-6/2022) | Individual | A,I | Continue supporting the adoption and implementation of legal acts related to controlled substances under the Montreal Protocol; develop national capacity to control HCFC imports and use and facilitate access to, and use of, alternative substances and technologies; continue training of technicians in the RAC servicing sector, customs officers and environment inspectors; foster partnership with stakeholders to comply with phase-out and reporting obligations; carry out public awareness campaigns in cooperation with non-governmental organizations; report HFC consumption for the first time in 2020; plan to request preparatory funding for stage II of the HPMP. |  | 139776 | 65016.69 | 0 | 74590 | 37379.655 | 0 |  |  | 2019-12-01 | 2020-09-01 | 2022-06-01 | 30 | 2022-06-01 | 30 |  |  |  | ALB | 38 | Albania | SEV
ALB/SEV/88/INS/45 | ONG | UNEP | Renewal of institutional strengthening project (phase X: 7/2022-6/2024) | Individual | A,I | Continue activities to adopt and implement legislation; build national capacity; monitor and control the import and use of HCFCs and HFCs; facilitate access to alternative substances and technologies; continue to train technicians in the RAC servicing sector, customs officers, and environment inspectors; support compliance with Montreal Protocol obligations in partnership with public- and private-sector stakeholders; and conduct public awareness campaigns. |  | 139776 | 0 | 0 | 0 | 34944 | 0 |  |  | 2021-11-01 |  | 2024-06-01 | 31 | 2024-06-01 | 31 |  |  |  | ALB | 45 | Albania | SEV
ALG/ARS/18/INV/12 | FIN | UNIDO | Investment project for phasing out CFCs at Enterprise Nationale des Detergents (ENAD) | Individual | A,I | Conversion of 2 filling lines, storage tanks, safety equipment and training. LPG is largely abundant in the country. |  | 614850 | 614850 | 150 | 0 |  | 0 | 150 | 0 | 1995-11-01 | 1996-07-01 | 1997-05-01 | 18 |  | 0 | 1997-12-01 | 2002-05-01 |  | ALG | 12 | Algeria | ARS
ALG/ARS/20/INV/15 | FIN | UNIDO | Phasing out CFCs at Etablissement Has Mohamed | Individual | A,I | Provision of an open air gas filling room, a semi-automatic gas filling machine, a manual water bath for testing, explosion-proof lighting and ventilation system, HAP storage and purification system, and a fire control system. The enterprise will finance costs associated with land acquisition, construction of platform, water storage tank and pump house, LPG storage tank, hydrocarbon filling room and conveyor system. |  | 82018 | 82018 | 22.5 | 0 |  | 0 | 22.5 | 0 | 1996-10-01 | 1997-08-01 | 1997-10-01 | 12 |  | 0 | 1998-12-01 | 2000-12-01 |  | ALG | 15 | Algeria | ARS
ALG/ARS/20/INV/16 | FIN | UNIDO | Phasing out CFCs at Vague de Fraicheur | Individual | A,I | Provision of an open air gas filling room, a water bath for testing, a conveyor system, explosion-proof lighting and ventilation system, HAP storage and purification system, a fire control system and training. The enterprise will finance costs associated with land acquisition, construction of platform, water storage tank and pump house. |  | 164623 | 164623 | 51.4 | 0 |  | 0 | 51.4 | 0 | 1996-10-01 | 1997-10-01 | 1997-10-01 | 12 |  | 0 | 1998-12-01 | 2001-12-01 |  | ALG | 16 | Algeria | ARS
ALG/ARS/20/INV/17 | FIN | UNIDO | Phasing out CFCs at Ets Wouroud | Individual | A,I | Provision of a semi-automatic gas filling machine, a manual water bath for testing, a conveyor system, explosion-proof lighting and ventilation system, HAP storage and purification system, a fire control system and training. The enterprise will finance costs associated with land acquisition, construction of platform, water storage tank and pump house. |  | 187352 | 187352 | 47 | 0 |  | 0 | 47 | 0 | 1996-10-01 | 1997-10-01 | 1997-10-01 | 12 |  | 0 | 1998-12-01 | 2000-12-01 |  | ALG | 17 | Algeria | ARS
ALG/ARS/20/INV/18 | CLO | UNIDO | Phasing out CFCs at Laboratoire Bendi | Individual | A,I | Installation of a manual water bath for testing, explosion-proof lighting and ventilation system and HAP storage and purification system. The enterprise will finance costs associated with land acquisition, construction of platform, water storage tank and pump house, LPG storage tank, gas filling line and conveyor system. |  | 53785 | 53785 | 19.2 | 0 |  | 0 | 19.2 | 0 | 1996-10-01 | 1997-10-01 | 1997-10-01 | 12 |  | 0 |  | 2002-05-01 |  | ALG | 18 | Algeria | ARS
ALG/ARS/20/INV/19 | FIN | UNIDO | Phasing out CFCs at Ets Cophyd | Individual | A,I | Installation of a manual water bath for testing, explosion-proof lighting and ventilation system, a gas detection and control system and training. The enterprise will finance costs associated with land acquisition, construction of the pump house, water storage tank, transfer of equipment and machinery. |  | 51733 | 51733 | 15 | 0 |  | 0 | 15 | 0 | 1996-10-01 | 1997-09-01 | 1997-10-01 | 12 |  | 0 | 1997-07-01 | 1999-08-01 |  | ALG | 19 | Algeria | ARS
ALG/ARS/25/INV/28 | FIN | UNIDO | Replacement of CFC-11 and CFC-12 with hydrocarbons in the aerosol sector at Ets Djadir | Individual | A,I | Installation of gas filling machine to be located in open air filling rooms including a propellant handling system, water bath for testing filled cans, HAP storage and purification system, gas detectors and fire control system, conveyor systems, explosion-proof lighting and ventilation systems. |  | 147491 | 147491 | 38.4 | 0 |  | 0 | 38.4 | 0 | 1998-07-01 | 1999-11-01 | 1999-08-01 | 13 |  | 0 | 2000-12-01 | 2002-08-01 |  | ALG | 28 | Algeria | ARS
ALG/ARS/27/PRP/36 | FIN | UNIDO | Project preparation in the aerosol sector | Individual | A,I |  |  | 14402 | 14402 | 0 | 0 |  | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 1999-12-01 | 9 |  | 0 | 2000-11-01 | 2001-09-01 |  | ALG | 36 | Algeria | ARS
ALG/ARS/28/INV/38 | FIN | UNIDO | Phase out of CFC11/CFC12 by conversion to hydrocarbons technology in the manufacture of aerosols at Floreal | Individual | A,I | Installation of a semi-automatic gas filling machine including safety devices, a manually-operated water bath for testing filled cans, a HAP purification and gas detection system, conveyor systems, explosion-proof lighting and ventilation systems, technical assistance for performance and supervision of engineering designs, equipment installation and commissioning of the plant, training in production, quality control and safety procedures. |  | 77067 | 77067 | 18.1 | 0 |  | 0 | 18.1 | 0 | 1999-07-01 | 2000-05-01 | 2000-08-01 | 13 |  | 0 | 2001-07-01 | 2002-09-01 |  | ALG | 38 | Algeria | ARS
ALG/ARS/28/INV/41 | FIN | UNIDO | Phase out of CFC-11/CFC-12 by conversion to hydrocarbon technology in the manufacture of aerosols at company Saco | Individual | A,I | Installation of a semi-automatic gas filling machine including safety devices, a manually-operated water bath for testing filled cans, a HAP purification and gas detection system, conveyor systems, explosion-proof lighting and ventilation systems, technical assistance for performance and supervision of engineering designs, equipment installation and commissioning of the plant, training in production, quality control and safety procedures. |  | 73617 | 73617 | 19 | 0 |  | 0 | 19 | 0 | 1999-07-01 | 2000-05-01 | 2000-08-01 | 13 |  | 0 | 2002-02-01 | 2003-05-01 |  | ALG | 41 | Algeria | ARS
ALG/ARS/36/PRP/52 | CLO | UNIDO | Preparation of 8 investment projects in the aerosol sector | Individual | A,I |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 | 13 |  | 0 |  | 2003-05-01 |  | ALG | 52 | Algeria | ARS
ALG/DES/59/PRP/74 | FIN | UNIDO | Preparation for a pilot demonstration project on ODS waste management and disposal | Individual | A,I | It will consider an approach for the destruction of 150 ODP tonnes of unwanted ODS in the country, i.e., a combination of CFC-11 and CFC-12 collected from the recovery and recycling programmes implemented in the country. It will provide the country with experiences on best technologies, policies and strategies for transportation, and destruction of ODS. It will cover transportation, storage and destruction (or export for destruction) of the amount of ODS identified (the Government of Italy has expressed an interest in working on this project, at both the preparation and implementation stage as part of their bilateral programme). |  | 79461.61 | 79462 | 0 | 0 |  | 0 | 0 | 0 | 2009-11-01 | 2009-12-01 | 2011-05-01 | 18 |  | 0 | 2014-12-01 | 2016-03-01 |  | ALG | 74 | Algeria | DES
ALG/DES/72/DEM/78 | CLO | France | Pilot demonstration project on ODS waste management and disposal | Individual | A,I | It includes modification of the cement kiln (project preparation, modification of the facility, personnel training and project monitoring); pilot testing and preparation of operation manuals and standards operational procedures; quality testing and aggregation (testing of stocks, ISO containers, tools, documentation and labelling); transportation of ODS waste; purification and testing of ISO containers at destruction facility and destruction; and policy support and project management. Jointly implemented with UNIDO. | Approved on the understanding that no further funds would be available for Algeria for any ODS disposal projects in future. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 24 |  | 0 |  | 2018-06-01 |  | ALG | 78 | Algeria | DES
ALG/DES/72/DEM/79 | CLO | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | A,I | It includes destruction of 61.09 metric tonnes of ODS waste through modification of the cement kiln (project preparation, modification of the facility, personnel training and project monitoring); pilot testing and preparation of operation manuals and standards operational procedures; quality testing and aggregation (testing of stocks, ISO containers, tools, documentation and labelling); transportation of ODS waste; purification and testing of ISO containers at destruction facility and destruction; and policy support and project management. Jointly implemented with France. | Approved on the understanding that no further funds would be available for Algeria for any ODS disposal projects in future. | 13556.68 | 13557 | 0 | 0 |  | 0 | 0 | 0 | 2014-05-01 | 2015-04-01 | 2016-12-01 | 31 |  | 0 |  | 2017-09-01 |  | ALG | 79 | Algeria | DES
ALG/FOA/15/PRP/06 | FIN | UNIDO | Preparation of an investment project proposal for the phase-out of CFC-11 in the manufacture of sandwich panels at Prosider (Annaba) | Individual | A,I |  |  | 23416 | 23416 | 0 | 0 |  | 0 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1995-06-01 | 6 |  | 0 | 1995-11-01 | 1999-08-01 |  | ALG | 6 | Algeria | FOA
ALG/FOA/15/PRP/08 | FIN | UNIDO | Preparation of an investment project for CFC phase-out in the production of rigid foam at Batimetal | Individual | A,I |  |  | 20755 | 20755 | 0 | 0 |  | 0 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1995-06-01 | 6 |  | 0 | 1995-11-01 | 1999-08-01 |  | ALG | 8 | Algeria | FOA
ALG/FOA/19/INV/13 | CLO | UNIDO | Phasing out CFC-11 in the manufacture of sandwich panels by discontinuous method at Prosider Berrahal | Individual | A,I | Installation of pentane storage tank, nitrogen production unit, pre-mixing unit, gas detection and fire protection systems and enhanced ventilation, retrofitting of 2 high-pressure foaming machines, production trials, testing and training. |  | 433936 | 433936 | 82 | 0 |  | 0 | 82 | 0 | 1996-05-01 | 1997-07-01 | 1997-11-01 | 18 |  | 0 |  | 2003-03-01 |  | ALG | 13 | Algeria | FOA
ALG/FOA/19/INV/14 | FIN | UNIDO | Phasing out CFC-11 in the manufacture of sandwich panels at Batimetal Béni Mansour | Individual | A,I | Installation of pentane storage tank and metering unit, nitrogen production unit, gas detection and fire protection systems and enhanced ventilation, retrofitting of 1 high-pressure foaming machine and a foaming portal, retrofitting of flow measuring unit and pre-heating unit, production trials, testing and training. |  | 496650 | 496650 | 110 | 0 |  | 0 | 110 | 0 | 1996-05-01 | 1997-07-01 | 1997-11-01 | 18 |  | 0 | 1998-12-01 | 2003-03-01 |  | ALG | 14 | Algeria | FOA
ALG/FOA/22/INV/21 | CLO | UNIDO | Phasing out CFC-11 at Ets Leulmi Essaid flexible polyurethane foam plant | Individual | A,I | Replacement of the metering system, ventilation in foam and cure areas and safety devices, commissioning and start up, technology transfer and training. | Project cancelled (29th ExCom Meeting) as per UNIDO’s request on the condition that any remaining funds should be returned and with the understanding that the company may not resubmit a request to the Multilateral Fund for any further support | 6508 | 6508 | 0 | 0 |  | 0 | 0 | 0 | 1997-05-01 | 1997-06-01 | 1998-06-01 | 13 |  | 0 |  | 2002-09-01 |  | ALG | 21 | Algeria | FOA
ALG/FOA/22/INV/22 | FIN | UNIDO | Phasing out CFC-11 at Société Nord Africaine des Mousees (Snam) flexible polyurethane foam plant | Individual | A,I | Replacement of the metering system, ventilation in foam and cure areas and safety devices, commissioning and start up, technology transfer and training. |  | 87952 | 87952 | 32 | 0 |  | 0 | 32 | 0 | 1997-05-01 | 1997-11-01 | 1998-06-01 | 13 |  | 0 | 1998-12-01 | 2002-08-01 |  | ALG | 22 | Algeria | FOA
ALG/FOA/22/INV/23 | FIN | UNIDO | Phasing out CFC-11 at Sammo flexible polyurethane foam plant | Individual | A,I | Replacement of the metering pump with a pump suitable for metering methylene chloride, encapsulation of appropriate sections of the foaming line, upgrading of the ventilation systems, safety devices (airflow meter and methylene chloride monitor), commissioning and start up, technology transfer and training. |  | 97359 | 97359 | 24 | 0 |  | 0 | 24 | 0 | 1997-05-01 | 1997-10-01 | 1998-06-01 | 13 |  | 0 | 1998-12-01 | 2002-08-01 |  | ALG | 23 | Algeria | FOA
ALG/FOA/23/INV/25 | FIN | UNIDO | Phasing out CFC-11 at La Mousse du Sud flexible polyurethane foam plant | Individual | A,I | Modification of existing production facilities and installation of supplementary equipment and instruments, including a LCD system, trials, technology transfer and training. |  | 552050 | 552050 | 95 | 0 |  | 0 | 95 | 0 | 1997-11-01 | 1998-06-01 | 1998-12-01 | 13 |  | 0 | 2002-10-01 | 2003-07-01 |  | ALG | 25 | Algeria | FOA
ALG/FOA/25/INV/27 | FIN | UNIDO | Phase out of CFC-11 in the manufacture of flexible polyurethane foam through the use of methylene chloride technology at Ets Matelas Djurdjura | Individual | A,I | Installation of a new metering system, reinforced ventilation system, safety devices, technology transfer and training, commissioning and start-up. The company will provide all costs cited in the project’s budget but not requested from the Fund. |  | 81855 | 81855 | 28 | 0 |  | 0 | 28 | 0 | 1998-07-01 | 1998-12-01 | 1999-08-01 | 13 |  | 0 | 2001-07-01 | 2002-09-01 |  | ALG | 27 | Algeria | FOA
ALG/FOA/26/INV/29 | FIN | UNIDO | Phase-out of CFC-11 in the manufacture of flexible polyurethane foam through the use of methylene chloride technology at Etablissement Maghreb Mousse | Individual | A,I | Installation of a new methylene chloride metering system, upgrade of ventilation system, safety devices), technology transfer, training and plant commissioning. | UNIDO’s request to transfer the equipment from the Leulmi Foam project on the condition that any remaining funds for this project (as a result of receiving equipment from the Leulmi Foam project) should be returned to the Multilateral Fund | 95992 | 95992 | 24 | 0 |  | 0 | 24 | 0 | 1998-11-01 | 1999-02-01 | 1999-12-01 | 13 |  | 0 | 2001-07-01 | 2002-09-01 |  | ALG | 29 | Algeria | FOA
ALG/FOA/27/INV/33 | FIN | UNIDO | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Matelas Atlas (Sam Atlas) | Individual | A,I | Installation of a methylene chloride storage and metering system on a discontinuous production line, a storage and metering system for a softening additive, upgrade of enclosure and ventilation of the production line and hall systems, installation of methylene chloride detectors and safety devices for the flexible foam machine, trials and technology transfer. |  | 120060 | 120060 | 22 | 0 |  | 0 | 22 | 0 | 1999-03-01 | 1999-12-01 | 2000-04-01 | 13 |  | 0 | 2002-06-01 | 2004-03-01 |  | ALG | 33 | Algeria | FOA
ALG/FOA/27/INV/34 | FIN | UNIDO | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at King's Matelas | Individual | A,I | Installation of a methylene chloride storage and metering system on a discontinuous production line, a storage and metering system for a softening additive, upgrade of enclosure and ventilation of the production line and hall systems, installation of methylene chloride detectors and safety devices for the flexible foam machine, trials and technology transfer. |  | 110141 | 110141 | 20 | 0 |  | 0 | 20 | 0 | 1999-03-01 | 1999-12-01 | 2000-04-01 | 13 |  | 0 | 2002-06-01 | 2003-07-01 |  | ALG | 34 | Algeria | FOA
ALG/FOA/27/PRP/31 | FIN | UNIDO | Project preparation in the foam sector (flexible) | Individual | A,I |  |  | 17980 | 17980 | 0 | 0 |  | 0 | 0 | 0 | 1999-03-01 | 1999-06-01 | 1999-12-01 | 9 |  | 0 | 2001-10-01 | 2002-12-01 |  | ALG | 31 | Algeria | FOA
ALG/FOA/28/INV/37 | FIN | UNIDO | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane slabstock foam at Matelas Mondial | Individual | A,I | Installation of a methylene chloride storage and metering system on the discontinuous production line, a storage and metering systems for a softening additive, upgrade of enclosure and ventilation systems of the production line and hall, methylene chloride detectors and safety devices for the flexible foam machine, trials and technology transfer. |  | 97920 | 97920 | 20 | 0 |  | 0 | 20 | 0 | 1999-07-01 | 1999-12-01 | 2000-08-01 | 13 |  | 0 | 2002-06-01 | 2003-07-01 |  | ALG | 37 | Algeria | FOA
ALG/FOA/28/INV/39 | FIN | UNIDO | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane slabstock foam at Orania Mousse Ameublement (OMA) | Individual | A,I | Installation of a methylene chloride storage and metering system on a block foam production line, a storage and metering systems for a softening additive, upgrade of enclosure and ventilation systems of the production line and hall, methylene chloride detectors and safety devices for the flexible foam machine, trials and technology transfer. |  | 99373 | 99373 | 18 | 0 |  | 0 | 18 | 0 | 1999-07-01 | 1999-12-01 | 2000-08-01 | 13 |  | 0 | 2002-06-01 | 2003-07-01 |  | ALG | 39 | Algeria | FOA
ALG/FOA/30/PRP/40 | FIN | UNIDO | Project preparation in the flexible foam sector | Individual | A,I |  |  | 19999 | 19999 | 0 | 0 |  | 0 | 0 | 0 | 2000-03-01 | 2000-10-01 | 2001-04-01 | 13 |  | 0 | 2001-11-01 | 2002-12-01 |  | ALG | 40 | Algeria | FOA
ALG/FOA/31/INV/44 | FIN | Germany | Conversion of Algeria Mousse Polyurethane (AMP) | Individual | A,I | Retrofitting of the existing Maxfoam machine and installation of LCD equipment, trials, technology transfer and training. |  | 565728 | 565728 | 152 | 0 | 0 | 0 | 152 |  | 2000-07-01 | 2000-08-01 | 2003-08-01 | 37 |  | 0 | 2004-12-01 | 2007-12-01 |  | ALG | 44 | Algeria | FOA
ALG/FOA/32/INV/45 | FIN | Germany | Conversion of SOFTPM, Choupot Oran, to LCD technology | Individual | A,I | Retrofit of the existing continuous machines, installation of an LCD system and ancillary equipment, technology transfer, training, trials and a license. Incremental operational savings are calculated for a period of 4 years |  | 498400 | 498400 | 80 | 0 | 0 | 0 | 80 |  | 2000-12-01 | 2001-01-01 | 2002-01-01 | 13 |  | 0 | 2004-12-01 | 2007-12-01 |  | ALG | 45 | Algeria | FOA
ALG/FOA/32/INV/46 | FIN | Germany | Conversion of Matelas Souf to LCD technology | Individual | A,I | Retrofit of the existing continuous machines, installation of an LCD system and ancillary equipment, technology transfer, training, trials and a license. Incremental operational savings are calculated for a period of 4 years |  | 561379 | 561379 | 95 | 0 | 0 | 0 | 95 |  | 2000-12-01 | 2001-01-01 | 2002-01-01 | 13 |  | 0 | 2004-12-01 | 2007-12-01 |  | ALG | 46 | Algeria | FOA
ALG/FOA/33/PRP/49 | FIN | Germany | Project preparation for the phase out of ODS use in the flexible foam sub-sector | Individual | A,I | Gather relevant technical information on the production processes for the already identified 11 SMEs and to identify eventually remaining smaller flexible foam producing enterprises in the country which are still using CFCs. Technical information on quantities of CFCs used, annual production, type of machinery and equipment used will be collected for all enterprises in the flexible foam sub-sector. | Approved on the understanding that the Government of Algeria should update the foam sector ODS consumption data in the country programme and submit, with the project proposal, the revised figures and detailed explanation of the reason for the variation. | 30900 | 30900 | 0 | 0 | 0 | 0 |  |  | 2001-03-01 | 2001-04-01 | 2002-04-01 | 13 |  | 0 | 2002-04-01 | 2007-12-01 |  | ALG | 49 | Algeria | FOA
ALG/FOA/59/PRP/73 | FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | A,I | Additional assistance for preparation of HCFC phase-out activities in the foam sector. |  | 38275.82 | 38276 | 0 | 0 |  | 0 | 0 | 0 | 2009-11-01 | 2010-04-01 | 2010-11-01 | 12 |  | 0 | 2010-12-01 | 2011-12-01 |  | ALG | 73 | Algeria | FOA
ALG/FOA/62/INV/75 | FIN | UNIDO | Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for domestic refrigerators at Cristor | Multi-Year | A,I | Completion of the installation of the cyclopentane storage tank, retrofit of the pre mixing station, retrofit of the three foam lines, ventilation and safety systems for the use of hydrocarbons, civil and electrical works, trials, testing, technical assistance and training. | Noted that the Government had agreed to establish as its starting point for sustained aggregate reduction in HCFC consumption the estimated baseline of 31.0 ODP tonnes, calculated using actual consumption reported in 2009 and estimated consumption for 2010. UNIDO and the Government were requested to deduct 2.4 ODP tonnes of HCFCs from the starting point for sustained aggregate reduction in HCFCs. UNIDO was also requested to provide to the Secretariat, at the end of each year of the project's implementation period, progress reports that addressed the issues pertaining to the collection of accurate data in line with the objectives of decision 55/43(b), and to include those reports in the implementation reports of the HPMP, once it had been approved. | 214944 | 214944 | 2.4 | 0 |  | 0 | 2.4 | 0 | 2010-12-01 | 2010-12-01 | 2012-12-01 | 24 |  | 0 | 2017-12-01 | 2018-09-01 |  | ALG | 75 | Algeria | FOA
ALG/FUM/22/PRP/24 | FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | A,I |  |  | 4207 | 4207 | 0 | 0 |  | 0 | 0 | 0 | 1997-05-01 | 1997-07-01 | 1998-06-01 | 13 |  | 0 | 2000-01-01 | 2000-07-01 |  | ALG | 24 | Algeria | FUM
ALG/FUM/34/PRP/50 | FIN | UNIDO | Project preparation to replace methyl bromide in fumigation of dates in ten units | Individual | A,I |  |  | 13277.46 | 13277 | 0 | 0 |  | 0 | 0 | 0 | 2001-07-01 | 2001-09-01 | 2002-08-01 | 13 |  | 0 | 2011-12-01 | 2011-12-01 |  | ALG | 50 | Algeria | FUM
ALG/FUM/50/TAS/65 | FIN | UNIDO | Technical assistance to phase out methyl bromide in pulses disinfestations | Individual | A,I | Local pulses are infested in the field by an insect pest (bruchids). The use of contact insecticides is costly and not too efficient since it does not penetrate into the grain and therefore does not kill all the insects. At the storage facilities, new infestations by other pests take place, therefore requiring fumigation with MB. The technology to be used to replace MB is phosphine applied in the same fumigation chambers. | Approved on the understanding that the remaining eligible consumption for MB in the country would be 2.03 ODP tonnes used for the fumigation of high moisture dates. | 49725.97 | 49726 | 1.6 | 0 |  | 0 | 1.6 | 0 | 2006-11-01 | 2007-12-01 | 2007-11-01 | 12 |  | 0 | 2008-12-01 | 2010-05-01 |  | ALG | 65 | Algeria | FUM
ALG/FUM/72/PRP/80 | FIN | UNIDO | Project preparation in the fumigants sector (high-moisture dates) | Individual | A,I |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2014-05-01 |  | 2015-05-01 | 12 |  | 0 | 2016-12-01 | 2017-03-01 |  | ALG | 80 | Algeria | FUM
ALG/HAL/31/PRP/42 | FIN | Germany | Project preparation, technical assistance in the halon sector | Individual | A,I |  |  | 10520 | 10520 | 0 | 0 | 0 | 0 |  |  | 2000-07-01 | 2001-01-01 | 2002-01-01 | 18 |  | 0 | 2001-06-01 | 2002-03-01 |  | ALG | 42 | Algeria | HAL
ALG/HAL/35/TAS/51 | FIN | Germany | Sectoral phase out programme: establishment of a halon bank | Individual | A,I | Establishment of a national halon bank that will ensure that Algeria can meet its obligations under the Protocol. It will concentrate on the natural gas industry. The halon reclamation centre will be located at Sonatrach, the state owned oil and gas company. Recovery services will be offered to other halon users from telecommunications, banks and other installations. It includes costs for the formulation of the halon banking management plan, the provision of recovery and recycling, storage and quality control equipment, and a training programme on the design of alternative fire protection systems. The Government will ban the importation of newly produced halons in line with the establishment of the reclamation centre. The halon bank will be sufficiently operational in 2002 to assist the country in meeting the year 2002 freeze and provide halon for essential uses. | Approved on the understanding that the importation of halon into Algeria will cease starting January 2004. | 259500 | 259500 | 392.3 | 0 | 0 | 0 | 392.3 |  | 2001-12-01 | 2002-10-01 | 2005-01-01 | 37 |  | 0 | 2010-07-01 | 2012-07-01 |  | ALG | 51 | Algeria | HAL
ALG/PHA/37/PRP/57 | CLO | Germany | Project preparation for terminal ODS phase out management plan, excluding the refrigeration sector | Individual | A,I | Prepare a terminal phase out management plan to ensure that Algeria achieves early phase out. It will serve as a strategy document, outlining a combination of policy-based actions, a locally managed action plan and performance based contracts to implement activities identified as well as monitor progress; it will provide overall operational and implementation arrangements, relying principally on performance-based contracts for specific phase out actions, including the annual reduction in CFC imports and consumption that are to be achieved. |  | 42000 | 42000 | 0 | 0 | 0 | 0 |  |  | 2002-07-01 | 2002-10-01 | 2003-08-01 | 13 |  | 0 |  | 2007-09-01 |  | ALG | 57 | Algeria | PHA
ALG/PHA/46/PRP/63 | FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | A,I |  | Approved to address residual consumption in Algeria, in conjunction with the TPMP being prepared by Germany. | 23404 | 23404 | 0 | 0 |  | 0 | 0 | 0 | 2005-07-01 | 2007-04-01 | 2006-03-01 | 8 |  | 0 | 2008-04-01 | 2008-12-01 |  | ALG | 63 | Algeria | PHA
ALG/PHA/51/PRP/66 | FIN | UNIDO | Project preparation for an ODS phase-out management plan | Individual | A,I | The project will be prepared in conjunction with the TPMP being prepared by the Government of Germany. | Approved on the understanding that this amount represents final funding for project preparation for a complete CFC phase-out plan. | 14118 | 14118 | 0 | 0 |  | 0 | 0 | 0 | 2007-03-01 | 2007-06-01 | 2008-03-01 | 12 |  | 0 | 2007-11-01 | 2007-12-01 |  | ALG | 66 | Algeria | PHA
ALG/PHA/53/INV/67 | FIN | UNIDO | National phase-out plan (first tranche) | Multi-Year | A,I | Complete phase out of CFCs, CTC and TCA used in the aerosol, foam, refrigeration servicing and solvent sectors. It includes policy and enforcement; training of refrigeration technicians and technical assistances activities including recovery and recycling; specific technical assistance for phasing out ODSs used in the in the aerosol, foam and solvent sectors; implementation of an MDI transition strategy; support for the project implementation and monitoring unit; and preparation of verification reports. | Approved in accordance with the Agreement between the Government and the Executive Committee. UNIDO was urged to take full account of the requirements of decisions 41/100 and 49/6 during the implementation of the phase-out plan. | 723500 | 723500 | 130.5 | 0 |  | 0 | 130.5 | 0 | 2007-11-01 | 2008-02-01 | 2009-03-01 | 16 |  | 0 | 2010-04-01 | 2012-07-01 |  | ALG | 67 | Algeria | PHA
ALG/PHA/55/PRP/68 | FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | A,I | Preparation of the HPMP including assistance for policy and legislation; survey of HCFC use and analysis of data; and development and finalization of the full HPMP including consultations. |  | 84744.79 | 84745 | 0 | 0 |  | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2009-07-01 | 12 |  | 0 | 2010-12-01 | 2012-05-01 |  | ALG | 68 | Algeria | PHA
ALG/PHA/58/INV/71 | FIN | UNIDO | National phase-out plan (second tranche) | Multi-Year | A,I | Training of three master trainers and of 100 customs officers, procurement of five identification sets and finalization of the ODS legislation review and update; finalized the code of practice and the refrigeration curricula; purchase 70 refrigeration service kits; start the procurement process for equipment for six foam conversions; implementation of awareness raising workshop for solvent users and the development of an MDI strategy; and project implementation and monitoring activities. | UNIDO was reqeusted to provide, to the 61st Meeting an additional verification report regarding the consumption of all ODS covered in the Agreement focussing in particular on the recording of imports at customs and the process of forwarding that data to the National Ozone Unit. | 194389.73 | 194390 | 154 | 0 |  | 0 | 154 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 | 12 |  | 0 | 2013-12-01 | 2014-07-01 |  | ALG | 71 | Algeria | PHA
ALG/PHA/58/PRP/70 | FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | A,I | Additional funding for the preparation of the HPMP. |  | 64978.26 | 64978 | 0 | 0 |  | 0 | 0 | 0 | 2009-07-01 | 2009-11-01 | 2010-07-01 | 12 |  | 0 | 2012-12-01 | 2012-12-01 |  | ALG | 70 | Algeria | PHA
ALG/PHA/66/INV/76 | ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (conversion from HCFC-22 in the manufacture of room air conditioners at Condor) | Multi-Year | A,I | Conversion to HFC-32 includes bulk storage tanks, converting non-metal elastomeric components; replacing refrigerant piping, nitrogen generator, transfer and vacuum pumps, refrigerant charging machines, sniffers for leak detectors; replacing instruments at testing stations; a new recovery machine, tooling for the tube bending machine; testing and training; additional safety related equipment. Incremental operating costs include the difference in costs for CKD kits. | Approved in accordance with the Agreement between the Government and the Executive Committee for the period 2010 to 2017 to reduce HCFC consumption by 20 per cent of the baseline. Noted that the Government had agreed to establish as its starting point for sustained aggregate reduction in HCFC consumption the baseline of 30.2 ODP tonnes, calculated using consumption of 30.2 ODP tonnes reported for each 2009 and 2010, plus 5.36 ODP tonnes of HCFC-141b contained in imported pre-blended polyol systems, resulting in 35.56 ODP tonnes; and that in the event that the Parties to the Montreal Protocol agreed to change the baseline for compliance as calculated in the HPMP, the starting point for aggregate reduction in HCFC consumption would be 67.46 ODP tonnes (i.e., 62.1 ODP tonnes as the revised baseline for compliance plus 5.36 ODP tonnes of HCFC-141b contained in imported pre-blended polyol systems). Noted that the project to phase out HCFC-141b used in the manufacture of polyurethane rigid insulation foam for domestic refrigerators at Cristor had already been approved at the 62nd meeting in 2010 and had subsequently been included in stage I of the HPMP. Noted the commitment of the Government to ban the import of HCFC-141b in bulk, by 1 January 2016 once the conversion of the enterprise Cristor was completed and an alternative process for cleaning refrigeration circuits was implemented. Noted that approval of stage I of the HPMP did not preclude Algeria from submitting, prior to 2015, a proposal to achieve a reduction in HCFCs beyond that addressed in stage I of the HPMP. Noted the deduction of 2.40 ODP tonnes of HCFCs from the starting point for sustained aggregate reduction in HCFC consumption for the project approved at the 62nd meeting, and UNIDO and the Government were requested to further deduct 12.08 ODP tonnes of HCFCs for implementation of stage I of the HPMP. The Fund Secretariat was requested, in the event that the baseline consumption for compliance is amended based on revised Article 7 data, to update Appendix 2-A to the Agreement to include the figures for maximum allowable consumption, and to notify the Executive Committee of the resulting change in the levels of maximum allowable consumption. In the event that the Parties did not agree to change the baseline for compliance, stage I of the HPMP would reduce HCFC consumption by 35 per cent of the baseline by 2020 and the Agreement would be revised accordingly. | 1379460 | 881270.72 | 8.3 | -0.01 | 1 | 0 | 8.3 | 0 | 2012-04-01 | 2013-01-01 | 2013-04-01 | 12 | 2023-12-31 | 141 |  |  | No Progress - Continued Monitoring | ALG | 76 | Algeria | PHA
ALG/PHA/66/INV/77 | ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (activities in the refrigeration servicing sector including phase-out of HCFC-141b used for flushing, and project monitoring) | Multi-Year | A,I | Training for technicians in good service practices including use of recovery and recycling equipment, and eliminating venting of HCFC-22 during service practices; workshops with stakeholders to discuss alternative technologies, encourage enterprises to introduce non-HCFC technologies, and establish a timetable for the complete conversion; distribution of recovery/recycling kits among technicians; update and distribution the code of good practice; pilot conversions of refrigeration and air conditioning installations to non-ODS technologies. Procurement of four recycling kits with eight cylinders; a stock of alternative non-HCFC-141b solvent for three months operation; and training for refrigeration technicians. Training of customs officers, enforcement of an electronic licensing system, and awareness campaign for key stakeholders; and project monitoring, verification and reporting. | Approved in accordance with the Agreement between the Government and the Executive Committee for the period 2010 to 2017 to reduce HCFC consumption by 20 per cent of the baseline. Noted that the Government had agreed to establish as its starting point for sustained aggregate reduction in HCFC consumption the baseline of 30.2 ODP tonnes, calculated using consumption of 30.2 ODP tonnes reported for each 2009 and 2010, plus 5.36 ODP tonnes of HCFC-141b contained in imported pre-blended polyol systems, resulting in 35.56 ODP tonnes; and that in the event that the Parties to the Montreal Protocol agreed to change the baseline for compliance as calculated in the HPMP, the starting point for aggregate reduction in HCFC consumption would be 67.46 ODP tonnes (i.e., 62.1 ODP tonnes as the revised baseline for compliance plus 5.36 ODP tonnes of HCFC-141b contained in imported pre-blended polyol systems). Noted that the project to phase out HCFC-141b used in the manufacture of polyurethane rigid insulation foam for domestic refrigerators at Cristor had already been approved at the 62nd meeting in 2010 and had subsequently been included in stage I of the HPMP. Noted the commitment of the Government to ban the import of HCFC-141b in bulk, by 1 January 2016 once the conversion of the enterprise Cristor was completed and an alternative process for cleaning refrigeration circuits was implemented. Noted that approval of stage I of the HPMP did not preclude Algeria from submitting, prior to 2015, a proposal to achieve a reduction in HCFCs beyond that addressed in stage I of the HPMP. Noted the deduction of 2.40 ODP tonnes of HCFCs from the starting point for sustained aggregate reduction in HCFC consumption for the project approved at the 62nd meeting, and UNIDO and the Government were requested to further deduct 12.08 ODP tonnes of HCFCs for implementation of stage I of the HPMP. The Fund Secretariat was requested, in the event that the baseline consumption for compliance is amended based on revised Article 7 data, to update Appendix 2-A to the Agreement to include the figures for maximum allowable consumption, and to notify the Executive Committee of the resulting change in the levels of maximum allowable consumption. In the event that the Parties did not agree to change the baseline for compliance, stage I of the HPMP would reduce HCFC consumption by 35 per cent of the baseline by 2020 and the Agreement would be revised accordingly. | 214400 | 133963.48 | 2.8 | 4164.28 | 1 | 0 | 2.8 | 0 | 2012-04-01 | 2012-10-01 | 2013-04-01 | 12 | 2023-12-31 | 141 |  |  | No Progress - Continued Monitoring | ALG | 77 | Algeria | PHA
ALG/PHA/85/PRP/84 | ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) (foam sector) | Individual | A,I |  |  | 50000 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 2020-06-01 |  | 2022-06-01 | 24 | 2023-12-31 | 43 |  |  |  | ALG | 84 | Algeria | PHA
ALG/PHA/85/PRP/85 | ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | A,I |  |  | 60000 | 28778.09 | 0 | 4253.44 | 15000 | 0 | 0 | 0 | 2020-06-01 | 2021-07-01 | 2022-06-01 | 24 | 2023-12-31 | 43 |  |  |  | ALG | 85 | Algeria | PHA
ALG/PHA/85/PRP/86 | ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) (air-conditioning sector) | Individual | A,I |  |  | 50000 | 5696.35 | 0 | 1387.57 | 10000 | 0 | 0 | 0 | 2020-06-01 | 2020-12-01 | 2022-06-01 | 24 | 2023-12-31 | 43 |  |  |  | ALG | 86 | Algeria | PHA
ALG/REF/15/INV/09 | FIN | UNIDO | Investment project for phasing out CFCs at Entreprise Nationale des Industries de l'Electroménager, Eniem (2 refrigerator plants and one chest freezer plant) | Individual | A,I | Replacement of existing low pressure foam machines with high pressure machines, retrofitting of existing high pressure machines, modification of fixtures, acquisition of cyclopentane storage and delivery system, replacement of premixing stations, safety programme (foam component), replacement of the current refrigerant evacuation and charging boards, leak detectors, retrofitting existing vacuum pumps, (refrigerant component), model prototyping, trials and reliability tests. Refrigeration services will be equipped to handle the recovery of both CFC-12 and HFC-134a. |  | 6506631 | 6506631 | 425 | 0 |  | 0 | 425 | 0 | 1994-12-01 | 1995-12-01 | 1996-06-01 | 18 |  | 0 | 1996-12-01 | 2002-09-01 |  | ALG | 9 | Algeria | REF
ALG/REF/15/PRP/07 | FIN | UNIDO | Preparation of a project for the establishment of a National Centre for Recovery and Recycling of CFC-11, CFC-12 and CFC-502 | Individual | A,I |  |  | 16746 | 16746 | 0 | 0 |  | 0 | 0 | 0 | 1994-12-01 | 1998-11-01 | 1995-06-01 | 6 |  | 0 | 1999-12-01 | 2001-11-01 |  | ALG | 7 | Algeria | REF
ALG/REF/25/INV/26 | FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Equipments Collectifs et Application Techniques (Enapat) | Individual | A,I | Installation of a new charging units, leak detectors, some new vacuum pumps (others will be retrofitted), and test instruments are requested for the performance testing. The cooling circuit will be redesigned. Incremental operating costs are requested for commercial refrigeration equipment and for small cold room production. The enterprise will fund the purchase of one HFC-134a refrigerant charging board and one production leak detector. |  | 122995 | 122995 | 9.2 | 0 |  | 0 | 9.2 | 0 | 1998-07-01 | 1999-03-01 | 1999-08-01 | 13 |  | 0 | 1998-12-01 | 2000-12-01 |  | ALG | 26 | Algeria | REF
ALG/REF/26/INV/30 | FIN | UNIDO | Replacement of CFC-12 with HFC-134a for domestic refrigeration at Enterprise Nationale d'Approvisionnement et de Production Electronique et Electroménager (Enapem) | Individual | A,I | Installation of one HFC-134a charging board, 6 portable semi-automatic HFC-134a charging machines, 5 manual leak detectors, testing equipment modification of 9 vacuum pumps, general consultancy and redesign of refrigerator models. Incremental operating costs are requested for a 6-month period. The enterprise is not involved in foam operation. |  | 164442 | 164442 | 12.8 | 0 |  | 0 | 12.8 | 0 | 1998-11-01 | 1999-06-01 | 1999-12-01 | 13 |  | 0 | 1999-12-01 | 2002-05-01 |  | ALG | 30 | Algeria | REF
ALG/REF/27/PRP/35 | FIN | UNIDO | Project preparation in the commercial refrigeration sector (commercial) | Individual | A,I |  |  | 3020 | 3020 | 0 | 0 |  | 0 | 0 | 0 | 1999-03-01 | 2000-10-01 | 1999-12-01 | 9 |  | 0 | 2000-11-01 | 2001-07-01 |  | ALG | 35 | Algeria | REF
ALG/REF/31/PRP/43 | FIN | UNIDO | Strategy for the preparation of an RMP | Individual | A,I |  |  | 58987 | 58987 | 0 | 0 |  | 0 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2002-01-01 | 18 |  | 0 | 2003-01-01 | 2003-06-01 |  | ALG | 43 | Algeria | REF
ALG/REF/32/INV/47 | FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration at the RCA (Societe de Refrigeration et de Conditionnement de l'air) | Individual | A,I | Replacement of existing low-pressure machines by 2 high-pressure foam dispensers (foam component), refrigerant charging units, vacuum pumps and leak detectors (refrigeration component), redesign, testing, trials, and training. Incremental operating costs are requested for a one-year period |  | 345905 | 345905 | 27.3 | 0 |  | 0 | 27.3 | 0 | 2000-12-01 | 2001-07-01 | 2003-05-01 | 29 |  | 0 | 2003-12-01 | 2004-12-01 |  | ALG | 47 | Algeria | REF
ALG/REF/36/PRP/53 | FIN | UNIDO | Preparation of a refrigeration sectoral phase-out plan | Individual | A,I |  |  | 50000 | 50000 | 0 | 0 |  | 0 | 0 | 0 | 2002-03-01 | 2002-08-01 | 2003-07-01 | 16 |  | 0 | 2004-12-01 | 2005-11-01 |  | ALG | 53 | Algeria | REF
ALG/REF/37/INV/56 | FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the first group of commercial refrigerator manufacturers | Individual | A,I | Replacement of production and portable charging equipment, vacuum pumps, leak detectors, redesign, testing, trials and training. The enterprises covered under the project are: Algerienne Frigorifique, Froid Climat, Sarl Bettiche, Sarl Indefrigo, Sarl INC Royal, Sarl Societe Algerienne d'Agencement et de Refrigeration |  | 201619 | 201619 | 18.6 | 0 |  | 0 | 18.6 | 0 | 2002-07-01 | 2002-12-01 | 2005-01-01 | 30 |  | 0 | 2004-12-01 | 2006-12-01 |  | ALG | 56 | Algeria | REF
ALG/REF/37/TAS/55 | FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in the refrigeration and air-conditioning sector: training in good refrigerant management practices, training of customs officers, and national recovery and recycling: first tranche | Multi-Year | A,I | The RMP includes a training programme for customs officers, a training programme on good refrigerant management practices and a national recovery and recycling project which includes 468 recovery bags, 468 refrigeration kits, 268 recovery machines, 212 recovery pumps and ancillary equipment for service workshops, and the establishment of 48 recycling centres. The Ozone Office will be the liaison between ODS users, Government agencies, technical institutions and relevant NGOs. It will develop and implement future measures including: monitoring the effectiveness of current regulations and processes; addressing the informal sector and illegal imports of ODSs; certifying refrigeration technicians; developing incentives to promote refrigerant recovery and recycling activities; and encouraging major stakeholders to promote ozone-friendly technologies and substances | Approved in principle US$1,424,647 as the total funds that will be available for Algeria to achieve the phase out of 245 ODP tonnes of CFCs by 2007, representing 85 per cent of the CFC consumption used in the refrigeration servicing sector, and that the Government of Algeria will not seek additional funding from the Fund to phase out an additional amount of 315 tonnes used in the informal sector and by a number of large users who import CFC directly. The Executive Committee also approved the first tranche of the RMP project with the understanding that a subsequent year’s funding will not be disbursed until the Executive Committee has favourably reviewed the prior year's progress report. | 200000 | 200000 | 0 | 0 |  | 0 | 0 | 0 | 2002-07-01 | 2002-10-01 | 2003-12-01 | 17 |  | 0 | 2004-06-01 | 2004-07-01 |  | ALG | 55 | Algeria | REF
ALG/REF/39/TAS/58 | FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in refrigeration and air-conditioning sector (including training in good refrigerant management practices, training of customs officers, and national recovery and recycling): second tranche | Multi-Year | A,I | It includes continuation of the implementation of training programmes for refrigeration servicing technicians, designation of recovery and recycling centres, and procurement of the equipment described under the recovery and recycling sub-project under the approved RMP. |  | 700000 | 700000 | 45 | 0 |  | 0 | 110 | 0 | 2003-04-01 | 2004-03-01 | 2004-04-01 | 12 |  | 0 | 2005-06-01 | 2007-05-01 |  | ALG | 58 | Algeria | REF
ALG/REF/42/TAS/59 | FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in the refrigeration and air-conditioning sector: training in good refrigerant management practices, training of customs officers, and national recovery and recycling: third tranche | Multi-Year | A,I | Training of 750 technicians on good refrigerant management practices through 30 training courses in six training centres; purchasing additional recovery/recycling equipment and distribution among service workshops; and installation of additional recovery/ recycling centres. The Government is also providing technical assistance to users in the informal sector, whom together with the licensing and quota system and legislative and regulative measures will phase out their CFC consumption. |  | 512104 | 512104 | 200 | 0 |  | 0 | 200 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 | 12 |  | 0 | 2007-11-01 | 2008-12-01 |  | ALG | 59 | Algeria | REF
ALG/REF/44/INV/62 | FIN | UNIDO | Conversion of CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the last group of commercial refrigerator manufactures (refrigeration sector terminal project) | Individual | A,I | Two enterprises use low-pressure foaming machines while the remaining companies are using pre-blended polyol and employ manual handling of polyurethane foam components or apply prefabricated polystyrene for insulation of part of their production; for the refrigerant-related operations the companies use vacuum pumps, semi-automatic or portable charging machines and leak detectors in the equipment baseline. It includes replacement of the low-pressure foaming machines with high pressure units, provision of industrial or portable charging units, new or retrofitted vacuum pumps and leak detectors, product redesigning, testing, trials and training. |  | 585370.14 | 585370 | 72.8 | 0 |  | 0 | 72.8 | 0 | 2004-12-01 | 2006-03-01 | 2007-04-01 | 28 |  | 0 | 2012-12-01 | 2014-07-01 |  | ALG | 62 | Algeria | REF
ALG/REF/59/PRP/72 | FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air-to-air air-conditioning sector) | Individual | A,I | Additional assistance for preparation of HCFC phase-out activities in the refrigeration manufacturing sector. |  | 59619.34 | 59619 | 0 | 0 |  | 0 | 0 | 0 | 2009-11-01 | 2009-12-01 | 2010-11-01 | 12 |  | 0 | 2012-12-01 | 2012-12-01 |  | ALG | 72 | Algeria | REF
ALG/SEV/09/CPG/01 | FIN | UNEP | Country programme preparation | Individual | A,I | The action plan has been developed on the basis of investment projects and training programmes in all sectors, with the following ODS phase-out phases: phase I (1993-1996): 60% reduction in ODS consumption compared to the consumption of 1991; phase II (1997-1999): additional 20% reduction in ODS consumption; and phase III (2000-2004): complete ODS phase-out, except for essential uses. |  | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1993-06-01 | 3 |  | 0 | 1993-11-01 | 1994-12-01 |  | ALG | 1 | Algeria | SEV
ALG/SEV/11/INS/02 | FIN | UNEP | Institutional support for ODS phase-out | Individual | A,I | An Ozone Commission headed by the Ministry of Education has been established by the Government The technical, administrative and financial support for the implementation of the Protocol will be provided by an Ozone Office under the supervision of the Ozone Commission. It will be responsible for identifying ODS users in order to assist them in developing phase-out project proposals; will determine the taxation levels; will prepare banning criteria; will establish an information programme to raise public awareness; and will publicize alternative technologies. NOTE: Approved as included in CPG. |  | 297000 | 297000 | 0 | 0 | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-01-01 | 1996-11-01 | 36 |  | 0 | 1999-03-01 | 2001-03-01 |  | ALG | 2 | Algeria | SEV